## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: ISLAND MATERNITY HOSPITAL
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVELS & TRANSPORTS | LIMH/NP/NM/001/22 | 804000 | Plan | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 67000 | 804000
Actual
2 | SERVICING OF VARIOUS COMMITTEE MEETINGS & PROMOTION EXERCISE | LIMH/NP/NM/002/22 | 500,000.00 | Plan | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 500000
Actual
3 |  |  |  | Plan
Actual
4 |  |  |  | Plan
Actual
5 |  |  |  | Plan
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: LAGOS ISLAND MATERNITY HOSPITAL 2022
Contract Description |  | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING |  | LIMH/S-NC-F/NS/001/22 | 1 |  | 1100000 | <50M | NS | Plan | POST | POST | 25/4/22 | N/A | 2/5/2022 | 16/5/2022 | 23/5/2022 | N/A | N/A | Plan | N/A | N/A | 1100000 | 6/6/2022 | 20/6/22 | 20/6/2023 | 21/6/2023
[8 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE REPAIRS |  | LIMH/S-NC-F/NS/002/22 | 1 |  | 200000 | <50M | NS | Plan | POST | POST | 23/5/22 | N/A | 30/5/2022 | 13/6/2022 | 20/6/2022 | N/A | N/A | Plan | N/A | N/A | 200000 | 4/7/2022 | 18/7/2022 | 18/7/2023 | 19/7/2023
[8 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF LIFT |  | LIMH/S-NC-F/NS/003/22 | 1 |  | 1000000 | <50M | NS | Plan | POST | POST | 20/6/22 | N/A | 27/6/2022 | 11/7/2022 | 18/7/2022 | N/A | N/A | Plan | N/A | N/A | 1000000 | 1/8/2022 | 15/8/2022 | 15/8/2023 | 16/8/2023
[8 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF ICT DEPARTMENT AND VARIOUS SERVERS |  | LIMH/S-NC-F/NS/004/22 | 1 |  | 5000000 | <50M | NS | PLAN | POST | POST | 2022-11-07 | N/A | 18/7/2022 | 2022-01-08 | 2022-08-08 | N/A | N/A | PLAN | N/A | N/A | 5000000 | 22/8/2022 | 2022-05-09 | 2023-05-09 | 2023-06-09
[8 empty] | Actual | [9 empty] | Actual
CELEBRATION OF FIRST BABY OF THE YEAR EVENT & STAFF WELFARE | HOSPITAL MANAGEMENT COMMITTEE EXPENSES Servicing of Various Committee Meetings & Promotion Exercise | LIMH/S-NC/NS/005/22 | 1 |  | 4000000 | <50M | NS | Plan | POST | POST | 2022-08-08 | N/A | 15/8/2022 | 29/8/2022 | 5/9/2022 | N/A | N/A | Plan | N/A | N/A | 4000000 | 19/9/2022 | 31/9/2022 | 10/10/2022 | 2022-12-10
[8 empty] | Actual | [9 empty] | Actual
PROCUREMENT OF FUEL FOR VEHICLE CONSUMPTIONS | SPECIAL DUTIES CELEBRATION OF FIRST BABY OF THE YEAR EVENT | LIMH/S-NC-F/NS/006/22 | 1 |  | 1150000 | <50M | NS | Plan | POST | POST | 5/9/2022 | N/A | 12/9/2022 | 26/9/2022 | 31/9/2022 | N/A | N/A | Plan | N/A | N/A | 1150000 | 10/10/2022 | 24/10/2022 | 24/10/2023 | 25/10/2023
[8 empty] | Actual | [9 empty] | Actual
PRINTING OF MEDICAL RECORD's FORMS & CARDS |  | LIMH/S-NC-F/NS/007/22 | 1 |  | 1000000 | <50M | NS | Plan | POST | POST | 2022-03-10 | N/A | 2022-10-10 | 24/10/2022 | 2022-07-11 | N/A | N/A | Plan | N/A | N/A | 1000000 | 21/11/2022 | 2022-05-12 | 2023-05-12 | 2023-06-12
[8 empty] | Actual | [9 empty] | Actual
PROCUREMENT OF COOKING GAS, PAYMENT OF HOSPITAL FAMILY LINE BILLS AND GSM |  | LIMH/S-NC-F/NS/008/22 | 1 |  | 50000 | <50M | NS | Plan | POST | POST | 2022-07-11 | N/A | 14/11/2022 | 28/11/2022 | 2022-05-12 | N/A | N/A | Plan | N/A | N/A | 50000 | 19/12/2022 | 26/12/2022 | 26/12/2023 | 27/12/2023
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[8 empty] | Actual | [9 empty] | Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS ISLAND MATERNITY HOSPITAL
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | National Women Conference (COWLSO) | LIMH/S-WTC/001/22 | Session with Governor's Wife definite Issues on Women's Health | 5 | 2 | Plan | EKO HOTEL | 50000 | 20000 | 10000 | 400000
Actual
2 | West African College of Surgeons Update Course In Clinical Obstetrics and Gynaecology | LIMH/S-WTC/002/22 | In Preparation for the Membership and Fellowship Examination | 3 | 2 | Plan | LAGOS | 50000 | 10000 | 10000 | 210000
Actual
3 | Training of Nurses on New Born Screening for Sickle Cell Disorder | LIMH/S-WTC/003/22 | Early detection of Sickle Cell Disorder among new born | 2 | 2 | Plan |  | 40000 | 10000 | 10000 | 120000
Actual
4 | Association of Hospital And Administrative Pharmacist of Nigeria Annual Conference (AHAPNAC) | LIMH/S-WTC/004/22 | Advancing Technological Revolution in Pharmaceutical Service Delivery | 4 | 2 | Plan | LAGOS | 30000 | 10000 | 10000 | 200000
Actual
5 | Mandatory Continuing Professional Development Programme for Accounts Staff | LIMH/S-WTC/005/22 | Technology Impact on Accounting Practices | 2 | 2 | Plan | IBADAN | 40000 | 10000 | 10000 | 120000
Actual
6 | Mandatory Course for Procurement Officers | LIMH/S-WTC/006/22 | Imperative of professionalizing procurement practice in Nigeria | 3 | 2 | Plan | LAGOS | 40000 | 10000 | 10000 | 180000
Actual
7 | National Conference And Workshop For Medical Social Welfare | LIMH/S-WTC/007/22 | To get updated knowledge about social work practice in the Hospital | 4 | 2 | Plan | LAGOS | 30000 | 10000 | 10000 | 200000
Actual
8 | Coaching and Mentoring for Line Managers in Administrative Dept. | LIMH/S-WTC/008/22 | To develop coaching and mentoring skills that helps to improve individual performance | 3 | 2 | Plan | LAGOS | 30000 | 10000 | 10000 | 150000
Actual
9 | Mandatory Continuing Professional Development Programme for Internal Auditors | LIMH/S-WTC/009/22 | Contemporary Auditing Governmenance, Forensics and Ethical Conduct | 2 | 2 | Plan | LAGOS | 40000 | 10000 | 10000 | 120000
Actual
10 | Annual Medical Laboratory Scientist of Nigeria | LIMH/S-WTC/010/22 | Continue Medical Education to Improve Technology in Medical Laboratory Science | 4 | 2 | Plan | LAGOS | 30000 | 10000 | 10000 | 200000
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS ISLAND MATERNITY HOSPITAL
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | BLOOD SCREENING | LIMH/S-C-F/QCBS/001/22 | QCBS | LUMP SUM | 7200000 | POST | Plan | 14/3/2022 | 21/3/2022 | 28/3/2022 | 2022-11-04 | 18/4/2022 | 25/4/2022 | 16/5/2022 | 23/5/2022 | 30/5/2022 | 2022-06-06 | 13/6/2022 | N/A | N/A | N/A | 7200000 | 20/6/2022 | 2022-04-07 | 18/7/2022 | 25/7/2022 | 2022-01-08 | 7200000
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS ISLAND MATERNITY HOSPITAL
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF UNIFORMS & PROTECTIVE OUTFITS | PROCUREMENT OF UNIFORMS & PROTECTIVE OUTFITS | LIMH/G-F/NS/001/22 | 1 |  | 1500000 | <50M | NS | POST | POST | Plan | 14/3/2022 | N/A | 21/3/2022 | 4/4/2022 | 11/4/2022 | N/A | N/A | N/A | 1500000 | 18/4/2022 | 25/4/2022 | 9/5/2022 | 9/5/2023 | 2023-10-05
Actual
2 | PROCUREMENT OF STATIONERIES |  | LIMH/G-F/NS/002/22 | 1 |  | 600000 | <50M | NS | POST | POST | Plan | 4/4/2022 | N/A | 11/4/2022 | 25/4/2022 | 2/5/2022 | N/A | N/A | N/A | 600000 | 2022-09-05 | 16/5/2022 | 30/5/2022 | 30/5/2023 | 31/5/2023
Actual
3 | PROCUREMENT OF CLEANING MATERIALS AND TORCH LIGHTS |  | LIMH/G-F/NS/003/22 | 1 |  | 475688 | <50M | NS | POST | POST | Plan | 2/5/2022 | N/A | 9/5/2022 | 23/5/2022 | 30/5/2022 | N/A | N/A | N/A | 475688 | 2022-06-06 | 13/6/2022 | 27/6/2022 | 27/6/2023 | 28/6/2023
Actual
4 | PROCUREMENT OF MEDICAL GAS |  | LIMH/G-F/NS/004/22 | 1 |  | 7958871 | <50M | NS | POST | POST | Plan | 6/6/2022 | N/A | 13/6/2022 | 27/6/2022 | 4/7/2022 | N/A | N/A | N/A | 7958871 | 2022-11-07 | 18/7/2022 | 1/8/2022 | 1/8/2023 | 2023-02-08
Actual
5 | PROCUREMENT OF CHEMICALS AND REAGENTS |  | LIMH/G-F/NS/005/22 | 1 |  | 7000000 | <50M | NS | POST | POST | Plan | 4/7/2022 | N/A | 11/7/2022 | 25/7/2022 | 1/8/2022 | N/A | N/A | N/A | 7000000 | 2022-08-08 | 15/8/2022 | 29/8/2022 | 29/8/2023 | 30/8/2023
Actual
Plan
Actual
Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS ISLAND MATERNITY HOSPITAL
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | [8 empty] | Plan | POST
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Sheet4
PROCUREMENT PLAN FOR IGR EXPENDITURE.
MINISTRY/AGENCY: LAGOS ISLAND MATERNITY HOSPITAL
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | DIET | LIMH/G-IGR/NS/001/21 | 1 |  | 43630542.9 | <50M | NS | POST | POST | Plan | 6/1/2021 | N/A | 13/1/2021 | 27/1/2021 | 3/2/2021 | N/A | N/A | N/A |  | 2021-10-02 | 17/2/2021 | 24/2/2021 | 3/3/2021 | 2021-04-03
[5 empty] | 36335388 |  |  |  |  | Actual
2 | THEATRE | LIMH/G-IGR/NS/002/21 | 1 |  | 140785331.4 | >100M | ICB | POST | POST | Plan | 3/2/2021 | N/A | 10/2/2021 | 24/2/2021 | 2/3/2021 | N/A | N/A | N/A |  | 2021-09-03 | 16/3/2021 | 30/3/2021 | 6/4/2021 | 2021-07-04
[5 empty] | 132090818 |  |  |  |  | Actual
3 | LABORATORY | LIMH/G-IGR/NS/003/21 | 1 |  | 82042797.42 | <100M | NCB | POST | POST | Plan | 2/3/2021 | N/A | 9/3/2021 | 23/3/2021 | 30/3/2021 | N/A | N/A | N/A |  | 2021-06-04 | 13/4/2021 | 27/4/2021 | 4/5/2021 | 2021-05-05
[5 empty] | 80380889 |  |  |  |  | Actual
4 | CASUALTY FEES | LIMH/G-IGR/NS/004/21 | 1 |  | 8716189.68 | <50M | NS | POST | POST | Plan | 6/4/2021 | N/A | 13/4/2021 | 27/4/2021 | 4/5/2021 | N/A | N/A | N/A |  | 2021-11-05 | 18/5/2021 | 1/6/2021 | 8/6/2021 | 2021-09-06
[5 empty] | 6654278 |  |  |  |  | Actual
5 | DRUGS | LIMH/G-IGR/NS/005/21 | 1 |  | 108911464.2 | >100M | ICB | POST | POST | Plan | 4/5/2021 | N/A | 11/5/2021 | 25/5/2021 | 1/6/2021 | N/A | N/A | N/A |  | 2021-08-06 | 15/6/2021 | 29/6/2021 | 6/7/2021 | 2021-07-07
[5 empty] | 105757159 |  |  |  |  | Actual
6 | ACCOMMODATION | LIMH/G-IGR/NS/006/21 | 1 |  | 134565314.5 | >100M | ICB | POST | POST | Plan | 1/6/2021 | N/A | 8/6/2021 | 22/6/2021 | 29/6/2021 | N/A | N/A | N/A |  | 2021-06-07 | 13/7/2021 | 27/7/2021 | 3/8/2021 | 2021-04-08
[5 empty] | 131875406 |  |  |  |  | Actual
7 | C.S.S.D | LIMH/G-IGR/NS/007/21 | 1 |  | 1343723.04 | <50M | NS | POST | POST | Plan | 2021-06-07 | N/A | 13/7/2021 | 27/7/2021 | 2021-03-08 | N/A | N/A | N/A |  | 2021-10-08 | 17/8/2021 | 31/8/2021 | 2021-07-09 | 2021-08-09
[5 empty] | 1005346 |  |  |  |  | Actual
8 | FORM-SHEET | LIMH/G-IGR/NS/008/21 | 1 |  | 4624220.88 | <50M | NS | POST | POST | Plan | 2021-03-08 | N/A | 2021-10-08 | 24/8/2021 | 31/8/2021 | N/A | N/A | N/A |  | 2021-07-09 | 14/9/2021 | 28/9/2021 | 2021-05-10 | 2021-06-10
[5 empty] | 4005247 |  |  |  |  | Actual
9 | ADMISSION PACK | LIMH/G-IGR/NS/009/21 | 1 |  | 38773285.83 | <50M | NS | POST | POST | Plan | 2021-07-09 | N/A | 14/9/2021 | 28/9/2021 | 2021-05-10 | N/A | N/A | N/A |  | 2021-12-10 | 19/10/2021 | 2021-02-11 | 2021-09-11 | 2021-10-11
[5 empty] | 34690739 |  |  |  |  | Actual
10 | SCAN | LIMH/G-IGR/NS/010/21 | 1 |  | 23207092.92 | <50M | NS | POST | POST | Plan | 2021-05-10 | N/A | 2021-12-10 | 26/10/2021 | 2021-02-11 | N/A | N/A | N/A |  | 2021-09-11 | 16/11/2021 | 30/11/2021 | 2021-07-12 | 2021-08-12
[5 empty] | 12000903 |  |  |  |  | Actual
11 | FAMILY PLANNING | LIMH/G-IGR/NS/011/21 | 1 |  | 689130.35 | <50M | NS | POST | POST | Plan | 2021-12-10 | N/A | 19/10/2021 | 2021-02-11 | 2021-09-11 | N/A | N/A | N/A |  | 16/11/2021 | 23/11/2021 | 2021-07-12 | 14/12/2021 | 15/12/2021
[5 empty] | 400000 |  |  |  |  | Actual
12 | X-RAY | LIMH/G-IGR/NS/012/21 | 1 |  | 10739368.8 | <50M | NS | POST | POST | Plan | 19/10/2021 | N/A | 26/10/2021 | 2021-09-11 | 16/11/2021 | N/A | N/A | N/A |  | 23/11/2021 | 30/11/2021 | 14/12/2021 | 21/12/2021 | 22/12/2021
[5 empty] | 4836958 |  |  |  |  | Actual
13 | ICU | LIMH/G-IGR/NS/013/21 | 1 |  | 29271538.08 | <50M | NS | POST | POST | Plan | 26/10/2021 | N/A | 2021-02-11 | 16/11/2021 | 23/11/2021 | N/A | N/A | N/A |  | 30/11/2021 | 2021-07-12 | 21/12/2021 | 28/12/2021 | 29/12/2021
[5 empty] | 20268706 |  |  |  |  | Actual
14 | NHIS | LIMH/G-IGR/NS/014/21 | 1 |  | 9000000 | <50M | NS | POST | POST | Plan | 2021-02-11 | N/A | 2021-09-11 | 23/11/2021 | 30/11/2021 | N/A | N/A | N/A |  | 2021-07-12 | 14/12/2021 | 28/12/2021 | 30/12/2021 | 31/12/2021
[5 empty] | 6234262 |  |  |  |  | Actual
15 | LSHS | LIMH/G-IGR/NS/015/21 | 1 |  | 7200000 | <50M | NS | POST | POST | Plan | 2021-02-11 | N/A | 2021-09-11 | 23/11/2021 | 30/11/2021 | N/A | N/A | N/A |  | 2021-07-12 | 14/12/2021 | 28/12/2021 | 30/12/2021 | 31/12/2021
[5 empty] | 5643060 |  |  |  |  | Actual