## Non-Proc items
NON PROCUREMENT ITEMS
MINISTRY/ AGENCY: LAGOS STATE FIRE AND RESCUE SERVICE
BUDGET YEAR : 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
Plan
1 | Travel & Transport | FS/NP/NS/001/22 | 65387700 | Plan | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975 | 5448975
2 | Audit Expenses, Staff auditing and verification exercise for all members of staff in the Headquarter and other Fire Stations. | FS/NP/002/22 | 720000 | Plan | 60000 | 60000 | 60000 | 60000 | 60000 | 2064-04-08 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
3 | Public relations expenses. Media Tour of Emergencies | FS/NP/003/22 | 500000 | Plan | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 2014-01-27 16:05 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67
4 | Production of 60 radio jingles in four languages (English, Pidgin, Yoruba, Igbo and Hausa | FS/NP/004/22 | 480000 | Plan | 40000 | 40000 | 40000 | 40000 | 40000 | 2009-07-06 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
5 | Monthly Newspaper for all Departments and Units. Monthly Television & Radio Performance | FS/NP/005/22 | 12180000 | Plan | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000 | 1015000
6 | Miscellaneous, Monthly Payment of 32 Cleaners | FS/NP/006/22 | 15360000 | Plan | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000 | 1280000
7 | Monthly Payment of 15 Gardners | FS/NP/007/22 | 7200000 | Plan | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000
8 | PMB Promotion Exit Conversion & Discipline | FS/NP/NS/008/22 | 2500000 | Plan | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL
9 | Special Duties Expenses, HOS Games, welfare expenses for Deceased and injured Officers | FS/NP/NS/009/22 | 218739110 | Plan | 18228259.17 | 18228259.17 | 18,228,259,17 | 18228259.17 | 18228259.17 | 18228259.17 | 18228259.17 | 18228259.17 | 18228259.17 | 18228259.17 | 18228259.17 | 18228259.17
Plan
7

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE FIRE & RESCUE SERVICE
BUDGET YEAR: Y2022
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference & Seminar | To facilitate the commitment of the staffs towards their respective assignment. | 21 | 3Days | Plan |  |  |  |  | 3876000
Actual
2 | Workshop & Training | Essential Building Capacity. Training with their respective institute e.g CIPSMN,ICAN, CPN etc. | 5 | 3Days | Plan |  |  |  |  | 2560000
Actual
3 | Specialised Training for Professionals. | Kind of Familiarization with other line and agencies to achieve a common goal. |  |  | Plan |  |  |  |  | 346249674.44
Actual
4 | ICT . | Annual Professional course for planners and Statistician | 2 |  | Plan
Actual
5 | Retreat |  | 2 |  | Plan
Actual
6 | Legal Conference |  |  |  | Plan
Actual
7 |  |  |  |  | Plan
Actual
8 |  |  |  |  | Plan
Actual
9 |  |  |  |  | Plan
Actual
10 |  |  |  |  | Plan
Actual
11 |  |  |  |  | Plan
Actual
12 |  |  |  |  | Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE FIRE AND RESCUE SERVICE
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
|  |  | 37,000,000.00 |  | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Stakeholders Meeting on implementation of Fire Service law | FS/S-C/CBS/001/21 | CBS | Lump Sum | 15000000 | Post | Plan | 25/02/2022 | 4/03/2022 | 11/03/2022 | 25/03/2021 | 6/4/2022 | 12/04/2022 | 3/5/2022 | 10/5/2022 | 1/5/2022 | 24/5/2022 | 31/5/2022 | 7/6/2022 | 21/6/2022 | 24/6/2022 |  | 01/7/2022 | 15/7/2022 | 22/7/2022 | 29/7/2022 | 5/8/2022
Actual
2 | Regulation | FS/S-C/CBS/002/22 | CBS | Lump Sum | 15000000 | Post | Plan | 28/3/2022 | 6/4/2022 | 14/4/2022 | 29/4/2022 | 10/5/2022 | 19/5/2022 | 17/6/2022 | 28/6/2022 | 7/7/2022 | 18/7/2022 | 27/7/2022 | 5/8/2022 | 12/9/2022 | 15/9/2022 |  | 26/9/2022 | 14/10/2022 | 2/11/2022 | 11/11/2022 | 21/11/2022
Actual
3 | Consultant Fee | FS/S-C/CQ/003/22 | CQ | Lump Sum | 43554000 | Post | Plan
[7 empty] | Actual | 7/4/2022 | 18/4/2022 | 27/4/2022 | 6/5/2022 | 17/5/2022 | 26/5/2022 | 13/6/2022 | 22/6/2022 | 1/7/2022 | 12/7/2022 | 21/7/2022 | 29/7/2022 | 16/8/2022 | 19/8/2022 |  | 30/8/2022 | 8/9/2022 | 19/9/2022 | 28/9/2022 | 7/10/2022
4 | Retreat | FS/S-C/CBS/004/22 | CBS | Lump Sum | 37000000 | Post | Plan | 16/4/2022 | 26/4/2022 | 2022-05-05 | 16/5/2022 | 25/5/2022 | 2022-03-06 | 2022-05-07 | 14/7/2022 | 25/7/2022 | 2022-03-08 | 2022-12-08 | 23/8/2022 | 2022-01-09 | 2022-07-09 |  | 16/9/2022 | 27/9/2022 | 2022-06-10 | 17/10/2022 | 26/10/2022
Actual
Plan
Actu+H1+H18
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE FIRE AND RESCUE SERVICE.
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION | [8 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Monthly fueling e.g AGO and PMS per annum for Fire Trucks,Water Tankers, Aerial Ladder, RIV and Hilux, P | FS/G/NS/001/22 |  | Lump sum | 396000000 | <500M | NCB | Post | Prior | Plan | 2022-01-04 | 13th-Jan-2022 | 2022-02-04 | 2022-02-18 | 2022-02-25 | 3rd - Mar-2022 | 25/3/2022 | 2022-03-29 |  | 7th-April-2022 | 2022-04-27 | 14th -May- 2022
Actual
2 | Procurement of Stationery | FS/G-F/002/22 |  |  | 2437300 | <50M | N/S | Post | Prior | Plan | 2021-01-07 | 18th- Jan - 2022 | 28th-Jan-2022 | 2022-02-11 | 2022-02-25 | 4th-Mar-2022 | 18th-Mar-2022 | 22nd-Mar-2022 |  | 8th-April-2022 | 22nd-April-2022 | 6th-April-2021
Actual
3 | Procurement of Office Equipment for Procurement Unit. | FS/G/NS/003/22 |  |  | 1,350,000,00 | <10M | N/S | Post | POST | Plan | 2nd-Feb-2022 | 9th-Feb-2022 | 16th-Feb-2022 | 24th-Feb-2022 | 3rd-Mar-2022 | 10th-Mar-2022 | 22nd-Mar-2022 | 24th Mar-2022 |  | 31st-Mar-2022 | 7th-April-2022 | 21st-April-2022
Actual
4 | Procurement of Uniform & Protective Outfits | FS/G/NS/004/22 |  |  | 454593000 | <500M | NCB | post | Prior | Plan | 3rd-Mar-2022 | 10th- Mar-2022 | 17th-Mar-2022 | 31st-Mar-2022 | 7th-April-2022 | 14th-April-2022 | 28th-April-2022 | 2nd-May-2022 |  | 6th-May-2022 | 13th-May-2022 | 27th-May-2022
Actual
5 | Procurement of Fuel for Plant & Heavy Equipment | FS/G/NS/005/22 |  |  | 487000000 | <500M | NCB | Post | Prior | Plan | 8th-Mar 2022 | 15th-Mar- 2022 | 22nd-Mar- 2022 | 5th-April-2022 | 12th-April-2022 | 19th-April-202 | 3rd-May-2022 | 6th-May-2022 |  | 14th-May-2022 | 28th-May-2022 | 10th-June-2022
Actual
6 | Procurement of Books for Library Services | FS/G/NS/006/22 |  |  | 10000000 | <50M | N/S | Post | Prior | Plan | 29th-Mar-2022 | 5th-April-2022 | 12th-April-2022 | 26th-April-2022 | 3rd-May-2022 | 10th-May-2022 | 24th-May-2022 | 26th-May-2022 |  | 2nd-June-2022 | 9th-June-2022 | 16th-June-2022
Actual
7 | Procurement of Firefighting plant & Equipment | FS/G/NS/007/22 |  |  | 67703125 | <100M | NCB | Post | Prior | Plan | 19th-April,2022 | 26th-April-2022 | 4th- May-2022 | 18th- May-2022 | 25th- May-2022 | 1st-June-2022 | 8th-June-2022 | 11th-June-2022 |  | 18th-June-2022 | 25th-June-2022 | 8th-July-2022
Actual
8 | Procurement of Office Furniture & Fittings | FS/G/NS/008/22 |  |  | 70000000 | <100M | NCB | Post | Prior | Plan | 10th-May-2022 | 17th-May-2022 | 24th-MAY-2022 | 7th-June-2022 | 14th-June-2022 | 21st-June-2022 | 12th-July-2022 | 15th-July-2022 |  | 44764 | 29th-July-2022 | 12th-Aug-2022
Actual
9 | Procurement of Computer Hardware | FS/G/NS/009/22 |  |  | 29000000 | <50M | N/S | Post | Post | Plan | 31st-May-2022 | 7th-June-2022 | 14th-June-2022 | 28th-June-2022 | 5th-July-2022 | 12th-July-2022 | 26th-July-2022 | 29th-July-2022 |  | 5th-Aug-2022 | 19th-Aug-2022 | 2nd-Sep-2022
Actual
10 | Procurement of Fuel Consumption for fueling of State Fire Director's Official Vehicle.70L WEEKLY FUELING OF 21Nos HOD & HOU'S Vehicles | FS/G/NS/010/21 |  |  | 8673999.96 | <10M | N/S | Post | Post | Plan | 9th-Aug-2022 | 23rd-Aug-2022 | 6th-Sep-2022 | 27th-Sep-2022 | 4th-Oct-2022 | 11th-Oct-2022 | 25th-Oct-2022 | 28th-Oct-2022 |  | 4th-Nov-2022 | 11th-Nov-2022 | 25th-Nov-2022
Actual
11 | Procurement of Office Equipment, fixed projector with screen, Photocopying Machine, Amplifiers/ Public Address System, Caged Machine with workout Bench and weight Bars, Defibinlator Machine | FS/G/NS/011/22 |  |  | 4625000 | <10M | N/S | Post | Post | Plan | 11th--Aug-2022 | 23rd-Aug-2022 | 31st-Aug-2022 | 20th-Sept-2022 | 28th-Sept-2022 | 7th- Oct- 2022 | 27th-Oct-2022 | 31st-Oct-2022 |  | 9th-Nov-2022 | 18th-Nov-2022 | 29th-Nov-2022
Actual

## non-consultancy
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE FIRE & RESCUE SERVICE
| BUDGET YEAR: 2021 | 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Motor vehicle Repairs | FS/S-NC/NS/001/21 | 1 | Lot 1 | 14940000 | <50M | NS | Plan | Post | Prior or Post review | 8th-Feb-2022 | 15th-Feb-2022 | 22nd-Feb-2022 | 1st-Mar-2022 | 8th-Mar-2022 | 15th-Mar-2022 | 22nd-Mar-2022 | Plan | 29th-Mar-2022 | 5th-April-2022 | 12th-April-2022 | 19th-April-2022 | 26th-April-2022
[8 empty] | Actual | [9 empty] | Actual
2 | Publicity & Press coverage | FS/S-N/NS/002/22 |  | 1 | 6200000 | <10M | NS | Plan | post | Post | 9th-Mar-2022 | 16th-Mar-2022 | 23rd-Mar-2022 | 30th-Mar-2022 | 6th-April-2022 | 13th-April-2022 | 20th-April-2022 | Plan | 27th-April-2022 | 4th-May-2022 | 11th-May-2022 | 18th-May-2022 | 25th-May-2022
[8 empty] | Actual | [9 empty] | Actual
3 | Maintenance of Office Building | FS/S-NC/NS/003/21 |  | 1 | 4743000 | <10M | NS | Plan |  | Prior or Post review | 8th-April-2022 | 15th-April-2022 | 22nd-April-2022 | 29th-April-2022 | 6th-May-2022 | 13th-May-2022 | 20th-May-2022 | Plan | 27th-May-2022 | 3rd-June-2022 | 10th-June-2022 | 17th-June-2022 | 24th-June-2022
[8 empty] | Actual | [9 empty] | Actual
4 | Maintenance of Firefighting Trucks | FS/S-NC/NS/004/22 |  | 1 | 910000000 | <100M | NCB | Plan |  | Prior | 10TH-May-2022 | 17th-May-2022 | 24th-May-2022 | 31st-May-2022 | 6th-June-2022 | 13th-June-2022 | 20th-June-2022 | Plan | 28th-June-2022 | 5th-July-2022 | 12th-July-2022 | 19th-July-2022 | 26th-July-2022
Actual
5 | Maintenance of Tractor & Heavy Equipment | FS/S-NC/NS/005/21 |  | 1 | 33734400 | <50M | NS |  |  | Prior | 10th-June-2022 | 17th-June-2022 | 24th-June-2022 | 1st-July-2022 | 8th-July-2022 | 15th-July-2022 | 22nd-July-2022 |  | 29th-July-2022 | 5th-Aug-2022 | 12th-Aug-2022 | 19th-Aug-2022 | 26th-Aug-2022
6 | Maintenance & Repair of Computer Hardware | FS/S-NC/NS/006/22 |  |  | ,1400,000.00 | <10M | NS |  |  | Prior | 16th-June-2022 | 5th-July-2022 | 12th-July-2022 | 19th-July-2022 | 26th-July-2022 | 2nd-Aug-2022 | 9th-Aug-2022 |  | 16th-Aug-2022 | 23rd-Aug-2022 | 30th-Aug-2022 | 6th-Sep-2022 | 13th-Sep-2022
7 | Enlightenment and Campaign | NC/NS/007/22 |  | 1 | 74880000 | <100M | NS |  |  | Prior | 29th-June-2022 | 7th-July-2022 | 14th-July-2022 | 21st-July-2022 | 28th-July-2022 | 4th-Aug-2022 | 11th-Aug-2022 |  | 18th-Aug-2022 | 25th-Aug-2022 | 1st-Sep-2022 | 8th-Sep-2022 | 15th-Sep-2022
8 | Printing of Fire Certificate & Forms | NC/NS/008/22 |  | 1 | 12000000 | <50M | NS | Plan | Post | Prior | 30th-June-2022 | 11th-July-2022 | 19th-July-2022 | 28th-July-2022 | 3rd-August-2022 | 12th-Aug-2022 | 23rd-Aug-2022 | Plan | 1st-Sept-2022 | 12th-Sept-2022 | 21st-Sept-2022 | 30th-Sept-2022 | 11th-oct-2022
9 | [7 empty] | Actual | [9 empty] | Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY/AGENCY: LAGOS STATE FIRE AND RESCUE SERVICE
BUDGET YEAR:2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[6 empty] | NCB | Bill of Quantity | Prior |  | Prior | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Fire Mechanic Maintenance Shop Alausa HQ | FS/W/NCB/001/22 |  | 202044813.53 | <500M | NCB | Bill of Quantity | Prior | Plan | Prior
[9 empty] | Actual |  | 7th-Jan-2022 | 21st-Jan-2022 | 28th-Jan-2022 | 4th-Feb-2022 | 11th-Feb-2022 | 18th-Feb-2022 | 25th-Feb-2022 | 4th-Mar-2022 |  | 11th- Mar-2022 | 18th- Mar-2022 | 6th-April-2022
2 | 30% Final Payment & Retention of Ijede Fire Station | FS/W/ST/002/22 |  | 43,651.374.25 | <100M | NS | Bill of Quantity | Prior | Plan | Prior | 7th-Jan-2022 | 21st-Jan-2022 | 28th-Jan-2022 | 4th-Feb-2022 | 11th-Feb-2022 | 18th-Feb-2022 | 25th-Feb-2022 | 4th-Mar-2022 |  | 11th-Mar-2022 | 18th-Mar-2022 | 6th-April-2022
Actual
3 | 60% Final Payment & Retention of Kosofe Fire Station | FS/W/ST/003/22 |  | 117210877.56 | <500M | NCB | Bill of Quantity | Prior | Plan | Prior | 8th-Feb-2022 | 22nd-Feb-2022 | 8th-Mar-2022 | 22nd-Mar-2022 | 29th-Mar-2022 | 6th-April-2022 | 13th-April-2022 | 20th-April-2022 |  | 4th-May-2022 | 11th-May-2022 | 25th-May-2022
Actual
4 | 30% Retention for Fuel Dump Alausa | FS/W/NS/004/22 |  | 4936140.67 | <50M | NS | Bill of Quantity | Prior | Plan | Prior | 27th-May-2022 | 3th-June-2022 | 10th-June-2022 | 24th-June-2022 | 4th-July-2022 | 8th-July-2022 | 15th-July-2022 | 22nd-July-2022 |  | 30th-July-2021 | 13th-Aug-2021 | 27th-Aug-2021
Actual
5 | Drilling of industrial Borehole/ Purchasr of Submersible Pump/Installation of Tank Tower & Purchase of Storage Tank each for Fire Station | FS/W/ST/005/22 |  | 90000 | <100M | NS | Bill of Quantity | Prior | Plan | Prior | 9th-Sep-2022 | 16th-Sep-2022 | 23rd-Sep-2022 | 4th-Oct-2022 | 11th-Oct-2022 | 18th-Oct-2022 | 20th-Oct-2022 | 27th-Oct-2022 |  | 3rd-Nov-2021 | 10th-Nov-2021 | 17th-Nov-2021
Actual
7 | [6 empty] | Bill of Quantity | Post | Plan | Prior
Actual
8 | [6 empty] | Bill of Quantity | Post | Plan
Actual
9 | [6 empty] | Bill of Quantity | Post | Plan
Actual
Plan
Actual
Plan
Actual

## goods Continuation
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE FIRE & RESCUE SERVICE
BUDGET YEAR:2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
12 | Procurement of Computer Accessories and Consumables for Headquarters & Other Stations | FS/G/NS/012/22 |  |  | 1309545.6 | <10M | N/S | Post | Post
[11 empty] | 23rd-Aug-2022 | 6th-Sep-2022 | 13th-Sep-2022 | 4th-Oct-2022 | 11th-Oct-2022 | 18th-Oct-2022 | 1st-Nov-2022 | 4th-Nov-2022 |  | 11th-Nov-2022 | 18th-Nov-2022 | 30th-Nov-2022
13 | Procurement of Planning unit Consumables/Equipment | FS/G/NS/013/22 |  |  | 900000 | <10M | N/S | Post | Post
[11 empty] | 23rd-Aug-2022 | 6th-Sep-2022 | 13th-Sep-2021 | 4th-Oct_2022 | 11th-Oct-2022 | 18th-Oct-2022 | 1st-Nov-2022 | 4th-Nov-2022 |  | 11th-Nov-2022 | 18th-Nov-2022 | 30th-Nov-2022
14 | Audit unit Expenses Procurement of asset register & postpayment audit | FS/G/NS/014/22 |  |  | 280008 | <10M | N/S | Post | Post
[11 empty] | 6th-Sep-2022 | 14th-Sep-2022 | 5th-Oct-2022 | 20th-Oct-2022 | 27th-Oct-2022 | 3rd-Nov-2022 | 17th-Nov-2022 | 18th-Nov-2022 |  | 25th-Nov-2022 | 2nd-Dec-2022 | 13th-Dec-2022
15 | Enligntenment & Campaign, Electronic Billboard Advertisement on Fire Sefety at 2 Locations | FS/G/NS/015/22 |  |  | 58072000 | <100M | NCB | Post | Prior
[11 empty] | 7th-Sept-2022 | 16th-Sept-2022 | 27th-Sept-2022 | 6th-Oct-2022 | 17th-Oct-2022 | 26th-Oct-2022 | 4th-Nov-2022 | 15th- Nov-2022 |  | 24th-Nov.2022 | 5th- Dec-2022
16 | Procurement of 34Nos First Aid Consumables for 16 Fire Stations | FS/G/NS/016/22 |  |  | 1258000 | <10M | N/S | Post | Post
[11 empty] | 8th-Sept-2022 | 19th-Sept-2022 | 28th-Sept-2022 | 7th-Oct-2022 | 18th-Oct-2022 | 27th-Oct-2022 | 7th- Nov-2022 | 16th-Nov-2022 |  | 25th-Nov-2022 | 6th-Dec-2022