## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE RECORDS AND ARCHIEVES BUREAU
BUDGET YEAR: 20202
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel and Tours | LASRAB/NP/NM/001/22 | 2530771 | Plan | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 210897.58 | 2530771
Actual
2 | General Utility :Procurement of rechargeable Cards, Payment of Telephone bills, LAWMA Bills etc Subscription of DSTV in the D.G Office, Bureau Secretary office and other offices | LASRAB/NP/NM/002/22 | 5,343,998.00 | Plan | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 445333.16 | 5,343,998.00
Actual
3 | Monthly unforseen Circumstances @N219,183.34 Per Month | LASRAB/NP/NM/003/21 | 2630200 | Plan | [8 empty] | N50,000 |  |  | N50,000 | N200,000.00
Actual
4 | Payment of course allowances and other incidentals to staff | PPA/NP/NM/001/20 | N400,000 | Plan |  |  | N100,000 |  |  | N100,000 |  |  | N100,000.00 |  |  | N100,000.00 | N400,000.00
Actual
5 | Private Engagement of 6Nos of Security Guard for 24 Hours Services @ N32,500 X 12 | MIS/G/NS/005/2O | N2,340,000.00 | Plan |  |  | N62,500 |  |  | N62,500 |  |  | N62,500 |  |  | N62,500 | N250,000.00
Actual
6 | Private Engagement of Additional Nos.of 2 Security Superevisors for 24 Hours Services @ N39,000 X 12 | PPA/NP/NM/006/20 | N936,000.00 | Plan | [8 empty] | N750,000.00 |  |  |  | N750,000.00
Actual
3 | Miscellanous: Payment for sundry expenses on office related matters | LASRAB/NP/NM/003/22 | 311073 | Plan | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 25922.75 | 311073
Actual
4 | Publicity of centres activities,Adverts of trg. Programs,Video coverage,Design of momentos with radio and television jingles at LTV, Production of documentary on LASRAB & airing on TV | LASRAB/NP/NM/004/22 | 2000000 | Plan |  |  | 500000 |  |  | 500000 |  |  | 500000 |  |  |  | N2,000,000.00
Actual
5 | PMB / MTB Meetings Expenses & Provision for Servicing of Monthly Management Meeting | LASRAB/NP/NM/005/22 | 2000000 | Plan | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | N2,000,000.00
Actual
9 | Conversion of paper records in the archives to digital copies. | LASRAB/NP/NM/006/21 | N3,000,000.00 | Plan | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N450,000 | N5,400,000.00
Actual
10 | Engagement of 9Nos of Private Cleaners @32,500.00x 12 | PPA/NP/NM/002/20 | N3,510,000.00 | Plan | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N300,000 | N3,600,000.00
Actual
| Engagement of Additional 1 No of Cleaner Supervisor @39,000.00x 12 | PPA/NP/NM/003/20 | N468,000.00 | Plan | [12 empty] | N5,500,000.00
Actual
| Engagement of 2Nos of Private Guardner @32,500.00x 12 | PPA/NP/NM/004/20 | N780,000.00 | Plan | [12 empty] | N2,400,000.00
Actual
| Engagement of Additional 1Nos of Private Guardne Supervisor @39,000.00x 12 | PPA/NP/NM/005/20 | N468,000.00 | Plan | [12 empty] | N2,400,000.00
Actual
6 | Conservation of archives, books and artifacts in the repositories, reference library and mini- museum against insects, pests and environmental hazards including dehumidification of records and repair of endangered records and artefacts. | LASRAB/NP/NM/006/22 | N450,000;00 | Plan | [8 empty] | 450000 |  |  |  | N450,000.00
Actual
| Documentation of oral history and tradition of the people, places and communities in Lagos State including the developmental history of the State tagged ‘Lagos Heritage Series.” Two Webinar interviews | LASRAB/NP/NM/008/21 | 700000 | Plan | [12 empty] | N20,000,000.00
Actual
| Production of 30 Documentaries on the THEMES Agenda@N1,500,000.00 X 30 Documentaries |  | N45,000,000.00 | Plan | [12 empty] | N45,000,000.00
Actual
7 | Mornitoring and Evaluation of Record Keeping System in all MDAs | LASRAB/NP/NM/007/22 | 200000 | Plan |  |  | 50000 |  |  | 50000 |  |  | 50000 |  |  | 50000 | 200.000.00
Actual
8 | 2nd Phase of digitizing all records and document into electronic format for archive purpose, commercial book scanner, Economic value, scanning and imaging software, archiving software | LASRAB/NP/NM/008/22 | 5000000 | Plan
Actual
9 | MTN Annual Internet Subscription for LASRAB and Procurement of 5 MBPs of MTN Internet data plans | LASRAB/NP/NM/009/22 | 332,500.00 | Plan
Actual
10 | Records and Archives Advocacy on showcasing the Bureau to Public, Visit to MDAs, organising Archives international day at a rented venue, Shareing of Sourvenier etc | LASRAB/NP/NM/010/22 | 10000000 | Plan |  |  |  |  | 10000000 | [7 empty] | N10,000,000.00
Actual
4 | Payment of course allowances and other incidentals to staff | PPA/NP/NM/001/20 | N400,000 | Plan |  |  | N100,000 |  |  | N100,000 |  |  | N100,000.00 |  |  | N100,000.00 | N400,000.00
Actual
5 | Private Engagement of 6Nos of Security Guard for 24 Hours Services @ N32,500 X 12 | MIS/G/NS/005/2O | N2,340,000.00 | Plan |  |  | N62,500 |  |  | N62,500 |  |  | N62,500 |  |  | N62,500 | N250,000.00
Actual
6 | Private Engagement of Additional Nos.of 2 Security Superevisors for 24 Hours Services @ N39,000 X 12 | PPA/NP/NM/006/20 | N936,000.00 | Plan | [8 empty] | N750,000.00 |  |  |  | N750,000.00
Actual
11 | Payment of Allowance to carry out documentary interview tagged Heritage Series | LASRAB/NP/NM/011/22 | 400394.99 | Plan | [6 empty] | 400394.99 | [5 empty] | N400,394.99
Actual
12 | Decongestion, Reorganisation of Registries of 3No. MDAs @ N5M | LASRAB/NP/NM/012/22 | 15000000 | Plan |  |  |  | 10000000 |  |  |  |  | 5000000 |  |  |  | N15,000,000.00
Actual
|  | PPA/NP/NM/015/20 | N6,800,000.00 | Plan | [12 empty] | N6,800,000.00
Actual
|  | PPA/NP/NM/016/20 | N24,916,629.00 | Plan | [12 empty] | N24,916,629.00
Actual
|  | PPA/NP/NM/017/20 | N5,000,000.00 | Plan | [12 empty] | N5,000,000.00
Actual
| Quarterly Production of TV Prog. On Govt. Topical issues / Activities for STATE ON FOCUS airing on LTV Every Qtr@ N500,000.00 X 4 | PPA/NP/NM/018/20 | N2,000,000.00 | Plan | [12 empty] | N2,000,000.00
Actual
| Consultancy fees for web & social media consultant | PPA/NP/NM/019/20 | N2,227,000.00 | Plan | [12 empty] | N2,227,000.00
Actual
| 30 Minutes Video Documentary on activities of the State Govt. Admin. | PPA/NP/NM/020/20 | N6,000,000.00 | Plan | [12 empty] | N6,000,000.00
Actual
| Broadcast of Documentary on 3 TV Stations | PPA/NP/NM/021/20 | N4,416,831.00 | Plan | [12 empty] | N4,416,831.00
Actual
| Production of Power Point presentation on Govt. Programme and Activities on quarterly basis @N250,000.00 X 4 | PPA/NP/NM/022/20 | N1,000,000.00 | Plan | [12 empty] | N1,000,000.00
Actual
| Advertisement of Govt Policies in Newspapers & Magazines | PPA/NP/NM/023/20 | N750,000.00 | Plan | [12 empty] | N750,000.00
Actual
| Production of 20 Radio Jinggles @ N50000.00 each | PPA/NP/NM/024/20 | N1,000,000.00 | Plan | [12 empty] | N1,000,000.00
Actual
| Placement of 25 slots of Radio Jinggles@N20,000.00 per slot spread across 5 Radio Stations | PPA/NP/NM/025/20 | N500,000.00 | Plan | [12 empty] | N500,000.00
Actual
| Public Relations on behalf of the Government by HC | PPA/NP/NM/026/20 | N2,000,000.00 | Plan | [12 empty] | N2,000,000.00
Actual
| Quarterly Electronic Media Stakeholder Meeting | PPA/NP/NM/027/20 | N400,000.00 | Plan | [12 empty] | N400,000.00
Actual
| Media Briefing | PPA/NP/NM/028/20 | N400,000.00 | Plan | [12 empty] | N400,000.00
Actual
| Production of special documentary in local languages on (THEMES) Transportation | PPA/NP/NM/029/20 | N500,000.00 | Plan | [12 empty] | N500,000.00
Actual
| Production of special documentary in local languages on (THEMES) Environment | PPA/NP/NM/030/20 | N500,000.00 | Plan | [12 empty] | N500,000.00
Actual
| Production of special documentary in local languages on (THEMES) Tourism | PPA/NP/NM/031/20 | N500,000.00 | Plan | [12 empty] | N500,000.00
Actual
| Production of special documentary in local languages on (THEMES) Technology | PPA/NP/NM/032/20 | N500,000.00 | Plan | [12 empty] | N500,000.00
Actual
| Procurement of News Papers & Magazines , | PPA/NP/NM/033/20 | N1,500,000.00 | Plan | [12 empty] | N1,500,000.00
Actual
| Servicing of Management Meetings per quarter@ N375,000.00 per Quarter | PPA/NP/NM/034/20 | N1,500,000.00 | Plan | [12 empty] | N1,500,000.00
Actual
| Quarterly Adhoc Committee Meetings | PPA/NP/NM/035/20 | N250,000.00 | Plan | [12 empty] | N250,000.00
Actual
| COWLSO Event expences | PPA/NP/NM/036/20 | N750,000.00 | Plan | [12 empty] | N750,000.00
Actual
| Production of Information Communication and Advocacy materials on THEMES | PPA/NP/NM/037/20 | N2,400,000.00 | Plan | [12 empty] | N2,400,000.00
Actual
| Binding of old Newspapers and Magazines on a quarterly basis | PPA/NP/NM/038/20 | N1,500,000.00 | Plan | [12 empty] | N1,500,000.00
Actual
| Conducting Annual Survey (Workstudy of the Activities of the Ministry and its allied Agencies for the assessment & evaluation of services) | PPA/NP/NM/039/20 | N2,400,000.00 | Plan | [12 empty] | N2,400,000.00
Actual
|  | PPA/NP/NM/040/20 | N625,000.00 | Plan | [12 empty] | N625,000.00
Actual
|  | PPA/NP/NM/014/21 | N625,000.00 | Plan | [12 empty] | N625,000.00
Actual
Plan
Actual
Plan
Actual
12 |  | LASRAB/NP/NM/009/22 |  | Plan
Actual
4 | Payment of course allowances and other incidentals to staff | PPA/NP/NM/001/20 | N400,000 | Plan |  |  | N100,000 |  |  | N100,000 |  |  | N100,000.00 |  |  | N100,000.00 | N400,000.00
Actual
5 | Private Engagement of 6Nos of Security Guard for 24 Hours Services @ N32,500 X 12 | MIS/G/NS/005/2O | N2,340,000.00 | Plan |  |  | N62,500 |  |  | N62,500 |  |  | N62,500 |  |  | N62,500 | N250,000.00
Actual
6 | Private Engagement of Additional Nos.of 2 Security Superevisors for 24 Hours Services @ N39,000 X 12 | PPA/NP/NM/006/20 | N936,000.00 | Plan | [8 empty] | N750,000.00 |  |  |  | N750,000.00
Actual
13 |  | LASRAB/NP/NM/010/22 | 400394.99 | Plan | [6 empty] | 400394.99 | [5 empty] | N400,394.99
Actual
14 |  | LASRAB/NP/NM/011/22 | 15000000 | Plan |  |  |  | 10000000 |  |  |  |  | 5000000 |  |  |  | N15,000,000.00
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
INFORMATION AND STRATEGY
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Management & Junior Staff Retreat | PPA/S-WTC/SS/001/20 |  | 60 | 3 Days | Plan |  |  |  |  | N6,000,000.00
Actual
2 | Renewal of NIPR Membership dues of 100 Public Affairs Officer in the Ministry | PPA/S-WTC/SS/001/20 |  | 100 | 1Day | Plan |  |  |  |  | N5,500,000.00
Actual
3 | Payment of Allowances to attend Short distance training for Staff between G/L 16 - G/L17 | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
4 | Payment of Allowances to attend Short distance training for G/L 15 Staff | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
|  | PPA/S-WTC/SS/003/22 |  |  |  | Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
|  | PPA/S-WTC/SS/004/22 |  |  |  | Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 |  |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
|  | PPA/S-WTC/SS/005/22 |  |  |  | Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 |  |  | 20 |  | Plan |  |  |  |  | N600,000.00
|  | PPA/S-WTC/SS/006/22 |  |  |  | Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 |  |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/007/22 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 |  | PPA/S-WTC/SS/008/22 |  |  |  | Plan
Actual
12 |  | PPA/S-WTC/SS/009/22 |  |  |  | 12
Actual
3 | Payment of Allowances to attend Short distance training for Staff between G/L 12 - G/L14 | PPA/S-WTC/SS/003/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
4 | Payment of Allowances to attend Short distance training for Staff between G/L 04 - G/L10 |  |  |  |  | Plan |  |  |  |  | N600,000.00
|  | PPA/S-WTC/SS/004/22 |  |  |  | Actual
5 | Payment of Allowances for officers to attend seminars and professional annual Conference for Admin & HR Officers |  |  |  |  | Plan |  |  |  |  | N800,000.00
|  | PPA/S-WTC/SS/005/22 |  |  |  | Actual
6 | Payment of Allowances for officers to attend seminars and professional annual Conference for Archivists | PPA/S-WTC/SS/006/22 |  |  |  | Plan |  |  |  |  | N1,400,000.00
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 | PPA/S-WTC/SS/005/20 |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 | PPA/S-WTC/SS/006/20 |  | 20 |  | Plan |  |  |  |  | N600,000.00
Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 | PPA/S-WTC/SS/007/20 |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/008/20 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | 12
Actual
7 | Payment of Allowances for officers to attend seminars and professional annual Conference for Finance & Account Officers | PPA/S-WTC/SS/007/22 |  |  |  | Plan |  |  |  |  | N400,000.00
Actual
8 | Payment of Allowances for officers to attend seminars and professional annual Conference for Auditors | PPA/S-WTC/SS/008/22 |  |  |  | Plan |  |  |  |  | N53,209.47
Actual
9 | Payment of Allowances for Professional Conference and Seminars for 2 Nos. of G/L 15 Officers to attend National Association of Statistician and Economic Summit at Abuja | PPA/S-WTC/SS/009/22 |  |  |  | Plan |  |  |  |  | N400,000.00
Actual
10 | Y2022 Staff Retreat for Staff of the Bureau (Cost of Rented Venue, Accommodation, Honourarium to Facilitators etc) | PPA/S-WTC/SS/010/22 |  |  |  | Plan |  |  |  |  | N3,000,000.000
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 | PPA/S-WTC/SS/005/20 |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 | PPA/S-WTC/SS/006/20 |  | 20 |  | Plan |  |  |  |  | N600,000.00
Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 | PPA/S-WTC/SS/007/20 |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/008/20 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | 12
Actual
11 | On going Training for 60 Nos. of officers of Registry from various MDAs | PPA/S-WTC/SS/011/22 |  |  |  | Plan |  |  |  |  | N2,000,000.00
Actual
12 | Revamping of records management service wide through trainning and conversion of clerical officers to archivist cadre | PPA/S-WTC/SS/012/22 |  |  |  | Plan |  |  |  |  | N20,000,000.00
Actual
13 | Foreign Trainning for the DG of the Bureau | PPA/S-WTC/SS/013/22 |  |  |  | Plan |  |  |  |  | N1,000,000.00
Actual
14 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 | PPA/S-WTC/SS/005/20 |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 | PPA/S-WTC/SS/006/20 |  | 20 |  | Plan |  |  |  |  | N600,000.00
Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 | PPA/S-WTC/SS/007/20 |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/008/20 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | 12
Actual
15 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
16 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
17 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
18 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 | PPA/S-WTC/SS/005/20 |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 | PPA/S-WTC/SS/006/20 |  | 20 |  | Plan |  |  |  |  | N600,000.00
Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 | PPA/S-WTC/SS/007/20 |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/008/20 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | 12
Actual
19 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
20 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
21 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
22 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 | PPA/S-WTC/SS/005/20 |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 | PPA/S-WTC/SS/006/20 |  | 20 |  | Plan |  |  |  |  | N600,000.00
Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 | PPA/S-WTC/SS/007/20 |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/008/20 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | 12
Actual
23 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
24 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
25 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
26 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual
5 | [5 empty] | Plan |  |  |  |  | N4,000,000.00
Actual
6 | [5 empty] | Plan |  |  |  |  | N2,500,000.00
Actual
7 | Payment of Conference & Seminar Fees for 6 nos. of Senior Staff @N250,,000.00 | PPA/S-WTC/SS/005/20 |  | 6 |  | Plan |  |  |  |  | N1,500,000.00
Actual
8 | Attending local trainning workshop at PSSDC and other venues within the State by 20 Senior Mgt Staff @N30,000.00 | PPA/S-WTC/SS/006/20 |  | 20 |  | Plan |  |  |  |  | N600,000.00
Actual
9 | Attending local trainning workshop at PSSDC and other venues within the State by 65 Nos. of Middle Level Mgt Staff @N20,000.00 | PPA/S-WTC/SS/007/20 |  | 65 |  | Plan |  |  |  |  | N1,300,000.00
Actual
10 |  | PPA/S-WTC/SS/008/20 |  | 10 |  | Plan |  |  |  |  | N100,000.00
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | 12
Actual
27 |  | PPA/S-WTC/SS/001/22 |  |  |  | Plan |  |  |  |  | N3,038,100.00
Actual
28 |  | PPA/S-WTC/SS/002/22 |  |  |  | Plan |  |  |  |  | N5,865,204.00
Actual

## non-cons
MINISTRY/AGENCY:
MINISTRY/AGENCY:
|  |  | LAGOS STATE RECORDS | AND
PROCUREMENT OF NON CONSUMABLE ITEMS (LASRAB, BUDGET 2022)
| Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Motor Vehicle Repairs and Maintenance | MIS/NCS -F/001/20 |  |  |  | N7,200,000 | <5OM |  | Plan |  | Post | 6/1/20 | 13/1/20 | 27/1/20 | 11/2/20 | 18/2/20 | 25/2/20 | 9/3/20 | Plan | 8/4/20 | 10/4/20 | 7200000 | 9/5/20 | 23/5/20 | 14/6/20
2 | [8 empty] | Actual | [9 empty] | Actual
3 |  | MIS/NCS- F/002/2O |  |  |  | N800,000.00 | <5OM |  | Plan |  | POST | 11th /2/20 | 18/2/20 | 25/2/20 | 9th /3/20 | 15/3/20 | 22/3/20 | 29/3/20 | Plan | 28/4/20 | 30/4/20 | N800,000.00 | 29/5/20 | 12th/6/2020 | 26th/6/20
4 | [8 empty] | Actual | [9 empty] | Actual
5 | Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
6 |  | Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
7 | General Office Maintenance per quarter@ N1,573,049.75 Per Qtre eg repair of faulty doors lock, Electrical appliances , fittings, energy saving bulbs etc | MIS/NCS -F/001/21 |  |  | 4 | N6,292,199.00 | <5OM |  | Plan |  | POST | 11th/1/2022 |  |  | 25/1/2022 | 28/1/22 | 29/1/22 |  | Plan | 10th/2/22 |  |  | 17/2/22 |  | 28/2/22 | 5th/3/22
8 | [8 empty] | Actual | [9 empty] | Actual
| Electrical Appliances & Fittings on quarterly basis @ N83,887.50 per qtre | MIS/NCS -F/002/21 |  |  | 4 | N335,550.00 | <5OM |  | Plan |  | POST | 13/1/21 |  |  | 27/1/21 | 30/1/21 | 3rd/2/21 |  | Plan | 18/2/21 |  | N335,550.00 | 25/2/21 |  | 2nd/3/21
[9 empty] | Actual | [9 empty] | Actual
| Procurement of 4Nos of Energy saving bulbs @ 83,887.50 | MIS/NCS -F/003/21 |  |  | 4 | N335,550.00 | <5OM |  | Plan |  | POST | 18th/1/21 |  |  | 4th /2/2021 | 6th/2/21 | 8th/2/21 |  | Plan | 22/2/21 |  | N335,550.00 | 1st 3/21 |  | 8th/3/2021
[9 empty] | Actual | [9 empty] | Actual
| Procurement and maintenance of Short Flouricent Tubes per quarter @ N83,887.50 Per Qtre | MIS/NCS -F/004/21 |  |  | 4 | N335,550.00 | <5OM |  | Plan |  | POST | 21/1/21 |  |  | 3rd/2/21 | 5th/2/21 | 9th/2/2021 |  | Plan | 23/2/21 |  | N335,550.00 | 2nd/3/21 |  | 9th/3/21
[9 empty] | Actual | [9 empty] | Actual
| Office Maintenance per quarter@ N83,887.50 Per Qtre | MIS/NCS -F/005/21 |  |  | 4 | N335,550.00 | <5OM |  | Plan |  | POST | 25th/1/21 |  |  | 8th/2/21 | 10th/2/2021 | 15th/2/21 |  | Plan | 1st/3/21 |  | N335,550.00 | 8th/3/21 |  | 15th/3/21
[9 empty] | Actual | [9 empty] | Actual
| Motor Vehicle Repair & Maintenance : Servicing of 3 Nos. of Vehicles,Procurement of 4 tyres each for 3 vehicles and Renewal of the DG Vehicle particulars | MIS/NCS -F/002/20 |  |  | 4 | N1,578,307.00 | <5OM |  | Plan |  | POST | 1st /2/22 |  |  | 9th/2/22 | 11th/2/22 | 16th/2/22 |  | Plan | 2nd/3/22 |  |  | 9th/3/22 |  | 16th/3/22 | 23/3/22
[9 empty] | Actual | [9 empty] | Actual
| Renewal of Vehicle Licences and Road worthines for Vehicles including the DG`s Official Vehicles | MIS/NCS -F/007/21 |  |  |  | N100,000.00 | <5OM |  | Plan |  | POST | 2nd/2/21 |  |  | 10th/2/21 | 12th/2/21 | 17th/2/21 |  | Plan | 3rd/3/21 |  | N100,000 | 10th/3/2021 |  | 17th/3/21
[9 empty] | Actual | [9 empty] | Actual
| Procurement of 4 Nos. of Tyres each for 5 vehicles @ N40,000 each | MIS/NCS -F/008/21 |  |  | 20 | N800,000.00 | <5OM |  | Plan |  | POST | 3rd/2/21 |  |  | 11th/2/21 | 15th/2/21 | 18th/2/21 |  | Plan | 4th/3/21 |  | N800,000 | 11th/3/21 |  | 18th/3/21
[9 empty] | Actual | [9 empty] | Actual
| Payment to 6 Staff of a Private Security Outfit and 1 Security Supervisor of same Private security firm | MIS/NCS -F/003/22 |  |  | 7 | N3,881,700 | <5OM |  | Plan |  | POST | 8th/3/22 |  |  | 15th/3/22 | 17th/3/22 | 22nd/2/22 |  | Plan | 8th/3/22 |  |  | 15/3/22 |  | 22/3/22 | 29/3/22
[9 empty] | Actual | [9 empty] | Actual
| Private Engagement of Additional Nos.of 2 Security Superevisors for 24 Hours Services @ N39,000 X 12 | MIS/NCS -F/010/21 |  |  | 2 | N936,000.00 | <5OM |  | Plan |  | POST | 5th/4/21 |  |  | 12th/4/21 | 14th/4/21 | 19th/4/21 |  | Plan | 3rd/5/21 |  | N936,000.00 | 10th/5/21 |  | 17th/5/21
[9 empty] | Actual | [9 empty] | Actual
| Publicity of centres activities,Adverts of trg. Programs,Video coverage,Design of momentos | MIS/NCS -F/008/20 |  |  |  |  | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 |  | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
|  | MIS/NCS -F/008/20 |  |  |  |  | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 |  | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
| Private Engagement of 9Nos of Cleaning Services @ N32,500 X 12 | MIS/NCS -F/011/21 |  |  | 9 | N3,510,000.00 | <5OM |  | Plan |  | POST | 3rd/5/21 |  |  | 10th/5/21 | 12th/5/21 | 17th/5/21 |  | Plan | 31st/5/21 |  | N3,510,000.00 | 7th/6/21 |  | 14th/6/21
[9 empty] | Actual | [9 empty] | Actual
| Private Engagement of 1Nos of Cleaner Supervisor @ N39,000 X 12 | MIS/NCS -F/012/21 |  |  | 1 | N468,000.00 | <5OM |  | Plan |  | POST | 1st/6/21 |  |  | 8th/6/21 | 10th/6/21 | 15th/6/21 |  | Plan | 28th/6/21 |  | N468,000.00 | 5th/7/21 |  | 12th/7/21
[9 empty] | Actual | [9 empty] | Actual
| Private Engagement of 2Nos of Guardners@ N32,500 X 12 | MIS/NCS -F/013/21 |  |  | 2 | N780,000.00 | <5OM |  | Plan |  | POST | 10th/5/21 |  |  | 17th/5/21 | 19th/5/21 | 25th/5/21 |  | Plan | 7th/6/21 |  | N780,000.00 | 14th/7/21 |  | 21st/7/21
[9 empty] | Actual | [9 empty] | Actual
| Private Engagement of 1Nos of Guardner Supervisor@ N39,000 X 12 | MIS/NCS -F/014/21 |  |  | 1 | N468,000.00 | <5OM |  | Plan |  | POST | 5th/7/21 |  |  | 12th/7/21 | 14th/7/21 | 20th/7/21 |  | Plan | 2nd/8/21 |  | N468,000.00 | 9th/8/21 |  | 16th/8/21
[9 empty] | Actual | [9 empty] | Actual
| Payment of Agreement Fee on Maintenance , servicing of 2 Generator sets, 250 KVA and 100 KVA Generators and Payment of maintenance for biometrics on CCTV Camera, time manager etc | MIS/NCS -F/004/21 |  |  | 2 | N1,020,747.54 | <5OM |  | Plan |  | POST | 2nd/6/22 |  |  | 9th/6/22 | 11th/6/22 | 17th/6/22 |  | Plan | 30th/6/22 |  |  | 7th/7/22 |  | 14th/7/22 | 21/7/22
[9 empty] | Actual | [9 empty] | Actual
| Payment to 6 Nos of Cleaners and 1 supervisor for 12 months | MIS/NCS -F/005/21 |  |  | 7 | N3,881,700 | <5OM |  | Plan |  | POST | 2nd/8/21 |  |  | 9th/8/21 | 11th/8/21 | 17th/8/21 |  | Plan | 30th/8/22 |  |  | 6th/9/22 |  | 13th/9/22 | 20/9/22
[9 empty] | Actual | [9 empty] | Actual
| Payment to 2 Nos. of Gardners and 1 Supervisor for 12 Months | MIS/NCS -F/006/22 |  |  | 4 | N1,701,600.00 | <5OM |  | Plan |  | POST | 3rd/9/22 |  |  | 10th/9/22 | 12th/8/22 | 19th/9/22 |  | Plan | 30th/9/22 |  |  | 7th/10/22 |  | 13th/10/22 | 20/10/22
[9 empty] | Actual | [9 empty] | Actual
| FUMIGATION Fumigation of the office @ 200,000 per quarter x 4qtrs | MIS/NCS -F/007/22 |  |  | 4 | N800,000.00 | <5OM |  | Plan |  | POST | 1st/9/22 |  |  | 8th/9/22 | 10th/8/22 | 17th/9/22 |  | Plan | 29th/9/22 |  |  | 5th/10/22 |  | 11th/10/22 | 18th/10/22
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST | 10th/5/21 |  |  | 17th/5/21 | 19th/5/21 | 25th/5/21 |  | Plan | 7th/6/21 |  | N22,000,000.00 | 14th/6/21 |  | 21st/6/21
[9 empty] | Actual | [9 empty] | Actual
| 2nd Phase of digitizing all records and document into electronic format for archive purpose, commercial book scanner, Economic value, scanning and imaging software, archiving software | MIS/NCS -F/018/22 |  |  |  | N5,000,000.00 | <5OM |  | Plan |  | POST | 1st/9/21 |  |  | 8th/9/21 | 10th/8/21 | 17th/9/21 |  | Plan | 29th/9/21 |  | N1,000,000.00 | 5th/10/21 |  | 11th/10/21
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST | 10th/5/21 |  |  | 17th/5/21 | 19th/5/21 | 25th/5/21 |  | Plan | 7th/6/21 |  | N22,000,000.00 | 14th/6/21 |  | 21st/6/21
[9 empty] | Actual | [9 empty] | Actual
|  | MIS/NCS -F/018/21 |  |  |  | N15,000,000.00 | <5OM |  | Plan |  | POST | 10th/5/21 |  |  | 17th/5/21 | 19th/5/21 | 25th/5/21 |  | Plan | 7th/6/21 |  | N22,000,000.00 | 14th/6/21 |  | 21st/6/21
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST | 1st/9/21 |  |  | 8th/9/21 | 10th/8/21 | 17th/9/21 |  | Plan | 29th/9/21 |  | N1,000,000.00 | 5th/10/21 |  | 11th/10/21
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST | 10th/5/21 |  |  | 17th/5/21 | 19th/5/21 | 25th/5/21 |  | Plan | 7th/6/21 |  | N22,000,000.00 | 14th/6/21 |  | 21st/6/21
[9 empty] | Actual | [9 empty] | Actual
|  | MIS/NCS -F/019/21 |  |  |  |  | <5OM |  | Plan |  | POST | [7 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
|  | MIS/NCS -F/020/21 |  |  |  |  | <5OM |  | Plan |  | POST | [7 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
|  | MIS/NCS -F/021/21 |  |  |  |  | <5OM |  | Plan |  | POST | [7 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual
[7 empty] | <5OM |  | Plan |  | POST |  |  | 20/4/20 | 7th/5/20 | 15th/5/20 | 22nd /5/20 | 6th/6/20 | Plan | 5th/7/20 | 7th/7/20 | N2,400,000.00 | 6th/8/20 | 20th/8/20 | 4th/9/20
[9 empty] | Actual | [9 empty] | Actual

## CONSULTANCY
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: INFORMATION AND STRATEGY
BUDGET YEAR: 2020
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Production of Weekly Weekly Grassroot Television Programme (Community Feedback) | MIS/S/SS/001/20 | SSS |  | N2,400,000.00 | POST | Plan | 23/1/20 |  | 30/1/20 |  |  | 6/2/20 | 27/2/20 | [5 empty] | 25/3/20 | 27/3/20 | N2.4M | 3/4/20 | 17/4/20 | 1/5/20 | 8/5/20 | 15/5/20
Actual
2 | Weekly Production of " O Kaju e" Programme on Radio | MIS/S/SS/002/20 | SSS |  | N2,400,000.00 | POST | Plan | 13/1/20 |  | 20/1/20 |  |  | 3/2/20 | 24/2/20 | [5 empty] | 18/3/20 | 20/3/20 | N2.4M | 27/3/20 | 10/4/20 | 30/4/20 | 14/5/20 | 28/5/20
Actual
3 | Mr Goveror`s Media Parley | MIS/S/SS/003/20 | SSS |  | N3,500,000.00 | POST | Plan | 3/1/20 |  | 10/1/20 |  |  | 24/1/20 | 14/2/20 | [5 empty] | 26/2/20 | 28/2/20 | N3.5M | 6/3/20 | 20/3/20 | 10/4/20 | 24/4/20 | 8/5/20
Actual
4 | Quarterly Media Parly with Editors @ N5,000,000.00 per Quarter | MIS/S/SS/004/20 | SSS |  | N20,000,000.00 | PRIOR | Plan | 3/2/20 | 10/2/20 | 17/2/20 | 2/3/20 | 17/3/20 | 24/3/20 | 14/4/20 | 21/4/20 | 28/4/20 | 5/5/20 | 19/5/20 | 9/6/20 | 23/6/20 | 25/6/20 | N20M | 2/7/20 | 16/7/20 | 30/7/20 | 6/8/20 | 20/8/20
Actual
1 | Production of 30 Documentaries on the THEMES Agenda@N1,500,000.00 X 30 Documentaries | MIS/S/SS/005/20 | SSS |  | N45,000,000 | PRIOR | Plan | 3/1/20 | 10/1/20 | 17/1/20 | 31/1/20 | 14/2/20 | 28/2/20 | 19/3/20 | 26/3/20 | 2/4/20 | 9/4/20 | 23/4/20 | 30/4/20 | 18/5/20 | 20/5/20 | N45M | 27/5/20 | 10/6/20 | 7/7/20 | 14/7/20 | 21/7/20
Actual
6 | Monthly Sponsorship of 5 Radio Programmes @ N1,400,000.00 X 12Months | MIS/S/SS/006/20 | SSS |  | N16,800,000.00 | PRIOR | Plan | 2/1/20 | 9/1/20 | 16/1/20 | 30/1/20 | 13/2/20 | 27/2/20 | 18/3/20 | 25/3/20 | 1/4/20 | 8/4/20 | 22/4/20 | 29/4/20 | 13/5/20 | 15/5/20 | N16.8M | 22/5/20 | 5/6/20 | 26/6/20 | 10/7/20 | 17/7/20
Actual
7 | Monthly Sponsorship of 5 Television Programmes @ N4,000,000.00 X 12Months | MIS/S/SS/007/20 | SSS |  | N48,000,000.00 | PRIOR | Plan | 2/3/20 | 9/3/20 | 23/3/20 | 6/4/20 | 20/4/20 | 27/4/20 | 15/5/20 | 29/5/20 | 5/6/20 | 12/6/20 | 26/6/20 | 9/7/20 | 29/7/20 | 31/7/20 | N48M | 10/8/20 | 28/8/20 | 21/9/20 | 28/9/20 | 5/10/20
Actual
2 | Production of 10 Nos. of short Documentary Drama @ N5,000,000.00 | MIS/S/SS/008/20 | SSS |  | N50,000,000.00 | PRIOR | Plan | 9/3/20 | 23/3/20 | 30/3/20 | 20/4/20 | 27/4/20 | 11/5/20 | 25/5/20 | 1/6/20 | 15/6/20 | 22/6/20 | 6/7/20 | 20/7/20 | 4/8/20 | 6/8/20 | N50M | 13/8/20 | 27/8/20 | 17/9/20 | 24/9/20 | 8/10/20
Actual
3 | Placement of Documentaries on selected TV Stations: LTV, CHANNELS, TVC,STV & MITV @N4M each x 5 | MIS/S/SS/009/20 | SSS |  | N20,000,000.00 | PRIOR | Plan | 6/1/20 | 13/1/20 | 20/1/20 | 3/2/20 | 17/2/20 | 24/2/20 | 12/3/20 | 26/3/20 | 2/4/20 | 9/4/20 | 16/4/20 | 30/4/20 | 20/5/20 | 22/5/20 | N20M | 29/5/20 | 12/6/20 | 26/6/20 | 3/7/20 | 17/7/20
Actual
10 | Advocacy / Media Campaign support for 25 MDAs @N10 M each x 25 | MIS/S/SS/010/20 | SSS |  | N250,000,000.00 | PRIOR | Plan | 20/1/20 | 27/1/20 | 3/2/20 | 17/2/20 | 24/2/20 | 2/3/20 | 23/3/20 | 30/3/20 | 6/4/20 | 13/4/20 | 27/4/20 | 11/5/20 | 18/5/20 | 20/5/20 | N250M | 27/5/20 | 10/6/20 | 1/7/20 | 15/7/20 | 22/7/20
Actual
11 | Production / Airing of State on Focus @N4 M per Quarter x 4 | MIS/S/SS/011/20 | SSS |  | N16,000,000.00 | PRIOR | Plan | 9/3/20 | 16/3/20 | 23/3/20 | 6/4/20 | 13/4/20 | 20/4/20 | 4/5/20 | 11/5/20 | 18/5/20 | 25/5/20 | 9/6/20 | 23/6/20 | 7/7/20 | 9/7/20 | N16M | 16/7/20 | 30/7/20 | 12/8/20 | 19/8/20 | 26/8/20
Actual
4 | Settlement of 4 years areas @N16,000,000.00 X 4 | MIS/S/SS/012/20 | SSS |  | N64,000,000.00 | PRIOR | Plan | 25/3/20 | 1/4/20 | 8/4/20 | 22/4/20 | 29/4/20 | 12/5/20 | 2/6/20 | 9/6/20 | 16/6/20 | 30/6/20 | 7/7/20 | 14/7/20 | 28/7/20 | 30/7/20 | N64M | 6/8/20 | 20/8/20 | 10/9/20 | 24/9/20 | 8/10/20
Actual
4 | Awareness Campaign to promote better attitude from lagosians on the environment and traffic laws(Drama Skit 20 local Govt Areas) @N1,061,000 X 20 | MIS/S/SS/013/20 | SSS |  | N21,220,000.00 | PRIOR | Plan | 20/3/20 | 27/3/20 | 3/4/20 | 17/4/20 | 24/4/20 | 7/5/20 | 18/6/20 | 25/6/20 | 9/7/20 | 16/7/20 | 30/7/20 | 6/8/20 | 26/8/20 | 28/8/20 | N21.220M | 4/9/20 | 18/9/20 | 15/10/20 | 22/10/20 | 29/10/20
Actual
14 | Production of Video Version of Campaign to promote better attitude from Lagosians | MIS/S/SS/014/20 | SSS |  | N2,631,000.00 | POST | Plan | 3/1/20 |  | 10/1/20 |  |  | 24/1/20 | 14/2/20 | [5 empty] | 26/2/20 | 28/2/20 | N2.631M | 6/3/20 | 20/3/20 | 10/4/20 | 24/4/20 | 8/5/20
Actual
15 | Mass Dubbing of the Video ment to Campaign and promote better attitude from Lagosians | MIS/S/SS/015/20 | SSS |  | N6,800,000.00 | PRIOR | Plan | 6/4/20 | 20/4/20 | 27/4/20 | 4/5/20 | 11/5/20 | 25/5/20 | 15/6/20 | 22/6/20 | 29/6/20 | 6/7/20 | 13/7/20 | 20/7/20 | 11/8/20 | 13/8/20 | N6.8M | 20/8/20 | 3/9/20 | 24/9/20 | 1/10/20 | 15/10/20
Actual
16 | Social Media Engagement withOn-line Editors / Publishers | MIS/S/SS/016/20 | SSS |  | N24,916,629.00 | PRIOR | Plan | 7/4/20 | 21/4/20 | 28/4/20 | 12/5/20 | 19/5/20 | 2/6/20 | 30/6/20 | 7/7/20 | 14/7/20 | 21/7/20 | 4/8/20 | 18/8/20 | 15/9/20 | 17/9/20 | N24.916.629M | 24/9/20 | 8/10/20 | 29/10/20 | 12/11/20 | 26/11/20
Actual
17 | Specialized Report writing in majour National News Papers 20 Columnists @ N250,000.00 | MIS/S/SS/017/20 | SSS |  | N5,000,000.00 | PRIOR | Plan | 1/6/20 | 15/6/20 | 22/6/20 | 6/7/20 | 20/7/20 | 27/7/20 | 17/8/20 | 31/8/20 | 7/9/20 | 14/9/20 | 28/9/20 | 5/10/20 | 26/10/20 | 28/10/20 | N5M | 4/11/20 | 18/11/20 | 9/12/20 | 16/12/20 | 23/12/20
Actual
18 | Quarterly Production of TV Prog. On Govt. Topical issues / Activities for STATE ON FOCUS airing on LTV Every Qtr@ N500,000.00 X 4 | MIS/S/SS/018/20 | SSS |  | N2,000,000.00 | POST | Plan | 3/4/20 |  | 10/4/20 |  |  | 24/4/20 | 22/5/20 | [5 empty] | 22/6/20 | 24/6/20 | N2M | 1/7/20 | 15/7/20 | 12/8/20 | 26/8/20 | 9/9/20
Actual
19 | Consultancy fees for web & social media consultant | MIS/S/SS/019/20 | SSS |  | N2,227,000.00 | POST | Plan | 4/5/20 |  | 11/5/20 |  |  | 25/5/20 | 15/6/20 | [5 empty] | 13/7/20 | 15/7/20 | N2.227M | 22/7/20 | 5/8/20 | 2/9/20 | 16/9/20 | 30/9/20
Actual
20 | 30 Minutes Video Documentary on activities of the State Govt. Admin. | MIS/S/SS/020/20 | SSS |  | N6,000,000.00 | PRIOR | Plan | 1/5/20 | 15/5/20 | 22/5/20 | 19/6/20 | 3/7/20 | 17/7/20 | 7/8/20 | 21/8/20 | 28/8/20 | 4/9/20 | 18/9/20 | 2/10/20 | 27/10/20 | 29/10/20 | N6M | 5/11/20 | 19/11/20 | 3/12/20 | 17/12/20 | 31/12/20
Actual
21 | Broadcast of Documentary on 3 TV Stations | MIS/S/SS/021/20 | SSS |  | N4,416,831.00 | POST | Plan | 4/6/20 |  | 11/6/20 |  |  | 25/6/20 | 30/7/20 | [5 empty] | 26/8/20 | 28/8/20 | N4.416.831M | 4/9/20 | 18/9/20 | 9/10/20 | 23/10/20 | 30/10/20
Actual
22 | Production of Power Point presentation on Govt. Programme and Activities on quarterly basis @N250,000.00 X 4 | MIS/S/SS/022/20 | SSS |  | N1,000,000.00 | POST | Plan | 4/5/20 |  | 11/5/20 |  |  | 25/5/20 | 15/6/20 | [5 empty] | 13/7/20 | 15/7/20 | N1M | 22/7/20 | 5/8/20 | 2/9/20 | 16/9/20 | 30/9/20
Actual
23 | Advertisement of Govt Policies in Newspapers & Magazines | MIS/S/SS/023/20 | SSS |  | N750,000.00 | POST | Plan | 23/1/20 |  | 30/1/20 |  |  | 6/2/20 | 27/2/20 | [5 empty] | 25/3/20 | 27/3/20 | N750K | 3/4/20 | 17/4/20 | 1/5/20 | 8/5/20 | 15/5/20
Actual
24 | Production of 20 Radio Jinggles @ N50000.00 each | MIS/S/SS/024/20 | SSS |  | N1,000,000.00 | POST | Plan | 13/1/20 |  | 20/1/20 |  |  | 3/2/20 | 24/2/20 | [5 empty] | 18/3/20 | 20/3/20 | N1M | 27/3/20 | 10/4/20 | 30/4/20 | 14/5/20 | 28/5/20
Actual
25 | Placement of 25 slots of Radio Jinggles@N20,000.00 per slot spread across 5 Radio Stations | MIS/S/SS/025/20 | SSS |  | N500,000.00 | POST | Plan | 3/4/20 |  | 10/4/20 |  |  | 24/4/20 | 22/5/20 | [5 empty] | 22/6/20 | 24/6/20 | N500K | 1/7/20 | 15/7/20 | 12/8/20 | 26/8/20 | 9/9/20
Actual
26 | Public Relations on behalf of the Government by HC | MIS/S/SS/026/20 | SSS |  | N2,000,000.00 | POST | Plan | 4/3/20 |  | 11/3/20 |  |  | 25/3/20 | 15/4/20 | [5 empty] | 13/5/20 | 15/5/20 | N2M | 22/6/20 | 6/7/20 | 4/8/20 | 18/8/20 | 25/8/20
Actual
27 | Quarterly Electronic Media Stakeholder Meeting | MIS/S/SS/027/20 | SSS |  | N400,000.00 | POST | Plan | 4/5/20 |  | 11/5/20 |  |  | 25/5/20 | 15/6/20 | [5 empty] | 13/7/20 | 15/7/20 | N400K | 22/7/20 | 5/8/20 | 2/9/20 | 16/9/20 | 30/9/20
Actual
28 | Media Briefing | MIS/S/SS/028/20 | SSS |  | N400,000.00 | POST | Plan | 4/6/20 |  | 11/6/20 |  |  | 25/6/20 | 15/7/20 | [5 empty] | 17/8/20 | 19/8/20 | N400K | 26/8/20 | 9/9/20 | 30/9/20 | 14/10/20 | 28/10/20
Actual
29 | Production of special documentary in local languages on (THEMES) Transportation | MIS/S/SS/029/20 |  |  |  |  | Plan
Actual
| Production of special documentary in local languages on (THEMES) Environment | MIS/S/SS/030/20 | SSS |  |  |  | Plan
Actual
| Production of special documentary in local languages on (THEMES) Technology | MIS/S/SS/031/20 | SSS |  |  |  | Plan
Actual
| Production of special documentary in local languages on (THEMES) Tourism | MIS/S/SS/032/20 | SSS |  |  |  | Plan
Actual
| Procurement of 16 Nos. of professional books published by Media professionals |  | SSS |  |  |  | Plan
Actual
| Conducting Annual Survey (Workstudy of the Activities of the Ministry and its allied Agencies for the assessment & evaluation of services) | [5 empty] | Plan
Actual
| Production of special documentary in local languages on (THEMES) Transportation |  |  |  | N500,000.00 | Post | Plan | 2020-02-07 |  | 2020-09-07 |  |  | 23/7/20 | 14/8/20 | [5 empty] | 13/9/20 | 15/9/20 | N500,000 | 22/9/20 | 2020-06-10 | 20/10/20 | 27/10/20 | 2020-04-11
Actual
| Production of special documentary in local languages on (THEMES) Environment |  |  |  | N500,000.00 | Post | Plan | 2020-08-07 |  | 15/7/20 |  |  | 22/7/20 | 13/8/20 | [5 empty] | 2020-12-09 | 14/9/20 | N500,000 | 21/9/20 | 2020-05-10 | 19/10/20 | 26/10/20 | 2020-03-11
Actual
| Production of special documentary in local languages on (THEMES) Technology |  |  |  | N500,000.00 | Post | Plan | 14/7/20 |  | 21/7/20 |  |  | 28/7/20 | 19/8/20 | [5 empty] | 18/9/20 | 20/9/20 | N500,000 | 27/9/20 | 2020-11-10 | 25/10/20 | 2020-02-11 | 2020-09-11
Actual
| Production of special documentary in local languages on (THEMES) Tourism |  |  |  | N500,000.00 | Post | Plan | 19/7/20 |  | 26/7/20 |  |  | 2020-03-08 | 24/8/20 | [5 empty] | 23/9/20 | 25/9/20 | N500,000 | 2020-02-10 | 16/10/20 | 30/10/20 | 2020-07-11 | 14/11/20
Actual
5 | Management & Junior Staff Retreat |  |  |  | N6,000,000.00 |  | Plan | 2020-07-07 |  | 14/7/20 |  |  | 28/7/20 | 2020-12-08 | [5 empty] | 2020-11-09 | 13/9/20 | N6,000,000.00 | 20/9/20 | 2020-04-10 | 18/10/20 | 25/10/20 | 2020-03-11
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## GOODS
| PROCUREMENT PLAN FOR GOODS. |  |  |  |  | GOODS
MINISTRY/AGENCY: LAGOS STATE RECORDS AND ARCHIVES BUREAU
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
|  | Package Number | [8 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Diesel fuel for Generators (250 KVA & 100 KVA Generators) and other Contigencies | LASRAB/G -F/NS/001/22 |  | 12 | 1500000 | < N50M | DC |  | PRIOR | Plan | 06/01/22 |  | 2022-01-20 | 2022-03-02 | 2022-03-16 |  | 2022-04-27 | 2022-04-29 |  | 2022-05-06 | 2022-05-20 | 2022-06-17 | 23/6/22 | 30/6/22
Actual
2 | Procurement of News Papers & Magazines , | MIS/G/NS/002/20 |  |  | N1,500,000.00 | < N50M | NS |  | POST | Plan | 2020-01-02 |  | 2020-01-09 | 2020-02-20 | 2020-02-27 |  | 2020-03-25 | 2020-03-27 | N1,500,000.00 | 03/04/2020 | 17/04/2020 | 2020-05-22
Actual
2 | Procurement of Hardware and Software maintenance and upgrading of LASRAB offices | LASRAB/G -F/NS/002/22 |  |  | N400,000.00 | < N50M | NS |  | POST | Plan | 2021-02-03 |  | 2021-02-17 | 2020-03-16 | 2021-03-30 |  | 2021-04-27 | 2021-04-29 | N89,625 | 2022-06-05 | 2022-05-20 | 2022-06-17 | 24/6/22 | 31/6/22 | E3
Actual
4 | Servicing of Management Meetings per quarter@ N375,000.00 per Quarter | MIS/G/NS/004/2O |  | 4 | N1,500,000.00 | < N50M | NS |  | POST | Plan | 2020-04-03 |  | 2020-04-10 | 2020-05-08 | 2020-05-22 |  | 2020-06-16 | 2020-06-18 | N1,500,000.00 | 2020-06-25 | 2020-07-09 | 06/08//2020
Actual
3 | Procurement of Records processing consumables Unit materials / expenses | LASRAB/G /NS/003/22 |  |  | 200000 | < N50M | NS |  | POST | Plan | 2022-05-04 |  | 2022-05-18 | 2022-06-29 | 2022-07-13 |  | 2022-08-10 | 2022-08-12 |  | 2022-08-19 | 2022-09-02 | 2022-09-30 | 2022-06-10 | 13/10/22
Actual
6 | Monthly Staff Audit @N41,666.66 per month | MIS/G/NS/006/2O |  | 12 | N500,000.00 | < N50M |  |  | POST | Plan | 2020-05-02 |  | 2020-12-02 | 26/2/20 | 2020-03-03 |  | 2020-02-04 | 2020-04-04 | N500,000.00 | 2020-11-04 | 18/4/20 | 2020-02-05
Actual
7 | Procurement of Audit Unit expenses per quarter | MIS/G/NS/007/2O |  |  | N500,000.00 | < N50M |  |  | POST | Plan | 2020-07-02 |  | 2020-04-24 | 2020-05-08 | 2020-06-05 |  | 2020-03-04 | 2020-05-04 | N500,000.00 | 2020-05-11 | 2020-05-25 | 2020-06-22
Actual
8 | Procurement of ICT Unit expenses N250,000.00 per quarter | MIS/G/NS/008/2O |  |  | N1,000,000.00 | < N50M |  |  | POST | Plan | 2020-02-07 |  | 2020-02-14 | 2020-03-06 | 2020-04-20 |  | 2020-04-15 | 2020-04-17 | N1,000,000.00 | 2020-04-24 | 2020-05-08 | 2020-06-05
Actual
9 | Procurement of Procurement Unit expenses per quarter | MIS/G/NS/009/2O |  |  | N1,500,000.00 | < N50M | NS |  | POST | Plan | 2020-02-14 |  | 2020-02-21 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N1,500,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-10
Actual
10 | Procurement of Procurement Unit expenses per quarter | MIS/G/NS/010/2O |  |  | N1,500,000.00 | < N50M |  |  | POST | Plan | 2020-02-03 |  | 2020-02-10 | 2020-03-23 | 2020-03-30 |  | 2020-04-20 | 2020-04-22 | N1,500,000.00 | 2020-04-29 | 2020-05-06 | 2020-06-27
Actual
11 | [9 empty] | Plan
Actual
12 | Quarterly Strategy Centre Expenses | MIS/G/NS/011/2O |  | 4 | N200,000.00 | < N50M |  |  | POST | Plan | 2020-02-05 |  | 2020-02-12 | 2020-03-11 | 2020-03-25 |  | 2020-04-22 | 2020-04-24 | N200,000.00 | 2020-05-01 | 2020-05-08 | 2020-06-05
Actual
13 | Quarterly Research Work/ FeedbaCK Mechanism | MIS/G/NS/012/2O |  | 4 | N200,000.00 | < N50M |  |  | POST | Plan | 2020-02-04 |  | 2020-02-11 | 2020-03-24 | 2020-03-31 |  | 2020-04-28 | 2020-04-30 | N200,000.00 | 2020-05-07 | 2020-05-14 | 2020-05-28
Actual
14 | Quarterly Content Analysis | MIS/G/NS/013/2O |  | 4 | N400,000.00 | < N50M |  |  | POST | Plan | 2020-03-04 |  | 2020-03-11 | 2020-04-08 | 2020-04-15 |  | 2020-04-29 | 2020-05-01 | N400,000.00 | 2020-05-08 | 2020-05-15 | 2020-05-29
Actual
4 | Procurement of Stationary items eg Cartons of A4 Papers, Cartons of fullscalp, Photocopier Toner, printer toner, Hard cover notebook, movement registers, biro, teppex and others | LASRAB/G /NS/004/22 |  |  | N867,531.00 | < N50M | NS |  | POST | Plan | 2022-01-07 |  | 2022-01-14 | 2022-01-28 | 2022-02-11 |  | 2022-02-25 | 2022-02-27 |  | 2022-03-05 | 2022-03-19 | 2022-04-16 | 23/4/22 | 30/4/22
Actual
16 | Quarterly Adhoc Committee Meetings | MIS/G/NS/015/2O |  | 4 | N250,000.00 | < N50M |  |  | POST | Plan | 2020-01-06 |  | 2020-01-13 | 2020-01-27 | 2020-02-10 |  | 2020-02-24 | 2020-02-26 | N250,000.00 | 2020-03-04 | 2020-03-18 | 2020-04-15
Actual
17 | Procurement of 244 Packets of Biro @357.00 | MIS/G -F/NS/005/21 |  | 244 | 87108 | < N50M | NS |  | POST | Plan | 2021-01-13 |  | 2021-01-27 | 2021-03-09 | 2021-03-23 |  | 2021-04-20 | 2021-04-22 | 87108 | 2021-04-29 | 2021-05-13 | 2021-05-27
Actual
18 | COWLSO Event expences | MIS/G/NS/017/2O |  |  | N750,000.00 | < N50M | NS |  | POST | Plan | 2020-01-14 |  | 2020-01-28 | 2020-03-10 | 2020-03-24 |  | 2020-04-21 | 2020-04-23 | N750,000.00 | 2020-04-30 | 2020-05-14 | 2020-05-28
Actual
19 | Production of special documentary in local languages on (THEMES) Transportation | MIS/G/NS/018/2O |  |  | N500,000.00 | < N50M |  |  | POST | Plan | 2020-02-03 |  | 2020-04-24 | 2020-05-08 | 2020-06-05 | 2020-04-24 | 2020-05-08 | 2020-06-05 | N500,000.00 | 2020-04-29 | 2020-05-13 | 2020-06-10
Actual
20 | Production of special documentary in local languages on (THEMES) Environment | MIS/G/NS/019/2O |  |  | N500,000.00 |  |  |  | POST | Plan | 2020-02-05 |  | 2020-02-12 | 2020-03-25 | 2020-04-08 |  | 2020-04-22 | 2020-04-24 | N500,000.00 | 2020-05-01 | 2020-05-15 | 2020-06-12
Actual
21 | Production of special documentary in local languages on (THEMES) Technology | MIS/G/NS/020/2O |  |  | N500,000.00 |  |  |  | POST | Plan | 2020-02-07 |  | 2020-02-14 | 2020-03-06 | 2020-04-20 |  | 2020-04-15 | 2020-04-17 | N500,000.00 | 2020-04-24 | 2020-05-08 | 2020-06-05
Actual
22 | Production of special documentary in local languages on (THEMES) Tourism | MIS/G/NS/021/2O |  |  | N500,000.00 |  |  |  | POST | Plan | 2020-02-17 |  | 2020-02-24 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N500,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-03
Actual
23 | Printing of43 Rims of A4 Letter headed paper @N3,472.00 | MIS/G -F/NS/006/21 |  | 43 | 149363 | < N50M | NS |  | POST | Plan | 2021-03-02 |  | 2021-03-09 | 2021-03-30 | 2021-04-13 |  | 2021-05-04 | 2021-05-06 | N149,363 | 2021-05-13 | 2021-05-27 | 2021-06-24
Actual
24 | Procurement of 6 Nos. of Scientific Calculators 12 Dgits @N3,350.00 | MIS/G -F/NS/007/21 |  | 6 | 21214 | < N50M | NS |  | POST | Plan | 2021-03-03 |  | 2021-03-10 | 2021-03-31 | 2021-04-14 |  | 2021-05-05 | 2021-05-07 | N21,214 | 2021-05-14 | 2021-05-28 | 2021-06-25
Actual
25 | Motor Vehicle Fuel Consumption for 7 Vehicles @ N658,800 per qtre | MIS/G -F/NS/008/21 |  | 4 | N2,635,200.00 | < N50M | NS |  | POST | Plan | 2021-03-05 |  | 2021-03-12 | 2021-03-02 | 2021-04-16 |  | 2021-05-13 | 2021-05-15 | N2,635,200 | 2021-05-22 | 2021-06-04 | 2021-07-02
Actual
5 | Procurement of fuel & Break oil for the Agency Vehicles | LASRAB/G /NS/005/22 |  |  | N1,276,121.00 | < N50M | NS |  | POST | Plan | 2022-03-09 |  | 2022-03-23 | 2022-05-04 | 2022-05-18 |  | 2022-06-15 | 2022-06-17 |  | 2022-06-24 | 2022-07-08 | 2022-07-29 | 2022-08-06 | 13/8/22
Actual
26 | Procurement of Fuel for 2 nos. Generators Set (250KVA & 100KVA ) | MIS/G -F/NS/009/21 |  | 4 | N1,500,000.00 | < N50M | NS |  | POST | Plan | 2021-03-09 |  | 2021-03-23 | 2021-05-04 | 2021-05-18 |  | 2021-06-15 | 2021-06-17 | N7,700,000 | 2021-06-24 | 2021-07-08 | 2021-07-29
Actual
28 | Conservation of archives, books and artifacts in the repositories, reference library and mini- museum against insects, pests and environmental hazards including dehumidification of records and repair of endangered records and artefacts. | MIS/G -F/NS/011/21 |  |  | N2,400,000.00 | < N50M | NS |  | POST | Plan | 2020-04-03 |  | 2020-04-10 | 2020-05-01 | 2020-05-15 |  | 2020-06-10 | 2020-06-12 | N2,400,000.00 | 2020-07-19 | 2020-07-03 | 2020-07-31
Actual
6 | Procurement of Public Affairs Unit Materials | LASRAB/G/NS/006/22 |  |  | 200000 | < N50M | NS |  | POST | Plan | 2022-04-05 |  | 2022-04-22 | 2022-05-27 | 2022-06-10 |  | 2022-06-30 | 2022-07-02 |  | 2022-07-09 | 2022-07-23 | 2022-08-20 | 27/8/22 | 2022-03-09
Actual
7 | Procurement of Planning Unit Materials /Expences | LASRAB/G/NS/007/22 |  |  | N300,000 | < N50M | NS |  | POST | Plan | 2022-04-06 |  | 2022-04-20 | 2022-05-25 | 2022-06-08 |  | 2022-06-29 | 2022-07-01 |  | 2022-07-08 | 2022-07-22 | 2022-08-19 | 26/8/22 | 2022-03-09
Actual
31 | Procurement of Rare Books for the Reference Library, Maps, Gazettes, Publicatons, Circulars e.t.c. | MIS/G/NS/013/21 |  |  | N1,000,000.00 | < N50M | NS |  | POST | Plan | 2020-05-01 |  | 2020-04-15 | 2020-06-26 | 2020-07-10 |  | 2020-08-05 | 2020-08-07 | N1,000,000 | 2020-08-14 | 2020-08-28 | 2020-09-18
Actual
32 |  | MIS/G/NS/031/2O |  |  |  | < N50M | NS |  | POST | Plan | 2020-05-04 |  | 2020-05-11 | 2020-06-22 | 2020-07-06 |  | 2020-07-27 | 2020-07-29 | N625,000.00 | 2020-08-05 | 2020-08-19 | 2020-09-16
Actual
33 | Procurement of Protective and working Tools for the Archivists Replacement of all Fire Indicators at LASRAB House, Obsolete Panel and Installation of dedicated Water Storage for Fire Hosery | MIS/G/NS/014/21 |  |  | N7,000,000.00 | < N50M | NS |  | POST | Plan | 2020-05-13 |  | 2020-05-27 | 2020-06-24 | 2020-07-08 |  | 2020-07-22 | 2020-07-24 | N7,00 | 2020-07-31 | 2020-09-14 | 2020-09-12
Actual
8 | Procurement of Internal Audit Unit Materials / Expences | LASRAB/G/NS/008/22 |  |  | N250,000.00 | < N50M | NS |  | POST | Plan | 2022-04-08 |  | 2022-04-22 | 2022-05-20 | 2022-06-03 |  | 2022-05-04 | 2022-07-03 |  | 2022-07-10 | 2022-07-24 | 2022-08-21 | 28/8/22 | 2022-04-09
Actual
9 |  | LASRAB/G/NS/012/21 |  |  |  | < N50M | NS |  | POST | Plan | 2021-04-08 |  | 2021-04-22 | 2021-05-20 | 2021-06-03 |  | 2021-05-04 | 2021-07-03 | N800,000 | 2021-07-10 | 2021-07-24 | 2021-08-21
Actual
36 |  | MIS/G/NS/031/2O |  |  |  | < N50M | NS |  | POST | Plan | 2020-05-04 |  | 2020-05-11 | 2020-06-22 | 2020-07-06 |  | 2020-07-27 | 2020-07-29 | N625,000.00 | 2020-08-05 | 2020-08-19 | 2020-09-16
Actual
9 | Procurement of Branded T-Shirts for each officers of LASRAB and procurement of suits for 2 drivers | LASRAB/G/NS/009/22 |  | 50 | N480,000 | < N50M | NS |  | POST | Plan | 2022-05-13 |  | 2022-05-27 | 2022-06-24 | 2022-07-08 |  | 2022-07-22 | 2022-07-24 |  | 2022-07-31 | 2022-09-14 | 2022-09-28 | 2022-10-05 | 2022-10-12
Actual
38 |  | MIS/G/NS/019/21 |  |  |  | < N50M | NS |  | POST | Plan | 2021-06-23 |  | 2021-06-30 | 2021-08-11 | 2021-08-25 |  | 2021-09-22 | 2021-09-24 | N1,000,000.00 | 2021-10-01 | 2021-10-15 | 2021-11-12
Actual
39 |  | MIS/G/NS/020/21 |  |  |  | < N50M | NS |  | POST | Plan | 2021-07-01 |  | 2021-07-15 | 2021-08-26 | 2021-09-09 |  | 2021-10-07 | 2020-10-09 | N400,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-27
Actual
10 | Payment for 2 phases of survey and acquisition of record from 4 MDAs of the State interms of fumigation of records, procurement of consumables, Stationery, Record removal bags, Archive Storage bags and other related expences | LASRAB/G/NS/010/22 |  |  | 3000000 | < N50M | NS |  | POST | Plan | 2022-07-07 |  | 2022-07-21 | 2022-09-01 | 2022-09-15 |  | 2022-10-13 | 2022-10-15 |  | 2022-10-22 | 2022-11-05 | 19/11/2022 | 26/11/22 | 2022-12-03
Actual
41 |  | MIS/G/NS/040/2O |  |  | N4,480,266.40 | < N50M | NS |  | POST | Plan | 2020-07-10 |  | 2020-07-17 | 2020-08-07 | 2020-08-21 |  | 2020-09-16 | 2020-09-18 | N4,480,266.40 | 2020-09-25 | 2020-10-09 | 2020-11-06
Actual
42 | Procurement of Seinheiser Body Pack Transmitter | MIS/G/NS/041/2O |  |  | N269,733.60 | < N50M | NS |  | POST | Plan | 2020-07-20 |  | 2020-07-27 | 2020-09-07 | 2020-09-21 |  | 2020-10-19 | 2020-10-21 | N269,733.60 | 2020-10-28 | 2020-11-11 | 2020-12-09
Actual
43 | Procurement of 2 nos. Photographic Camera Canon Eos 7D Mark II+ Lens | MIS/G/NS/042/2O |  | 2 | N1,400,000.00 | < N50M | NS |  | POST | Plan | 2020-07-21 |  | 2020-07-28 | 2020-09-08 | 2020-09-22 |  | 2020-10-20 | 2020-10-22 | N1,400,000.00 | 2020-10-29 | 2020-11-12 | 2020-12-10
Actual
44 | Procurement of Video Camera Sony PMW-300 XDCAM HD422 + Lens | MIS/G/NS/043/2O |  | 1 | N2,350,000.00 | < N50M | NS |  | POST | Plan | 2020-08-07 |  | 2020-08-21 | 2020-09-25 | 2020-10-09 |  | 2020-10-28 | 2020-10-30 | N2,350,000.00 | 2020-11-06 | 2020-11-20 | 2020-12-18
Actual
45 | Procurement of 12 nos. Samsung Galaxy Tablet (S4) with case. For PA Dept. | MIS/G/NS/044/2O |  | 12 | N3,000,000.00 | < N50M | NS |  | POST | Plan | 2020-06-15 |  | 2020-06-22 | 2020-08-03 | 2020-08-17 |  | 2020-09-14 | 2020-09-16 | N3,000,000.00 | 2020-09-23 | 2020-10-07 | 2020-10-28
Actual
46 | Procurement of 8 Nos. of Radio Set for News Mornitoring |  |  | 13 | N325,000.00 | < N50M | NS |  | POST | Plan | 2020-06-16 |  | 2020-06-23 | 2020-08-27 | 2020-09-10 |  | 2020-10-07 | 2020-10-09 | N200,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-13
Actual
47 | Procurement of 6 nos.of Printer HP Desk jet advantage 2545 All-in-one (Wifi) | MIS/G/NS/046/2O |  | 6 | N450,000.00 | < N50M | NS |  | POST | Plan | 2020-09-04 |  | 2020-09-11 | 2020-10-16 | 2020-10-30 |  | 2020-11-18 | 2020-11-20 | N450,000.00 | 2020-11-27 | 2020-12-11 | 2020-12-31
Actual
48 | Procurement of 20 no. of Midget (Voice Recorder) | MIS/G/NS/047/2O |  | 30 | N750,000.00 | < N50M | NS |  | POST | Plan | 2020-03-05 |  | 2020-03-12 | 2020-03-02 | 2020-04-16 |  | 2020-05-13 | 2020-05-15 | N350,000.00 | 2020-05-22 | 2020-06-04 | 2020-07-02
Actual
49 | Procurement of 2 nos. of Counting Machine (Glory GFB 800) | MIS/G/NS/048/2O |  | 2 | N560,000.00 | < N50M | NS |  | POST | Plan | 2020-02-17 |  | 2020-02-24 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N560,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-03
Actual
50 | Procurement of 6 nos. of HP Laptops | MIS/G/NS/049/2O |  | 6 | N2,100,000.00 | < N50M | NS |  | POST | Plan | 2020-03-03 |  | 2020-03-10 | 2020-03-31 | 2020-04-14 |  | 2020-05-05 | 2020-05-07 | N2,100,000.00 | 2020-05-14 | 2020-05-28 | 2020-06-25
Actual
51 | Procurement of 6 nos. of HP Desktops | MIS/G/NS/050/2O |  | 6 | N780,000.00 | < N50M | NS |  | POST | Plan | 2020-05-01 |  | 2020-04-15 | 2020-06-26 | 2020-07-10 |  | 2020-08-05 | 2020-08-07 | N780,000.00 | 2020-08-14 | 2020-08-28 | 2020-09-18
Actual
52 | Procurement of 4 nos. of Split 1.50z Airconditioners | MIS/G/NS/051/2O |  | 4 | N828,000.00 | < N50M | NS |  | POST | Plan | 2020-04-07 |  | 2020-04-21 | 2020-06-02 | 2020-06-09 |  | 2020-06-30 | 2020-07-02 | N828,000.00 | 2020-07-09 | 2020-07-23 | 2020-08-20
Actual
53 | Procurement of 12 nos. of Office Chairs | MIS/G/NS/052/2O |  | 12 | N1,320,000.00 | < N50M | NS |  | POST | Plan | 2020-04-13 |  | 2020-04-20 | 2020-06-01 | 2020-06-15 |  | 2020-07-13 | 2020-07-15 | N1,320,000.00 | 2020-07-22 | 2020-08-05 | 2020-09-02
Actual
54 | Procurement of 2 nos. of Photocopier Machines | MIS/G/NS/053/2O |  | 2 | N2,000,000.00 | < N50M | NS |  | POST | Plan | 2020-05-13 |  | 2020-05-20 | 2020-07-01 | 2020-07-08 |  | 2020-07-29 | 2020-07-31 | N2,000,000.00 | 2020-08-07 | 2020-08-21 | 2020-09-18
Actual
55 | Procurement of 8 nos. of laser jet Pro printers (Colour) P2055d | MIS/G/NS/054/2O |  | 8 | N2,960,000.00 | < N50M | NS |  | POST | Plan | 2020-06-15 |  | 2020-06-29 | 2020-08-10 | 2020-08-24 |  | 2020-09-21 | 2020-09-23 | N2,960,000.00 | 2020-09-30 | 2020-10-14 | 2020-11-11
Actual
56 | Procurement of 10 nos. of Lasser jet pro printer (Black & White) P2055 | MIS/G/NS/055/2O |  | 15 | N1,475,000.00 | < N50M | NS |  | POST | Plan | 2020-06-23 |  | 2020-06-30 | 2020-08-11 | 2020-08-25 |  | 2020-09-22 | 2020-09-24 | N1,100,000.00 | 2020-10-01 | 2020-10-15 | 2020-11-12
Actual
57 | Procurement of One set of Cabinet for both Open Registry & Secrete Registry | MIS/G/NS/056/2O |  | 1 | N1,153,361.00 | < N50M | NS |  | POST | Plan | 2020-09-04 |  | 2020-09-11 | 2020-10-16 | 2020-10-30 |  | 2020-11-18 | 2020-11-20 | N1,153,361.00 | 2020-11-27 | 2020-12-11 | 2020-12-31
Actual
58 | Procurement of 7nos. Of Shredding Machines | MIS/G/NS/057/2O |  | 7 | N910,000.00 | < N50M | NS |  | POST | Plan | 2020-03-05 |  | 2020-03-12 | 2020-03-02 | 2020-04-16 |  | 2020-05-13 | 2020-05-15 | N910,000.00 | 2020-05-22 | 2020-06-04 | 2020-07-02
Actual
59 | Procurement of 12. nos of Office Desk (1.6 meters) | MIS/G/NS/058/2O |  | 12 | N3,720,000.00 | < N50M | NS |  | POST | Plan | 2020-02-03 |  | 2020-02-10 | 2020-03-23 | 2020-03-30 |  | 2020-04-20 | 2020-04-22 | N3,720,000.00 | 2020-04-29 | 2020-05-06 | 2020-06-27
Actual
60 | Procurement of 6 nos. of Refridgerators | MIS/G/NS/059/2O |  | 6 | N900,000.00 | < N50M | NS |  | POST | Plan | 2020-04-08 |  | 2020-04-22 | 2020-06-03 | 2020-06-17 |  | 2020-07-15 | 2020-07-17 | N900,000.00 | 2020-07-24 | 2020-08-07 | 2020-09-04
Actual
61 | Procurement of 5 nos. of Book Shelves | MIS/G/NS/060/2O |  | 5 | N500,000.00 | < N50M | NS |  | POST | Plan | 2020-04-01 |  | 2020-04-15 | 2020-05-20 | 2020-06-03 |  | 2020-06-24 | 2020-06-26 | N500,000.00 | 2020-07-03 | 2020-07-17 | 2020-08-14
Actual
62 | Procurement of 9 nos. of Laptops HP Eclipse 14 - Intel Core 15 - 2.5GHz for the 5 Divisional Offices | MIS/G/NS/061/2O |  | 15 | N4,620,000.00 | < N50M | NS |  | POST | Plan | 2020-05-13 |  | 2020-05-27 | 2020-06-24 | 2020-07-08 |  | 2020-07-22 | 2020-07-24 | N2,520,000.00 | 2020-07-31 | 2020-09-14 | 2020-09-12
Actual
63 | Procurement of 5 nos. of Printers (HP Desk Jet) | MIS/G/NS/062/2O |  | 5 | N375,000.00 | < N50M | NS |  | POST | Plan | 2020-06-16 |  | 2020-06-23 | 2020-08-27 | 2020-09-10 |  | 2020-10-07 | 2020-10-09 | N375,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-13
Actual
64 | Procurement of5 nos. of Desk Top Computers | MIS/G/NS/063/2O |  | 11 | N1,380,000.00 | < N50M | NS |  | POST | Plan | 2020-06-23 |  | 2020-06-30 | 2020-08-11 | 2020-08-25 |  | 2020-09-22 | 2020-09-24 | N600,000.00 | 2020-10-01 | 2020-10-15 | 2020-11-12
Actual
65 | Procurement of Uplink / downlink Equipment for the 5 Divisional Offices | MIS/G/NS/064/2O |  | 5 | N600,000.00 | < N50M | NS |  | POST | Plan | 2020-02-17 |  | 2020-02-24 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N600,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-03
Actual
66 | Procurement of 15 nos. of Mobile Evo mi-Fi | MIS/G/NS/065/2O |  | 15 | N375,000.00 | < N50M | NS |  | POST | Plan | 2020-09-04 |  | 2020-09-11 | 2020-10-16 | 2020-10-30 |  | 2020-11-18 | 2020-11-20 | N375,000.00 | 2020-11-27 | 2020-12-11 | 2020-12-31
Actual
67 | Procurement of 10 nos. of Digital Voice Recorder | MIS/G/NS/066/2O |  | 15 | N400,000.00 | < N50M | NS |  | POST | Plan | 2020-09-02 |  | 2020-09-10 | 2020-10-15 | 2020-10-22 |  | 2020-11-18 | 2020-11-20 | N400,000.00 | 2020-12-04 | 2020-12-11 | 2020-12-30
Actual
68 | Procurement of 5 nos. of Radio Sets (for News Mornitoring) | MIS/G/NS/067/2O |  | 5 | N125,000.00 | < N50M | NS |  | POST | Plan | 2020-06-08 |  | 2020-06-22 | 2020-07-20 | 2020-08-03 |  | 2020-08-31 | 2020-09-02 | N125,000.00 | 2020-09-09 | 2020-09-23 | 2020-10-28
Actual
69 | Procurement of 6nos. Of Public Address System | MIS/G/NS/068/2O |  | 5 | N475,000.00 | < N50M | NS |  | POST | Plan | 2020-08-07 |  | 2020-08-21 | 2020-09-25 | 2020-10-09 |  | 2020-10-28 | 2020-10-30 | N475,000.00 | 2020-11-06 | 2020-11-20 | 2020-12-18
Actual
70 | Procurement of 10 nos. of 32GB Flash Drive | MIS/G/NS/069/2O |  | 10 | N50,000.00 | < N50M | NS |  | POST | Plan | 2020-06-11 |  | 2020-06-25 | 2020-07-23 | 2020-08-06 |  | 2020-09-01 | 2020-09-03 | N50,000.00 | 2020-09-10 | 2020-09-24 | 2020-10-15
Actual
71 | Procurement of 5 nos.External Hard Drive of 500GB | MIS/G/NS/070/2O |  | 5 | N150,000.00 | < N50M | NS |  | POST | Plan | 2020-07-08 |  | 2020-07-22 | 2020-08-26 | 2020-09-09 |  | 2020-10-07 | 2020-10-09 | N150,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-27
Actual
72 | Procurement of Furniture (Table / Chair) 5 sets x 5 Offices | MIS/G/NS/071/2O |  | 25 | N1,250,000.00 | < N50M | NS |  | POST | Plan | 2020-07-10 |  | 2020-07-17 | 2020-08-07 | 2020-08-21 |  | 2020-09-16 | 2020-09-18 | N1,250,000.00 | 2020-09-25 | 2020-10-09 | 2020-11-06
Actual
73 | Procurement of 5 Nos. of Soundpoof Generator | MIS/G/NS/072/2O |  | 5 | N2,500,000.00 | < N50M | NS |  | POST | Plan | 2020-08-07 |  | 2020-08-21 | 2020-09-25 | 2020-10-09 |  | 2020-10-28 | 2020-10-30 | N2,500,000.00 | 2020-11-06 | 2020-11-20 | 2020-12-18
Actual
74 | Procurement of 10 Nos. of Digital Camera | MIS/G/NS/073/2O |  | 10 | N500,000.00 | < N50M | NS |  | POST | Plan | 2020-04-01 |  | 2020-04-15 | 2020-05-20 | 2020-06-03 |  | 2020-06-24 | 2020-06-26 | N500,000.00 | 2020-07-03 | 2020-07-17 | 2020-08-14
Actual
75 | Procurement of 10 nos. of Television Set for News Monitoring | MIS/G/NS/074/2O |  | 10 | N800,000.00 | < N50M | NS |  | POST | Plan | 2020-07-20 |  | 2020-07-27 | 2020-09-07 | 2020-09-21 |  | 2020-10-19 | 2020-10-21 | N800,000.00 | 2020-10-28 | 2020-11-11 | 2020-12-09
Actual
76 | Procurement of 5 Nos of Refrigerator | MIS/G/NS/075/2O |  | 11 | N1,400,000.00 | < N50M | NS |  | POST | Plan | 2020-03-03 |  | 2020-03-10 | 2020-03-31 | 2020-04-14 |  | 2020-05-05 | 2020-05-07 | N500,000.00 | 2020-05-14 | 2020-05-28 | 2020-06-25
Actual
77 | Procurement of 5 nos. of Air -Conditioner (Standing 2HP) @N400,000.00 | MIS/G/NS/076/2O |  | 5 | N2,000,000.00 | < N50M | NS |  | POST | Plan | 2020-03-04 |  | 2020-03-11 | 2020-04-22 | 2020-05-06 |  | 2020-05-27 | 2020-05-29 | N2,000,000.00 | 2020-06-05 | 2020-06-19 | 2020-07-17
Actual
78 | Procurement of 8 nos. of Go TV Decoder @ N5000.00 | MIS/G/NS/077/2O |  | 8 | N40,000.00 | < N50M | NS |  | POST | Plan | 2020-04-06 |  | 2020-04-20 | 2020-06-01 | 2020-06-15 |  | 2020-07-13 | 2020-07-15 | N40,000.00 | 2020-07-22 | 2020-08-05 | 2020-09-02
Actual
79 | Procurement of 5 Nos. of Go TV Subscription Annually @48,000.00 | MIS/G/NS/078/2O |  | 5 | N240,000.00 | < N50M | NS |  | POST | Plan | 2020-05-06 |  | 2020-05-13 | 2020-06-24 | 2020-07-08 |  | 2020-08-05 | 2020-08-07 | N240,000.00 | 2020-08-14 | 2020-08-28 | 2020-09-25
Actual
80 | Procurement of 5 Nos. of Office Cabinet @N100,000.00 | MIS/G/NS/079/2O |  | 5 | N500,000.00 | < N50M | NS |  | POST | Plan | 2020-05-07 |  | 2020-05-14 | 2020-06-11 | 2020-06-25 |  | 2020-07-21 | 2020-07-23 | N500,000.00 | 2020-07-30 | 2020-08-13 | 2020-09-10
Actual
81 | Procurement of 2Nos. Of Toyota Pick-up Hillux@ N22,000,000.00 Each | MIS/G/NS/080/2O |  | 2 | N44,000,000.00 | < N50M | NS |  | PRIOR | Plan | 2020-08-07 | 2020-08-14 | 2020-08-21 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-11-04 | 2020-11-06 | N44,000,000.00 | 2020-11-13 | 2020-11-27 | 2020-12-25
Actual
82 | Procurement of Tricaster + intermediary System and Installation for LTV | MIS/G/NS/081/2O |  | 1 | N10,000,000.00 | < N50M | NS |  | PRIOR | Plan | 2020-07-07 | 2020-07-14 | 2020-07-21 | 2020-09-01 | 2020-09-15 | 2020-09-29 | 2020-10-27 | 2020-10-29 | N10,000,000.00 | 2020-11-05 | 2020-11-19 | 2020-12-17
Actual
83 | Procurement of Studio Talk back System (Studio- MCR) @N1.5M | MIS/G/NS/082/2O |  | 1 | N1,500,000.00 | < N50M | NS |  | POST | Plan | 2020-02-17 |  | 2020-02-24 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N1,500,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-03
Actual
84 | Procurement of Audio Equipment (Cabling, Audio Mixer & Lavalier Microphone) | MIS/G/NS/083/2O |  | 1 | N1,500,000.00 | < N50M | NS |  | POST | Plan | 2020-06-16 |  | 2020-06-23 | 2020-08-27 | 2020-09-10 |  | 2020-10-07 | 2020-10-09 | N1,500,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-13
Actual
85 | Procurement of 30 KVA Automatic Voltage Regulator for Radio Lagos | MIS/G/NS/084/2O |  |  | N2,500,000.00 | < N50M | NS |  | POST | Plan | 2020-06-15 |  | 2020-06-22 | 2020-08-03 | 2020-08-17 |  | 2020-09-14 | 2020-09-16 | N2,500,000.00 | 2020-09-23 | 2020-10-07 | 2020-10-28
Actual
86 | Procurement of 20 KVA Uninterupted Power Supply | MIS/G/NS/085/2O |  | 1 | N4,000,000.00 | < N50M | NS |  | POST | Plan | 2020-06-11 |  | 2020-06-25 | 2020-07-23 | 2020-08-06 |  | 2020-09-01 | 2020-09-03 | N4,000,000.00 | 2020-09-10 | 2020-09-24 | 2020-10-15
Actual
87 | Procurement of 20 Nos. of 26AH 12 VOLTS Batteries @N37,500.00 each | MIS/G/NS/086/2O |  | 20 | N750,000.00 | < N50M | NS |  | POST | Plan | 2020-06-23 |  | 2020-06-30 | 2020-08-11 | 2020-08-25 |  | 2020-09-22 | 2020-09-24 | N750,000.00 | 2020-10-01 | 2020-10-15 | 2020-11-12
Actual
88 | Procurement of 2 Nos. Projector with 50 meter VGA Cable @ N500,000.00 | MIS/G/NS/087/2O |  | 2 | N1,000,000.00 | < N50M | NS |  | POST | Plan | 2020-06-08 |  | 2020-06-22 | 2020-07-20 | 2020-08-03 |  | 2020-08-31 | 2020-09-02 | N1,000,000.00 | 2020-09-09 | 2020-09-23 | 2020-10-28
Actual
89 | Procurement of 10 Nos. of 2HP Air-conditioner @ N300,000.00 each | MIS/G/NS/088/2O |  | 10 | N3,000,000.00 | < N50M | NS |  | POST | Plan | 2020-02-05 |  | 2020-02-12 | 2020-03-11 | 2020-03-25 |  | 2020-04-22 | 2020-04-24 | N3,000,000.00 | 2020-05-01 | 2020-05-08 | 2020-06-05
Actual
90 | Procurement of HP 7 Nos. 22-BO13W ALL - IN - ONE Desktop PC @ N250,000.00 | MIS/G/NS/089/2O |  | 7 | N1,750,000.00 | < N50M | NS |  | POST | Plan | 2020-02-17 |  | 2020-02-24 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N1,750,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-03
Actual
91 | Procurement of 8 nos. of Air Conditioners Split 2HP for Traffic Radio @ N325,000.00 | MIS/G/NS/090/2O |  | 8 | N2,600,000.00 | < N50M | NS |  | POST | Plan | 2020-04-01 |  | 2020-04-15 | 2020-05-20 | 2020-06-03 |  | 2020-06-24 | 2020-06-26 | N2,600,000.00 | 2020-07-03 | 2020-07-17 | 2020-08-14
Actual
92 | Procurement of 3 Nos. of Photocopier Machine @N1,000,000.00 | MIS/G/NS/091/2O |  | 3 | N3,000,000.00 | < N50M | NS |  | POST | Plan | 2020-05-01 |  | 2020-05-15 | 2020-06-26 | 2020-07-10 |  | 2020-08-05 | 2020-08-07 | N3,000,000.00 | 2020-08-14 | 2020-08-28 | 2020-09-25
Actual
93 | Procurement of 10 Nos. of Computer system @ N200,000.00 | MIS/G/NS/092/2O |  | 10 | N2,000,000.00 | < N50M | NS |  | POST | Plan | 2020-07-08 |  | 2020-07-22 | 2020-08-26 | 2020-09-09 |  | 2020-10-07 | 2020-10-09 | N2,000,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-27
Actual
94 | Procurement of Specialiseed equipment for News Gathering | MIS/G/NS/093/2O |  | 1 | N2,500,000.00 | < N50M | NS |  | POST | Plan | 2020-07-07 |  | 2020-07-21 | 2020-09-01 | 2020-09-15 |  | 2020-10-13 | 2020-10-15 | N2,500,000.00 | 2020-10-22 | 2020-11-05 | 2020-12-03
Actual
95 | Procurement of Furniture & Fittings | MIS/G/NS/094/2O |  |  | N900,000.00 | < N50M | NS |  | POST | Plan | 2020-02-17 |  | 2020-02-24 | 2020-03-30 | 2020-04-06 |  | 2020-04-27 | 2020-04-29 | N900,000.00 | 2020-05-06 | 2020-05-20 | 2020-06-03
Actual
96 | Procurement of 1 No. of Bruynzeel Mechanical Archive Mobile Shelve for LASRAB | MIS/G/NS/095/2O |  | 1 | N40,000,000.00 | < N50M | NS |  | PRIOR | Plan | 2020-04-01 | 2020-04-08 | 2020-04-15 | 2020-05-27 | 2020-06-03 | 2020-06-10 | 2020-07-08 | 2020-07-10 | N40,000,000.00 | 2020-07-17 | 2020-07-31 | 2020-08-21
Actual
97 | Procurement of Satelite down link for ITB Cloud Storage | MIS/G/NS/096/2O |  |  | N35,000,000.00 | < N50M | NS |  | PRIOR | Plan | 2020-08-07 | 2020-08-14 | 2020-08-21 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-11-04 | 2020-11-06 | N35,000,000.00 | 2020-11-13 | 2020-11-27 | 2020-12-25
Actual
98 | Procurement of 12 Nos. of Imac 21"4K intel Core 15(3.4GHz)8GB,1TB @ N850,000 X 12Units | MIS/G/NS/097/2O |  |  | N10,200,000.00 | < N50M | NS |  | PRIOR | Plan | 2020-06-08 | 2020-06-22 | 2020-07-06 | 2020-08-17 | 2020-08-31 | 2020-09-14 | 2020-10-12 | 2020-10-14 | N10,200,000.00 | 2020-10-21 | 2020-10-28 | 2020-11-25
Actual
99 | Procurement of Furniture, fittings and electrical work | MIS/G/NS/098/2O |  |  | N20,077,646.00 | < N50M | NS |  | PRIOR | Plan | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-11-02 | 2020-11-16 | 2020-11-30 | 2020-12-07 | 2020-12-14 | N20,077,646.00 | 2020-12-21 | 2020-12-28 | 2020-12-31
Actual
100 | Procurement of Consumables e.g Mobile Internet Data Subscription | MIS/G/NS/099/2O |  |  | N4,980,000.00 | < N50M | NS |  | POST | Plan | 2020-03-09 |  | 2020-03-23 | 2020-05-04 | 2020-05-18 |  | 2020-06-15 | 2020-06-17 | N4,980,000.00 | 2020-06-24 | 2020-07-08 | 2020-07-29
Actual
101 | Procurement of working tools eg editing suit, anti virus, table top computer, 5 nos. of 1TB Hard drives | MIS/G/NS/100/2O |  |  | N7,025,000.00 | < N50M | NS |  | POST | Plan | 2020-03-03 |  | 2020-03-10 | 2020-03-31 | 2020-04-14 |  | 2020-05-05 | 2020-05-07 | N7,025,000.00 | 2020-05-14 | 2020-05-28 | 2020-06-25
Actual
102 | Procurement of 2 nos. of Wi-fi enableed Camera and Accessories @ N3.4M each | MIS/G/NS/101/2O |  |  | N6,800,000.00 | < N50M | NS |  | POST | Plan | 2020-07-01 |  | 2020-07-15 | 2020-08-26 | 2020-09-09 |  | 2020-10-07 | 2020-10-09 | N6,800,000.00 | 2020-10-16 | 2020-10-30 | 2020-11-27
Actual
103 | Enhancement Tools & 12 months subscription for Apps & online plug-ins for more effective output | MIS/G/NS/102/2O |  |  | N7,968,000.00 | < N50M | NS |  | POST | Plan | 2020-08-07 |  | 2020-08-21 | 2020-09-25 | 2020-10-09 |  | 2020-10-28 | 2020-10-30 | N7,968,000.00 | 2020-11-06 | 2020-11-20 | 2020-12-18
Actual
104 | Procurement of 15 IPADS (Media Relations)@ N150,000.00 each | MIS/G/NS/103/2O |  |  | N2,250,000.00 | < N50M | NS |  | POST | Plan | 2020-04-06 |  | 2020-04-20 | 2020-05-25 | 2020-06-08 |  | 2020-06-29 | 2020-07-01 | N2,250,000.00 | 2020-07-08 | 2020-07-22 | 2020-08-19
Actual
105 | Production of 5000 Calendars @N1,950.00 | MIS/G/DC/104/2O |  | 5000 | N9,750,000.00 | < N50M | DC |  | POST | Plan | 2020-07-06 |  | 2020-07-20 | 2020-08-24 | 2020-09-07 |  | 2020-10-05 | 2020-10-07 | N9,750,000.00 | 2020-10-14 | 2020-10-28 | 2020-11-25
Actual
106 | Production of 500 Executive Diaries @ N7,000.00 | MIS/G/DC/105/2O |  | 500 | N3,500,000.00 | < N50M | DC |  | POST | Plan | 2020-08-03 |  | 2020-08-17 | 2020-08-31 | 2020-09-14 |  | 2020-10-12 | 2020-10-14 | N3,500,000.00 | 2020-10-21 | 2020-11-04 | 2020-12-02
Actual
107 | Production of 600 Desk Diaries @N3,000.00 | MIS/G/DC/106/2O |  | 600 | N1,800,000.00 | < N50M | DC |  | POST | Plan | 2020-08-05 |  | 2020-08-19 | 2020-09-30 | 2020-10-14 |  | 2020-11-11 | 2020-11-13 | N1,800,000.00 | 2020-11-20 | 2020-12-04 | 2020-12-30
Actual
108 | Production of 615 Pocket Diaries @N1,700.00 | MIS/G/DC/107/2O |  | 615 | N1,045,500.00 | < N50M | DC |  | POST | Plan | 2020-05-13 |  | 2020-05-27 | 2020-06-24 | 2020-07-08 |  | 2020-07-22 | 2020-07-24 | N1,045,500.00 | 2020-07-31 | 2020-09-14 | 2020-09-12
Actual
109 | Production of 600 Year Planner @N1,600.00 | MIS/G/DC/108/2O |  | 600 | N960,000.00 | < N50M | DC |  | POST | Plan | 2020-03-03 |  | 2020-03-10 | 2020-03-31 | 2020-04-14 |  | 2020-05-05 | 2020-05-07 | N960,000.00 | 2020-05-14 | 2020-05-28 | 2020-06-25
Actual
110 | Production of 601 Table Calendarr @N1,700.00 | MIS/G/DC/109/2O |  | 601 | N961,600.00 | < N50M | DC |  | POST | Plan | 2020-07-10 |  | 2020-07-17 | 2020-08-07 | 2020-08-21 |  | 2020-09-16 | 2020-09-18 | N961,600.00 | 2020-09-25 | 2020-10-09 | 2020-11-06
Actual
111 | Motor Vehicle Fuel Consumption | MIS/G -F/NS/110/2O |  |  | N10,800,000.00 | < N50M | NS |  | PRIOR | Plan | 2020-04-01 | 2020-04-08 | 2020-04-15 | 2020-05-27 | 2020-06-03 | 2020-06-10 | 2020-07-08 | 2020-07-10 | N10,800,000.00 | 2020-07-17 | 2020-07-31 | 2020-08-21
Actual
| Procurement of Computer Accessories and Servicing of Computers | MIS/G/NS/111/2O |  |  | N2,500,000.00 | < N50M | NS |  |  | Plan
Actual
11 | LASRAB Building Renovation: Installation of New & Directional Signage of the building frontage, Roofing, Broken doors, tiles /flooring, POP Roofing, face lifting of the building etc | LASRAB/G/NS/011/22 |  |  | N12,255,000.00 |  |  |  |  | Plan | 2022-01-06 |  | 2022-01-13 | 2022-01-27 | 2022-02-10 |  | 2022-02-24 | 2022-02-26 |  | 2022-03-04 | 2022-03-18 | 2022-04-15 | 22/4/22 | 29/4/22 |  | 2022-03-05 | 2022-03-19 | 2022-04-16 | 23/4/22 | 30/4/22
Actual
12 | Establihment of Model Registries and Archives and Procurement of Equipment eg Specialized Scanning Machines, Fire Equipment, Solar light , Historical Artifacts, Upgrading of Mini museum etc in selected Established MDAs | LRB/G/NS/012/22 |  |  | N230,000,000.00 |  |  |  |  | Plan | 2022-03-11 |  | 2022-03-25 | 2022-05-06 | 2022-05-20 |  | 2022-06-17 | 2022-06-19 |  | 2022-06-26 | 2022-07-10 | 2022-07-24 | 2022-08-01 | 2022-08-08
Actual
13 | Procurement of ICT Equipment eg 3 in 1 Printers, HP Laptops, computer desktops for ICT Unit, Photocopier for Amin & HR, Records Dept, Archives Dept., Account Dept & Planning Unit. | LASRAB/G/NS/021/22 |  |  | N22,120,000.00 |  |  |  |  | Plan | 2022-03-10 |  | 2022-03-24 | 2022-05-08 | 2022-05-15 |  | 2022-06-14 | 2022-06-16 |  | 2022-06-23 | 2022-07-07 | 2022-07-21 | 2022-07-29 | 2022-08-05
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## WORKS
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Maintenance & Repair of Specialised Equipment in the editing unit of the Ministry. | MIS/W/NS/001/20 |  | N800,000.00 | < N50M | NS |  |  | Plan | POST | 6/1/20 | 20/1/20 | 3/2/20 | 16/2/20 | 29/2/20 | 13/3/20 | 12th/4/2020 | 14/4/20 |  | 21/4/20 | 4/5/20 | 18/5/20
Actual
2 | Repair and Servicing of Photo & Video Camera in the Ministry | MIS/W/NS/002/20 |  | N800,000.00 | < N50M | NS |  |  | Plan | POST | 8/1/20 | 15/1/20 | 22/1/20 | 5/2/20 | 12/2/20 | 19/2/20 | 18/3/20 | 20/3/20 |  | 27/3/20 | 4/4/20 | 18/4/20
Actual
3 | Procurement of Computer Accessories and Servicing of Computers | MIS/W/NS/003/20 |  | N2,500,000.00 | < N50M | NS |  |  | Plan | POST | 10/1/20 | 17/1/20 | 24/1/20 | 7/2/20 | 14/2/20 | 21/2/20 | 20/3/20 | 22/3/20 |  | 29/3/20 | 6/4/20 | 27/4/20
Actual
1 | [8 empty] | Plan | POST | 7/1/20 | 14/1/20 | 21/1/20 | 4/2/20 | 11/2/20 | 18/2/20 | 17/3/20 | 19/3/20 |  | 26/3/20 | 3/4/20 | 24/4/20
Actual
2 | [8 empty] | Plan | POST | 7/2/20 | 14/2/20 | 21/2/20 | 20/3/20 | 27/3/20 | 3/3/20 | 2nd/4/2020 | 4th/4/2020 |  | 11/4/20 | 18/4/20 | 2/5/20
Actual
3 | [8 empty] | Plan | POST | 10/1/20 | 17/1/20 | 24/1/20 | 7/2/20 | 15/2/20 | 23/2/20 | 22/3/20 | 24/3/20 |  | 31/3/20 | 7/4/20 | 21/4/20
Actual
4 | [8 empty] | Plan | POST | 2/3/20 | 9/3/20 | 16/3/20 | 13/4/20 | 20/4/20 | 27/4/20 | 26/5/20 | 28/5/20 |  | 4/5/20 | 18/5/20 | 2/6/20
Actual
5 | [8 empty] | Plan | POST | 6/3/20 | 13/3/20 | 20/3/20 | 13/4/20 | 1/5/20 | 8/5/20 | 7th/6/2020 | 9th/6/2020 |  | 16/6/20 | 23/6/20 | 7/7/20
Actual
6 | [9 empty] | POST | 8/1/20 | 15/1/20 | 22/1/20 | 5/2/20 | 12/2/20 | 19/2/20 | 18/3/20 | 20/3/20 |  | 26/2/20 | 4/3/20 | 18/4/20
7 | Rehabilitation of Bureau Information Office @ Epe | MIS/W/NS/010/20 |  | N2,000,000.00 | < N50M | NS |  |  | Plan | POST | 1/4/20 | 8/4/20 | 15/4/20 | 29/4/20 | 6/5/20 | 20/5/20 | 19/6/20 | 21/6/20 |  | 27/5/20 | 3/6/20 | 24/6/20
Actual
8 | Installation of 6 Nos. of Soft Touch Digital Media Screens @N1,300,000.00 each x 6 Units | MIS/W/NS/011/20 |  | N7,800,000.00 | < N50M | NS |  |  | Plan | POST | 13/4/20 | 20/4/20 | 27/4/20 | 11/5/20 | 18/5/20 | 25/5/20 | 24/6/20 | 26/6/20 |  | 6/7/20 | 20/7/20 | 17/8/20
Actual
9 | Re-plastering of the building and outer walls | MIS/W/NS/012/20 |  | N4,500,000.00 | < N50M | NS |  |  | Plan | POST | 4/5/20 | 18/5/20 | 1/6/20 | 8/6/20 | 22/6/20 | 29/6/20 | 28/6/20 | 30/6/20 |  | 6/7/20 | 13/7/20 | 27/7/20
Actual
10 | Re-painting of the building and walls | MIS/W/NS/013/20 |  | N2,500,000.00 | < N50M | NS |  |  | Plan | POST | 2/6/20 | 16/6/20 | 30/6/20 | 28/7/20 | 11/8/20 | 25/8/20 | 24/9/20 | 26/9/20 |  | 3/10/20 | 10/10/20 | 14/10/20
Actual
11 | Printing of information, Communication and Advocacy Materials on THEMES | MIS/W -F/NS/014/20 |  | N2,400,000.00 | < N50M | NS |  |  | Plan | POST | 10/1/20 | 17/1/20 | 24/1/20 | 7/2/20 | 14/2/20 | 21/2/20 | 20/3/20 | 22/3/20 |  | 29/3/20 | 6/4/20 | 27/4/20
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual