## GOODS FINAL (C)
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: LAGOS STATE PENSION COMMISSION
BUDGET YEAR: 2022
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION (DATES)
|  | Contract Description | Package Number | Lot Number | No. of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Subtantial Completion/Install | Inspection and Final Acceptance
[6 empty] | 0 | 0 |  |  |  | Plan | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4 wks | 48hrs | 0 | 1wk | 1-2 wks | 2-4 wks
| 1 | PROCUREMENT OF OFFICE FURNITURE | LASPEC/G/NS/001/22 |  |  | 16825290 | <N50M | NS | POST | PRIOR | Plan | 3/2/22 | 15/2/22 | 24/2/22 | 12/3/22 | 26/3/22 | 2/4/22 | 17/4/22 | 21/4/22 |  | 28/4/22 | 7/5/22 | N/A | 25/5/22 | 13/6/22
Actual
| 2 | PROCUREMENT OF REFRIGERATORS (7 UNIT DOUBLE DOORS AND 12 UNIT SINGLE DOOR), | LASPEC/G/NS/002-1/22 | 1 |  | 1660608.8 | <N10 M | NS | POST | POST | Plan | 1/2/22 | NA | 17/2/22 | 1/3/22 | 14/3/22 | N/A | 29/3/22 | 14/4/22 |  | 21/4/22 | 6/5/22 | N/A | 24/5/22 | 11/6/22
Actual
| 3 | PROCUREMENT OF 20 UNITS OF OFFICE CABINET | LASPEC/G/NS/002-2/22 | 2 | 20 | 1580000 | <N10 M | NS | POST | POST | Plan | 5/2/22 | NA | 14/2/22 | 8/3/22 | 22/3/22 | N/A | 13/4/22 | 19/4/22 |  | 23/4/22 | 6/5/22 | N/A | 25/5/22 | 13/6/22
Actual
| 4 | PROCUREMENT OF 12 UNITS OF 32'' LED TV | LASPEC/G/NS/002-3/22 | 3 | 12 | 612400 | <N10 M | NS | POST | POST | Plan | 14/2/22 | NA | 11/3/22 | 26/3/22 | 9/4/21 | N/A | 20/4/22 | 22/4/21 |  | 29/4/21 | 8/5/21 | N/A | 15/5/21 | 21/5/21
Actual
-
| 5 | PROCUREMENT OF STATIONERY | LASPEC/G-F/NS/003/22 |  |  | 4952213 | <N10 M | NS | POST | POST | Plan | 10/1/22 | NA | 24/1/22 | 31/1/22 | 17/2/22 | N/A | 28/2/22 | 3/3/23 |  | 10/3/22 | 19/3/22 | N/A | 26/3/22 | 30/3/22
Actual
| 6 | PROCUREMENT OF COMPUTERS, ICT ACCESSORIES AND COMSUMABLES | LASPEC/G/NS/004/22 |  |  | 25469157.15 | <N50M | NS | POST | PRIOR | Plan | 15/2/22 | 27/2/22 | 12/3/22 | 24/3/22 | 14/4/22 | 27/4/22 | 19/5/22 | 30/5/22 |  | 28/4/22 | 7/5/22 | N/A | 25/5/22 | 13/6/22
Actual
| 7 | UNIFORM AND PROTECTIVE OUTFITS | LASPEC/G/NS/005/22 |  |  | 464000 | <N10M | NS | POST | POST | Plan | 4/2/22 | NA | 15/2/22 | 5/3/22 | 22/3/22 | N/A | 10/4/22 | 17/4/22 |  | 25/4/22 | 4/5/22 | N/A | 23/5/22 | 11/6/22
Actual
| 8 | PROCUREMENT OF CONSUMABLES/EXPENSES (PROCUREMENT UNIT) | LASPEC/G/NS/006/22 |  |  | 400000 | <N10M | NS | POST | POST | Plan | 6/2/22 | NA | 11/2/22 | 13/3/22 | 27/3/22 | N/A | 16/4/22 | 27/4/22 |  | 30/4/22 | 12/5/22 | N/A | 22/5/22 | 15/6/22
Actual
| 9 | PROCUREMENT OF 25KVA UPS | LASPEC/G/NS/007/22 |  | 1 | 4300000 | <N10 M | NS | POST | POST | Plan | 10/1/22 | NA | 20/1/22 | 31/1/22 | 17/2/22 | N/A | 28/2/22 | 3/3/22 |  | 10/3/22 | 19/3/22 | N/A | 26/3/22 | 30/3/22
Actual
| 10 | PROCUREMENT OF CLOCKING DEVICES FOR ATTENDANCE | LASPEC/G/NS/008/22 |  |  | 970000 | <N10 M | NS | POST | POST | Plan | 7/1/22 | NA | 19/1/22 | 27/1/22 | 16/2/22 | N/A | 25/2/22 | 1/3/22 |  | 8/03/22 | 16/3/22 | N/A | 24/3/22 | 28/3/22
Actual
| 11 | PROCUREMENT OF MOTOR VEHICLE FUEL | LASPEC/G-F/NS/009/22 |  |  | 2946000 | <N10 M | NS | POST | POST | Plan | 5/2/22 | NA | 25/2/22 | 14/3/22 | 27/3/22 | N/A | 2022-08-04 | 2022-10-04 |  | 2022-04-16 | 22/4/22 | N/A | 6/5/22 | 12/5/22
Actual
|  | Total Cost |  |  |  | 60179668.95 |  |  |  |  | Plan
Actual
[12 empty] | 12/2/22 | NA | 11/3/22 | 26/3/22 | 9/4/22 | N/A | 20/4/22 | 22/4/22 |  | 29/4/22 | 8/5/22 | N/A | 15/5/22 | 21/5/22
|  | 90627985 |  |  |  | 1819777.79 |  |  | 899000
|  | 65550005 |  |  |  | 1872369.19 |  |  | 998000 |  |  |  | 740000 | 1
|  | 53361897 | [6 empty] | 447982 |  |  |  | 2508000 | 2
|  | 148985441 | [6 empty] | 980000 |  |  |  | 1655000 | 3
|  | 22976000 | [6 empty] | 1000000 |  |  |  | 200000 | 4
|  | SUMMARY: | [6 empty] | 1000000 |  |  |  | 259996 | 5
|  | Procurement Plan for Goods: |  |  |  | 90627985 |  |  | 726673 |  |  |  | 6026000 | 6
|  | Procurement Plan for Consulting Services: |  |  |  | 65550005 |  |  | 1000000 |  |  |  | 500000 | 7
|  | Procurement Plan for Non Consulting Services: |  |  |  | 53361897 |  |  | 7051655 |  |  |  | 11888996
|  | Procurement Plan for Non-Procurable Items: |  |  |  | 148985441
|  | Procurement Plan for Training/Workshop/Conference |  |  |  | 22976000
|  | TOTAL |  |  |  | 381501328
[13 empty] | 1771000 | 1
[13 empty] | 948000 | 2
|  | SUBVENTION |  |  |  | 177677432 | [6 empty] | 1580000 | 3
|  | DEDICATED EXPENDITURE |  |  |  | 125000000 | [6 empty] | 812400 | 4
|  | CAPITAL |  |  |  | 78823896
|  | TOTAL |  |  |  | 381501328 | [6 empty] | 966000 | 5
740000 | [12 empty] | 1207500 | 6
2508000 | [12 empty] | 1900000 | 7
1655000 |  | 712608.8 | [10 empty] | 1575000
200000 |  | 948000 | [10 empty] | 10759900
1082996 |  | 1580000
6026000 |  | 612400 | [10 empty] | 22648896
4613294.2 |  | 3853008.8 | 20678299
16825290.2

## NON CONSULTING (C)
PROCUREMENT PLAN FOR NON CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE PENSION COMMISSION
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION | BASIC DATA | [5 empty] | Plan vs Actual | Pre-or Post Qualification | Prior or Post Review | BIDDING PERIOD (DATES) |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION (DATES)
| Contract Description | Package Number | Lot No. | No. of Unit | Budget Avail in Naira | Approval Threshold | Procurement Method |  |  |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Eval Rpt | Minute of Negotiation | PPA Issues Certificate of Compliance Date/MDA Approval | Plan vs Actual | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount N | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
[5 empty] | 0 | 0 |  | Plan |  |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1 wk | 1-2 wks | Plan | 1-4 wks | 48hrs | 0 | 4-6 wks | 2-4 wks | 2-8 wks
[8 empty] | Actual | [9 empty] | Actual
1 | ACCOMMODATION FEES(1 YEAR) | LASPEC/S-NC/NS/001/22 |  | 1 | 16108897 | <N50 M | NS | Plan | POST | PRIOR | 6/2/22 | 14/2/22 | 28/2/22 | 13/3/22 | 27/3/22 | 17/4/22 | 2022-04-24 | Plan | 28/4/22 | 29/4/22 |  | 5/6/22 | N/A | 30/6/22 | 9/7/22
[8 empty] | Actual | [9 empty] | Actual
2 | MAINTENANCE OF OFFICE BUILDING | LASPEC/S-NC/F-NS/002/22 |  |  | 1320000 | <N10 M | NS | Plan | POST | POST | 15/2/22 | 28/2/22 | 11/3/22 | 22/3/22 | 12/4/22 | 20/4/22 | 27/4/22 | Plan | 13/5/22 | 14/5/22 |  | 16/5/22 | N/A | 30/5/22 | 15/6/22
[8 empty] | Actual | [9 empty] | Actual
3 | OFFICIAL VEHICLES OVERHAULING | LASPEC/S-NC/NS/003/22 |  |  | 2500000 | <N10 M | NS | Plan | POST | POST | 10/2/22 | 20/2/22 | 2/3/22 | 18/3/22 | 30/3/22 | 19/4/22 | 21/4/22 | Plan | 7/5/22 | 8/5/22 |  | 17/6/22 | 24/6/22 | 9/7/22 | 22/7/22
[8 empty] | Actual | [9 empty] | Actual
4 | MOTOR VEHICLE REPAIRS AND MAINTENANCE | LASPEC/S-NC/NS/004/22 |  |  | 3357468 | <N10 M | NS | Plan | POST | POST | 3/1/22 | 17/1/22 | 23/1/22 | 3/2/22 | 14/2/22 | 21/2/22 | 28/02/22 | Plan | 21/3/22 | 25/3/22 |  | 23/4/22 | N/A | 30/4/22 | 5/5/22
[8 empty] | Actual | [9 empty] | Actual
5 | REPAIR AND MAINTENANCE OF HARDWARE AND NETWORKING POWER EQUIPMENTS | LASPEC/S-NC/F-NS/005/22 |  |  | 6467825.67 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 30/04/22 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
6 | PAYMENT FOR RENEWAL OF CLOUD SUBSCRIPTION | LASPEC/S-NC/NS/006/22 |  |  | 2750000 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 30/04/22 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
7 | ENTERPRISE ANTIVIRUS APPLICATION FOR THE CORPORATE SERVERS, LAPTOPS AND DESKTOPS | LASPEC/S-NC/F-NS/007/22 |  | 1 | 750000 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 30/04/2022 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
8 | ONLINE VERIFICATION WEB PLATFORM(.NET)/TESTING, DEPLOYMENT & TRAINING WITH ZOOM INTEGRATION | LASPEC/S-NC/F-NS/008/22 |  | 1 | 2750000 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 2022-04-30 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
9 | MAINTENANCE & PROCUREMENT OF ICT ACCESSORIES | LASPEC/S-NC/F-NS/009/22 |  |  | 5672595 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 2022-04-30 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
10 | PUBLICITY OF MONTHLY BOND PRESENTATION AND OTHER PROGRAMMES | LASPEC/S-NC/NS/010/22 |  |  | 4297539.48 | <N10 M | NS | Plan | POST | POST | 10/2/22 | 20/2/22 | 2/3/22 | 18/3/22 | 30/3/22 | 22/4/22 | 29/4/22 | Plan | 7/5/22 | 8/5/22 |  | 17/6/22 | 24/6/22 | 9/7/22 | 22/7/22
[8 empty] | Actual | [9 empty] | Actual
11 | PRODUCTION OF TELEVISION AND RADIO JINGLES | LASPEC/S-NC/F-NS/011/22 |  |  | 3150000 | <N10 M | NS | Plan | POST | POST | 19/3/22 | 26/3/22 | 6/4/22 | 30/4/22 | 11/5/22 | 19/5/22 | 2022-05-25 | Plan | 17/6/22 | 19/6/22 |  | 15/7/22 | 30/7/22 | 10/8/22 | 27/8/22
[8 empty] | Actual | [9 empty] | Actual
12 | DISASTER RECOVERY PLAN SUCH AS RECTIFICATION OF FAULTY ELECTRICAL APPLIANCES, WATER LEAKAGES ETC | LASPEC/S-NC/NS/012/22 |  |  | 3000000 | <N10 M | NS | Plan | POST | POST | 19/3/22 | 26/3/22 | 6/4/22 | 30/4/22 | 11/5/22 | 19/5/22 | 2022-05-25 | Plan | 17/6/22 | 19/6/22 |  | 15/7/22 | 30/7/22 | 10/8/22 | 27/8/22
[8 empty] | Actual | [9 empty] | Actual
13 | PRODUCTION OF SOUVENIRS | LASPEC/S-NC/F-NS/013/22 |  |  | 964024 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 2022-04-30 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
14 | VERIFICATION OF RETIREES TWICE A YEAR | LASPEC/S-NC/014/22 |  |  | 3000000 | <N10 M |  | Plan | POST | POST | 3/1/22 | 17/1/22 | 23/1/22 | 3/2/22 | 14/2/22 | 21/2/22 | 2022-02-28 | Plan | 21/3/22 | 25/3/22 |  | 23/4/22 | N/A | 30/4/22 | 5/5/22
[8 empty] | Actual | [9 empty] | Actual
15 | ANNUAL RENEWAL OF DEDICATED INTERNET BANDWIDTH FOR PRODUCTION SYSTEM 10MB DUPLEX | LASPEC/S-NC/NS/015/22 |  |  | 3000000 | <N10 M | NS | Plan | POST | POST | 19/3/22 | 26/3/22 | 6/4/22 | 30/4/22 | 11/5/22 | 19/5/22 | 2022-05-25 | Plan | 17/6/22 | 19/6/22 |  | 15/7/22 | 30/7/22 | 10/8/22 | 27/8/22
[8 empty] | Actual | [9 empty] | Actual
16 | ANNUAL RENEWAL OF EMPLOYEE RETIREMENT EVALUATION SYSTEM (ERES)/EMPLOYEE MANAGED PORTAL | LASPEC/S-NC/NS/016/22 |  |  | 2800000 | <N10 M | NS | Plan | POST | POST | 12/2/22 | 13/3/22 | 23/3/22 | 30/3/22 | 16/4/22 | 23/4/22 | 2022-04-30 | Plan | 11/5/22 | 12/5/22 |  | 29/5/22 | N/A | 24/6/22 | 14/7/22
[8 empty] | Actual | [9 empty] | Actual
17 | ANNUAL RENEWAL/MAINTENANCE OF WEBSITE | LASPEC/S-NC/017/22 |  |  | 550000 | <N10 M | NS | Plan | POST | POST | 3/1/22 | 17/1/22 | 23/1/22 | 3/2/22 | 14/2/22 | 21/2/22 | 2022-02-28 | Plan | 21/3/22 | 25/3/22 |  | 23/4/22 | N/A | 30/4/22 | 5/5/22
[8 empty] | Actual | [9 empty] | Actual
18 | ANNUAL RENEWAL SUBSCRIPTION OF SALARY PROGRESSION | LASPEC/S-NC/018/22 |  |  | 750000 | <N10 M | NS | Plan | POST | POST | 3/1/22 | 17/1/22 | 23/1/22 | 3/2/22 | 14/2/22 | 21/2/22 | 2022-02-28 | Plan | 21/3/22 | 25/3/22 |  | 23/4/22 | N/A | 30/4/22 | 5/5/22
[8 empty] | Actual | [9 empty] | Actual
| Total Cost |  |  |  | 63188349.15 |  |  | Plan | [9 empty] | Plan |  |  | #REF!
[8 empty] | Actual | [9 empty] | Actual |  |  | #REF!

## CONSULTING(C)
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE PENSION COMMISSION
BUDGET YEAR: YEAR 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | PFA SECURITY VPN REMOTE ACCESS SOLUTION | LASPEC/S-C/CQS/001/22 | CQS | Lump sum | 6093000 | POST | Plan | 16/2/22 | 24/2/22 | 4/3/22 | 17/3/22 | 29/3/22 | 29/3/22 | 7/4/22 | 22/4/22 | 28/4/22 | 5/5/22 | 11/5/22 | 21/5/22 | 24/5/22 | 24/5/22 |  | 1/6/22 | 13/6/22 | 14/7/22 | 14/7/22 | 29/7/22
Actual
2 | CLOUD BACKUP INFRASTRUCTURE | LASPEC/S-C/CQS/002/22 | CQS | Lump sum | 3000000 | POST | Plan | 3/2/22 | 19/2/22 | 2/3/22 | 15/3/22 | NA | 29/3/22 | 24/4/22 | 30/4/22 | 7/5/22 | 18/5/22 | 18/5/22 | 25/5/22 | 31/5/22 | 1/6/22 |  | 7/6/22 | 14/6/22 | 28/6/22 | 19/7/22 | 15/8/22
Actual
3 | PAYMENT OF PROFFESSIONAL FEES TO ZAMARA CONSULTING ACTUARIES NIGERIA LTD. | LASPEC/S-C/CQS/003/22 | CQS | Lump sum | 3150000 | POST | Plan | 19/2/22 | 10/3/22 | 18/3/22 | 31/3/22 | NA | 21/4/22 | 21/4/22 | 20/5/22 | 27/5/22 | 4/6/22 | 14/6/22 | 25/6/22 | 8/6/22 | 28/6/22 |  | 5/7/22 | 12/7/22 | 29/7/22 | 11/8/22 | 23/8/22
Actual
4 | PAYMENT FOR REVIEW AND PREPARATION OF Y2021 AUDITED FINANCIAL REPORT EXTERNAL TO AUDITORS | LASPEC/S-C/CQS/004/22 | CQS | Lump sum | 3600000 | POST | Plan | 16/2/22 | 24/2/22 | 4/3/22 | 17/3/22 | NA | 29/3/22 | 7/4/22 | 22/4/22 | 28/4/22 | 5/5/22 | 11/5/22 | 21/5/22 | 24/5/22 | 24/5/22 |  | 1/6/22 | 13/6/22 | 14/7/22 | 14/7/22 | 29/7/22
Actual
5 | CONDUCT OF SEMINAR ON PROCUREMENT FOR STAFF | LASPEC/S-C/CQS/005/22 | CQS | Lump sum | 200000 | POST | Plan | 3/2/22 | 19/2/22 | 2/3/22 | 15/3/22 | NA | 29/3/22 | 24/4/22 | 30/4/22 | 7/5/22 | 18/5/22 | 18/5/22 | 25/5/22 | 31/5/22 | 1/6/22 |  | 7/6/22 | 14/6/22 | 28/6/22 | 19/7/22 | 15/8/22
Actual
6 | ROUTINE OF DATA ACCESS | LASPEC/S-C/CQS/006/22 | CQS | Lump sum | 1539000 | POST | Plan | 1/2/22 | 15/2/22 | 3/3/22 | 17/3/22 | NA | 28/3/22 | 20/4/22 | 29/4/22 | 5/5/22 | 19/5/22 | 25/5/22 | 31/5/22 | 8/6/22 | 17/6/22 |  | 28/6/2 | 3/7/22 | 20/7/22 | 31/7/22 | 7/8/22
Actual
7 | SYSTEM DEVELOPMENT AND FULL AUTOMATION OF BUSINESS PROCESS | LASPEC/S-C/CQS/007/22 | CQS | Lump sum | 45000000 | PRIOR | Plan | 16/2/22 | 24/2/22 | 4/3/22 | 17/3/22 | 25/3/22 | 29/3/22 | 7/4/22 | 22/4/22 | 28/4/22 | 5/5/22 | 11/5/22 | NA | 21/5/22 | 24/5/22 |  | 1/6/22 | 7/6/22 | 25/6/22 | 14/7/22 | 22/7/22
Actual
8 | ANNUAL MAINTENANCE FEES OF SAGE200 ACCOUNTING AND BOOKING KEEPING SOFTWARE | LASPEC/S-C/CQS/008/22 | SS | Lump sum | 1000000 | POST | Plan | 1/2/22 | 25/2/22 | 5/3/22 | 17/3/22 | NA | 24/3/22 | 8/4/22 | 15/4/22 | 7/5/22 | 18/5/22 | 27/5/22 | NA | 6/6/22 | 13/6/22 |  | 24/6/22 | 5/7/22 | 21/7/22 | 19/8/22 | 30/8/22
Actual
|  |  |  | Lump sum | 63582000 |  | Plan
Actual

## NON-PROCURABLE (C)
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE PENSION COMMISSION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Demand notice on service charge(Jan-Dec. 2021 by LASPEC to NECA-Apportionment to Commission | LASPEC/NP/NM/001/22 | 5692580.11 | Plan | [7 empty] | 5692580.11
Actual
2 | Travel & Transport | LASPEC/NP/NM/002/22 | 2450000 | Plan | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667 | 204166.6667
Actual
3 | Apportioned Annual Payment of Diesel Consumption | LASPEC/NP/NM/003/22 | 8074162.79 | Plan | [6 empty] | 8074162.79
Actual
4 | General Utility Service | LASPEC/NP/NM/004/22 | 2230000 | Plan | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333 | 185833.3333
Actual
5 | Staff salaries for 40 employed staff of the Commission | LASPEC/NP/NM/005/22 | 50060466 | Plan | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5 | 4171705.5
Actual
6 | Monthly apportioned Electricity bills and related Charges from NECA | LASPEC/NP/NM/006/22 | 10100000 | Plan | 841666.6667 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333 | 633333.3333
Actual
7 | Retirees Welfare | LASPEC/NP/NM/007/22 | 9948000 | Plan | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000 | 829000
Actual
8 | Servicing of Meetings such as PTB, PMB, Mgt. meetings etc | LASPEC/NP/NM/008/22 | 3510000 | Plan | 877500 |  |  | 867500 |  |  |  | 867500 |  |  |  | 867500
Actual
9 | Dir. General TV appearances at different press and electronic media | LASPEC/NP/NM/009/22 | 904500 | Plan | 180900 |  |  | 180900 |  | 180900 |  |  | 180900 |  |  | 180900
Actual
10 | Monitoring Expenses | LASPEC/NP/NM/010/22 | 30000000 | Plan | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Actual
11 | Bi-Annual Sponshorship of Pre-Retirement Seminar by PFAs | LASPEC/NP/NM/011/22 | 13000000 | Plan | 6500000 | [9 empty] | 6500000
Actual
12 | Bond presentation | LASPEC/NP/NM/012/22 | 14000000 | Plan | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667 | 1166666.6667
Actual
13 | Quarterly Consultative Forum with PENCOM in Abuja | LASPEC/NP/NM/013/22 | 2000000 | Plan | 500000 |  |  | 500000 |  |  | 500000 |  |  | 500000
Actual
14 | Payment of premium for the Group Life Assurance cover for Commission employed staff | LASPEC/NP/NM/014/22 | 1200000 | Plan |  |  |  | 564608
Actual
15 | Market & Statistical Surveys and preparation of Cost Analysis | LASPEC/NP/NM/015/22 | 240000 | Plan |  | 60000 |  |  | 60000 |  |  | 60000 |  |  | 60000
Actual
16 | Compilation and printing of bulletin | LASPEC/NP/NM/016/22 | 100000 | Plan | [8 empty] | 100000
Actual
17 | Sitting Allowance of Board Members and Tea break | LASPEC/NP/NM/017/22 | 1280000 | Plan |  | 256000 |  |  | 456000 |  |  | 456000 |  | 456000 |  | 456000
Actual
18 | Insurance of the Agency Assets | LASPEC/NP/NM/018/22 | 285941 | Plan | [5 empty] | 285941
Actual
19 | Logistics and General Expenses | LASPEC/NP/NM/019/22 | 23958555 | Plan | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25 | 1996546.25
Actual
20 | Health Insurance for 40 employed Staff | LASPEC/NP/NM/020/22 | 990000 | Plan | [5 empty] | 990000
Actual
21 | Allowances for both employed and deployed Staff of the Commission | LASPEC/NP/NM/021/22 | 14884059 | Plan | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25 | 1240338.25
Actual
22 | Budget Preparation | LASPEC/NP/NM/022/22 | 400000 | Plan | 400000
Actual
23 | Payment of Budget Monthly International and Local Journals | LASPEC/NP/NM/023/22 | 320000 | Plan | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667 | 26666.6667
Actual
24 | Pension Awareness Week | LASPEC/NP/NM/024/22 | 10000000 | Plan | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333 | 833333.3333
Actual
25 | Mega Bond Presentation | LASPEC/NP/NM/025/22 | 20000000 | Plan | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667 | 1666666.6667
Actual
26 | CUG Subscription | LASPEC/NP/NM/026/22 | 850000 | Plan | [6 empty] | 850000
Actual
27 | Subscription for Modem for Mobile Internet(3 Devices) | LASPEC/NP/NM/027/22 | 450000 | Plan | [5 empty] | 450000
Actual
28 | Payment for Domain Name & Disinfection of Technical Equipment | LASPEC/NP/NM/028/22 | 910000 | Plan |  | 455000 | [5 empty] | 455000
Actual
|  | TOTAL | 227838263.9 | Plan
Actual
| 90627985 | 302677432
| 47940000 | 78823896
| 66453005 | 381501328
165094338
| 11386000 |  |  |  | 148985441
381501328
0
| 90627985 | G
| 65550005 | C
| 148985441 | NPI
| 53361897 | NC
| 22976000 | TWC
381501328

## WORKSHOP
PROCUREMENT PLAN FOR CONFERENCE/TRAINING/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE PENSION COMMISSION
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/Conference | Objective of Description of Training/Workshop/Conference | Package No. | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Institute of Chartered Accountant of Nigerian Conference for ICAN members | To improve the knowledge of participants in the elements of good governance with emphasis of transparency and Accountability | LASPEC/WTC/SS/001/22 | 10 | 5 days | Plan | Abuja | 1300000 | 1200000 | 2804475 | 5304475
Actual
2 | Chartered Institute of Personnel Management Workshop for members | To upgrade participants managerial skills through management strategies and practices | LASPEC/WTC/SS/002/22 | 15 | 4days | Plan | Abuja | 825000 | 1800000 | 3705000 | 6330000
Actual
3 | Nigerian Institute Management Workshop for Members | To enhance participants skills in policy analysis and development of effective managerial skills | LASPEC/WTC/SS/003/22 | 15 | 4 days | Plan | Port Harcourt | 750000 | 1800000 | 3150000 | 5700000
Actual
4 | Chartered Institute of Purchasing and Supply Management of Nigeria Mandatory Proficiency Training on Supply Chain Management | To continually build capacity and enhance the carreer development of members. To upgrade to higher Proffessional Grade(Compulsory Credit Hours) | LASPEC/WTC/SS/004/22 | 1 | 5 days | Plan | Abuja | 60000 | 120000 | 320000 | 500000
Actual
5 | Conference of Association of National Accountants of Nigeria for members | To improve the knowledge of participants and enhance career progression of members | LASPEC/WTC/SS/005/22 | 12 | 4 days | Plan | Abuja | 1200000 | 1440000 | 1680000 | 4320000
Actual
[12 empty] | 41543500 | 60179668.95
6 | NES Conference | Create opportunity for members to rub minds together on garmane issues with a view to proffering pragmatic solutions. | LASPEC/WTC/SS/006/22 | 1 | 4 days | Plan | Kogi | 55000 | 60000 | 266525 | 381525 | 260688263.9 | 63188349.15
[6 empty] | Actual | [5 empty] | 53802349.15 | 63582000
[12 empty] | 84275445 | 227838263.9
7 | Generic Training for Junior, Senior, Management Staff, ED(F&I) and DG | To facilitate the exchange of knowledge , skills and experience for a better utilisasion of human ability and potential in Public Service. | LASPEC/WTC/SS/007/22 | 77 | 3days | Plan | Lagos | 6900000 | 3400000 | 7557500 | 17857500 | 53722944.59 | 84836945
[6 empty] | Actual | [5 empty] | 494032502.64 | 499625227 | 60179668.95
8 | NSA Annual Pre-Conference and Conference | To facilitate the exchange of knowledge and skills experience in the Public Service. | LASPEC/WTC/SS/008/22 | 2 | 5days | Plan | Kaduna | 110000 | 240000 | 800000 | 1150000 |  | 499625227 | 63582000
[6 empty] | Actual | [6 empty] | 0 | 63188349.15
[13 empty] | 24876432.79 | 227838263.9
9 | World Pension Sumit | The Summit provides an exceptional opportunity to share perspectives and insights from around the world. It enables pension professionals to discuss long-term components of vital ‘pension cross-roads. | LASPEC/WTC/SS/009/22 | 3 | 7days | Plan | Netherlands | 3500000 | 9500000 | 10000000 | 23000000 |  | 24876432.79 | 84836945
[6 empty] | Actual | [7 empty] | 499625227
10 | Staff Retreat | Create opportunity for members to rub minds together on garmane issues with a view to proffering pragmatic solutions. | LASPEC/WTC/SS/010/22 | 77 | 3days | Plan | Lagos | 5000000 | 3000000 | 12293445 | 20293445
Actual
| PLAN TOTAL |  |  |  |  | Plan |  |  |  |  | 84836945
| ACTUAL TOTAL |  |  |  |  | Actual
and

## Sheet1
3225000