## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Travel and Transport within lagos | LSSC/NP/NM/001/22 | 1,920,000.00 | Plan | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000 | 160000
Actual
2 | payment for dstv, phone cards and internet subscriptions | LSSC/NP/NM/002/22 | 5,280,000.00 | Plan | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000 | 440000
Actual
S | servicing of MTB and Staff Forums | LSSC/NP/NM/003/22 | 1620000 | Plan | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000
Actual
4 | Personel Insurance of 500 State Athletes | LSSC/NP/NM/004/22 | 1,000,000.00 | Plan | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33
Actual
5 | SSA to Gov on Sports and Facility | LSSC/NP/NM/010/22 | 2,400,000.00 | Plan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
Actual
6 | Miscellaneous for unforseen sporting activities | LSSC/NP/NM/012/22 | 1620000 | Plan | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000 | 135000
Actual
7 | Grants for 43 sports Association Secretariat's annual running cost and Donations at functions | LSSC/NP/NM/013/22 | 4000000 | Plan | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333 | 333333.3333
Actual
8 | Sitting Allowance for 12 Board Members | LSSC/NP/NM/014/22 | 3000000 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
Actual
12 | Games and Sporting Expenses | LSSC/NP/NM/018/22 | 160000000 | Plan | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333
Actual
13 | Hosting of International Taekwando Competition | LSSC/NP/NM/020/22 | 10000000 | Plan
Actual
14 | Hosting of International Badminton Competition | LSSC/NP/NM/021/22 | 10000000 | Plan
Actual
15 | Marathon and other Races | LSSC/NP/NM/023/21 | 500000000 | Plan
Actual
16 | National Youth Sports Festival | LSSC/NP/NM/024/22 | 80000000 | Plan
Actual
17 | Monthly meeting of committee member of sports development department and quarterly Zonal meeting | LSSC/NP/NM/025/22 | 2000000 | Plan | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667
Actual
18 | Lagos State secondary school Handball copmpetition | LSSC/NP/NM/028/22 | 6000000 | Plan
Actual
19 | Lagos State secondary school Combat sports competition | LSSC/NP/NM/029/21 | 6100000 | Plan
Actual
20 | Lagos State secondary school Cycling competition | LSSC/NP/NM/030/21 | 5200000 | Plan
Actual
21 | Lagos State secondary school relay | LSSC/NP/NM/031/22 | 4500000 | Plan
Actual
22 | Lagos State Secondary school Deaf games competition | LSSC/NP/NM/032/22 | 4000000 | Plan
Actual
23 | Lagos State secondary school Swimming competition | LSSC/NP/NM/033/22 | 4200000 | Plan
Actual
24 | Lagos State secondary school Racket games fiesta | LSSC/NP/NM/034/22 | 5028000 | Plan
Actual
25 | Organisation of Association sports across 20 LGs and 37 LCDAs | LSSC/NP/NM/037/22 | 2000000000 | Plan
Actual
26 | School Sports | LSSC/NP/NM/030/22 | 60000000 | Plan
Actual
27 | Eko Basketball league | LSSC/NP/NM/040/22 | 9000000 | Plan
Actual
28 | Delegates to Y2022 National Sports Festival(Asaba) | LSSC/NP/NM/041/22 | 700000000 | Plan
Actual
29 | Lagos State Ayo Olopon Open Challenge | LSSC/NP/NM/042/22 | 4999994 | Plan
Actual
30 | Ashoju Oba Table Tennis | LSSC/NP/NM/043/22 | 7000000 | Plan
Actual
31 | Southwest Judo Championship | LSSC/NP/NM/044/22 | 8000000 | Plan
Actual
32 | Rugby independence day international 7s | LSSC/NP/NM/045/22 | 7000000 | Plan
Actual
33 | Gymnastic southwest Artistic and Trampoline | LSSC/NP/NM/046/22 | 9000000 | Plan
Actual
34 | Community sports project (Sports coonect) | LSSC/NP/NM/048/22 | 10000000 | Plan
Actual
35 | Samaritan feet,youth clininc and volleyball Tournament | LSSC/NP/NM/048/22 | 9000000 | Plan
Actual
36 | Lagos Open Para Powerlifting Challenge | LSSC/NP/NM/049/22 | 10000000 | Plan
Actual
37 | 42 Sports Association Athletes Training grants | LSSC/NP/NM/050/22 | 132000000 | Plan | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000
Actual
38 | Monthly allowance for Honourary coaches | LSSC/NP/NM/051/22 | 28800000 | Plan | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
Actual
39 | Special Duties Expenses | LSSC/NP/NM/052/22 | 200000000 | Plan | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667 | 16666666.6667
Actual
40 | Lagos State football supporters club subvention | LSSC/NP/NM/053/22 | 1500000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
Actual
41 | Servicing of (14) Fourteen Vehicles | LSSC/NPINM/054/22 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Local workshop for Executive Chairman and Director General | LSSC/S-WTC/SS/001/22 | Development and Capacity Building | 442 |  | Plan | Lagos/Abuja | 37900000 | 15960000 | 27840000 | 81700000
Actual
2 | PSSDC training for Middle Mgt & Junior staff |  |  |  |  | Plan
Actual
3 | Conferences and seminars for CIPM,NIM,ICAN,NBA & NPMCN |  |  |  |  | Plan
Actual
4 | Training of Sports Officers |  |  |  |  | Plan
Actual
5 | MTSS & PMR training and conferences for Planners |  |  |  |  | Plan
Actual
6 | CIPSM AND NIPR conferences and seminars |  |  |  |  | Plan
Actual
7 | Retreat for 12 Board members |  |  |  |  | Plan
Actual
8 | Training for Coaches (staff & Contract) |  |  |  |  | Plan
Actual
9 | Training for facilities managers |  |  |  |  | Plan
Actual
10 | Training for staff of ICT&Planning Units(CPN ,NSA &NES Confrences |  |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LA GOS STATE SPORTS COMMISSION
BUDGET YEAR: 2022
YEAR 2022 PROCUREMENT PLAN :LAGOS STATE SPORTS COMMISSION
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Servicing of 14 Buses | LSSC/S-NC/NS/001/22 |  | 14 | 2400000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2020 | 24th feb,2020 | 2nd Mar,2020 | 9th Mar.2020 | 16th Mar.2020 | 23rd Mar,2020 | 30th Mar,2020 | Plan | 27th Aprl,2020 | 29th Aprl,2020 |  | 27th May,2020 | 10th June,2020 | 24th June,2020
[7 empty] | Actual | [9 empty] | Actual
Numbering and engraving of Fixed Assests | LSSC/S-NC/NS/002/22 |  |  | 450000 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 |  | 27th May,2021 | 10th June,2021 | 24th June,2021
[7 empty] | Actual | [9 empty] | Actual
Teslim Balogun Stadium Facility Maintenance | LSSC/S-NC/NS/003/22 |  |  | 8307692.35 | <50,000,000.00 | NS | Plan | POST | PRIOR | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 |  | 27th May,2021 | 10th June,2021 | 24th June,2021
[7 empty] | Actual | [9 empty] | Actual
Agege Stadium Facility Maintenance | LSSC/S-NC/NS/004/22 |  |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 |  | 27th May,2021 | 10th June,2021 | 24th June,2021
[7 empty] | Actual | [9 empty] | Actual
Rowe-Park Stadium Facility maintenance | LSSC/S-NC/NS/005/22 |  |  | 8307692.35 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 16th Mar.2021 | 23rd Mar,2021 | 30th Mar,2021 | Plan | 27th Aprl,2021 | 29th Aprl,2021 |  | 27th May,2021 | 10th June,2021 | 24th June,2021
[7 empty] | Actual | [9 empty] | Actual
Araromi Stadium facility maintenance | LSSC/S-NC/NS/006/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Amuto Stadium facility maitenance | LSSC/S-NC/NS/007/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Ijede Stadium Faiclity maitenance | LSSC/S-NC/NS/008/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Isheri Stadium Facility maintenance | LSSC/S-NC/NS/009/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Badagry Stadium Facility maitenance | LSSC/S-NC/NS/010/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,202 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Epe Stadium facility maintenance | LSSC/S-NC/NS/011/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Jalisco Stadium facility maintenance | LSSC/S-NC/NS/012/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Sari-Iganmu Stadium facility maintenance | LSSC/S-N/NS/013/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Elegbeta Stadium facility maintenance | LSSC/S-NC/NS/014/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2021 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual
Ajele Campus-Mini Stadium facility maintenance | LSSC/S-NC/NS/015/22 |  |  | 8307692.31 | <10,000,000.00 | NS | Plan | POST | POST | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 16th Mar.2022 | 23rd Mar,2022 | 30th Mar,2022 | Plan | 27th Aprl,2022 | 29th Aprl,2022 |  | 27th May,2022 | 10th June,2022 | 24th June,2022
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Publication of Commission Annual Reports | LSSC/S-C/QCBS/001/21 | QCBS | Lump sum | 250000 |  | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th Feb, 2022 | 2nd March,2022 | 16th March,2022 | 6th April,2022 | 13th April,2022 | 20th April,2022 | 27th April,2022 | 4th May,2022 | 11th May,2022 | 25th May,2022 | 26th May,2022 | 250000 | 2nd June,2022 | 16th June,2022 | 30th June,2022 | 7th July,2022 | 14th June,2022
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Locks and Electrical items | LSSC/G/NS/001/21 |  |  | 1200000 | <10M | NS | POST Qualification | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
2 | Purchase of 15 units of (15R/196)Tyres for Buses(6) | LSSC/G/NS/002/21 |  |  | 1200000 | <10M | NS | POST Qualification | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
s | Procurement of Stationeries | LSSC/G/NS/003/21 |  |  | 2240000 | <10M | NS | POST Qualification | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
[10 empty] | Actual | [9 empty] | 15th Aprl,2020 | 22nd Aprl,2020 | 6th May,2020
4 | Procurement of Information & Comuunication Consumables | LSSC/G/NS/004/21 |  |  | 3300000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
5 | Uniforms and Protective outfit for Security Personel | LSSC/G/NS/005/21 |  |  | 1500000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
6 | Audit Consumables(Inventry card, casting Paper, endorse ink etc. | LSSC/G/NS/006/21 |  |  | 350000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
8 | Medical Consumables(Drugs / Physoterapiest equipment | LSSC/G/NS/008/21 |  |  | 8521529 | <50,000,000.00 | NS | PRE | PRIOR | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
9 | Sendforth Party for retired Staffs( Gift items and others) | LSSC/G/NS/009/21 |  |  | 2500000 | <50,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
10 | Consumables for HOS CUP( Sports kits, equipment etc) | LSSC/G/NS/010/21 |  |  | 3000000 | <50,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
11 | Qauterly stadia inspection and Annual Auditing(Fueling of vehicles, Food/ refreshent for the Team, stationeries,etc. | LSSC/G/NS/011/21 |  |  | 540000 | <50,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
12 | Sendforth Party for retired Staffs( Gift items and others) | LSSC/G/NS/012/22 |  |  | 1000000 | <10,000,000.00 | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
13 | FuelIing of Motor Vehicles | LSSC/G-F/NS/051/22 |  |  | 4800000 | <10M | NS | POST | POST | Plan | 20th Jan,2021 | 3rd feb,2021 | 10th Feb,2021 | 24th feb,2021 | 2nd Mar,2021 | 9th Mar.2021 | 6th Aprl,2021 | 8th Aprl,2021 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
14 | Publicity (Procurement of ,events advert flex,sovenires, etc. | LSSC/G-F/NS/091/22 |  |  | 3000000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
15 | Procurement of computer consumables/ICT Accessories. | LSSC/G-F/NS/041/22 |  |  | 4000000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
16 | Procuerment of books | LSSC/G-F/NS/013/22 |  |  | 1200000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
17 | Procurement of office consumables for Procurement Unit. | LSSC/G-F/NS/017/22 |  |  | 800000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,202 | 8th Aprl,2022 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
18 | Procurement Audit and other Expenses | LSSC/G-F/NS/0061/22 |  |  | 350000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022 | 24th feb,2022 | 2nd Mar,2022 | 9th Mar.2022 | 6th Aprl,2022 | 8th Aprl,2022 |  | 15th Aprl,2021 | 22nd Aprl,2021 | 6th May,2021
Actual
19 | Procurement of Goods | LSSC/G-F/NS/011/22 |  |  | 250000 | <10M | NS | POST | POST | Plan | 20th Jan,2022 | 3rd feb,2022 | 10th Feb,2022
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE SPORTS COMMISSION
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Upgrading of Teslim Balogun Stadium | LSSC/NCB/WK/002/22 | 1 | #1,680,560,655.128 | <1B | ICB |  | Pre | Plan | Prior | ongoing
Actual
2 | Construction of Ikorodu Mini Stadium Igbogbo. | LSSC/NCB/WK/003/22 | 1 | #1,236,686,041.15 | <1B | ICB |  |  | Plan
Actual
3 | Construction of Badagry Mini Stadium | LSSC/NCB/WK/004/22 | 1 | #1,236,686,041.15 | <1B | ICB |  |  | Plan
Actual
4 | Construction of Ifako Ijaye Mini Stadium | LSSC/NCB/WK/005/22 | 1 | #985,626,030.33 | >1B | NCB |  |  | Plan
Actual
5 | Construction of Ajelogo Mini Stadium, Ketu | LSSC/NCB/WK/005/22 | 1 | #926,188,802.18 | >1B | NCB |  |  | Plan
Actual
6 | Construction of Epe Mini Stadium | LSSC/NCB/WK/006/22 | 1 | #896,643,986.15 | >1B | ICB |  |  | Plan
Actual
7 | Construction of Lekki Mini Stadium, Ogombo,Lekki. | LSSC/NCB/WK/007/22 | 1 | #926,188,802.18 | >1B | NCB |  |  | Plan
Actual
8 | Construction Sari - Iganmu Mini Stadium. Orile. | LSSC/NCB/WK/0082/22 | 1 | #644,746,542.32 | >1B | NCB |  |  | Plan
Actual
9 | Construction of Ajeromi Mini Stadium (Gbagada) | LSSC/NCB/WK/009/22 | 1 | #556,355,547.42 | >1B | NCB |  |  | Plan
Actual
| Pre- contract fee & Financials(cost of Fund) |  |  | #657,939,123.00 |  |  |  |  | Plan
Actual