## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: TRANSPORTATION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Annual Retreat | MOT/S-C/CQ/01/22 | CQ | Lumpsum | 14524934.04 | PRIOR | Plan | 8-2-22 | 15-2-22 | 23-2-22 | 2-3-22 | 9-3-22 | 16-3-22 | 5-4-22 | 13-4-22 | 21-4-22 | 27-4-22 | 4-5-22 | 11-5-22 | 18-5-22 | 19-5-22 |  | 26-5-22 | 11-6-22 | 24-6-22 | 1-7-22 | 8-7-22
Actual
2 | Advocacy and Documentary | MOT/S-C/CQ/02/22 | CQ | Lumpsum | 5983413.16 | PRIOR | Plan | 8-2-22 |  | 23-2-22 | 2-3-22 |  | 16-3-22 | 5-4-22 | 13-4-22 | 21-4-22 | 27-4-22 | 4-5-22 | 11-5-22 | 18-5-22 | 19-5-22 |  | 26-5-22 | 11-6-22 | 24-6-22 | 1-7-22 | 8-7-22
Actual
3 | Festive Campaign And Safety Measures | MOT/S-C/CQ/03/22 | CQ | Lumpsum | 5249574 | PRIOR | Plan | 8-2-22 |  | 23-2-22 | 2-3-22 |  | 16-3-22 | 5-4-22 | 13-4-22 | 21-4-22 | 27-4-22 | 4-5-22 | 11-5-22 | 18-5-22 | 19-5-22 |  | 26-5-22 | 11-6-22 | 24-6-22 | 1-7-22 | 8-7-22
Actual
4 | Media Coverage /Publicity and Enlightenement | MOT/S-C/CQ/04/22 | CQ | Lumpsum | 18713438.1 | PRIOR | Plan | 10-2-22 | 17-2-22 | 25-2-22 | 4-3-22 | 11-3-22 | 18-3-22 | 7-4-22 | 15-4-22 | 22-4-22 | 29-4-22 | 6-5-22 | 13-5-22 | 20-5-22 | 21-5-22 |  | 28-5-22 | 13-6-22 | 26-6-22 | 3-7-22 | 10-7-22
Actual
5 | Traffic Safety Audit Intervention | MOT/S-C/CQ/05/22 | CQ | Lumpsum | 50000000 | PRIOR | Plan | 10-2-22 | 17-2-22 | 25-2-22 | 4-3-22 | NIL | 18-3-22 | 7-4-22 | 15-4-22 | 22-4-22 | 29-4-22 | 6-5-22 | NIL | 20-5-22 | 21-5-22 |  | 28-5-22 | 13-6-22 | 26-6-22 | 3-7-22 | 10-7-22
Actual
6 | Polaris and Technology To Latch On MOST Digital Centre | MOT/S-C/CQ/06/22 | CQ | Lumpsum | 58665320 | PRIOR | Plan | 10-2-22 | 17-2-22 | 25-2-22 | 4-3-22 | NIL | 18-3-22 | 7-4-22 | 15-4-22 | 22-4-21 | 29-4-22 | 6-5-22 | NIL | 20-5-22 | 21-5-22 |  | 28-5-22 | 13-6-22 | 26-6-22 | 3-7-22 | 10-7-22
Actual
7 | Plateia Ultimate(Road Way Sign) and Construction Of SWOTH PATh Analysis /Road Making Design | MOT/S-C/CQ/06/22 | CQ | Lumpsum | 10000000 | PRIOR | Plan | 10-2-22 | 17-2-22 | 25-2-22 | 4-3-22 | NIL | 18-3-22 | 7-4-22 | 15-4-22 | 22-4-21 | 29-4-22 | 6-5-22 | NIL | 20-5-22 | 21-5-22 |  | 28-5-20 | 13-6-20 | 26-6-20 | 3-7-20 | 10-7-20
Actual

## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/AGENCY: TRANSPORTATION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Facility Management | MOT/NP/01/22 | 187040690 | Plan | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 15586724 | 187040690
Actual
2 | Hosting Of Meeting | MOT/NP/02/22 | 5000000 | Plan | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 13895834 | 5000000
Actual
3 | Promotion Expenses | MOT/NP/03/22 | 41998562 | Plan | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 3499880.17 | 41998562
Actual
4 | Exhibition of Materials | MOT/NP/04/22 | 500000 | Plan | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 41666.67 | 500000
Actual
5 | Transport Allowance for attending meeting | MOT/NP/05/22 | 7270400 | Plan | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 605866.67 | 7270400
Actual
6 | Allowances of Security Personel | MOT/NP/06/22 | 44192176 | Plan | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 3682681.33 | 44192176
Actual
7 | Janitorial Expenses | MOT/NP/07/22 | 3150000 | Plan | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 262500 | 3150000
Actual
8 | operation cost for Transport Unions | MOT/NP/08/22 | 11500000 | Plan | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 958333.33 | 11500000
Actual
9 | Expenses on Enforcement and Operational Programme | MOT/NP/09/22 | 255,500,000 | Plan | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 21291666.67 | 255,500,000
Actual
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISRY/ AGENCY: TRANSPORTATION
BUDGET YEAR:2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference and Seminars for professional Staff | Mot/S-WTC/01/21 | To allow professional members be abreast of issues in the professional body | 30 |  | Plan |  |  |  |  | 12052026
Actual
2 | Training programmes to be attended by Junior officers(GL04-06) | Mot/S-WTC/02/22 | To update officers on the effective and efficient ways of discharging duties | 12 |  | Plan |  |  |  |  | 400000
Actual
3 | Training programmes to be attended by Senior officers | Mot/S-WTC/03/22 | How to cope with challenges faced in the course of discharging duty | 65 |  | Plan |  |  |  |  | 18568174
Actual
Plan
Actual
Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance of Traffic Signal Light | MOT/S-NC/DL/01/22 |  |  | 100000000 | <500,000,000 | DL | Plan | POST | Prior | 2022-02-01 | 2022-02-08 | 2022-02-14 | 2022-02-28 | 2022-03-06 | 2022-03-13 | 2022-03-20 | Plan | (27/3/22) | (1-4-22) |  | 2022-04-27 | 2022-05-11 | 2022-05-18 | 2022-05-19
[7 empty] | Actual | [9 empty] | Actual
maintenance of vehicles and operational vehicles | MOT/S-NC-F/NS/01/22 |  |  | 42003549.9 | <50,000,000 | NS | Plan | POST | PRIOR | 2022-02-01 | 2022-02-08 | 2022-02-14 | 2022-02-28 | 2022-03-06 | 2022-03-13 | 2022-03-20 | Plan | (27/3/22) | (1-4-22) |  | 2022-04-27 | 2022-05-11 | 2022-05-18 | 2022-05-19
[7 empty] | Actual | [9 empty] | Actual
maintenance of Photocopier | MOT/S-NC-F/NS/02/22 |  |  | 6546882.84 | <10,000,000 | NS | Plan | POST | POST | 2022-02-01 | Nil | 2022-02-14 | 2022-02-28 | 2022-03-06 | 2022-03-13 | Nil | Plan | (27/3/22) | (1-4-22) |  | 2022-04-27 | 2022-05-11 | 2022-05-18 | 2022-05-19
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Offices And Toilets | MOT/S-NC-F/NS/02/22 |  |  | 1093286.96 | <10,000,000 | NS | Plan | POST | POST | 2022-02-01 | Nil | 2022-02-14 | 2022-02-28 | 2022-03-06 | 2022-03-13 | Nil | Plan | (27/3/22) | (1-4-22) |  | 2022-04-27 | 2022-05-11 | 2022-05-18 | 2022-05-19
[7 empty] | Plan | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: TRANSPORTATION
BUDGET YEAR: 2022
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
|  | Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
| 1 | Procurement of Stationeries and computer accesories | MOT/G-F/NS/O1/22 |  |  | 20392635 | <50,000,000 | NS | POST | PRIOR | Plan | 2022-02-08 | (15-feb-2022) | 2021-02-21 | 2022-03-03 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-06 |  | (13-4-2022) | 2022-04-20 | 2022-05-04 | 2022-05-11
Actual
| 2 | Fuel consumption for operational Vehicles | MOT/G-F/NCB/O1/22 |  |  | 66978342 | <100,000,000 | NCB | POST | PRIOR | Plan | 2022-02-08 | (15-feb-2022) | 2022-02-21 | 2022-03-03 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-06 |  | (13-4-2022) | 2022-04-20 | 2022-05-04 | 2022-05-11
Actual
| 3 | Fuel Consumption of Heavy Duty Equipments | MOT/G-F/NS/02/22 |  |  | 25000000 | <50,000,000 | NS | POST | PRIOR | Plan | 2022-02-08 | (15-feb-2022) | 2022-02-21 | 2022-03-03 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-06 |  | (13-4-2022) | 2022-04-20 | 2022-05-04 | 2022-05-11
Actual
| 4 | Printing of road worthiness certificate | MOT/G/DC/01/22 |  | 2 | 52000000 | <100,000,000 | DC | POST | PRIOR | Plan | 2022-02-08 | (15-feb-2022) | 2022-02-21 | 2022-03-03 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-06 |  | (13-4-2022) | 2022-04-20 | 2022-05-04 | 2022-05-11
Actual
| 5 | Procurement of Tyres and Cosumables Parts for Heavy Equipmwent Vehicles | MOT/G/NS/01/22 |  |  | 10192787 | <50,000,000 | NS | POST | PRIOR | Plan | 2022-02-10 | (17-feb-2022) | 2022-02-24 | 2022-03-06 | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-09 |  | (16-4-2022) | 2022-04-26 | 2022-05-07 | 2022-05-14
1 | [10 empty] | Actual
| 6 | Procurement of Allen Ware for Transport Engineering | MOT/G/NS/02/22 |  |  | 2000000 | <10,000,000 | NS | POST | POST | Plan | 2022-02-10 |  | 2022-02-24 | 2022-03-06 | 2022-03-23 |  | 2022-04-06 | 2022-04-09 |  | (16-4-2022) | 2022-04-26 | 2022-05-07 | 2022-05-14
Actual
| 7 | Procurement of uniform and outfits | MOT/G/NS/03/22 |  |  | 2000000 | <10,000,000 | NS | POST | POST | Plan | 2022-02-10 |  | 2022-02-24 | 2022-03-06 | 2022-03-23 |  | 2022-04-06 | 2022-04-09 |  | (16-4-2022) | 2022-04-26 | 2022-05-07 | 2022-05-14
Actual
| 8 | Procurement of Toileteries | MOT/G-F/NS/03/22 |  | 15 | 850000 | <10,000,000 | NS | POST | POST | Plan | 2022-02-10 |  | 2022-02-24 | 2022-03-06 | 2022-03-23 |  | 2022-04-06 | 2022-04-09 |  | (16-4-2022) | 2022-04-26 | 2022-05-07 | 14/05/202
Actual
| 9 | Procurement of drawing materials and tools | MOT/G/NS/04/22 |  |  | 181350 | <10,000,000 | NS | POST | POST | Plan | 2022-02-15 |  | 2022-03-07 | 2022-03-21 | 2022-04-06 |  | 2022-05-06 | 2022-05-20 |  | (27-5-2022) | 2022-06-04 | 2022-06-18 | 2022-07-01
Actual
| 10 | Procurement of window Blind | MOT/G/NS/04/22 |  | 2 | 50000 | <10,000,000 | NS | POST | POST | Plan | 2022-02-15 |  | 2022-03-07 | 2022-03-21 | 2022-04-06 |  | 2022-05-06 | 2022-05-20 |  | (27-5-2022) | 2022-06-04 | 2022-06-18 | 2022-07-01
Actual
Plan
1 | [10 empty] | Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: TRANSPORTATION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Junction improvement works | MOT/W/ICB/01/21 | 2 | 1200000000 | >500,000,000 | ICB | BOQ | PRE | Plan | PRIOR | 2022-02-12 | 2022-02-18 | 2022-02-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-29 | 2022-04-30 |  | (7-May-2022) | 1900-01-01 | 2022-06-14 | 2022-12-14 | 2022-12-15
Actual
2 | Lane Marking Across The State | MOT/W/ICB/02/21 |  | 1100000000 | >500,000,000 | ICB | BOQ | PRE | Plan | PRIOR | 2022-02-12 | 2022-02-18 | 2022-02-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-29 | 2022-04-30 |  | (7-May-2022) | 2022-05-14 | 2022-06-14 | 2022-12-14 | 2022-12-15
Actual
3 | Provision of traffic signal lights | MOT/W/ICB/03/21 | 8 | 520000000 | >520,000,000 | ICB | BOQ | POST | Plan | PRIOR | 2022-02-12 | 2022-02-18 | 2022-02-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-29 | 2022-04-30 |  | (7-May-2022) | 2022-05-14 | 2022-06-14 | 2022-12-14 | 2022-12-15
Actual
4 | Provision Of Median Barriers | MOT/W/NCB/01/22 | 4 | 500000000 | <500,000,000 | NCB | BOQ | POST | Plan | PRIOR | 2022-02-12 | 2022-02-18 | 2022-02-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 |  | 2022-04-30 |  | (7-May-2022) | 2022-05-14 | 2022-06-14 | 2022-12-14 | 2022-12-15
Actual
5 | Painting of Kerbs and Median | MOT/W/NCB/02/22 |  | 470000000 | <500,000,000 | NCB | BOQ | POST | Plan | PRIOR | 2022-02-19 | 2022-02-25 | 2022-03-03 | 2022-04-07 | 2022-04-15 | 2022-04-22 | 2022-05-04 | 2022-05-05 |  | (12-May-2022 | 2022-05-19 | 2022-06-19 | 2022-08-14 | 2022-08-17
Actual
6 | Production and Insdtallation of Signages | MOT/W/NCB/03/22 |  | 222000000 | <500,000,000 | NCB | BOQ | POST | Plan | PRIOR | 2022-02-19 | 2022-02-25 | 2022-03-03 | 2022-04-07 | 2022-04-15 | 2022-04-22 | 2022-05-04 | 2022-05-05 |  | (12-May-2022 | 2022-05-19 | 2022-06-19 | 2022-08-14 | 2022-08-17
Actual
7 | Reinstatement And Repair of Wire Mesh | MOT/W/NCB/04/22 |  | 150000000 | <500,000,000 | NCB | BOQ | POST | Plan | PRIOR | 2022-02-19 | 2022-02-25 | 2022-03-03 | 2022-04-07 | 2022-04-15 | 2022-04-22 | 2022-05-04 | 2022-05-05 |  | (12-May-20212 | 2022-05-19 | 2022-06-19 | 2022-08-14 | 2022-08-17
Actual
8 | Provision and Installation of Solar Stud | MOT/W/NCB/05/22 |  | 100000000 | <500,000,000 | NCB | BOQ | POST | Plan | PRIOR | 2022-02-19 | 2022-02-25 | 2022-03-03 | 2022-04-07 | 2022-04-15 | 2022-04-22 | 2022-05-04 | 2022-05-05 |  | (12-May-2022 | 2022-05-19 | 2022-06-19 | 2022-08-14 | 2022-08-17
Actual
9 | Provision Of Zebra Crossing | MOT/W/NCB/06/22 |  | 80000000 | <100,000,000 | NCB | BOQ | POST | Plan | POST | 2022-02-26 | 2022-03-05 | 2022-03-10 | 2022-04-13 | 2022-04-22 | 2022-04-29 | 2022-05-11 | 2022-05-12 |  | (19-May-2022 | 2022-05-26 | 2022-06-26 | 2022-08-21 | 2022-08-22
Actual
10 | Construction of 2 Stop Centres | MOT/W/NCB/07/22 |  | 80000000 | <100,000,000 | NCB | BOQ | POST | Plan | POST | 2022-02-26 | 2022-03-05 | 2022-03-10 | 2022-04-13 | 2022-04-22 | 2022-04-29 | 2022-05-11 | 2022-05-12 |  | (19-May-2022 | 2021-05-26 | 2021-06-26 | 2022-08-21 | 2022-08-22
Actua[
11 | Provision of Truck Barriers and Maintenance of Existing Ones | MOT/W/NCB/08/22 |  | 80000000 | <100,000,000 | NCB | BOQ | POST | Plan | POST | 2022-02-26 | 2022-03-05 | 2022-03-10 | 2022-04-13 | 2022-04-22 | 2022-04-29 | 2022-05-11 | 2022-05-12 |  | (19-May-2022 | 2022-05-26 | 2022-06-26 | 2022-08-21 | 2022-08-22
Actual
12 | Renovation of PTCS Offices and Stop Centres | MOT/W/NS/01/22 |  | 2500000 | <10,000,000 | NS | BOQ |  | Plan | POST | 2022-02-26 |  | 2022-03-10 | 2022-04-13 | 2022-04-22 |  | 2022-05-11 | 2022-05-12 |  | (19-May-2022 | 2022-05-26 | 2022-06-26 | 2022-08-21 | 2022-08-22
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual