## Non-Proc items
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/ Actual | JANUARY | FEB | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPT. | OCTOBER | NOV. | DEC | TOTAL
1 | Personnel Cost | CERUD/NP/NM/001/22 | 6980932 | Plan | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 581744.33 | 6980931.96
Actual
2 | Weekly travel and Monthly trips. (TRAVEL & TRANSPORT) | CERUD/NP/NM/002/22 | 15840000 | Plan | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 1320000 | 15840000
Actual
3 | Electricity & Telephone Payment and Ipad & Internet Subscription. (GENERAL UTILITY) | CERUD/NP/NM/003/22 | 3660000 | Plan | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 305000 | 3660000
Actual
4 | Servicing of Management meeting (SPECIAL DUTY EXPENSES) | CERUD/NP/NM/004/22 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
Actual
5 | Participation in annual Agricultural shows/celebration (SPECIAL DUTY EXPENSES) | CERUD/NP/NM/005/22 | 5000000 | Plan | 416666.66 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 5000000.03
Actual
6 | Cost of rendering of Consultancy services to Organs of Government and International Agencies that execute rural Development Programmes and Policy (SPECIAL DUTY EXPENSES) | CERUD/NP/NM/006/22 | 10000000 | Plan | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.33 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 10000000
Actual
7 | Staff and General welfare programme (SPECIAL DUTY EXPENSES) | CERUD/NP/NM/007/22 | 36000000 | Plan | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 36000000
Actual
8 | Preparation & Updating of Y2022 Annual Procurement Plan for the Centre, Conduct of PTB Meetings and other Statutory Procurement Activities. (PROCUREMENT UNIT EXPENSES) | CERUD/NP/NM/008/22 | 2200000 | Plan | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.33 | 183333.34 | 183333.34 | 183333.34 | 183333.34 | 2200000
Actual
9 | Preparation of Annual Budget & Bi-lateral Discussion with MEPB,Quartely & Bi-annual Defences of the Centre annual Budget, Monitoring of the Centre Projects & Programme for Certification & Planning Materials. (PLANNING UNIT EXPENSES) | CERUD/NP/NM/009/22 | 2000000 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 2000000
Actual
10 | Purchase of Digital photo & motion Cameras, Production of CERUD sign post, Monthly Newspapers & Annual Press Briefing and outdoor Public address system (PUBLICITY AND PRESS COVERAGE) | CERUD/NP/NM/010/22 | 4380000 | Plan | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 365000 | 4380000
Actual
11 | Servicing of Quaterly Audit Committee Meeting,Subscription to Professional Organisation i.e ANNA,IIA,CITN and Audit materials (AUDIT UNIT EXPENSES) | CERUD/NP/NM/011/22 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
Actual
12 | Standing Technical Committee of Technocrats on Rural Development (RESEARCH) | CERUD/NP/NM/012/22 | 30000000 | Plan | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 30000000
Actual
13 | On-Farm Adaptive Research on Economy/Farming activities of farmers / Women in Rural Areas (RESEARCH) | CERUD/NP/NM/013/22 | 21300000 | Plan | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 1775000 | 21300000
Actual
14 | Research survey collaboration with Lagos Bureau of Statistcs(LBS) for Development of CERUD Data Bank on Socio-economics activities of Rural Dwellers across Lagos State (RESEARCH) | CERUD/NP/NM/014/22 | 30000000 | Plan | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 30000000
Actual
15 | Listings & Classifing of Communities in Lagos State (RESEARCH) | CERUD/NP/NM/015/22 | 20000000 | Plan | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.66 | 1666666.66 | 1666666.66 | 1666666.66 | 20000000
Actual
16 | Research Collaboration with other research Institute (RESEARCH) | CERUD/NP/NM/016/22 | 15000000 | Plan | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
Actual
17 | Staff Insurance Cover (INSURANCE) | CERUD/NP/NM/018/22 | 220000 | Plan | 18333.33 | 18333.33 | 18333.33 | 18333.33 | 18333.33 | 18333.33 | 18333.33 | 18333.33 | 18333.34 | 18333.34 | 18333.34 | 18333.34 | 220000
Actual
18 | Audit Expenses (AUDIT EXPENSES) | CERUD/NP/NM/019/22 | 1000000 | Plan | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.33 | 83333.34 | 83333.34 | 83333.34 | 83333.34 | 1000000
Actual
19 | Bank Charges (BANK CHARGES) | CERUD/NP/NM/020/22 | 70000 | Plan | 5833.33 | 5833.33 | 5833.33 | 5833.33 | 5833.33 | 5833.33 | 5833.33 | 5833.33 | 5833.34 | 5833.34 | 5833.34 | 5833.34 | 70000
Actual
206050932

## trg conf wsh
S/N | Description of Training/Workshop/Conference | Package Number | Objective of Training/Workshop /Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost (N)
1 | Organizing Training & Workshop for all members of Staff to attend both Locally & Internationally and Conference (WORKSHOP & TRAINING ALLOWANCES) | CERUD/S-WTC /001/22 |  |  |  | Plan |  |  |  |  | 38500000
Actual
2 | Attending Annual Conferences & Seminars for Staffs (CONFERENCES AND SEMINARS) | CERUD/S-WTC /002/22 |  | 5 |  | Plan |  |  |  |  | 45000000
Actual
3 | Develop Informal Education Programmes for Rural Dwellers in Lagos State (RESEARCH) | CERUD/S-WTC /003/22 |  |  |  | Plan |  |  |  |  | 10500000
Actual
4 | Sensitization Workshops and Seminars/Rally on Civic Rights and Social Responsibilities of Rural Dwellers (RESEARCH) | CERUD/S-WTC /004/22 |  |  |  | Plan |  |  |  |  | 50500000
Actual
5 | Honey Bee Training and Empowerment for Youths across Lagos State & Provision for Honey Processing Centre (RESEARCH) | CERUD/S-WTC /005/22 |  |  |  | Plan |  |  |  |  | 32750000
Actual
6 | Workshops on Health and Nutrition in Collaboration with Ministry of Health (RESEARCH) | CERUD/S-WTC /006/22 |  |  |  | Plan |  |  |  |  | 24354520
Actual
7 | Training /Workshop on Livestock (Piggery, Sheep & Goat, Rabbittery, Grasscutter and Snailery (RESEARCH) | CERUD/S-WTC /007/22 |  |  |  | Plan |  |  |  |  | 5500000
Actual
207104520

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: CENTRE FOR RURAL DEVELOPMENT
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's Approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[8 empty] | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Training & Youths Empowerment Programmes for Interested Participants across the State (IBILE) in Fish Breeding, Management, Harvesting, Processing, Storage and Marketing @N575,000 x 163 Participants X 5 times i.e (5 Division) (SOCIAL ENGAGEMENT & CONSTITUENCY EMPOWERMENT) | MLGCA/S-NC /CQS/001/22 | Consultant's Qualifications Selection (CQS) | Lump Sum | 500000000 | Prior | Plan | 4th May 22 | 11th May 22 | 18th May 22 | 1st June 22 | 8th June 22 | 15th June 22 | 6th July 22 | 13th July 22 | 20th July 22 | 27th July 22 | 3rd Aug. 22 | 10th Aug. 22 | 17th Aug. 22 | 19th Aug. 22 | NIL | 26th Aug. 22 | 9th Sept 22 | 23rd Sept 22 | 30th Sept 22 | 7th Oct. 22
Actual
500000000

## non-cons
|  | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot No | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening Date | Submission of Bid Evaluation Report | Minutes of Negotiation | PPA issue "Cert. of Compliance Date/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount in Naira | Date Contract Signature | Mobilization Advance Payment | Complete Delivery/ Install | Inspection & Final Acceptance
[11 empty] | 1-4wks | 1-2wks | 1-2wks | 2-6wks | 1-2wks | 1wk | 1-2wks |  | 1-4wks | 48Hrs |  | 4-6wks | 1-2wks | 2-8wks
1 | Maintenance of CERUD Building & Repair of 5 office Building used by the Military Men and weekly clearing of Administrative office, guest quarters, fish pond etc. (MAINTENANCE OF OFFICE BUILDING) | CERUD/S-NC /NS/001/22 |  |  | 51000000 | <100M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 | NIL | 2022-06-16 | 2022-06-30 | 2022-12-23 | 2022-12-30
Actual
2 | Electrical & Plumbing works, AC & Photocopier repairs & Servicing, Fumigation of office quarterly and weekly clearing of Admin office , guest quarters, fish pond etc. (MAINTENANCE OF OFFICE BUILDING) | CERUD/S-NC /NS/002/22 |  |  | 19700000 | <50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
3 | Servicing & Repairs of Vehicles, replacement of tyres and General Overhauling of Official Vehicles. (MOTOR VEH. REPAIRS & MAINT.) | CERUD/S-NC /NS/003/22 |  |  | 12716000 | < 50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
4 | Website Creation & Maintenance, Local area Network & System Maintenance and Repair & Servicing of 25 Computers. (GENERAL UTILITY) | CERUD/S-NC /SSS/001/22 |  |  | 5800000 | <10M | Single Source Selection (SSS) | Plan | POST | POST | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
5 | Management Retreat (SPECIAL DUTY EXPENSES) | CERUD/S-NC /SSS/002/22 |  |  | 8000000 | < 10M | Single Source Selection (SSS) | Plan | POST | POST | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | Plan | 2022-04-12 | 2022-04-14 | NIL | 2022-05-12 | 2022-05-26 | 2022-05-29 | 2022-05-31
Actual
6 | Special Requirement for the Office of the Director/CEO, PRO, Account,& Planning (SPECIAL DUTY EXPENSES) | CERUD/S-NC/ NS/004/22 |  |  | 14000000 | < 50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
[8 empty] | Actual | [9 empty] | Actual
7 | Special Sensitization programmes on Civil Rights & Social Responsibilities of CERUD Host Community and It's Environment (SPECIAL DUTY EXPENSES) | MLGCA/S-NC /CQS/001/22 |  |  | 50000000 | < 100M | Consultant's Qualifications Selection (CQS) | Plan | PRE | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
[8 empty] | Actual | [9 empty] | Actual
8 | Provision for CERUD Research Library & CERUD Research Studies (SPECIAL DUTY EXPENSES) | MLGCA/S-NC /CQS/002/22 |  |  | 50000000 | < 100M | Consultant's Qualifications Selection (CQS) | Plan | PRE | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
[8 empty] | Actual | [9 empty] | Actual
9 | Special Operational Expenses (SPECIAL DUTY EXPENSES) | CERUD/S-NC/ NS/005/22 |  |  | 13019068 | < 50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
[8 empty] | Actual | [9 empty] | Actual
10 | Health Programmes for Communities Dwellerst (SPECIAL DUTY EXPENSES) | CERUD/S-NC /SSS/003/22 |  |  | 20000000 | < 50M | Single Source Selection (SSS) | Plan | POST | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
Actual
11 | Assesement of felt needs in rural Communities (SPECIAL DUTY EXPENSES) | CERUD/S-NC/ NS/006/22 |  |  | 20000000 | < 50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
Actual
12 | Provision of 2 Green houses, Provision for CERUD Training Complex & Implementation of other programmes aimed at improving the quality of lives in the rural areas (SPECIAL DUTY EXPENSES) | MLGCA/S-NC /CQS/003/22 |  |  | 48000000 | < 50M | Consultant's Qualifications Selection (CQS) | Plan | PRE | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
13 | Development of Craft Industries on Appropriate Technology in Rural Areas (SPECIAL DUTY EXPENSES) | MLGCA/S-NC /CQS/004/22 |  |  | 50000000 | < 100M | Consultant's Qualifications Selection (CQS) | Plan | PRE | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
14 | Maintenance of CERUD Existing Projects (Guest Charlets) (SPECIAL DUTY EXPENSES) | CERUD/S-NC/ NS/007/22 |  |  | 15000000 | < 50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
15 | Maintenance of CERUD Data Bank (SPECIAL DUTY EXPENSES) | CERUD/S-NC/ NS/008/22 |  |  | 10000000 | < 50M | National Shopping (NS) | Plan | POST | PRIOR | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
16 | Installation of fire Fighting Equipment at CERUD office complex (SPECIAL DUTY EXPENSES) | CERUD/S-NC /SSS/004/22 |  |  | 2000000 | < 10M | Single Source Selection (SSS) | Plan | POST | POST | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
Actual
17 | Routine Maintainance of CERUD Conserved Medicinal Plants for use of Researchers/Botanists N1,000,000 x 12 (RESEARCH) | CERUD/S-NC /SSS/004/22 |  |  | 12000000 | <50M | Single Source Selection (SSS) | Plan | POST | PRIOR | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
Actual
18 | 40 KVA Generator repairs . (GENERATOR REPAIRS & DIESEL CONSUMPTION.) | CERUD/S-NC /NS/009/22 |  |  | 1440000 | <10M | National Shopping (NS) | Plan | POST | POST | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-13 |  | 2022-06-10 | 2022-06-24 | 2022-06-28 | 2022-07-05
Actual
19 | Refurbishment of Operational Vehicles. (CAPITAL ITEM) | CERUD/S-NC /NS/010/22 |  |  | 3000000 | <10M | National Shopping (NS) | Plan | POST | POST | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
20 | Reinstallation of Solar Light at the Medicinal Plant Arena. (CAPITAL ITEM) | CERUD/S-NC /NS/011/22 |  |  | 2500000 | < 10M | National Shopping (NS) | Plan | POST | POST | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-07-29 | 2022-08-05
Actual
408175068

## goods
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot No | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount (N) | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hrs) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Fuelling of Official Vehicles, Brake oil, Engine oil, and Transmission oil (MOTOR VEHICLE FUEL CONSUMPTION) | CERUD/G /DC/001/22 |  |  | 2664480 | < 10M | Direct Contracting (DC) | POST | POST | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 | NIL | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-04-29 | 2022-05-06
Actual
2 | Procurement of A4 Papers,Toner Catridges for Printers & Photocopiers, Developer & Drum for Photocopier and other Consumables (STATIONERIES) | CERUD/G /NS/001/22 |  |  | 920000 | < 10M | National Shopping (NS) | POST | POST | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 | NIL | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-04-29 | 2022-05-06
Actual
3 | Procurement of Mobbing Sticks & buckets ,Toiletries and other Consumables (MISCELLANOUS) | CERUD/G /NS/002/22 |  |  | 1175000 | < 10M | National Shopping (NS) | POST | POST | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2021-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 | NIL | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-04-29 | 2022-05-06
Actual
4 | Printing of Letter Head , Memo Pads for HOD/HOU ,Printing of Confidential & Open file jackets, Envelopes and other Publications. (To be done by LSPC) (PUBLICATION, PRINTING OF LETTER HEAD PAPER, FILES ETC.) | MLGCA/G /DC/002/22 |  |  | 1650000 | < 10M | Direct Contracting | POST | POST | Plan | 2022-01-13 | 2022-01-20 | 2022-01-27 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-04 | NIL | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-29 | 2022-05-06
Actual
5 | Provision for 20 units of Desktops, procurement of 10 of 200 AH Inverter Batteries,3 HP Colour printer & Scanner,5 HP Laptops & 5 Ipad for Research officer and Other Computer Accessories. (ICT UNIT EXPENSES) | CERUD/G /NS/003/22 |  |  | 15560000 | < 50M | National Shopping (NS) | POST | PRIOR | Plan | 2022-01-13 | 2022-01-20 | 2022-01-27 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-04 | NIL | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-29 | 2022-05-06
Actual
6 | Publishing of the Centre's Existing Research Reports. (RESEARCH) | MLGCA/G /DC/003/22 |  |  | 5000000 | < 10M | National Shopping (NS) | POST | POST | Plan | 2022-01-13 | 2022-01-20 | 2022-01-27 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-04 | NIL | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-29 | 2022-05-06
Actual
7 | Diesel Consumption and Replacement of 2 nos CERUD Petrol Generators (ELEMAX) 6.5 KVA used by Military Men @ Igbodu Office. ((GENERATOR REPAIRS & DIESEL CONSUMPTION.)) | MLGCA/G /DC/004/22 |  |  | 7200000 | < 10M | National Shopping (NS) | POST | POST | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 | NIL | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-04-29 | 2022-05-06
Actual
8 | Procurement of Office Furniture and Equipment (CAPITAL ITEM) | CERUD/G /NS/004/22 |  |  | 3000000 | < 10M | National Shopping (NS) | POST | POST | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2021-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 | NIL | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-04-29 | 2022-05-06
Actual
37169480

## works
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA |  |  |  |  | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot No | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's Approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion /Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hrs) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Upgrade of CERUD Medicinal Plant Arena | CERUD/NS/ W/001/22 |  | 5000000 | < 10M | National Shopping (NS) | BOQ | POST | Plan | POST | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-06-02 | 2022-06-09 | 2022-06-16 | 2022-06-23 | 2022-06-30 |  | 2022-07-08 | 2022-07-15 | 2022-07-29 | 2022-08-30 | 2022-09-06
Actual
2 | Construction of 3 Nos. 3-Bedroom Chalets for Research and Trainig @ Igbodu, Epe | CERUD/NCB/ W/001/22 |  | 75000000 | < 100M | National Competitve Bidding (NCB) | BOQ | POST | Plan | PRIOR | 2022-01-11 | 2022-01-18 | 2022-01-25 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-03 |  | 2022-03-10 | 2022-03-17 | 2022-03-31 | 2022-12-23 | 2022-12-30
Actual
3 | Upgrade of CERUD Cottage Mill & Training Centre at Igboguka | CERUD/NS/ W/002/22 |  | 7000000 | < 10M | National Shopping (NS) | BOQ | POST | Plan | POST | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-02 |  | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-30 | 2022-10-07
Actual
4 | Setting up of CERUD Honey Processing Centre at Igbodu , Epe | CERUD/NS/ W/003/22 |  | 5000000 | < 10M | National Shopping (NS) | BOQ | POST | Plan | POST | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-02 |  | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-30 | 2022-10-07
Actual
5 | Establishment of CERUD office Complex at Badagry, Eti-Osa and Alimosho | CERUD/NS/ W/004/22 |  | 30000000 | < 50M | National Shopping (NS) | BOQ | POST | Plan | PRIOR | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-02 |  | 2021-08-09 | 2021-08-16 | 2021-08-30 | 2021-10-29 | 2021-11-05
Actual
6 | Landscapping of Centre's Road Network for Beautification and ease of movement within the Office Complex & Construction of drainages for Erelu way road at Amikanle | CERUD/NCB/ W/002/22 |  | 84000000 | < 100M | National Competitve Bidding (NCB) | BOQ | POST | Plan | PRIOR | 2022-06-10 | 2022-06-17 | 2022-06-24 | 2022-07-08 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-02 |  | 2021-08-09 | 2021-08-16 | 2021-08-30 | 2021-10-29 | 2021-11-05
Actual
7 | Upgrade of CERUD Mini Water Project to supply water to its host community | CERUD/NS/ W/005/22 |  | 5079272 | < 10M | National Shopping (NS) | BOQ | POST | Plan | POST | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-06-02 | 2022-06-09 | 2022-06-16 | 2022-06-23 | 2022-06-30 |  | 2022-07-08 | 2022-07-15 | 2022-07-29 | 2022-08-30 | 2022-09-06
Actual
211079272