## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: ADENIRAN OGUNSANYA COLLEGE OF EDUCATION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel & Transport | AOCOED/NP/NM /001/22 | 38421000 | Plan | 9605250 |  |  | 9605250 |  |  | 9605250 |  |  | 9605250
Actual
2 | General Utility ( Payment of Electricity Bills, Maintenance of Solar light system, Payment of Bank Charges & Stamp duty) | AOCOED/NP/NM /002/22 | 37540000 | Plan | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33 | 3128333.33
Actual
3 | Miscellaneous / Contingency (Payment for unanticipated events e.g donations to royalities, matters relating to Staff Welfare) | AOCOED/NP/NM /003/22 | 42440000 | Plan | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67 | 3536666.67
Actual
4 | Student Grant / Sponsorship | AOCOED/NP/NM /005/22 | 6122000 | Plan | 1530500 |  |  | 1530500 |  |  | 1530500 |  |  | 1530500
Actual
5 | Programme Honoraria | AOCOED/NP/NM /006/22 | 129451668 | Plan | [6 empty] | 129451668
Actual
6 | Payment for Security Personnel & Services | AOCOED/NP/NM /008/22 | 18720000 | Plan | 4680000 |  |  | 4680000 |  |  | 4680000 |  |  | 4680000
Actual
7 | Academic Board Meetings Expenses | AOCOED/NP/NM /009/22 | 13407560 | Plan | 3351890 |  |  | 3351890 |  |  | 3351890 |  |  | 3351890
Actual
8 | Governing Council Expenses | AOCOED/NP/NM /010/22 | 50000000 | Plan | 12500000 |  |  | 12500000 |  |  | 12500000 |  |  | 12500000
Actual
| TOTAL |  | 336102208 | Plan | [12 empty] | 336102228
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: ADENIRAN OGUNSANYA COLLEGE OF EDUCATION
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training of Deans & HODs on the job | AOCOED/S-WTC/SS/001/22 | Research / Training in area of Teacher Education | 9 | 1 month | Plan | Local |  |  |  | 20460500
Actual
2 | Training / Local Conference of Audit / Bursary / Other Staff | AOCOED/S-WTC/SS/002/22 | Training to encourage professionalism & specialization | 5 | 1 month | Plan | Local |  |  |  | 20460500
Actual
3 | Overseas Training for Principal Officers | AOCOED/S-WTC/SS/003/22 | Training in improving effective administration | 5 | 3 days | Plan | Outside |  |  |  | 12500000
Actual
4 | Training for Administrative Officers | AOCOED/S-WTC/SS/004/22 | Training in area to enhance effcetice administration | 5 | 1 month | Plan | Local |  |  |  | 14030000
Actual
5 | Local Conferences for Academic Staff | AOCOED/S-WTC/SS/005/22 | Research / Training in area of improving Curriculum | 9 | 1 month | Plan | Local |  |  |  | 25000000
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | TOTAL |  |  |  |  | Plan |  |  |  |  | 92451000
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON -CONSULTING SERVICES
MINISTRY/ AGENCY: ADENIRAN OGUNSANYA COLLEGE OF EDUCATION
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance of Office Building | AOCOED/S-NC/SSS/001/22 |  |  | 76200000 | <100m | SSS | Plan | Post | Post | 2-Mar,2022 | 10-Mar,2022 | 23-Mar,2022 | 12-Apr,2022 | 21-Apr,2022 | 27-Apr,2022 | 6-May,2022 | Plan | 1-Jun,2022 | 3-Jun,2022 | 76200000 | 4-Jul,2022 | 14-Jul,2022 | 30-Aug,2022
[7 empty] | Actual | [9 empty] | Actual
Motor Vehicle Repairs & Maintenance | AOCOED/S-NC/SSS/002/22 |  |  | 16522500 | <50m | SSS | Plan | Post | Post | 22-Feb,2022 | 8-Mar,2022 | 17-Mar,2022 | 8-Apr,2022 | 19-Apr,2022 | 26-Apr,2022 | 5-May,2022 | Plan | 23-May,2022 | 25-May,2022 | 16522500 | 2-Jun,2022 | 15-Jun,2022 | 20-Jul,2022
[7 empty] | Actual | [9 empty] | Actual
Plant & Machinery Maintenance | AOCOED/S-NC/SSS003/22 |  |  | 42020000 | <50m | SSS | Plan | Post | Post | 21-Mar,2022 | 30-Mar,2022 | 7-Apr,2022 | 26-Apr,2022 | 2-May,2022 | 9-May,2022 | 12-May,2022 | Plan | 30-May,2022 | 31-May,2022 | 42020000 | 20-Jun,2022 | 30-Jun,2022 | 20-Jul,2022
[7 empty] | Actual | [9 empty] | Actual
Publicity (Radio & TV Adverts) | AOCOED/S-NC/SSS/004/22 |  |  | 54245000 | <100m | SSS | Plan | Post | Post | 22-Feb,2022 | 2-Mar,2022 | 14-Mar,2022 | 30-Mar,2022 | 5-Apr,2022 | 12-Apr,2022 | 22-Apr,2022 | Plan | 9-May,2022 | 11-May,2022 | 54245000 | 14-Jun,2022 | 28-Jun,2022 | 20-Jul,2022
[7 empty] | Actual | [9 empty] | Actual
Special Academic Programmes | AOCOED/S-NC/SSS/005/22 |  |  | 16890000 | <50m | SSS | Plan | Post | Post | 25-Feb,2022 | 9-Mar,2022 | 30-Mar,2022 | 5-Apr,2022 | 12-Apr,2022 | 20-Apr,2022 | 27-Apr,2022 | Plan | 9-May,2022 | 13-May,2022 | 16890000 | 13-Jun,2022 | 24-Jun,2022 | 22-Jul,2022
[7 empty] | Actual | [9 empty] | Actual
Other Ceremonies/Special Duties, Expenses/ Convocation/ Acad. Ceremonies & Lecture Series | AOCOED/S-NC/SSS/006/22 |  |  | 73782500 | <100m | SSS | Plan | Post | Post | 2-Mar,2022 | 12-Mar,2022 | 26-Mar,2022 | 15-Apr,2022 | 23-Apr,2022 | 30-Apr,2022 | 14-May,2022 | Plan | 3-Jun,2022 | 4-Jun,2022 | 73782500 | 9-Jun,2022 | 28-Jun,2022 | 30-Aug,2022
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 279660000 |  |  | Plan | [9 empty] | Plan |  |  | 279660000
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: ADENIRAN OGUNSANYA COLLEGE OF EDUCATION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Consultancy & Legal Services | AOCOED/S-C/QCBS/001/22 | CQS | Lump sum | 36000000 | Post | Plan | 8-Feb,2022 | 18-Feb,2022 | 24-Feb,2022 | 14-Mar,2022 | 25-Mar,2022 | 4-Apr,2022 | 3-May,2022 | 13-May,2022 | 23,May,2022 | 30,May,2022 | 10-Jun,2022 | 20-Jun,2022 | 5-Jul,2022 | 7-Jul,2022 | 36000000 | 2-Aug,2022 | 15-Aug,2022 | 2-Sept,2022 | 14-Sept,2022 | 20-Sept,2022 | 36000000
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| TOTAL |  |  |  | 36000000 |  | Plan | [14 empty] | 36000000
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: ADENIRAN OGUNSANYA COLLEGE OF EDUCATION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Motor Vehicle Fuel | AOCOED/G-F/NS/001/22 |  |  | 10300000 | <50m | NS | Post | Prior | Plan | 24-Feb, 2022 | 8-Mar, 2022 | 29-Mar, 2022 | 13-Apr, 2022 | 20-Apr, 2022 | 4-May, 2022 | 25-May, 2022 | 27-May,2022 | 10300000 | 2-Jun,2022 | 13-Jun,2022 | 29-Jun,2022
Actual
2 | Procurement of Stationery | AOCOED/G-F/NCB/002/22 |  |  | 70455522 | <100m | NCB | Post | Prior | Plan | 7-Mar,2022 | 18-Mar,2022 | 6-Apr,2022 | 9-May,2022 | 19-May,2022 | 2-Jun,2022 | 16-Jun,2022 | 17-Jun,2022 | 70455522 | 20-Jun,2022 | 4-Jul,2022 | 14-Jul,2022
Actual
3 | Procurement of Examination Materials | AOCOED/G/NCB/001/22 |  |  | 62850000 | <100m | NCB | Post | Prior | Plan | 22-Mar,2022 | 5-Apr,2022 | 12-Apr,2022 | 2-May,2022 | 13-May,2022 | 24-May,2022 | 2-Jun,2022 | 3-Jun,2022 | 62850000 | 9-Jun,2022 | 17-Jun,2022 | 6-Jul,2022
Actual
4 | Procurement of Teaching Consumables | AOCOED/G-F/NS/003/22 |  |  | 45931250 | <50m | NS | Post | Prior | Plan | 22-Mar,2022 | 30-Mar,2022 | 4-Apr,2022 | 18-Apr,2022 | 29-Apr,2022 | 9-May,2022 | 24-May,2022 | 26-May,2022 | 45931250 | 3-Jun,2022 | 17-Jun,2022 | 28-Jun,2022
Actual
5 | Procurement of Health Care Products | AOCOED/G/NS/002/22 |  |  | 16250000 | <50m | NS | Post | Prior | Plan | 4-Feb,2022 | 18-Mar,2022 | 30-Mar,2022 | 8-Apr,2022 | 20-Apr,2022 | 28-Apr,2022 | 10-May,2022 | 12-May,2022 | 16250000 | 18-May,2022 | 30-May,2022 | 13-Jun,2022
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| TOTAL |  |  |  | 205786772 |  |  |  |  | Plan | [8 empty] | 205786772
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual