## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/AGENCY : LASEMA
YEAR:2022
S/N | Activity Description | Package Number | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel & Transport (Local)-Quaterly Tranport within the State to strenghten local emergency in the LCDA& LGAs,Transportation of the Officers in the Agency. | PPA/NP/NM/002/21 | PPA/NP/NM/001/22 | 15,000,000.00 | Plan | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
Actual
2 | Special Duties and Expenses(Special Allowance for all LASEMA staff in the year 2022) | PPA/NP/NM/002/21 | PPA/NP/NM/002/22 | 62,820,000.00 | Plan | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 5235000 | 62,820,000.00
Actual
3 | Audit Expenses(a). Statutory Annual Audit Fee =N1,000,000.00 (b)Sensitization program on payment due process=N600,000.00 (c) Periodic visit to all zone/unit/base =N300,000.00 (d) Quaterly Audit Committee meetings =N400,000.00 (e) Miscelaneous/Other Audit Assignment=N200,000.00 | PPA/NP/NM/002/21 | PPA/NP/NM/003/22 | 2500000 | Plan | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 2500000 | 2500000
Actual
4 | Quaterly Stakeholders meetings |  | PPA/NP/003/22 | 20,000,000.00 | Plan | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67 | 1666666.67
[5 empty] | Actual | [12 empty] | 20000000
5 | Miscellaneous(Servicing of Meetings,Dissemination of Information,Public Service Celebration, Purchase of Newspapers et.c) | PPA/NP/NM/002/21 | PPA/NP/NM/005/22 | 7,380,000.00 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 7,380,000.00
Actual
6 | General Utility Services e.g Payment of Telephone Bills, DSTV, Purchase of Recharge Cards et.c |  | PPA/NP/NM/006/22 | 1791000 | Plan | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 149250 | 1791000
Actual
7 | Planning, Reseach & Statistics Unit Expenses (a) Documents for Personnel Cost for 2023 =200,000.00 (b) Annual Budget Preparation for 2023 =300,000.00 © Research & Documentation = 300,000.00 (d) Other unexpected Expenses pertaining to PRS Unit = 200,000.00 |  | PPA/NP/NM/007/22 | 1000000 | Plan | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 83333 | 1000000
Actual
8 | Procurement Unit Expenses (a) Inauguration of the yr.2022 Procurement Planning Committee = 150,000.00 (b) Presentation of the Agency Budget at Procurement Clinic 2023 = 200,000.00 © Preparation of bidding document/RFQ=N350,000.00 (D) Procurement Audit Exercise for yr. 2022 =N250,000.00 (e) Monitoring of project yr 2022=300,000.00 (f) Procurement Process Review yr 2022 = 250,000.00 |  | PPA/NP/NM/008/22 | 1500000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
Actual
| Standing Operational Imprest: Funds expended on every emergency scenee.g Road Accident,Fire, Building Collapse, Boat Mishap et.c |  | PPA/NP/NM/008/22 | 100000000 | Plan | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 8333333.33 | 100000000
Actual
357020000

## WTC
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LASEMA
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Capacity Building(Training of all staff on their various discipline GL 1-17)) | PPA/S-WTC/S/001/22 | To facilitate the commitment of the staffs towards their respective assignment. | 124 | 1week | Plan |  |  |  |  | 30000000
Actual
2 | Capacity Building(Training for only seniour Officers on GL 7-17 | PPA/S-WTC/S/002/22 | Essential Training with their respective institute e.g CIPSMN, ICAN et.c | 35 | 1week | Plan |  |  |  |  | 11000000
Actual
3 | Conference & Seminars (Department/Units Conference, COWLSO et.c | PPA/S-WTC/S/003/21 | Kind of Familirization with other line and agencies e.g Emergency Disaster Training | 110 | 1week | Plan |  |  |  |  | 14000000
Actual
55000000

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING
MDA: LASEMA
BUDGET YEAR: 2022
| Contract Description |  | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  |  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual |  | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Maintenance of Office Building e.g Electrical, Fumigation Et.c |  | PPA/S-NC/SS/001/22 | 1 | Lot 1 | 1200000 | <10m | SS | Plan | Post | post | 2022-01-21 | 2022-01-28 | 2022-02-06 | 2022-02-20 | 2022-03-06 | 2022-03-10 | 2022-03-13 | Plan | 2022-03-15 | 2022-03-17 | 1200000 | 2022-04-15 | 2022-04-20 | 2022-06-21 | Inspection & Final Acceptance
[9 empty] | Actual | [9 empty] | Actual
2 | Motor Vehicle repair & Maintenance |  | PPA/S-NC/SS/002/22 |  | 1 | 9000000 | <50M | SS | Plan | post | Post | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | Plan | 2022-03-02 | 9,Mar,2022 | 17940000 | 2022-03-13 | 23,Mar,2022 | 30,Mar,2022 | 2022-06-25
[9 empty] | Actual | [9 empty] | Actual
3 | Maintenance & Repair of Plant/Machineries |  | PPA/S-NC/NCB/006/003/22 |  | 1 | 12000000 | <50M | SS | Plan | prior | prior | 2022-01-03 | 2022-01-13 | 2022-01-20 | 2022-01-27 | 2022-02-03 | 2022-02-10 | 2022-02-17 | Plan | 2022-02-24 | 2022-02-24 | 12000000 | 2022-03-02 | 2022-03-09 | 2022-03-13
[9 empty] | Actual | [9 empty] | Actual
4 | Publicity & Press Coveragei.e Production of radio jingles,press briefing et.c |  | PPA/S-NC/SS/006/003/22 |  | 1 | 2000000 | <10M | SS | Plan | post | post | NA | NA | NA | NA | NA | NA | NA | Plan | NA |  | 2000000 | NA | NA | NA
[9 empty] | Actual | [9 empty] | Actual
5 | Monthly Upkeep/Maintanance allowance for 5 zonal offices |  | PPA/S-NC-F/SS/001/22 |  | 5 | 80000000 | <100M | SS | Plan | prior | prior | 2022-01-03 | 2022-01-23 | 2022-01-20 | 2022-01-30 | 2022-02-03 | 2022-02-15 | 2022-02-17 | Plan | 2022-02-28 | 2022-02-24 | 80000000 | 2022-03-02 | 2022-03-09 | 2022-03-13
[9 empty] | Actual |  |  | , | [6 empty] | Actual
6 | Celebration/Ceremony (e.g World Disaster Day,LASEMA at Fifteen years, SEMA Summit) |  | PPA/S-NC/SS/002/22 |  | 1 | 33000000 | <N50 | SS | Plan | prior | prior | 2022-03-03 | 2022-01-23 | 2022-04-20 | 2022-01-30 | 2022-05-03 | 2022-02-15 | 2022-02-17 | Plan | 2022-02-28 | 2022-02-24 | 33000000 | 2022-03-02 | 2022-03-09 | 2022-03-13
[9 empty] | Actual | [9 empty] | Actual
7 | Retreat/Summit(Training of Emergency Mgt. Volunteer 2022 |  | PPA/S-NC/SS/003/22 |  | 1 | 23333306 | <50M | SS | Plan | prior | prior | 2022-01-03 | 2022-01-23 | 2022-01-20 | 2022-01-30 | 2022-02-03 | 2022-02-15 | 2022-02-17 | Plan | 2022-02-28 | 2022-02-24 | 23333306 | 2022-03-02 | 2022-03-09 | 2022-03-13
[9 empty] | Actual | [9 empty] | Actual
8 | Provision for Victims of Emergency/Disaster that may need to be sheltered in any of the Agency Camp |  | PPA/S-NC/SS/002/22 |  | 1 | 10000000 | <N50 | SS | Plan | prior | prior | 2022-03-03 | 2022-01-23 | 2022-04-20 | 2022-01-30 | 2022-05-03 | 2022-02-15 | 2022-02-17 | Plan | 2022-02-28 | 2022-02-24 | 10000000 | 2022-03-02 | 2022-03-09 | 2022-03-13
[9 empty] | Actual | [9 empty] | Actual
9 | Repair of 5 Laptops, 10 Nos HP Laserjet Printers,Snanners,Shreder et.c |  | PPA/S-NC/SS/002/22 |  | 1 | 400000 | <N50 | SS | Plan | prior | prior | 2022-03-03 | 2022-01-23 | 2022-04-20 | 2022-01-30 | 2022-05-03 | 2022-02-15 | 2022-02-17 | Plan | 2022-02-28 | 2022-02-24 | 400000 | 2022-03-02 | 2022-03-09 | 2022-03-13
[9 empty] | Actual | [9 empty] | Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LASEMA
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION | [8 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Fuelling for LASEMA light and heavy duty vehicle for daily operationa activities |  | PPA/G-F/NS/001/22 | Lot | 280000000 | <500m | NS | prior | Post | Plan | 2022-02-28 | 2022-03-05 | 2022-03-13 | 2022-03-27 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-17 | 280000000 | 2022-04-22 | 2022-04-29 | 2022-05-05 | 2022-06-05 | 2022-07-05
Actual
2 | Procurement of Uniform & Protective Outfits for 150 operations Staff |  | PPA/G/NS/002/22 | Lot | 5000000 | <50m | NS | Post | Post | Plan | 2022-06-24 | 2022-07-08 | 2022-06-24 | 2022-07-08 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 5000000 | 2022-07-26 | 2022-07-30 | 2022-09-30 | 2022-10-10 | 2022-11-14
Actual
3 | Procurement of Stationeries |  | PPA/G-F/NS/003/22 | Lot | 6000000 | <10m | NS | Post | Post | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-24 | 2022-03-26 | 6000000 | 2022-03-30 | 2022-04-05 | 2022-07-14 | 2022-08-14 | 2022-09-14
Actual
4 | Procurement of Management Information System Equipment e.g. Laptop, Destop, Printers et.c |  | PPA/G/NS/004/22 | Lot | 500000 | <10m | NS | Post | Post | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-25 | 2022-03-30 | 3000000 | 2022-03-27 | 2022-04-09 | 2022-04-16 | 2022-05-16 | 2022-06-16
Actual
5 | Purchase of some computer accessories e.g UPS, Keboard, mouse, Flash drive hard et.c |  | PPA/G/NS/005/22 | Lot | 100000 | <10m | NS | Post | Post | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-25 | 2022-03-30 | 3000000 | 2022-03-27 | 2022-04-09 | 2022-04-16 | 2022-05-16 | 2022-06-16
Actual
6 | Procurement of Equipment for Public Affairs Unit(Drone, PAS, Photocopier et.c) 1. Laptops=40,Destop=40,Printers=40,UPS=40 |  | PPA/G/NS/001/2022 | Lot | 40000000 | <100m | NS | Prior | Prior | Plan | 2022-02-28 | 2022-03-05 | 2022-03-13 | 2022-03-27 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-17 | 40000000 | 2022-04-22 | 2022-04-29 | 2022-05-05 | 2022-06-05 | 2022-07-05
Actual
7 | Furnishing of LASEMA Response Unit in LGA/LCDA |  | PPA/G/NS/002/2022 | Lot | 40000000 | <100m | NS | Prior | Prior | Plan | 2022-06-24 | 2022-07-08 | 2022-06-24 | 2022-07-08 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 40000000 | 2022-07-26 | 2022-07-30 | 2022-09-30 | 2022-10-10 | 2022-11-14
Actual
8 | Procurement of 3 Toyota Hilux Van,1 Toyota Coaster Bus, 4 Power Motor Bike |  | PPA/G/NS/003/2022 | Lot | 244000000 | <500m | NCB | Prior | Prior | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-24 | 2022-03-26 | 244000000 | 2022-03-30 | 2022-04-05 | 2022-07-14 | 2022-08-14 | 2022-09-14
Actual
9 | Procurement of Light Rescue Equipment (Shreader, cutter,Air lifting Bag, Ram Power Unit,et.c to strenghten Local Emergency Management Committee. |  | PPA/G/NS/004/22 | Lot | 150000000 | <500m | NCB | Prior | Prior | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-25 | 2022-03-30 | 150000000 | 2022-03-27 | 2022-04-09 | 2022-04-16 | 2022-05-16 | 2022-06-16
Actual
| 1 | Director General/CEO |  |  | Chairman
| 2 | The Procurement Officer |  |  | Secretary
| 3 | Director, DA&HR |  |  | Member
| 4 | Director, Engineering/Operations |  |  | Member
| 5 | Asst. Director, Finance and Accounts |  |  | Member
| 6 | Head, Public Relations Unit |  |  | Member
| 7 | Head, ICT |  |  | Member
| 8 | Head, Audit Unit |  |  | Member
| 9 | Head, Planning Unit |  |  | Member

## Good(Capital)
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LASEMA
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION | [7 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[10 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Equipment for Public Affairs Unit(Drone, PAS, Photocopier et.c) 1. Laptops=40,Destop=40,Printers=40,UPS=40 | PPA/G/NS/001/2022 | Lot | 40000000 | <100m | NS | Prior | Prior | Plan | 2022-02-28 | 2022-03-05 | 2022-03-13 | 2022-03-27 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-17 | 40000000 | 2022-04-22 | 2022-04-29 | 2022-05-05 | 2022-06-05 | 2022-07-05
Actual
2 | Furnishing of LASEMA Response Unit in LGA/LCDA | PPA/G/NS/002/2022 | Lot | 40000000 | <100m | NS | Prior | Prior | Plan | 2022-06-24 | 2022-07-08 | 2022-06-24 | 2022-07-08 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-12 | 40000000 | 2022-07-26 | 2022-07-30 | 2022-09-30 | 2022-10-10 | 2022-11-14
Actual
3 | Procurement of 3 Toyota Hilux Van,1 Toyota Coaster Bus, 4 Power Motor Bike | PPA/G/NS/003/2022 | Lot | 244000000 | <500m | NCB | Prior | Prior | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-24 | 2022-03-26 | 244000000 | 2022-03-30 | 2022-04-05 | 2022-07-14 | 2022-08-14 | 2022-09-14
Actual
4 | Procurement of Light Rescue Equipment (Shreader, cutter,Air lifting Bag, Ram Power Unit,et.c to strenghten Local Emergency Management Committee. | PPA/G/NS/004/22 | Lot | 150000000 | <500m | NCB | Prior | Prior | Plan | 2022-01-23 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-05 | 2022-03-19 | 2022-03-25 | 2022-03-30 | 150000000 | 2022-03-27 | 2022-04-09 | 2022-04-16 | 2022-05-16 | 2022-06-16
Actual