## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE PHYSICAL PLANNING PERMIT AUTHORITY
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel & Transport Cost - (Local) | PPA/NP/NM/001/22 | 10360000 | Plan
Actual
2 | General Utility Services | PPA/NP/NM/002/22 | 4,000,000.00 | Plan
Actual
3 | Miscellaneous | PPA/NP/NM/003/22 | 1,500,000.00 | Plan
Actual
4 | Upkeep for District offices | PPA/NP/NM/004/22 | 33537718 | Plan
Actual
5 | Grants, Contribution & Subvention | PPA/NP/NM/005/22 | 500000 | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE PHYSICAL PLANNING PERMIT AUTHORITY
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Workshop and Training | PPA/S-WTC/001/22 |  | 10 PARTICIPANTS | 3 DAYS | Plan |  | 9000000 |  |  | 9000000
Actual
2 | Seminar and Conferences | PPA/S-WTC/.002/22 |  | Town Planner (31), Admin & HR (6), Account (3), Auditor (1), Planning Unit (1), Procurement (1), Legal (1), ICT (1) |  | Plan |  | 16000000 |  |  | 16000000
Actual
4 | [5 empty] | Plan
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN NON - CONSULTING SERVICE
MINISTRY/ AGENCY: LAGOS STATE PHYSICAL PLANNING PERMIT AUTHORITY
BUDGET YEAR: 2021 | [9 empty] | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
[10 empty] | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | [7 empty] | Plan
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual | [9 empty] | Actual
Motor Vehicle Maintenance & Repairs | PPA/S-NC-F/NS/001/22 | 01 | Various | 6000000 | <10m | NS | Plan | POST | POST | 4/01/2022 | 11/01/2022 | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | Plan | 22/02/2022 |  | 6000000 | 01/03/2022 | 08/03/2022 | 15/03/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Office Building | PPA/S-NC-F/NS/002/22 | 01 | Various | 6000000 | <10m | NS | Plan | POST | POST | 11/01/2022 | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | Plan | 01/03/2022 |  | 6000000 | 08/03/2022 | 15/03/2022 | 22/03/2022
[7 empty] | Actual | [9 empty] | Actual
Retreat for Management Staff | PPA/S-NC-F/NS/003/22 | 01 | Various | 10000000 | <10M | NS | Plan | POST | PRIOR | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | Plan | 08/03/2022 |  | 10000000 | 15/03/2022 | 22/03/2022 | 29/03/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of GIS Equipment | PPA/S-NC-F/NS/004/22 | 01 | Various | 1500000 | <10M | NS | Plan | POST | POST | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | Plan | 15/03/2022 |  | 1500000 | 22/03/2022 | 29/03/2022 | 4/4/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance and Repair of Generating Set | PPA/S-NC-F/NS/005/22 | 01 | Various | 500000 | <10M | NS | Plan | POST | POST | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | Plan | 22/03/2022 |  | 500000 | 29/03/2022 | 04/04/2022 | 11/04/2022
[7 empty] | Actual | [9 empty] | Actual
Goods procured for Press Coverage & Enlightenment Campaign | PPA/S-NC-F/NS/006/22 | 01 | Various | 25000000 | >10M | NS | Plan | POST | PRIOR | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | Plan | 29/03/2022 |  | 25000000 | 04/04/2022 | 11/4/2022 | 18/04/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Office Equipment | PPA/S-NC-F/NS/007/22 | 01 | Various | 3500000 | <10M | NS | Plan | POST | POST | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | Plan | 04/04/2022 |  | 3500000 | 11/4/2022 | 18/04/2022 | 25/04/2022
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE PHYSICAL PLANNING PERMIT AUTHORITY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
| Post Physical Planning Technical Report Clearance Audit | PPA/S-C/CQS/001/22 |  | LUMPSUM | 2000000 | POST | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
[7 empty] | Actual | 4/01/2022 | 11/01/2022 | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 2000000 | 04/04/2022 | 11/04/2022 | 18/04/2022 | 25/04/2022 | 01/05/2022
| Direct approach and Consultation with various Community Development Association | PPA/S-C/CQS/002/22 |  | Lumpsum | 5000000 | POST | Plan | 11/01/2022 | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 04/04/2022 | 5000000 | 11/04/2022 | 18/04/2022 | 25/04/2022 | 02/05/2022 | 09/05/2022
Actual
| Interactive Session with stakeholders | PPA/S-C/CQS/003/22 |  | Timebased | 26000000 | PRIOR | Plan | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 04/04/2022 | 11/04/2022 | 26000000 | 18/04/2022 | 25/04/2022 | 02/05/2022 | 09/05/2022 | 16/05/2022
Actual
| Preparation of Development Guide for Ajido, Badagry, Odogunyan and Adeba Parcel A & B | PPA/S-C/CQS/004/22 |  | Lumpsum | 68775200 | PRIOR | Plan | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 04/04/2022 | 11/04/2022 | 18/04/2022 | 68775200 | 25/04/2022 | 02/05/2022 | 09/05/2022 | 16/05/2022 | 23/05/2022
Actual
| Preparation of Georeferenced Mapping | PPA/S-C/CQS/005/22 |  | Lumpsum | 27500000 | PRIOR | Plan | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 04/04/2022 | 11/04/2022 | 18/04/2022 | 25/04/2022 | 27500000 | 02/05/2022 | 09/05/2022 | 16/05/2022 | 23/05/2022 | 30/05/2022
Actual

## goods
PROCUREMENT PLAN FOR GOODS
MINISTRY/AGENCY: LAGOS STATE PHYSICAL PLANNING PERMIT AUTHORITY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Computer Equipment and Accessories | LASPPA/G-F/NS/001/212 | 01 | Various | 34755000 | >100m | NS | POST | PRIOR | Plan | 18/01/2022 | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 34755000 | 15/03/2022 | 22/03/2022 | 29/03/2022 |  | AO
Actual
2 | Procurement and Installation of Security Gadgets and its devices | LASPPA/G-F/NS/002/22 | 01 | Various | 2000000 | >50m | NS | POST | POST | Plan | 25/01/2022 | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 2000000 | 22/03/2022 | 29/03/2022 | 01/04/2022 |  | AO
Actual
3 | Procurement of Office furniture for 30 District Office & Headquarters | LASPPA/G-F/NS/003/22 | 01 | Various | 50000000 | >50m | NS | POST | PRIOR | Plan | 01/02/2022 | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 50000000 | 29/03/2022 | 01/04/2022 | 08/04/2022 |  | AO
Actual
4 | Procurement of Monitoring/Enforcement Equipment for Monitoring and Compliance Unit (MCU) | LASPPA/G-F/NS/004/22 | 1 | Various | 25000000 | >50m | NS | POST | PRIOR | Plan | 08/02/2022 | 15/02/2022 | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 25000000 | 01/04/2022 | 08/04/2022 | 15/04/2022
Actual
5 | Procurement of Tyres & Batteries (Dunlop & Michellin) | LASPPA/G-F/NS/005/22 | 01 | Various | 4000000 | <10m | NS | POST | POST | Plan | 22/02/2022 | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 01/04/2022 | 08/04/2022 | 4000000 | 15/04/2022 | 22/04/2022 | 29/04/2022 |  | AO
Actual
6 | Procurement of Uniforms & Protective Outfits | LASPPA/G-F/NS/006/22 | 01 | Various | 3500000 | <5m | NS | POST | POST | Plan | 01/03/2022 | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 01/04/2022 | 08/04/2022 | 15/04/2022 | 3500000 | 22/04/2022 | 29/04/2022 | 2022-02-05 |  | AO
Actual
7 | Procurement of Management Information System | LASPPA/G-F/NS/007/22 | 01 | Various | 10000000 | <10m | NS | POST | PRIOR | Plan | 08/03/2022 | 15/03/2022 | 22/03/2022 | 29/03/2022 | 01/04/2022 | 08/04/2022 | 15/04/2022 | 22/04/2022 | 10000000 | 29/04/2022 | 02/05/2022 | 09/05/2022 |  | AO
Actual
8 | Procurement of First Aid Drugs | LASPPA/G-F/NS/008/22 | 01 | Various | 2000000 | <5m | NS | POST | POST | Plan | 22/03/2022 | 29/03/2022 | 01/04/2022 | 08/04/2022 | 15/04/2022 | 22/04/2022 | 29/04/2022 | 2022-02-05 | 2000000 | 09/05/2022 | 16/05/2022 | 23/05/2022 |  | AO
Actual
9 | Procurement of Professional Books and Consumables for One Dept and Four Units (Procurement, Legal, Audit, Account & Budget) in HQ | LASPPA/G-F/NS/009/22 | 01 | Various | 8000000 | <10m | NS | POST | POST | Plan | 29/03/2022 | 01/04/2022 | 08/04/2022 | 15/04/2022 | 22/04/2022 | 29/04/2022 | 2022-02-05 | 2022-09-05 | 8000000 | 16/05/2022 | 23/05/2022 | 30/05/2022 |  | AO
Actual
10 | Procurement of Library Books (Library Services) | LASPPA/G-F/NS/010/22 | 01 | Various | 6500000 | <5m | NS | POST | POST | Plan | 01/04/2022 | 08/04/2022 | 15/04/2022 | 22/04/2022 | 29/04/2022 | 2022-02-05 | 2022-09-05 | 16/05/2022 | 6500000 | 23/05/2022 | 30/05/2022 | 2022-01-06 |  | AO
Actual
11 | Procurement for Statistical Publication | LASPPA/G-F/NS/011/22 | 01 | Various | 12000000 | <10m | NS | POST | PRIOR | Plan | 08/04/2022 | 15/04/2022 | 22/04/2022 | 29/04/2022 | 2022-02-05 | 2022-09-05 | 16/05/2022 | 23/05/2022 | 12000000 | 30/05/2022 | 01/06/2022 | 2022-08-06 |  | AO
Actual
12 | Procurement of External Auditor Materials | LASPPA/G-F/NS/012/22 | 01 | Various | 2500000 | <5m | NS | POST | POST | Plan | 2022-02-05 | 2022-09-05 | 16/05/2022 | 23/05/2022 | 30/05/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 2500000 | 22/06/2022 | 29/06/2022 | 2022-01-07 |  | AO
Actual
13 | Procurement of 5 units of photocopying machine with stand | LASPPA/G-F/NS/013/22 | 01 | Various | 6000000 | <5m | NS | POST | POST | Plan | 23/05/2022 | 30/05/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | 29/06/2022 | 2022-01-07 | 6000000 | 08/07/2022 | 15/07/2022 | 22/07/2022 |  | AO
Actual
14 | Motor Vehicle Fuel Consumption | LASPPA/G-F/NS/014/22 | 01 | Various | 10360000 | <20M | NS | POST | PRIOR | Plan | 30/05/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | 29/06/2022 | 2022-01-07 | 08/07/2022 | 10340000 | 15/07/2022 | 22/07/2022 | 29/07/2022 |  | AO
Actual
15 | Procurement of Stationeries and Consumable items | LASPPA/G-F/NS/015/22 | 01 | Various | 6676000 | <10M | NS | POST | POST | Plan | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | 29/06/2022 | 2022-01-07 | 08/07/2022 | 15/07/2022 | 6676120 | 22/07/2022 | 29/07/2022 | 2022-01-08 |  | AO
Actual
16 | Procurement of Annual Fairs & Exhibition Materials | LASPPA/G-F/NS/016/22 | 01 | Various | 3000000 | <5m | NS | POST | POST | Plan | 15/06/2022 | 22/06/2022 | 29/06/2022 | 2022-01-07 | 08/07/2022 | 15/07/2022 | 22/07/2022 | 29/07/2022 | 3000000 | 2022-01-08 | 2022-08-08 | 15/08/2022 |  | AO
Actual
17 | Monitoring and Compliance Materials | LASPPA/G-F/NS/017/22 | 01 | Various | 35871376 | <50m | NS | POST | PRIOR | Plan | 29/06/2022 | 2022-01-07 | 08/07/2022 | 15/07/2022 | 22/07/2022 | 29/07/2022 | 2022-01-08 | 2022-08-08 | 35871376 | 15/08/2022 | 22/08/2022 | 29/08/2022 |  | AO
Actual
18 | Printing of Security/Statutory Notices Materials | LASPPA/G-F/NS/018/22 | 01 | Various | 15000000 | <10m | NS | POST | PRIOR | Plan | 08/07/2022 | 15/07/2022 | 22/07/2022 | 29/07/2022 | 2022-01-08 | 2022-08-08 | 15/08/2022 | 22/08/2022 | 15000000 | 29/08/2022 | 2022-02-09 | 2022-09-09 |  | AO
Actual
19 | Special Duties | LASPPA/G-F/NS/019/22 | 01 | Various | 25119170 | <5m | NS | POST | PRIOR | Plan | 22/07/2022 | 29/07/2022 | 2022-01-08 | 2022-08-08 | 15/08/2022 | 22/08/2022 | 29/08/2022 | 2022-02-09 | 25119170 | 2022-09-09 | 16/09/2022 | 23/09/2022 |  | AO
Actual
20 | LASPPPA E - PP Records and Maintenance | LASPPA/G-F/NS/020/22 | 01 | Various | 12000000 | <5m | NS | POST | PRIOR | Plan | 29/07/2022 | 2022-01-08 | 2022-08-08 | 15/08/2022 | 22/08/2022 | 29/08/2022 | 2022-02-09 | 2022-09-09 | 12000000 | 16/09/2022 | 23/09/2022 | 30/09/2022 |  | AO
Actual
21 | Inventory of Physical Planning Activities in Lagos State (I) Educational Institution (ii) Health Institution | LASPPA/G-F/NS/021/22 | 01 | Various | 15000000 | <10m | NS | POST | PRIOR | Plan | 2022-08-08 | 15/08/2022 | 22/08/2022 | 29/08/2022 | 2022-02-09 | 2022-09-09 | 16/09/2022 | 23/09/2022 | 15000000 | 30/09/2022 | 2022-03-10 | 2022-10-10
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE PHYSICAL PLANNING PERMIT AUTHORITY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | Construction of 2 District Offices & Renovation of HQ and District Offices | LASPPA/W-F/NS/001/212 |  | 354637027.71 | >100M | NS | LUMP | POST | Plan | PRIOR | 1/2/2022 | 8/2/2022 | 15/02/2022 | 22/02/2022 | 28/02/2022 | 07/03/2022 | 14/03/2022 | 21/03/2022 | 354637027.71 | 28/03/2022 | 4/4/2022 | 11/4/2022 | 18/04/2022
Actual
Plan
Actual

## Sheet4
DULY SIGNED BY MEMBERS OF PROCUREMENT PLANNING COMMITTEE
CHAIRMAN:
ACCOUNTANT:
LEGAL:
AUDITOR:
PLANNING AND BUDGET:
RESEARCH & STATISTICS:
USER DEPARTMENT:
SECRETARY: