## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT I(LASEDI)
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | PAYMENT FOR TRAVEL & TRANSPORT | LASEDI/NPI/NM/001 | 5,030,000.00 | Plan | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 419166.67 | 5,030,000.00
Actual
2 | GENERAL UTILITY SERVICES | LASEDI/NPI/NM/002 | 4047000 | Plan | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 4047000
Actual
3 | MISCELLANEOUS | LASEDI/NPI/NM/003 | 1790000 | Plan |  |  | 198888.89 | 198888.89 | 198888.89 | 198888.89 | 198888.89 | 198888.89 | 198888.89 | 198888.89 | 198888.89 |  | 2800000
Actual
4 | SPECIAL DUTIES EXPENSES | LASEDI/NPINMC/004 | 45,170,500.00 | Plan |  |  | 15056833.3 |  |  |  | 15056833.3 |  |  |  |  | 15056833.3 | 45,170,500.00
Actual
5 | WORLD TEACHERS DAY | LASEDI/NPI/NM/005 | 5,000,000.00 | Plan |  | 1250000 |  |  | 1250000 |  |  |  |  | 1250000 | 1250000 |  | 5,000,000.00
Actual
6 | AUDIT EXPENSES | LASEDI/NPI/NM/006 | 2 ,500,000.00 | Plan |  |  | 500000 |  | 500000 |  | 500000 |  |  | 500000 |  | 500000 | 2,500,000.00
Actual
7 | ANNUAL AWARDS & REWARDS | LASEDI/NPI/NM/007 | 8,000,000.00 | Plan | [6 empty] | 2666666.67 | 2666666.67 |  |  | 2666666.67 |  | 8000000
Actual
8 | RUNNING COST FOR SCHOOL (SNR & JNR) | LASEDI/NPI/NM/008 | 297,000,000.00 | Plan | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 24750000 | 297,000,000.00
Actual
9 | MONITORING EXPENSES FOR QUALITY ASSURANCE OFFICERS | LASEDI/NPI/NM/009 | 5,000,000.00 | Plan | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 416666.67 | 5000000
Actual
10 | PLANNING RESEARCH & STATISTICS UNIT EXPENSES. | LASEDI/NPI/NM/010 | 3,500,000.00 | Plan |  |  |  |  | 700000 | 700000 |  |  |  | 700000 | 700000 | 700000 | 3,500,000.00
Actual
11 | PROCUREMENT EXPENSES | LASEDI/NPI/NM/011 | 800,000.00 | Plan | 200000 |  |  | 200000 |  |  | 200000 |  |  | 200000 |  |  | 800000
Actual
12 | PUBLIC AFFAIR EXPENSES | LASEDI/NPI/NM/012 | 500,000.00 | Plan |  |  |  |  | 100000 | 100000 |  |  |  | 100000 | 100000 | 100000 | 500,000.00
Actual
13 | WELFARE EXPENSES | LASEDIV/NPI/NM/013 | 6,500,00.00 | Plan |  |  |  |  | 1300000 | 1300000 |  |  |  | 1300000 | 1300000 | 1300000 | 6,500,00.00
Actual
14 | SPORT DEVELOPMENT GRANTS | LASEDIV/NPI/NM/014 | 17000000 | Plan |  |  | 4250000 |  |  | 4250000 |  |  | 4250000 |  |  | 4250000 | 17000000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT I (LASEDI)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP AND TRAINING for Officers within Lagos State. | LASEDI/S-WTC/001/22 | TRAININNG OF STUDENTS | LASEDII/SS/001/22 | TO TRAIN STUDENT | Plan |  |  |  |  | 3000000
Actual
2 | CONFERENCE & SEMINAR | LASEDI/S-WTC/002/22 | LEADERSHIP TRAINING | LASEDII/SS/002/22 | ENHANCE CAPACITY BUILDING | Plan |  |  |  |  | 6.700,000.00
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/DEPARTMENT/AGENCY : LAGOS STATE EDUCATION DISTRICT I (LASEDI)
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | LASEDI/S-NC/LC/001/22 |  |  | 4162500 | <10M | Single Sourcing Selection | #REF! | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 7/5/22 | 14/5/22 | Plan | 24/5/22 | 24 Hours | 4162500 | 24/8/22 | 15/6/22 | 13/7/22 | 30/7/22
[7 empty] | #REF! | [9 empty] | Actual
UPKEEP OF TEACHERS BUS & GENERATORS | LASEDI/S-NC/LC/002/22 |  | 7 | 10000000 | <10M |  |  | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 10/5/22 | 16/5/22 | Plan | 25/5/22 | 24 Hours | 7276800 | 24/8/22 | 15/6/22 | 13/7/22 | 28/7/22
WEAC REPORT EVALUATION WORK | LASEDI/S-NC/LC/003/22 |  |  | 4000000 | <10M | Single Sourcing Selection | Plan | POST | POST | N/A | N/A | N/A | N/A | N/A | 2/6/22 | 10/6/22 | Plan | 22/6/22 | 48 Hours | 4000000 | 30/6/22 | N/A | 17/8/22 | 31/8/22
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT I (LASEDI)
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | PROMOTION EXPENSES | LASEDI/S-C/QCBS/001/22 | Single Source Selectiion | TIME-BASE | 3000000 | POST | Plan | 22/2/22 | 4/3/22 | N/A | N/A | 17/3/22 | 24/3/22 | 6/4/22 | N/A | N/A | N/A | 13/4/22 | 16/4/22 | N/A | N/A | 2500000 | 22/4/22 | 29/4/22 | 12/5/22 | 9/6/22 | 23/6/22 | 2500000
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE EDUCATION DISTRICT I (LASEDI)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | MOTOR VEHICLE REPAIRS: Procurement of tyres for all vehicles, teachers staff bus and others. | LASEDI/G-F/NS/001/22 |  | VARIOUS | 4400000 | <10M | NS | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 1/4/22 | 11/4/22 | 21/4/22 | 30/6/22 | 4/7/22
Actual
2 | MOTOR VEHICLE FUEL CONSUMPTION: Yearly Procurement of fuel for all operational Vehicle & Teachers Bus AND FUEL DUMP. | LASEDI/G-F/NS/002/22 |  | 532 | 11538000 | <50M | DC | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2/3/22 | 24 Hours | 11538000 | 30/3/22 | 6/4/22 | 20/4/22 | 25/5/22 | 26/5/22
Actual
3 | STATIONERIES: Procurement of various office stationeries items as follows; i. Printing of 40 Reams of Letter Head Paper ii. 60 Reams of Duplicating & Photocopy Sheet . Iv. Other Accessories(Biro,Staplers, Cellotape, File Jackets e.t.c.) | LASEDVI/G-F/NS/003/22 |  | Framework | 7092500 | <10M | NS | POST | POST | Plan | 18/2/22 | 17/3/22 | 31/3/22 | 14/4/22 | 26/5/22 | 9/6/22 | 23/6/22 | 24 Hours | 7092500 | 21/7/22 | 29/7/22 | 4/8/22 | 2/9/22 | 6/9/22
Actual
4 | MANAGEMENT & INFORMATION SYSTEMS: Procurement of Computers accessories ;40 pck of HP toner, 4in 1 colour ink and provision for replacement of MIS item. | LASEDI/G/NS/001/22 |  | Various | 2500000 | <10M | NS | POST | POST | Plan | N/A | N/A | 6/4/22 | 20/4/22 | 1/6/22 | N/A | N/A | N/A | 2500000 | 15/6/22 | 22/6/212 | 6/7/22 | 3/8/22 | 4/8/22
Actual
5 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFITS | LASEDI/G/NS/002/22 |  | 1 | 2000000 | <10M | NS | POST | POST | Plan | 4/5/22 | 1/6/22 | 15/6/22 | 29/6/22 | 20/7/22 | 3/8/22 | 17/8/22 | 48 Hours | 2000000 | 13/9/22 | 21/9/22 | 5/10/22 | 2/11/22 | 7/11/22
Actual
6 | CATERING SERVICE FOR STAKEHOLDER'S MEETING AND OTHERS | LASEDI/G-F/NS/004/22 |  | Framework | 4000000 | <10M | NS | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2/3/22 | 24 Hours |  | 30/3/22 | 6/4/22 | 20/4/22 | 25/5/22 | 30/5/22
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE EDUCATION DISTRICT I (LASEDI)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | FACILITY MANAGEMENT | LASEDI/W/NCB/001/22 | 1 | 50053325 | 50053325 | NCB | BOQ | PRQ |  |  | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
[9 empty] | Plan | POST | 2WKS | 2WKS | 1WKS | 3WKS | 1WKS | 1WKS | 2WKS | 2WKS
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Sheet4
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT I (LASEDI)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP AND TRAINING for Officers within Lagos State. | LASEDI/WSH/DC/001 | TRAININNG OF STUDENTS | LASEDII/SS/001/22 | TO TRAIN STUDENT | Plan |  |  |  |  | 3000000
Actual
2 | CONFERENCE & SEMINAR | LASEDI/CON/SSS/002 | LEADERSHIP TRAINING | LASEDII/SS/002/22 | ENHANCE CAPACITY BUILDING | Plan |  |  |  |  | 6.700,000.00
Actual