## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | PAYMENT FOR TRAVEL & TRANSPORT | LASEDII/NPI/NM/001 | 5,702,000.00 | Plan | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 475166.67 | 5,702,000.00
Actual
2 | GENERAL UTILITY SERVICES | LASEDII/NPI/NM/002 | 4343456 | Plan | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 361954.67 | 4343456
Actual
3 | MISCELLANEOUS | LASEDII/NPI/NM/003 | 3809000 | Plan | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 317,416,67 | 3809000
Actual
4 | SPECIAL DUTIES EXPENSES | LASEDII/NPI/NM/004 | 81,871,871.00 | Plan | 20467967.8 |  |  | 20467967.8 |  |  | 20467967.8 |  |  | 20467967.8 |  |  | 81,871,871.00
Actual
5 | WORLD TEACHERS DAY | LASEDII/NPI/NM/005 | 5,000,000.00 | Plan | [8 empty] | 5,000,000.00 |  |  |  | 5,000,000.00
Actual
6 | AUDIT EXPENSES | LASEDII/NPI/NM/006 | 2,000,000.00 | Plan | 500000 |  |  | 500000 |  |  | 500000 |  |  | 500000 |  |  | 2,000,000.00
Actual
7 | ANNUAL AWARDS & REWARDS | LASEDII/NPI/NM/007 | 5,000,000.00 | Plan | 1,250.000.00 |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 |  |  | 5000000
Actual
8 | RUNNING COST FOR SCHOOL (SNR & JNR) | LASEDII/NPI/NM/008 | 330,000,000.00 | Plan | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 330000000
Actual
9 | PLANNING /MONITORING AND EVALUATION EXPENSES | LASEDII/NPI/NM/009 | 2,500,000.00 | Plan | 625000 |  |  | 625000 |  |  | 625000 |  |  | 625000 |  |  | 2500000
Actual
10 | PROCUREMENT EXPENSES | LASEDII/NPI/NM/011 | 3,000,000.00 | Plan | 750000 |  |  | 750000 |  |  | 750000 |  |  | 750000 |  |  | 3000000
Actual
11 | PUBLIC AFFAIR EXPENSES | LASEDII/NPI/NM/012 | 3,000,000.00 | Plan |  |  |  |  | #REF! | #REF! |  |  |  | #REF! | #REF! | 300000 | 1,500,000.00
Actual
12 | WELFARE EXPENSES | LASEDII/NPI/NM/013 | 3,000,000.00 | Plan | 750000 |  |  | 750000 |  |  | 750000 |  |  | 750000 |  |  | 3,000,000.00
Actual
13 | MONITORING ALLOWANCE FOR QUALITY ASSURANCE OFFICERS | LASEDII/NPI/NM/014 | 3,000,000.00 | Plan | 750000 |  |  | 750000 |  |  | 750000 |  |  | 750000 |  |  | 3,000,000.00
Actual
14 | SPORT DEVELOPMENT GRANTS | LASEDII/NPI/NM/015 | 5500000 | Plan |  | 5500000 | [10 empty] | 5500000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | TRAININNG STUDENTS | LASEDII/S-WTC/001/22 | TO TRAIN STUDENT |  |  | Plan |  |  |  |  | 1500000
Actual
2 | LEADERSHIP TRAINING | LASEDII/S-WTC/002/22 | ENHANCE CAPACITY BUILDING |  |  | Plan |  |  |  |  | 11500000
Actual
3 | VOCATIONAL TRAINNG | LASEDII/S-WTC/003/22 | ENHANCE CAPACITY BUILDING |  |  | Plan |  |  |  |  | 2000000
Actual
1500000

## Sheet2
0
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | TRAININNG OF STUDENTS | LASEDII/SS/001/22 | TO TRAIN STUDENT |  |  | Plan |  |  |  |  | 1500000
Actual
2 | LEADERSHIP TRAINING | LASEDII/SS/002/22 | ENHANCE CAPACITY BUILDING |  |  | Plan |  |  |  |  | 11500000
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/DEPARTMENT/AGENCY : LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | MAINTENANCE OF OFFICE BUILDING | LASEDII/S-NC/LC/001/22 |  | 3 | 4580001 | <10M | Frame work | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 7/5/22 | 14/5/22 | Plan | 24/5/22 | 24 Hours | 4580001 | 24/8/22 | 15/6/22 | 13/7/22 | 30/7/22
[8 empty] | Actual | [9 empty] | Actual
2 | UPKEEP OF TEACHERS BUS & GENERATORS | LASEDII/S-C-F/LC/001/22 |  | 7 | 7276800 | <10M | Frame work | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 10/5/22 | 16/5/22 | Plan | 25/5/22 | 24 Hours | 7276800 | 24/8/22 | 15/6/22 | 13/7/22 | 28/7/22
[8 empty] | Actual | [9 empty] | Actual
3 | MAINTENANCE & REPAIRS OF MOTOR VEHICLES | LASEDII/S-NC/LC/004/22 |  | 15 | 2250000 | <10M | Single Sourcing Selection | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 10/5/22 | 16/5/22 | Plan | 23/5/22 | 24 Hours | 2250000 | 22/8/22 | 15/6/22 | 29/7/22 | 29/7/22
[8 empty] | Actual | [9 empty] | Actual
4 | WEAC REPORT EVALUATION WORK | LASEDII/S-NC/LC/005/22 |  |  | 4000000 | <10M | Single Sourcing Selection | Plan | POST | POST | N/A | N/A | N/A | N/A | N/A | 2/6/22 | 10/6/22 | Plan | 22/6/22 | 48 Hours | 4000000 | 30/6/22 | N/A | 17/8/22 | 31/8/22
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | PROMOTION EXPENSES | LASEDII/S-C/QCBS/001/22 | Single Source Selectiion | TIME-BASE | 4000000 | POST | Plan | 22/2/22 | 4/3/22 | N/A | N/A | 17/3/22 | 24/3/22 | 6/4/22 | N/A | N/A | N/A | 13/4/22 | 16/4/22 | N/A | N/A | 2500000 | 22/4/22 | 29/4/22 | 12/5/22 | 9/6/22 | 23/6/22
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | MOTOR VEHICLE REPAIRS: Procurement of tyres battery for all vehicles, servicing and general repairs for teachers staff bus and others. | LASEDII/G-F/NS/001/22 |  | VARIOUS | 4580001 | <10M | NS | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 1/4/22 | 11/4/22 | 21/4/22 | 30/6/22 | 4/7/22
Actual
2 | MOTOR VEHICLE FUEL CONSUMPTION: Yearly Procurement of fuel for all operational Vehicle,Generator & Teachers Staff Bus | LASEDII/G-F/NS/002/22 |  | 532 | 13238000 | <10M | DC | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2/3/22 | 24 Hours | 13238000 | 30/3/22 | 6/4/22 | 20/4/22 | 25/5/22 | 26/5/22
Actual
3 | STATIONERIES: Procurement of various office stationeries items as follows; i. Printing of 40 Reams of Letter Head Paper ii. 60 Reams of Duplicating & Photocopy Sheet . Iv. Other Accessories(Biro,Staplers, Cellotape, File Jackets e.t.c.) | LASEDII/G-F/NS/003/22 |  | Framework | 5363544 | <10M | NS | POST | POST | Plan | 18/2/22 | 17/3/22 | 31/3/22 | 14/4/22 | 26/5/22 | 9/6/22 | 23/6/22 | 24 Hours | 5363544 | 21/7/22 | 29/7/22 | 4/8/22 | 2/9/22 | 6/9/22
Actual
4 | MANAGEMENT & INFORMATION SYSTEMS: Repair and Maintanance of Laptops ,Procurement of Computers accessories, replacement of MIS item. | LASEDII/G/NS/001/22 |  | Various | 2.000,000.00 | <10M | NS | POST | POST | Plan | N/A | N/A | 6/4/22 | 20/4/22 | 1/6/22 | N/A | N/A | N/A | 2.000,000.00 | 15/6/22 | 22/6/212 | 6/7/22 | 3/8/22 | 4/8/22
Actual
5 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFITS | LASEDII/G/NS/002/22 |  | 1 | 1,500,000.00 | <10M | NS | POST | POST | Plan | 4/5/22 | 1/6/22 | 15/6/22 | 29/6/22 | 20/7/22 | 3/8/22 | 17/8/22 | 48 Hours | 1,500,000.00 | 13/9/22 | 21/9/22 | 5/10/22 | 2/11/22 | 7/11/22
Actual
6 | SPORT DEVELOPMENT GRANTS | LASEDII/G/NS/003/22 |  | 1 | 5500000 | <10M | NS | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2/3/22 | 24 Hours | 5500000 | 30/3/22 | 6/4/22 | 20/4/22 | 25/5/22 | 27/5/22
Actual
7 | CATERING SERVICE FOR STAKEHOLDER'S MEETING AND OTHERS | LASEDII/G-F/NS/004/22 |  | Framework | 4000000 | <10M | NS | POST | POST | Plan |  |  |  | N/A | N/A | N/A | 2/3/22 | 24 Hours | 2,500,000.00 | 30/3/22 | 6/4/22 | 20/4/22 | 25/5/22 | 30/5/22
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
I | FACILITY MANAGEMENT | LASEDII/W/NCB/001/22 | I | 65923892 | 65923892 | NCB | BOQ | PRQ |  |  | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
[9 empty] | Plan | POST | 2WKS | 2WKS | 1WKS | 3WKS | 1WKS | 1WKS | 2WKS | 2WKS
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Sheet4
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT II (LASEDII)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP/TRAINNING | LASEDII/SS/001/22 | TO TRAIN STUDENT |  |  | Plan |  |  |  |  | 1500000
Actual
2 | CONFERNCE/SEMINAR | LASEDII/SS/002/22 | ENHANCE CAPACITY BUILDING |  |  | Plan |  |  |  |  | 11500000
Actual
3 | CAPACITY BUILDING | LASEDII/SS/003/22 | ENHANCE CAPACITY BUILDING |  |  | Plan |  |  |  |  | 2000000
Actual