## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT V (LASEDV)
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
STANDARD LINE / RUNNING COST
1 | TRAVEL & TRANSPORT | LASEDV/NP/NM/001/22 | 5,341,226.00 | Plan | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 445102.17 | 5,600,000.00
Actual
2 | GENERAL UTILITY SERVICES | LASEDV/NP/NM/002/22 | 5000574 | Plan | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 416714.5 | 5000574.5
Actual
3 | MISCELLANEOUS | LASEDV/NP/NM/003/22 | 1036701 | Plan |  |  | 115189 | 115189 | 115189 | 115189 | 115189 | 115189 | 115189 | 115189 | 115189 |  | 1036701
Actual
4 | MAINTENANCE AND REPAIRS OF MOTOR VEHICLES | LASEDV/NP/NM/004/22 | 1680000 | Plan |  |  | 186666.67 | 186666.67 | 186666.67 | 186666.67 | 186666.67 | 186666.67 | 186666.67 | 186666.67 | 186666.67 |  | 1680000
Actual
5 | MAINTENANCE OF OFFICE BUILDING | LASEDV/NP/NM/005/22 | 3752712 | Plan |  |  | 416968 | 416968 | 416968 | 416968 | 416968 | 416968 | 416968 | 416968 | 416968 |  | 3752712
Actual
6 | MOTOR VEHICLE FUEL CONSUMPTION | LASEDV/NP/NM/006/22 | 4291885 | Plan |  |  | 476876 | 476876 | 476876 | 476876 | 476876 | 476876 | 476876 | 476876 | 476876 |  | 4291885
Actual
7 | STATIONERY | LASEDV/NP/NM/007/22 | 3509235 | Plan |  |  | 389915 | 389915 | 389915 | 389915 | 389915 | 389915 | 389915 | 389915 | 389915 |  | 3509235
Actual
8 | SPECIAL DUTIES EXPENSES | LASEDV/NP/NM/008/22 | 48,600,000.00 | Plan |  |  | 16200000 |  |  |  | 16200000 |  |  |  |  | 16200000 | 48,600,000.00
Actual
9 | WORLD TEACHERS DAY | LASEDV/NP/NM/009/22 | 3,000,000.00 | Plan | [9 empty] | 3,000,000.00 |  |  | 3,000,000.00
Actual
10 | ANNUAL AWARDS & REWARDS | LASEDIV/NPI/DC/010/22 | 6,000,000.00 | Plan | [6 empty] | 2000000 | 2000000 |  |  | 2000000 |  | 6,000,000.00
Actual
11 | RUNNING COST FOR SCHOOL (SNR) | LASEDV/NP/NM/011/22 | 204,000,000.00 | Plan | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 204,000,000.00
Actual
12 | MONITORING EXPENSES FOR QUALITY ASSURANCE OFFICERS | LASEDV/NP/NM/012/22 | 4,160,000.00 | Plan | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 346667 | 4,160,000.00
Actual
13 | RUNNING COST FOR SCHOOL (JNR) | LASEDV/NP/NM/013/22 | 213,000,000.00 | Plan | 17750000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 4,500,000.00
Actual
14 | CELEBRATION & ANNUAL CEREMONIES | LASEDV/NP/NM/014/22 | 8,000,000.00 | Plan | [6 empty] | 2666666.67 | 2666666.67 |  |  | 2666666.67 |  | 8,000,000.00
Actual
15 | STAFF BUS EXPENSES | LASEDV/NP/NM/015/NM | 4,000,000.00 | Plan |  |  |  |  | 800000 | 800000 |  |  |  | 800000 | 800000 | 800000 | 4,000,000.00
Actual
16 | DISTRICT VOCATIONAL AQUIS (CENTERS) | LASEDV/NP/NM/016/22 | 6,000,000.00 | Plan | [6 empty] | 2000000 | 2000000 |  |  | 2000000 |  | 6000000
Actual
17 | COMMITTEE MEETING/INTERACTIVE FORUM | LASEDV/NP/NM/017/22 | 4,500,000.00 | Plan | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 4,500,000.00
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/DEPARTMENT/AGENCY : LAGOS STATE EDUCATION DISTRICT V (LASEDV)
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
FACILITY MANAGEMENT | LASEDV/NCS/DC/001/22 |  | 104 | 54936576 | <100M | Direct Contracting Selection | Plan | POST | PRIOR | N/A | N/A | N/A | N/A | N/A | 2/6/22 | 10/6/22 | Plan | 22/6/22 | 48 Hours | 54936576 | 30/6/22 | N/A | 17/8/22 | 31/8/22
[7 empty] | Actual | [9 empty] | Actual
AUDIT EXPENSES | LASEDV/NCS/SSS/002/22 |  |  | 3000000 | <10M | Single Sourcing Selection | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 7/5/22 | 14/5/22 | Plan | 24/5/22 | 24 Hours | 3000000 | 24/8/22 | 15/6/22 | 13/7/22 | 30/7/22
[7 empty] | Actual | [9 empty] | Actual
WEAC REPORT EVALUATION WORK | LASEDV/NCS/SSS/003/22 |  |  | 4000000 | <10M | Single Sourcing Selection | Plan | POST | POST | N/A | N/A | N/A | N/A | N/A | 2/6/22 | 10/6/22 | Plan | 22/6/22 | 48 Hours | 4000000 | 30/6/22 | N/A | 17/8/22 | 31/8/22
[7 empty] | Actual | [9 empty] | Actual
PROCUREMENT EXPENSES | LASEDVI/NCS/SSS/004/22 |  |  | 1000000 | <10M | Single Sourcing Selection | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 7/5/22 | 14/5/22 | Plan | 24/5/22 | 24 Hours | 1000000 | 24/8/22 | 15/6/22 | 13/7/22 | 30/7/22
[7 empty] | Actual | [9 empty] | Actual
PUBLIC AFFAIR EXPENSES | LASEDV/NCS/SSS/005/22 |  |  | 1000000 | <10M | Single Sourcing Selection | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 7/5/22 | 14/5/22 | Plan | 24/5/22 | 24 Hours | 1000000 | 24/8/22 | 15/6/22 | 13/7/22 | 30/7/22
[7 empty] | Actual | [9 empty] | Actual
PLANNING EXPENSES | LASEDV/NCS/SSS/006/22 |  |  | 2200000 | <10M | Single Sourcing Selection | Plan | POST | POST | 9/3/22 | N/A | 6/4/22 | 20/4/22 | 4/5/22 | 10/5/22 | 16/5/22 | Plan | 23/5/22 | 24 Hours | 2200000 | 22/8/22 | 15/6/22 | 29/7/22 | 29/7/22
[7 empty] | Actual | [9 empty] | Actual
DIRECT REPAIRS & MAINTENANCE,SNR SEC. SCH | LASEDVI/NCS/SSS/005 |  |  | 4000000 | <10M | Single Sourcing Selection | Plan | POST | POST | N/A | N/A | N/A | N/A | N/A | 2/6/22 | 10/6/22 | Plan | 22/6/22 | 48 Hours | 4000000 | 30/6/22 | N/A | 17/8/22 | 31/8/22
[7 empty] | Actual | [9 empty] | Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT V (LASEDV)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP AND TRAINING for Officers within Lagos State.1. Capacity building for Subject Teachers 2.Capacity building for non-teaching staff | LASEDV/WSH/DC/001 |  |  |  | Plan |  |  |  |  | 5000000
Actual
2 | HUMAN RESOURCES DEVELOPMENT 1. National Institute of Personnel Management, NIPM | LASEDV/WSH/DC/002 |  |  |  | Plan |  |  |  |  | 3744094
Actual
3 | CONFERENCE & SEMINAR: 1.Charter Institute of Purchasing and Supply Management of Nigeria 2.Association ofNational Accountant of Nigeria 3.Institute of Charter Accountants of Nigeria 3.National Statistical Association of Nigeria 4.Subject Teachers Association of Nigeria | LASEDV/CON/SSS/003 |  |  |  | Plan |  |  |  |  | 5208000
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE EDUCATION DISTRICT V (LASEDV)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | CAPITAL EXPENDITURE: | LASEDV/GD/NS/001/22 |  | Various | 10000000 | <50M | NS | POST | POST | Plan | 24/2/22 | 16/3/22 | 30/3/22 | 13/4/22 | 25/5/22 | 8/6/22 | 22/6/22 | 24 Hours | 10000000 | 20/7/22 | 27/7/22 | 10/8/22 | 7/9/22 | 19/9/22
Actual
2 | MANAGEMENT & INFORMATION SYSTEMS: Procurement of Computers accessories ;40 pck of HP toner, 4in 1 colour ink and provision for replacement of MIS item. | LASEDV/GD/NS/002/22 |  | Various | 3000000 | <10M | NS | POST | POST | Plan | N/A | N/A | 6/4/22 | 20/4/22 | 1/6/22 | N/A | N/A | N/A | 3000000 | 15/6/22 | 22/6/212 | 6/7/22 | 3/8/22 | 4/8/22
Actual
3 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFITS | LASEDVI/GD/NS/003/22 |  | 1 | 860000 | <10M | NS | POST | POST | Plan | 4/5/22 | 1/6/22 | 15/6/22 | 29/6/22 | 20/7/22 | 3/8/22 | 17/8/22 | 48 Hours | 860000 | 13/9/22 | 21/9/22 | 5/10/22 | 2/11/22 | 7/11/22
Actual
4 | SPORT DEVELOPMENT GRANTS | LASEDVI/GD/NS/004/22 |  | 1 | 8400000 | <10M | NS | POST | POST | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2/3/22 | 24 Hours | 8400000 | 30/3/22 | 6/4/22 | 20/4/22 | 25/5/22 | 27/5/22
Actual
5 | WELFARE EXPENSES | LASEDV/GD-F/NS/005/22 |  | Framework | 7000000 | <10M | NS | POST | POST | Plan | 18/2/22 | 17/3/22 | 31/3/22 | 14/4/22 | 26/5/22 | 9/6/22 | 23/6/22 | 24 Hours | 7000000 | 21/7/22 | 29/7/22 | 4/8/22 | 2/9/22 | 6/9/22
Actual
6 | FUEL DUMP | LASEDV/GD/NS/006/22 |  | Various | 15000000 | <50M | NS | POST | POST | Plan | 24/2/22 | 16/3/22 | 30/3/22 | 13/4/22 | 25/5/22 | 8/6/22 | 22/6/22 | 24 Hours | 15,000,000.00 | 20/7/22 | 27/7/22 | 10/8/22 | 7/9/22 | 19/9/22
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE EDUCATION DISTRICT V (LASEDV)
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | PROMOTION EXPENSES | LASEDVI/CS/SSS/001/22 | Single Source Selectiion | TIME-BASE | 3016000 | POST | Plan | 22/2/21 | 4/3/21 | N/A | N/A | 17/3/21 | 24/3/21 | 6/4/21 | N/A | N/A | N/A | 13/4/21 | 16/4/21 | N/A | N/A | 3016000 | 22/4/22 | 29/4/22 | 12/5/22 | 9/6/22 | 23/6/22 | 3016000
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE EDUCATION DISTRICT VI (LASEDVI)
BUDGET YEAR: 2020
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual