## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: HEALTH FACILITY MONITORING AND ACCREDITATION AGENCY
BUDGET YEAR: PROCUREMENT PLAN Y2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Monitoring and inspection expenses | HEF/NP/NM/001/22 | 18,000,000.00 | Plan |  |  | 6000000 |  |  |  |  | 6000000 |  |  | 6000000 |  | 18000000
Actual
2 | Special duties | HEF/NP/NM/002/22 | 17,000,000 | Plan |  |  |  | 7000000 |  |  |  | 7000000 |  |  | 3000000 |  | 17000000
Actual
3 | Publicity and Enligthenment Campaign | HEF/NP/NM/003/22 | 35000000 | Plan |  |  |  | 10000000 |  |  | 10000000 |  | 10000000 |  | 5000000 |  | 35000000
Actual
4 | Quarterly stakeholders meeting | HEF/NP/NM/004/22 | 8,500,000 | Plan |  |  |  | 4500000 |  |  |  |  | 4000000 |  |  |  | 8500000
Actual
5 | Medical records & Statistics | HEF/NP/NM/005/22 | 13,000,000 | Plan |  |  |  | 6000000 |  |  |  |  | 7000000 |  |  |  | 13000000
Actual
6 | Janitorial Services | HEF/NP/NM/006/22 | 2,700,000 | Plan |  |  |  | 1000000 |  |  |  | 1700000 |  |  |  |  | 2700000
Actual
7 | General Utility Services | HEF/NP/NM/008/22 | 2,500,000.00 | Plan |  |  | 1000000 |  |  |  |  | 1500000 |  |  |  |  | 2500000
Actual
8 | Miscellaneous | HEF/NP/NM/009/22 |  | Plan |  |  | 1500000 |  |  |  |  | 1,000-,000 |  |  |  |  | 2500000
Actual
10 | Payment of remuniration to minimum of 7 franchising companies | HEF/NP/NM/010/22 | 166320000 | Plan |  |  | 41580000 |  |  | 41580000 |  | 41580 |  | 41580000 |  |  | 166320000
Actual
11 | Travel and Transport | HEF/NP/NM/011/22 | 7000000 | Plan |  |  | 2000000 |  |  | 2000000 |  | 3000000 |  |  |  |  | 7000000
Actual
12 | Honoraria for facilitators | HEF/NP/NM/012/22 | 1000000 | Plan |  |  | 500,000,00 |  |  |  |  | 500000 |  |  |  |  | 1000000
Actual
13 | Monthlyreview of meeting | HEF/NP/NM/013/22 | 6000000 | Plan |  |  | 2000000 |  |  |  |  | 2000000 |  | 2000000 |  |  | 6000000
Actual
14 | Spot checks of health facilities | HEF/NP/NM/014/22 | 4284000 | Plan |  |  | 2000000 |  |  |  |  | 2284000 |  |  |  |  | 4284000
Actual
15 | Allowances to Project staff | HEF/NP/NM/015/22 | 9600000 | Plan |  |  | 2400000 |  |  |  | 2400000 |  | 4800000 |  |  |  | 9600000
Actual
16 | Quarterly survelliance | HEF/NP/NM/016/22 | 2000000 | Plan |  |  | 500000 |  |  | 500000 |  | 500000 |  | 500000 |  |  | 2000000
Actual
17 | Allowances to artisians | HEF/NP/NP/016/22 | 3280000 | Plan |  |  | 1000000 |  |  | 1000000 |  | 1000000 |  | 280000 |  |  | 3280000
Actual
18 | Board members Allowances | HEF/NP/NM/017/22 | 9000000 | Plan |  |  | 3000000 |  |  | 3000000 |  | 3000000 |  |  |  |  | 9000000
Actual
19 | Capacity development of staff | HEF/NP/NM/018/22 | 7250000 | Plan |  |  | 2500000 |  |  | 2500000 |  | 2500000 |  |  |  |  | 7250000
Actual
20 | Monitoring Committee on | HEF/NP/NM/018/22 | 1500000 | Plan |  |  | 750000 |  |  |  |  | 750000 |  |  |  |  | 1500000
| Artificial Therapy |  |  | Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/AGENCY HEALTH FACILITY MONITORING AND ACCREDITATION AGENCY
BUDGET YEAR 2022
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Certified Professional in Healthcare | Capacity building | 4 | 5 days | Plan | Abuja | 100000 | 500000 | 1520000 | 2120000
Actual
2 | Digital Transformation | Capacity building | 1 | 2 days | Plan | kaduna | 65000 | 110000 | 133500 | 308500
Actual
3 | Chartered institute of purchasing and supply | To improve proficiency in procurement | 1 | 3 days | Plan | Abuja | 100000 | 110000 | 189000 | 399000
Actual
4 | Understanding core HR proces courses | To enhance administrative skills | 1 | 3 days | Plan | Cross Rivers | 200000 | 110000 | 247000 | 557800
Actual
5 | Event management protocol skills for PRO | Capacity building | 1 | 3 days | Plan | Lagos | 165000 |  | 97800 | 269550
Actual
6 | Annual conference of certified accountant | Capacity building | 1 | 5 days | Plan | Abuja | 65000 | 110000 | 395000 | 570,000,00
Actual
7 |  |  |  |  | Plan
Actual
8 |  |  |  |  | Plan
Actual
9 |  |  |  |  | Plan
Actual
10 |  |  |  |  | Plan
Actual
11 |  |  |  |  | Plan
Actual
12 |  |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/ AGENCY: HEALTH FACILITY MONITORING AND ACCREDITATION AGENCY
BUDGET YEAR: | 2022 | [14 empty] | 2022-04-05
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance of office building | HEF/N-CS/001/22 |  |  | 2499996 | <10 | NS | Plan | Post | Post | 2022-03-03 | 2022-03-09 | 2022-03-16 | 2022-03-29 | 2022-04-06 | 2022-04-13 | 2022-04-20 | Plan | 22/4/2022 | 26/4/2022 | 2499996 | 2022-05-09 | 2022-05-23 | 2022-06-02 | 2022-06-08
[7 empty] | Actual | [9 empty] | Actual
Motor Vehicle Maintenance and repairs | HEF/N-CS/002/22 |  |  | 6000000 | <10 | NS | Plan | Post | Post | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-04-06 | 2022-04-11 | 2022-04-18 | 2021-04-25 | Plan | 26/4/2022 | 28/4/2022 | 6000000 | 2022-05-18 | 2022-05-25 | 2022-06-15 | 2022-06-16
[7 empty] | Actual | [9 empty] | Actual
Hotel accomodation | HEF/N-C/003/22 |  |  | 11006000 | <50 | NS | Plan | PRE | PRIOR | 2022-03-10 | 2022-03-15 | 2022-03-22 | 2022-03-28 | 2022-04-05 | 2022-04-11 | 2022-04-18 | Plan | 28/4/2022 | 21/4/2022 | 11006000 | 2022-06-01 | 2022-06-13 | 2022-06-20 | 2022-06-27
[7 empty] | Actual | [9 empty] | Actual
Calligraphic writing on certificates | HEF/N-C/004/22 |  |  | 2240000 | <10 | NS | Plan | Post | Post | 2022-03-15 | 2022-03-23 | 2022-03-30 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | Plan | 29/4/2022 | 2022-04-05 | 2240000 | 2022-05-18 | 2022-05-26 | 2022-05-30 | 2022-06-01
[7 empty] | Actual | [9 empty] | Actual
Repairs/servicing of equipment | HEF/N-C/005/22 |  |  | 1870000 | <10 | NS | Plan | Post | Post | 2022-03-17 | 2022-03-24 | 2022-03-30 | 2022-04-13 | 2022-04-22 | 2022-04-28 | 2022-05-11 | Plan | 18/5/2022 | 20/5/2022 | 1870000 | 2022-06-02 | 2022-06-09 | 2021-06-21 | 2022-06-28
[7 empty] | Actual | [9 empty] | Actual
Janitorial services | HEF/N-C/006/22 |  |  | 2700000 | <10 | NS | Plan | POST | POST | 2022-03-18 | 2022-03-23 | 2022-03-28 | 2022-04-19 | 2022-04-26 | 2022-05-04 | 2022-05-11 | Plan | 18/5/2022 | 2022-05-19 | 2700000 | 2022-06-03 | 2022-06-08 | 2022-06-20 | 2022-06-27
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/AGENCY HEALTH FACILITY MONITORING AND ACCREDITATION AGENCY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
| E-HEFAMAA | HEF/S-C/SSS/001/22 | SSS | LUMP | 37925000 |  | Plan | 1/03/22 | 7/03/22 |  | 14/03/22 | 21/03/22 | 28/03/22 | 4/04/22 | 11/04/22 | 18/03/22 | 25/03/22 | 2/05/22 | 9/05/22 | 16/05/22 | 23/05/22 | 37925000 | 1/06/22 | 13/06/22 | 20/06/22 | 27/06/22 | 1/07/21
Actual
| HEFAMAA ACCREDITATION | HEF/S-C/SSS/002/22 | SSS | LUMP | 50000000 |  | Plan | 3/03/22 | 9/03/22 |  | 22/03/22 | 30/03/22 | 6/04/22 | 19/04/22 | 26/04/22 | 4/05/22 | 11/05/22 | 18/05/22 | 25/05/22 | 1/06/22 | 3/06/22 | 50000000 | 7/06/22 | 14/06/22 | 22/06/22 | 28/06/22 | 5/07/22
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: HEALTH FACILITY MONITORING AND ACCREDITATION AGENCY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Office Furniture and Equipment | HEF/G/NS/001/22 |  |  | 10000000 | <50M | NS | PRE |  | Plan | 2022-03-07 | 2022-03-15 | 2022-03-22 | 2022-04-12 | 2022-04-21 | 2022-04-28 | 2022-05-16 | 2022-05-19 | 10000000 | 2022-05-24 | 2022-05-09 | 2022-05-27
Actual
2 | Procurement of Identification logo | HEF/G/NS/002/22 |  | 400 | 11653099 | <50M | NS | PRE |  | Plan | 2022-03-14 | 2022-03-21 | 2022-04-05 | 2022-04-15 | 2022-04-22 | 2022-05-02 | 2022-05-25 | 2022-05-27 | 11653099 | 2022-06-03 | 44734 | 2022-07-04
Actual
3 | Procurement of stationery | HEF/G-NS/003/22 |  |  | 7610000 | <10M | NS | POST |  | Plan | 2022-03-17 | 2022-03-23 | 4/04/2022 | 2022-04-26 | 2022-05-04 | 2022-05-10 | 2022-06-01 | 2022-06-15 | 5000000 | 2022-06-22 | 44741 | 2022-07-01
Actual
4 | Procurement of fuel | HEF/G-NS/004//22 |  |  | 7500000 | <10M | NS | POST |  | Plan | 2022-03-10 | 2022-03-17 | 2022-03-24 | 2022-03-30 | 2022-04-06 | 2022-04-14 | 2022-04-27 | 2022-04-29 | 7000000 | 2022-05-03 | 44691 | 2022-05-18
Actual
5 | Printing | HEF/G-NS/005/22 |  |  | 2500000 | <10M | NS | POST |  | Plan | 2022-03-03 | 44629 | 2022-03-16 | 2022-03-23 | 2022-04-01 | 2022-04-13 | 2022-04-20 | 2022-04-28 | 5000000 | 44683 | 2022-05-10 | 2022-05-11
Actual
6 | Procurement of enforcement materials and closure kits | HEF/G-NS/006/22 |  |  | 18720000 | <50M | NS | Pre |  | Plan | 2022-03-08 | 44635 | 2022-03-22 | 2022-04-01 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 18720000 | 44685 | 2022-06-01 | 2022-06-07
Actual
Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: HEALTH FACILITY MONITORING AND ACCREDITATION AGENCY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Partitioning of office space | HEF/W/NS/001/22 |  | 10000000 | <50M | NS | LUMP SUM |  | Plan | prior | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-04-20 | 2022-04-29 | 2022-05-05 | 2022-05-18 | 2022-05-23 | 10000000 | 44711 | 2022-06-03 | 2022-06-15 | 2022-06-16 | 2022-06-17
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual