## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS FERRY SERVICES
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Public Affairs Unit Expenses | LFSC/NP/NM/001/22 | 2,000,000.00 | Plan | 500,000,00 |  |  | 500000 |  |  | 500000 |  |  | 500000 |  |  | 2000000
Actual
2 | Servicing of Meeting | LFSC/NP/NM/002/22 | 546571 | Plan | 136642.75 |  |  | 136642.75 |  |  | 136642.75 |  |  | 136642.75 |  |  | 546571
Actual
3 | Payment for Attendance of COWSLO for 10 Nos Management staff | LFSC/NP/NM/003/22 | 1,640,000.00 | Plan | [12 empty] | 1640000
|  |  |  | Actual | [9 empty] | 1640000
4 | Allowances for Despatch of Correspondence | LFSC/NP/NM/004/22 | 1,500,000.00 | Plan | 375000 |  |  | 375000 |  |  | 375000 |  |  | 375000 |  |  | 1500000
Actual
5 | Payment for Out of Station Expenses incurred by MD/CEO and Staff | LFSC/NP/NM/005/22 | 900,000.00 | Plan | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 900000
Actual
6 | Payment for PHCN Bill | LFSC/NP/NM/006/22 | 420,000.00 | Plan | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 420000
Actual
7 | Payment for Telephone Bill | LFSC/NP/NM/007/22 | 600,000.00 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
8 | Payment for Water Bill | LFSC/NP/NM/008/22 | 360000 | Plan | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 360000
Actual
9 | Payment for DSTV Subscription for MD/CEO | LFSC/NP/NM/009/22 | 300,000.00 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
Actual
10 | Payment for Internet Subscription | LFSC/NP/NM/010/22 | 456,000.00 | Plan | 114000 |  |  | 114000 |  |  | 114000 |  |  | 114000 |  |  | 456000
Actual
11 | Payment Monitoring and Visitation to LAGFERRY Jetties | LFSC/NP/NM/011/22 | 3000000 | Plan | 750000 |  |  | 750000 |  |  | 750000 |  |  | 750000 |  |  | 3000000
Actual
12 | Payment for Matters Affecting Staff Welfare | LFSC/NP/NM/012/22 | 7,200,000.00 | Plan | 1800000 |  |  | 1800000 |  |  | 1800000 |  |  | 1800000 |  |  | 7200000
Actual
13 | Procurement Expenses | LFSC/NP/NM/013/22 | 1,951,644.00 | Plan | 975822 |  |  |  |  | 975822 | [6 empty] | 1951644
Actual
14 | Payment of Salaries to 144 LAGFERRY Employed Staff | LFSC/NP/NM/014/22 | 180,000,000.00 | Plan | 15000000 | 15000000 | 15000000 | 15000000 | 15,000,000,00 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 180000000
Actual
15 | Annual Payment for External Auditor | LFSC/NP/NM/015/22 | 3,000,000.00 | Plan | [11 empty] | 3000000 | 3000000
Actual
16 | Payment for Insurance Policy on Boats, Crew Members and Passengers | LFSC/NP/NM/016/22 | 52,401,809.00 | Plan | 52401809 | [11 empty] | 52401809
Actual
17 | Expenses for Advocacy Programmes for Marketing Department | LFSC/NP/NM/017/22 | 2,767,764.00 | Plan | 691941 |  |  | 691941 |  |  | 691941 |  |  | 691941 |  |  | 2767764
Actual
18 | Payment for Security Outfit | LFSC/NP/NM/018/22 | 4,800,000.00 | Plan | 1200000 |  |  | 1200000 |  |  | 1200000 |  |  | 1200000 |  |  | 4800000
Actual
19 | Payment for Cleaning Services of Boats and Jetties | LFSC/NP/NM/019/22 | 6,000,000.00 | Plan | 1500000 |  |  | 1500000 |  |  | 1500000 |  |  | 1500000 |  |  | 6000000
Actual
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS FERRY SERVICES
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Designing and Managing PR Budget for Impact, Value and Assessment | LFSC/S-WTC/NM/SS/001/22 | To enhance the performance of Public Affairs Unit | 1 | 5 Days | Plan | Abuja | 105000 | 55000 | 248000 | 408000
Actual
2 | Strategic Human Resources Management | LFSC/S-WTC/NM/SS/002/22 | To enhance the performance of A&HR | 1 | 5 Days | Plan | Kano | 105000 | 55000 | 248000 | 408000
Actual
3 | Mandatory Continuing Professional Development (MCPD) | LFSC/S-WTC/NM/SS/003/22 | To enhance the performance of Accounts department | 1 | 5 Days | Plan | Abuja | 40000 | 55000 | 187000 | 282500
Actual
4 | The Contribution of Stores Management And Inventory Control In Achieving Value For Money In Procurement | LFSC/S-WTC/NM/SS/004/22 | To enhance the performance of Procurement unit | 1 | 5 Days | Plan | Owerri | 65000 | 55000 | 187500 | 307500
Actual
5 | Y2020 CPNIT Professional Assembly | LFSC/S-WTC/NM/SS/005/22 | To enhance the performance of ICT unit | 1 | 4 Days | Plan | Abuja | 150000 | 55000 | 147000 | 307000
Actual
6 | Mandatory Continuing Professional Development (MCPD) | LFSC/S-WTC/NM/SS/006/22 | To enhance the performance of Audit unit | 1 | 5 Days | Plan | Abuja | 40000 | 55000 | 125500 | 220500
Actual
7 | Advance Project Leadership Training | LFSC/S-WTC/NM/SS/007/22 | To enhance the performance of Planning unit | 1 | 6 Days | Plan | Abuja | 150000 | 55000 | 148000 | 353500
Actual
8 | Basic Offshore Safety Induction And Emergency Training | LFSC/S-WTC/NM/SS/008/22 | To enhance the performance of Operations department | 1 | 5 Days | Plan | P/H | 250000 | 55000 | 93250 | 398250
Actual
9 | Basic Offshore Safety Induction And Emergency Training | LFSC/S-WTC/NM/SS/009/22 | To enhance the performance of Maintenanace unit | 1 | 5 Days | Plan | P/H | 250000 | 55000 | 93250 | 398250
Actual
10 | Developing And Implementing Strategic Marketing Plans Training | LFSC/S-WTC/NM/SS/010/22 | To enhance the performance of Marketing department | 1 | 5 Days | Plan | Abuja | 195000 | 55000 | 93250 | 343250
Actual
11 | Advanced Microsoft Spreadsheet Application In Financial And Business Analysis | LFSC/S-WTC/NM/SS/011/22 | To enhance the performance Of Finance And Accounts | 1 | 2 Days | Plan | Lagos | 170000 |  | 3500 | 173,500,00
Actual
12 | Effective Office Management | LFSC/S-WTC/NM/SS/012/22 | To enhance the performance of Public Affairs Unit | 1 | 3 Days | Plan | Lagos | 200000 |  | 4500 | 204500
Actual
13 | Health And Safety Organisation And Management | LFSC/S-WTC/NM/SS/013/22 | To enhance the performance of Operations department | 1 | 2 Days | Plan | Lagos | 195000 |  | 3500 | 198500
Actual
14 | Team Building Skills For Business Growth | LFSC/S-WTC/NM/SS/014/22 | To enhance the performance of Operations department | 1 | 3 Days | Plan | Lagos | 190000 |  | 4500 | 194500
Actual
15 | Viral Team Management Training | LFSC/S-WTC/NM/SS/015/22 | To enhance the performance of Operations department | 1 | 2 Days | Plan | Lagos | 125000 |  | 3500 | 128500
Actual
16 | Team Building Skills For Business Growth | LFSC/S-WTC/NM/SS/016/22 | To enhance the performance of Operations department | 1 | 2 Days | Plan | Lagos | 190000 |  | 4500 | 194500
Actual
17 | Networking Skills for Business Development Executives | LFSC/S-WTC/NM/SS/017/22 | To enhance the performance of Marketing department | 3 | 2 Days | Plan | Lagos | 150000 |  | 10500 | 460500
Actual
18 | Environmental Impact & Risk Assessment | LFSC/S-WTC/NM/SS/018/22 | To enhance the performance of Operations department | 1 | 2 Days | Plan | Lagos | 185000 |  | 3500 | 188500
Actual
19 | Human Resources Management | LFSC/S-WTC/NM/SS/019/22 | To enhance the performance of A &HR dept. | 1 | 3 Days | Plan | Lagos | 210,000,00 |  | 4500 | 214500
Actual
20 | Emotional & Personal Intellegence | LFSC/S-WTC/NM/SS/020/22 | To enhance the performance of Planning unit | 1 | 2 Days | Plan | Lagos | 150000 |  | 3500 | 153500
Actual
21 | Effective Office Management | LFSC/S-WTC/NM/SS/021/22 | To enhance the performance of Marketing department | 2 | 2 Days | Plan | Lagos | 200000 |  | 9000 | 409000
Actual
22 | Viral Team Management Training | LFSC/S-WTC/NM/SS/022/22 | To enhance the performance of Operations department | 2 | 2 Days | Plan | Lagos | 125000 |  | 6200 | 246200
Actual
23 | Fleet, Logistics And Safety Management | LFSC/S-WTC/NM/SS/023/22 | To enhance the performance of Operations department | 3 | 3 Days | Plan | Lagos | 100000 |  | 10500 | 310500
Actual
l

## non-cons
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/AGENCY: LAGOS FERRY SERVICES
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Servicing of Generating Set | LFSC/S/NC-F/NS/001/22 |  | 3 | 320000 | <50M | NS | Plan | Post | Post | 2022-02-15 | N/A | 2022-02-28 | 2022-03-28 | 2022-04-04 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 |  | 2022-05-18 | 2022-06-15 | 2022-07-13 | 2022-10-12
[7 empty] | Actual | [9 empty] | Actual
Servicing of 10 Nos Cars per Quarter | LFSC/S/NC-F/NS/002/22 |  | 10 | 1000000 | <50M | NS | Plan | Post | Post | 2022-02-15 | N/A | 2022-02-28 | 2022-03-28 | 2022-04-04 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 |  | 2022-05-18 | 2022-06-15 | 2022-07-13 | 2022-10-12
[7 empty] | Actual | [9 empty] | Actual
Servicing of 12 Nos Ferries per Annum | LFSC/S-NC-F/NS/003/22 |  | 12 | 38640000 | <50M | NS | Plan | Post | Post | 2022-02-15 | N/A | 2022-02-28 | 2022-03-28 | 2022-04-04 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 |  | 2022-05-18 | 2022-06-15 | 2022-07-13 | 2022-10-12
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Official Vehicles | LFSC/S-NC-F/NS/004/22 |  | Various | 900000 | <50M | NS | Plan | Post | Post | 2022-02-15 | N/A | 2022-02-28 | 2022-03-28 | 2022-04-04 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 |  | 2022-05-18 | 2022-06-15 | 2022-07-13 | 2022-10-12
[7 empty] | Actual | [9 empty] | Actual
Retrofitting of Boats | LFSC/S-NC-F/NS/005/22 |  | Various | 20000000 | <50M | NS | Plan | Post | Post | 2022-02-15 | N/A | 2022-02-28 | 2022-03-28 | 2022-04-04 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 |  | 2022-05-18 | 2022-06-15 | 2022-07-13 | 2022-10-12
[7 empty] | Actual | [9 empty] | Actual
Staff Retreat | LFSC/S-NC/NS/001/21 |  | Various | 5000000 | <50M | NS | Plan | Post | Post | 2022-02-15 | N/A | 2022-02-28 | 2022-03-28 | 2022-04-04 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 |  | 2022-05-18 | 2022-06-15 | 2022-07-13 | 2022-10-12
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
Note on A4: ELETU OLABODE:

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGFERRY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Collection of Data on Lagferry Activities | LFSC/S-C/LC/001/22 | LC | LS | 1200000 |  | Plan | 21-Feb-2022 | 14-Mar-2022 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11-Apr-2022 | 15-Apr-2022 |  | 22-Apr-2022 | 6-May-2022 | 3-Jun-2022 | 17-Jun-2022 | 1-Jul-2022
Actual
2 | Conducting Survey on Passengers patronage | LFSC/S-C/LC/002/22 | LC | LS | 800000 |  | Plan | 21-Feb-2022 | 14-Mar-2022 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11-Apr-2022 | 15-Apr-2022 |  | 22-Apr-2022 | 6-May-2022 | 3-Jun-2022 | 17-Jun-2022 | 1-Jul-2022
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS FERRY SERVICES
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Stationeries and Consumables | LFSC/G-F/NS/001/22 | N/A | Various | 4200000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
2 | Procurement of Fuel for Generating Set | LFSC/G-F/NS/002/22 | N/A | 12331.3 | 2010000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
3 | Procurement of 10 Nos Battries | LFSC/G/NS/001/22 | N/A | 10 | 500000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
4 | Procurement of 28 Nos Tyres | LFSC/G/NS/002/22 | N/A | 28 | 1080000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
5 | Procurement of Fuel for Chairman's Car and Official Cars during Official duty | LFSC/G-F/NS/003/22 | N/A | 2161.35 | 2956000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
6 | Procurement of Toiletries | LFSC/G/NS/003/22 | N/A | Various | 526000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
7 | Procurement of Uniforms and Protective Wears | LFSC/G/NS/004/22 | N/A | Various | 1440000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
8 | Procurement of 1 No Colour Printer | LFSC/G/NS/005/22 | N/A | 1 | 120000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
9 | Procurement of 1 No Photocopier Machine | LFSC/G/NS/006/22 | N/A | 1 | 2000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
10 | Procurement of 8 Nos Six 4TB hard Disk | LFSC/G/NS/007/22 | N/A | 8 | 40000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
11 | Procurement of Fuel for 12 Nos Ferries | LFSC/G/NCB/001/22 | N/A | 827,160L | 206360000 | 100M -500M | NCB | Pre | Prior | Plan | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-04-04 | 2022-04-11 | 2022-04-25 | 2022-05-23 | 2022-05-27 |  | 2022-06-03 | 2022-06-17 | 2022-07-15 | 2022-08-12 | 2022-08-26
Actual
12 | Procurement of One (1) No HIAB 5 Tons Truck Mounted Crane | LFSC/G/NS/008/22 | N/A | 1 | 20000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
13 | Procurement of One (1) No DAHAN 3 Tons Crane | LFSC/G/NS/009/22 | N/A | 1 | 10000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
14 | Procurement of Two (1) No Trailer Loader (CAT) | LFSC/G/NS/010/22 | N/A | 1 | 10000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
15 | Procurement of Crane Chain | LFSC/G/NS/011/22 | N/A | 1 | 10000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
16 | Procurement of Spare Parts for the Maintenance of Boats | LFSC/G/NS/012/22 | N/A | 1 | 20000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
17 | Procurement of Furniture for MD's Office, Ante-Room and Management Staff | LFSC/G/NS/013/22 | N/A | Various | 5000000 | <50M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
18 | Procurement and Installation of Office Accounting Automation Process | LFSC/G/NS/014/22 | N/A | 1 | 50000000 | 500M-100M | NS | Post | Post | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-02-16 | N/A | N/A | 2021-03-15 | 2021-03-18 |  | 2021-03-25 | 2021-04-01 | 2021-04-29 | 2021-05-27 | 2021-06-10
Actual
19 | Procurement of Additional 4 Nos Passenger Boats | LFSC/G/NBC/002/22 | N/A | 4 | 418731200 | 100M -500M | NCB | Pre | Prior | Plan | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-04-04 | 2022-04-11 | 2022-04-25 | 2022-05-23 | 2022-05-27 |  | 2022-06-03 | 2022-06-17 | 2022-07-15 | 2022-08-12 | 2022-08-26
Actual
20 | Provision of 24Hrs Online, Real Time Tech Control Room for Tracking and Monitoring of All Operational Boats ( Phase 3) | LFSC/G/NCB/003/22 | N/A | Various | 132730775.7 | 100M -500M | NCB | Pre | Prior | Plan | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-04-04 | 2022-04-11 | 2022-04-25 | 2022-05-23 | 2022-05-27 |  | 2022-06-03 | 2022-06-17 | 2022-07-15 | 2022-08-12 | 2022-08-26
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS FERRY SERVICES
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Drydock yard and Maintenance Workshop at Ijegun Egba Terminal | LFSC/W/NCB/001/22 | N/A | 219638951 | 100M - 500M | NCB | BOQ | Pre | Plan | Prior | 2022-02-16 | 2022-02-23 | 2022-03-09 | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-18 | 2022-05-20 |  | 2022-05-27 | 2022-06-10 | 2022-07-08 | 2023-01-06 | 2023-02-03
Actual
2 | Office Renovation and Maintenance | LFSC/W/NS/001/22 | N/A | 170000 | <50M | NS | BOQ | Post | Plan | Post | 2022-02-16 | 2022-02-23 | 2022-03-09 | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-18 | 2022-05-20 |  | 2022-05-27 | 2022-06-10 | 2022-07-08 | 2023-01-06 | 2023-02-03
Actual
| ON-GOING PROJECT | [7 empty] | Plan | [10 empty] | 2022-05-27 | 2022-06-10 | 2022-07-08 | 2023-01-06 | 2023-02-03
Actual
3 | Completion of the 2-Storey LAGFERRY Office at Oyinkan Abayomi Drive, Ikoyi, Eti-Osa L. G. A. Lagos State | LFSC/W/DC/001/19 On-Gong Project | N/A | 443011515 | 100M-500M | DC | BOQ | Pre | Plan | Prior | 2022-02-16 | 2022-02-23 | 2022-03-09 | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-18 | 2022-05-20 |  | 2022-05-27 | 2022-06-10 | 2022-07-08 | 2023-01-06 | 2023-02-03
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual