## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE RESIDENTS' REGISTRATION AGENCY
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | LOCAL TRAVEL AND TRANSPORTATION | LASRRA/NP/NM/001/22 | 8,870,000.00 | Plan | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 739167 | 8870000
Actual
2 | VEHICLE LICENSE AND INSURANCE RENEWALS | LASRRA/NP/NM/002/22 | 253,900.00 | Plan | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 21158.33 | 253899.96
Actual
3 | GENERAL UTILITY SERVICES | LASRRA/NP/NM/003/22 | 7,808,000.00 | Plan | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 650666.66 | 7807999.92
Actual
4 | SERVICING OF MEETINGS | LASRRA/NP/NM/004/22 | 1,400,000.00 | Plan | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 116666.67 | 1400000.04
Actual
5 | PRESS/PUBLIC RELATIONS | LASRRA/NP/NM/005/22 | 3000650 | Plan | 1500162.5 | - | - | 1500162.5 | - | - | 1500162.5 | - | - | 1500162.5 | - | - | 6000650
Actual
6 | PAYMENT OF LASRRA HQ RENT | LASRRA/NP/NM/006/22 | 12500000 | Plan | - | - | - | - | - | 12500000 | - | - | - | - | - | - | 12500000
Actual
7 | PLANNING UNIT EXPENSES | LASRRA/NP/NM/007/22 | 1830475 | Plan | 457618.75 | - | - | 457618.75 | - | - | 457618.75 | - | - | 457618.75 | - | - | 1830475
Actual
Plan
Actual
8 | LASRRA ENROLMENT STAFF SALARY | LASRRA/NP/NM/008/22 | 120449238.04 | Plan | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 10079103.17 | 120949238.04
Actual
9 | PROCUREMENT UNIT EXPENSES | LASRRA/NP/NM/009/22 | 637500 | Plan | 159375 | - | - | 159375 | - | - | 159375 | - | - | 159375 | - | - | 637500
Actual
10. | PAYMENT FOR CLOUD HOSTING | LASRRA/NP/NM/010/22 | 8000000 | Plan | 2000000 | - | - | 2000000 | - | - | 2000000 | - | - | 2000000 | - | - | 8000000
Actual
11. | BACKEND INFRASTRUCTURE, SOFTWARE, LICENSE ETC | LASRRA/NP/NM/011/22 | 688200000 | Plan | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 57350000 | 688200000
Actual
12. | INTERNET SERVICE SUBSCRIPTION FOR REGISTRATION STATIONS | LASRRA/NP/NM/012/22 | 8640000 | Plan | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 8640000
Actual
13. | ENROLMENT INFRASTRUCTURE (BACKEND SERVERS, SIGNATURE PAD, ENROLMENT SOFTWARE) | LASRRA/NP/NM/013/22 | 131000000 | Plan | - | - | - | - | - | 65500000 | - | - | - | - | - | 65500000 | 131000000
Actual
18. | 4-4-2 FINGERPRINT SCANNERS | LASRRA/NP/NM/019/21 | 11000000 | Plan | 2750000 | - | - | 2750000 | - | - | 2750000 | - | - | 2750000 | - | - | 11000000
Actual
| TOTAL COST |  | 992589763.04 | [13 empty] | 996089762.96

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE REGISTRATION AGENCY (LASRRA)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Plan vs Actual | Duration | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | CONFERENCE & SEMINARS FOR STAFF | LASRRA/S-WTC/001/22 |  | 150 | Plan | September |  |  |  |  | 18400000
Actual
2 | ANNUAL WORKSHOP & TRAINING | LASRRA/S-WTC/002/22 |  | 250 | Plan | January |  |  |  |  | 7000000
Actual
| TOTAL COST |  |  |  | Plan | [5 empty] | 25400000
Actual
Mrs. Ibilola Kasunmu
(Chairman) General Manager
|  | Mrs. Seriki Oriola A.R. | [9 empty] | Mrs. Lawal Basirat A. | Talabi Olubukola (Mrs.)
|  | Director, Admin & HR Dept. | [9 empty] | Deputy Director, Public Affairs. | Deputy Director, Procurement (Secretary)
|  | Bamidele-Alao T.A. | [9 empty] | Mr. Abari J.A. | Mr. Adeyemi W.O.
|  | Asst. Director Statistics, Budget & Planning | [9 empty] | Asst. Director (Registration Dept.) | Asst.Director,Finance & Accounts Dept.
|  | Engr. Farotimi Christiana S | [9 empty] | Olowoidiaba R.K.(Mrs.)
|  | Asst. Director, IM & DP Dept. | [9 empty] | Head of Unit, Internal Audit

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE RESIDENTS' REGISTRATION AGENCY (LASRRA)
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1. | DOCUMENTARY & PLACEMENT/ADVERT | LASRRA/S-C/SS/001/22 | Single Sourcing | Time Base | 4500650 | PRIOR | Plan | 21/2/2022 | 18/3/2022 | 2022-01-04 | 2022-11-04 | 2022-06-05 | 13/5/2022 | 30/5/2022 | 2022-08-07 | 18/7/2022 | 2022-01-08 | 2022-08-08 | 24/8/2022 | 2022-05-09 | 24 Hrs |  | 2022-07-09 | 14/9/2022 | 28/9/2022 | 24/10/2022 | 2022-07-11
Actual
2. | ADVOCACY, SENSITIZING AND ENLIGHTENING THE CITIZENS | LASRRA/S-C/SS/002/22 | Single Sourcing | Time Base | 113010000 | PRIOR | Plan | 24/1/2022 | 14/2/2022 | 2022-01-03 | 2022-07-03 | 31/3/2022 | 14/4/2022 | 25/4/2022 | 2022-06-06 | 23/6/2022 | 2022-08-07 | 14/7/2022 | 25/7/2022 | 2022-08-08 | 24 Hr |  | 2022-11-08 | 17/8/2022 | 29/8/2022 | 30/9/2022 | 14/10/2022
Actual
3. | VALUATION OF THE ASSETS OF THE AGENCY (HQ & STATIONS) | LASRRA/S-C/CQ/001/22 | Consultancy Qualification | Lump sum | 5,000,000.00 |  | Plan | 2022-02-02 | 2022-01-03 | 14/3/2022 | 21/3/2022 | 20/4/2022 | 2022-02-05 | 16/5/2022 | 30/6/2022 | 13/7/2022 | 25/7/2022 | 2022-01-08 | 15/8/2022 | 31/8/2022 | 24 Hr |  | 2022-02-09 | 2022-12-09 | 26/9/2022 | 24/10/2022 | 2022-07-11
Actual
4. | PUBLICATION & DOCUMENTATION OF DATA | LASRRA/S-C/CQ/002/22 | Consultancy Qualification | Time Base | 600,000.00 |  | Plan | 2022-04-02 | 28/2/2022 | 14/3/2022 | 21/3/2022 | 18/4/2022 | 2022-02-05 | 16/5/2022 | 20/6/2022 | 2022-04-07 | 18/7/2022 | 27/7/2022 | 2022-10-08 | 22/8/2022 | 24 Hr |  | 23/8/2022 | 30/8/2022 | 2022-12-09 | 2022-07-10 | 21/10/2022
Actual
5. | CONTACT CENTER SOLUTION | LASRRA/S-C/CQ/003/22 | Consultancy Qualification | Time Base | 1,500,000.00 | POST | Plan | 17/1/2022 | 14/2/2022 | 21/2/2022 | 28/2/2022 | 28/3/2022 | 2022-11-04 | 21/4/2022 | 30/5/2022 | 13/6/2022 | 27/6/2022 | 2022-04-07 | 18/7/2022 | 2022-01-08 | 24 Hr |  | 2022-03-08 | 2022-10-08 | 22/8/2022 | 16/9/2022 | 26/9/2022
Actual
6. | SUBSCRIPTION FOR BACKUP INTERNET | LASRRA/S-C/SS/002/22 | Single Sourcing | Time Base | 2,096,000.00 |  | Plan | 2022-05-04 | 25/4/2022 | N/A | N/A | N/A | 2022-09-05 | 23/5/2022 | 2022-06-06 | 23/6/2022 | 2022-08-07 | 14/7/2022 | 25/7/2022 | 2022-08-08 | 24 Hr |  | 2022-11-08 | 17/8/2022 | 29/8/2022 | 30/9/2022 | 14/10/2022
Actual
7. | REPAYMENT OF FRONT-END DATA CAPTURE | LASRRA/S-C/QCBS/001/22 | Quality Consultancy Base | Lump Sum | 75000000 |  | Plan | 21/1/2022 | 2022-04-02 | 2022-08-02 | 2022-11-02 | 21/2/2022 | 28/2/2022 | 14/3/2022 | N/A | N/A | 2022-04-04 | N/A | 2022-12-04 | 25/4/2022 | 24 Hr |  | 27/4/2022 | 29/4/2022 | 2022-09-05 | 2022-11-07 | 2022-01-08
Actual
8. | BILLING SOFTWARE | LASRRA/S-C/CQ/004/22 | Consultancy Qualification | Lump Sum | 10200000 |  | Plan | 31/1/2022 | 2022-03-02 | N/A | N/A | N/A | 14/2/2022 | 25/2/2022 | 2022-03-03 | 2022-07-03 | 17/3/2022 | 21/3/2022 | 28/3/2022 | 2022-08-04 | 24 Hr |  | 2022-11-04 | 18/4/2022 | 2022-02-05 | 13/5/2022 | 23/5/2022
Actual
9. | AUDIT EXPENSES | LASRRA/S-C/CQ/005/22 | Consultancy Qualification | Lump Sum | 1,200,000.00 |  | Plan | 19/1/2022 | 24/1/2022 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-11-02 | 15/2/2022 | 28/2/2022 | 24 Hr |  | N/A | N/A | N/A | 28/3/2022 | 26/4/2022
Actual
15.
10. | DOCUMENT MANAGEMENT SYSTEM | LASRRA/S-C/QCBS/002/22 | Quality Consultancy Base | Time Base | 2,400,000.00 |  | Plan | 2022-08-04 | 25/4/2022 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-09-05 | 26/5/2022 | 30/5/2022 | 24 Hr |  | 2022-10-06 | 20/6/2022 | N/A | 30/6/2022 | 15/7/2022
Actual
| TOTAL |  |  |  | 215506650 |  | Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE RESIDENTS REGISTRATION AGENCY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF STATIONERY. | LASRRA/G-F/NS/001/22 |  |  | 7665000 | <10M | NS | POST | POST | Plan | 17/1/2022 | 25/1/2022 | 2022-07-02 | 14/2/2022 | 28/2/2022 | 2022-07-03 | 14/3/2022 | 24 Hours |  | 17/3/2022 | 21/3/2022 | N/A | N/A | 31/10/2022
Actual
2 | PROCUREMENT OF TYRES (COASTER-7.0,TOYOTA-195/60, COROLLA-205/65, HILUX/HIACE-195/15) | LASRRA/G/NS/001/22 |  |  | 1200000 | <10M | NS | POST | POST | Plan | 28/1/2022 | 15/2/2022 | 16/2/2022 | 2022-01-03 | 15/3/2022 | 18/3/2022 | 30/3/2022 | 24 Hours |  | 2022-04-04 | 2022-11-04 | N/A | 2022-09-05 | 2022-12-05
Actual
3 | PROCUREMENT OF FUEL FOR MOTOR VEHICLES | LASRRA/G-F/DC/001/22 |  |  | 24000000 | <50M | DC | POST | PRIOR | Plan | 31/1/2022 | 2022-07-02 | 14/2/2022 | 25/2/2022 | 28/2/2022 | N/A | 2022-07-03 | 24 Hours |  | 2022-11-03 | 14/3/2022 | N/A | 2022-06-12 | 27/12/2022
Actual
4 | PROCUREMENT OF UNIFORM AND PROTECTIVE WEARS | LASRRA/G/NS/002/22 |  |  | 4900000 | <10M | NS | POST | POST | Plan | 2022-10-02 | 15/2/2022 | 1/3/2022 | 14/3/2022 | 31/3/2022 | 2022-06-04 | 15/4/2022 | 24 Hours |  | 18/4/2022 | 25/4/2022 | N/A | 30/5/2022 | 2022-03-06
Actual
5 | PROCUREMENT OF IT CONSUMABLES ( TONERS, FLASH DRIVES, HARD DRIVES, KEYBOARDS) | LASSRRA/G/NS/003/22 |  |  | 8405680 | <10M | NS | POST | POST | Plan | 2022-03-03 | 28/3/2022 | 5/4/2022 | 18/4/2022 | 2022-10-05 | 23/5/2022 | 2022-03-06 | 24 Hours |  | 2022-06-06 | 14/6/2022 | N/A | 2022-02-07 | 15/7/2022
Actual
6 | PROCUREMENT OF IT CONSUMABLES ( STAFF ID CARDS CONSUMABLES) | LASSRRA/G/SSS/001/22 | 1 | 50 | 16000000 | <50M | SSS | POST | PRIOR | Plan | 2022-03-03 | 28/3/2022 | 5/4/2022 | 18/4/2022 | 2022-10-05 | 23/5/2022 | 2022-03-06 | 24 Hours |  | 2022-06-06 | 14/6/2022 | N/A | 2022-02-07 | 15/7/2022
Actual
7 | END OF THE YEAR WELFARE PACKAGE FOR STAFF | LASRRA/G/NS/004/22 |  |  | 8250000 | <10M | NS | POST | POST | Plan | 2022-10-08 | 24/8/2022 | N/A | N/A | N/A | N/A | 30/9/2022 | 24 Hours |  | 18/10/2022 | 31/10/2022 | N/A | 13/12/2022 | 22/12/2022
Actual
8 | PROCUREMENT OF DIESEL & PETROL FOR GENERATING SET AT HQ AND REGISTRATION STATIONS | LASSRA/G-F/DC/002/22 |  |  | 15000000 | <50M | DC | POST | PRIOR | Plan | 31/1/2022 | 17/2/2022 | N/A | N/A | N/A | N/A | 18/2/2022 | 24 Hours |  | 31/3/2022 | 2022-06-04 | N/A | 29/12/2022 | 30/12/2022
Actual
9 | PROCUREMENT OF JANITORIALS TOILETRIES | LASRRA/G-F/NS/002/22 |  |  | 1500000 | <10M | NS | POST | PRIOR | Plan | 17/1/2022 | 25/1/2022 | 2022-07-02 | 14/2/2022 | 28/2/2022 | 2022-07-03 | 14/3/2022 | 24 Hours |  | 17/3/2022 | 21/3/2022 | N/A | N/A | 31/10/2022
Actual
10 | PROCUREMENT OF REGISTRATION/ENROLMENT INK CONSUMABLES | LASRRA/G-F/NS/003/22 |  |  | 7800000 | <10M | NS | POST | POST | Plan | 25/1/2022 | 2022-07-02 | 18/2/2022 | 28/2/2022 | 2022-07-03 | 28/2/2022 | 18/3/2022 | 24 Hours |  | 28/3/2022 | 2022-04-04 | N/A | 16/11/2022 | 21/11/2022
Actual
11 | PROCUREMENT OF FIRE EXTINGUISHER | LASRRA/G/NS/005/22 |  |  | 115500 | <10M | NS | POST | POST | Plan | 2022-05-04 | 22/4/2022 | 25/4/2022 | 2022-06-05 | 16/5/2022 | 23/5/2022 | 2022-03-06 | 24 Hours |  | 2022-08-06 | 17/6/2022 | N/A | 15/7/2022 | 18/7/2022
Actual
12 | PROCUREMENT OF 4-4-2 SCANNERS | LASRRA/G/DS/001/22 |  | 20 | 12190000 | <50M | NS | POST | PRIOR | Plan | 2022-02-05 | 23/5/2022 | 2022-06-06 | 24/6/2022 | 30/6/2022 | 2022-04-07 | 2022-07-07 | 24 Hours |  | 15/7/2022 | 25/7/2022 | N/A | 29/8/2022 | 31/8/2022
Actual
13 | PROCUREMENT OF CARD PRINTING EQUIPMENTS FOR LAGOS STATE STAFF IDENTITY CARD PROJECT | LASRRA/G-F/NS/004/22 |  |  | 20000000 | <50M | NS | POST | PRIOR | Plan | 2022-11-02 | 2022-02-03 | 2022-07-03 | 21/3/2022 | 30/3/2022 | 2022-04-04 | 2022-08-04 | 24 Hours |  | 18/4/2022 | 22/4/2022 | N/A | 2022-06-06 | 2022-09-06
Actual
14 | PROCUREMENT OF 1.5KVA MANUAL START GENERATOR (SV2500 100% COPPER) FOR REGISTRATION STATIONS | LASRRA/G/NS/006/22 |  | 24 | 2520000 | <10M | NS | POST | POST | Plan | 17/5/2022 | 31/5/2022 | 2022-06-06 | 20/6/2022 | 30/6/2022 | 2022-04-07 | 15/7/2022 | 24 Hours |  | 21/7/2022 | 25/7/2022 | N/A | 30/7/2022 | 31/7/2022
Actual
15 | PROCUREMENT OF DESKTOPS & LAPTOPS , UPS AND PRINTERS | LASRRA/G/NS/007/22 |  | 20 | 9228058.4 | <10M | NS | POST | PRIOR | Plan | 2020-12-07 | 25/7/2022 | 2022-08-08 | 19/8/2022 | 22/8/2022 | 30/8/2022 | 2022-05-09 | 48 Hours |  | 2022-12-09 | 16/9/2022 | N/A | 18/10/2022 | 19/10/2022
Actual
16 | PROCUREMENT OF WATER DISPENSER, MICROWAVE AND 32INCHES TELEVISION SET | LASRRA/G/NS/008/22 |  | 3 | 780000 | <10M | NS | POST | PRIOR | Plan | 25/1/2020 | 2022-04-02 | 18/2/2022 | 2022-07-03 | 28/3/2022 | 2022-04-04 | 20/4/2022 | 24 Hours |  | 29/4/2022 | 2022-07-05 | N/A | 16/5/2022 | 13/5/2022
Actual
| TOTAL |  |  |  | 139554238.4

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE RESIDENTS' REGISTRATION AGENCY (LASRRA)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PAINTING AND DECORATION OF HQ. | LASRRA/W/NS/001/22 |  | 1000000 | <10M | NS | BOQ | POST | Plan | Post | 2022-10-02 | 2022-10-03 | 24/3/2022 | 2022-07-04 | 19/5/2022 | 2022-01-06 | 15/6/2022 | 23/6/2022 |  | 24/6/2022 | 2022-01-07 | N/A | 2022-10-08 | 22/8/2022
Actual
2 | PAINTING AND DECORATION OF REGISTRATION STATIONS | LASRRA/W/NS/002/22 |  | 638789.96 | <10M | NS | BOQ | POST | Plan | Post | 2022-10-02 | 2022-10-03 | 24/3/2022 | 2022-07-04 | 19/5/2022 | 2022-01-06 | 15/6/2022 | 23/6/2022 |  | 24/6/2022 | 2022-01-07 | N/A | 2022-10-08 | 22/8/2022
Actual
| TOTAL COST |  |  | 1638789.96 |  |  |  |  | Plan
Actual

## MAI
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/DEPARTMENT/AGENCY: LAGOS STATE RESIDENTS REGISTRATION AGENCY (LASRRA)
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | LASRRA/S-NC-F/NS/001/22 |  |  | 4552500 | <10M | NS | Plan | POST | POST | 21/2/2022 | 25/2/2022 | 2022-07-03 | 2022-01-12 | 18/3/2022 | 25/3/2022 | N/A | Plan | 2022-01-04 | 24 Hours |  | 2022-08-04 | N/A | 30/6/2022 | 2022-04-07
[7 empty] | Actual | [9 empty] | Actual
SERVICING AND REPAIRS OF MOTOR VEHICLES | LASRRA/S-NC-F/NS/002/22 |  |  | 5000000 | <10M | NS | Plan | POST | POST | 28/3/2022 | 31/3/2022 | 2022-04-04 | 2022-11-04 | 13/4/2022 | 15/4/2022 | N/A | Plan | 29/4/2022 | 24 Hours |  | 2022-02-15 | N/A | 2022-05-05 | 2022-10-08
[7 empty] | Actual | [9 empty] | Actual
SPRAY AND REBRANDING OF LASRRA VEHICLES | LASRRA/S-NC/NS/001/22 |  |  | 1510000 | <10M | NS | Plan | POST | POST | 28/3/2022 | 31/3/2022 | 2022-04-04 | 2022-11-04 | 13/4/2022 | 15/4/2022 | N/A | Plan | 29/4/2022 | 24 Hours |  | 2022-02-15 | N/A | 2022-05-05 | 2022-10-08
[7 empty] | Actual | [9 empty] | Actual
PROVISION FOR REPAIRS, SERVICING AND GENERAL MAINTENANCE | LASRRA/S-NC/NS/002/22 |  |  | 5200000 | <10M | NS | Plan | POST | POST | 24/1/2022 | 31/1/2022 | N/A | N/A | N/A | N/A | N/A | Plan | 28/2/2022 | 24 Hours |  | 2022-06-04 | N/A | 14/6/2022 | 30/6/2022
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE AND REPAIR OF GENERATORS AT HQ AND REGISTRATION STATIONS | LASRRA/S-NC-F/NS/003/22 |  |  | 1200000 | <10M | NS | Plan | POST |  | 2022-06-04 | 18/4/2022 | 29/4/2022 | 27/4/2022 | 31/5/2022 | 2022-06-06 | 14/6/2022 | Plan | 27/6/2022 | 24 Hours |  | 2022-01-07 | N/A | 15/8/2022 | 18/8/2022
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF HEAVY DUTY INDUSTRIAL PHOTOCOPY MACHINES | LASRRA/S-NC-F/NS/004/22 |  |  | 500000 | <10M | NS | Plan | POST | POST | 2022-07-03 | N/A | 14/3/2022 | 21/3/2022 | 2022-01-04 | N/A | N/A | Plan | 14/4/2022 | 48 Hours |  | 18/4/2022 | N/A | 2022-02-05 | 2022-06-05
[7 empty] | Actual | [9 empty] | Actual
FUMIGATION OF 60 REGISTRATION STATIONS | LASRRA/S-NC-F/NS/005/22 |  |  | 600000 | <10M | NS | Plan | POST | POST | 30/5/2022 | 13/6/2022 | 17/6/2022 | 27/6/2022 | 29/6/2022 | 2022-05-07 | 2022-11-07 | Plan | 29/7/2022 | 24 Hours |  | 2022-01-08 | N/A | 19/9/2022 | 23/9/2022
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE AND REPAIR OF COMPUTER HARDWARE | LASRRA/S-NC-F/NS/006/22 |  |  | 1832000 | <10M | NS | Plan | POST | POST | 31/5/2022 | 2022-10-06 | N/A | N/A | N/A | N/A | N/A | Plan | 30/6/2022 | 48 Hours |  | 2022-11-07 | N/A | 29/7/2022 | 2022-05-07
[7 empty] | Actual | [9 empty] | Actual
ENGAGEMENT OF CONSULTANTS FOR PROJECT MANAGEMENT SOFTWARE (INTERNAL & EXTERNAL STAKEHOLDER ENGAGEMENT) | LASRRA/S-NC/NS/007/22 |  |  | 6000000 | <10M | NS | Plan | POST | POST | 16/2/2022 | 21/2/2022 | N/A | N/A | N/A | N/A | N/A | Plan | 30/3/2022 | 48 Hours |  | 18/4/2022 | N/A | 28/10/2022 | 31/10/2022
[7 empty] | Actual | [9 empty] | Actual
ENGAGEMENT OF CONSULTANT SECURITY AND SPECIAL DUTIES | LASRRA/S-NC/NS/008/22 |  |  | 2773500 | <10M | NS | Plan | POST | POST | 28/1/2022 | 21/2/2022 | N/A | N/A | N/A | N/A | N/A | Plan | 2022-08-08 | 48 Hours |  | 15/8/2022 | N/A | 26/9/2022 | 2022-10-10
[7 empty] | Actual | [9 empty] | Actual
STAFF RETREAT | LASRRA/S-NC/NS/009/22 |  |  | 28000000 | <50M | NS | Plan | POST | POST | 31/1/2022 | 21/2/2022 | N/A | N/A | N/A | N/A | N/A | Plan | 2022-02-05 | 48 Hours |  | N/A | N/A | 2022-08-06 | 22/6/2022
[7 empty] | Actual | [9 empty] | Actual
DEPLOYMENT OF ACCOUNTING SOFTWARE | LASRRA/S-NC/NS/010/22 |  |  | 3000000 | <10M | NS | Plan | POST | POST | 21/2/2022 | 24/2/2022 | 28/2/2022 | 2022-11-03 | 2022-01-04 | 2022-07-04 | 18/4/2022 | Plan | 29/4/2022 | 48 Hours |  | 2022-03-05 | N/A | 30/5/2022 | 31/10/2022
[7 empty] | Actual | [9 empty] | Actual
ENGAGEMENT OF DATA CAPTURE PARTNERS | LASRRA/S-NC/NS/011/22 |  |  | 300000000 | <500M | NS | Plan | POST | POST | 17/1/2022 | 2022-07-02 | N/A | N/A | N/A | 2022-09-05 | 26/5/2022 | Plan | 30/5/2022 | 48 Hours |  | 20/6/2022 | N/A | 30/6/2022 | 15/7/2022
[7 empty] | Actual | [9 empty] | Actual
TOTAL COST |  |  |  | 360168000 | <500M |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual