## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LASUBEB
BUDGET YEAR: Y2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/ Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Travel & Transport for Despatch of Letters, Mails to and fro Alausa and other agencies within Lagos, 20 LGEAs, UBEC office Abuja and Federal Ministry of Education | LASUBEB/NP/NM/001/22 | 40996992 | Plan
Actual
3 | Payment of Electricity Bills monthly. | LASUBEB/NP/NM/003/22 | 14400000 | Plan
Actual
4 | Subscrition for cable Television | LASUBEB/NP/NM/004/22 | 600000 | Plan
Actual
5 | Payment of official phone (CUG) bills | LASUBEB/NP/NM/005/22 | 612000 | Plan
Actual
6 | Payment for Waste Disposal in Schools & LGEAs | LASUBEB/NP/NM/006/22 | 4800000 | Plan
Actual
8 | Monthly contigencies Expenses | LASUBEB/NP/NM/008/22 | 31200000 | Plan
Actual
9 | Payment of Allowance to Civil Defence Officers | LASUBEB/NP/NM/009/22 | 2400000 | Plan
Actual
13 | Provision of Medical Facilities/ First Aids to staff and Organization of Health Week and Free Medical checkup for Staff | LASUBEB/NP/NM/013/22 | 16000000 | Plan
Actual
14 | Provision of Lunch at subsidise rate to Staff | LASUBEB/NP/NM/014/22 | 12000000 | Plan
Actual
15 | Annual Children's Day | LASUBEB/NP/NM/015/22 | 3000000 | Plan
Actual
16 | Pupils Interactive Forum During Muslims & Christians Festivals ( 4 Festivals) | LASUBEB/NP/NM/016/22 | 7200000 | Plan
Actual
17 | Social Welfare Packages for Staff | LASUBEB/NP/NM/017/22 | 18000000 | Plan
Actual
18 | Packages for retired Septugenarians | LASUBEB/NP/NM/018/22 | 10500000 | Plan
Actual
19 | Last Days in Office for SUBEB Staff and Teaching and Non- Teaching Staff | LASUBEB/NP/NM/019/22 | 30000000 | Plan
Actual
20 | Preparation of Annual Audited Account report and meetings with Offices of Auditor Generals for state & Local Government and Public Account Committees | LASUBEB/NP/NM/020/22 | 4500000 | Plan
Actual
21 | Handling UBEC/TETFUND Matters | LASUBEB/NP/NM/021/22 | 2200000 | Plan
Actual
22 | Store Verification in LGEAs & Primary Schools | LASUBEB/NP/NM/022/22 | 2102000 | Plan
Actual
23 | Monitoring & Inspection of books of Accounts at 20 LGEAs | LASUBEB/NP/NM/023/22 | 3000000 | Plan
Actual
24 | Audit of the financial Statement of the Board & Schools | LASUBEB/NP/NM/024/22 | 2500000 | Plan
Actual
25 | Updating of Office Inventory Cards & Fixed Assets of Vocational Centres in SUBEB and 20 LGEAs | LASUBEB/NP/NM/025/22 | 1300000 | Plan
Actual
26 | Formal Execution of Contract Agreement | LASUBEB/NP/NM/026/22 | 1200000 | Plan
Actual
27 | Researching & Profering prompt Legal Advise | LASUBEB/NP/NM/027/22 | 500000 | Plan
Actual
28 | Provision of Lagalpedia software | LASUBEB/NP/NM/028/22 | 250000 | Plan
Actual
29 | Yearly subscription for Nigerian Weekly Law report | LASUBEB/NP/NM/029/22 | 250000 | Plan
Actual
30 | Provision of sets of Legal reference Books and Journals | LASUBEB/NP/NM/030/22 | 300000 | Plan
Actual
31 | Routine Placement of Advertisement on Bidding of SUBEB Projects in National Newspaper | LASUBEB/NP/NM/031/22 | 1900000 | Plan
Actual
32 | Opening Bid Ceremony | LASUBEB/NP/NM/032/22 | 595000 | Plan
Actual
33 | Market Survey | LASUBEB/NP/NM/033/22 | 200000 | Plan
Actual
34 | Conduct of Annual School Census (ASC) Exercise | LASUBEB/NP/NM/034/22 | 10000000 | Plan
Actual
35 | Internet Subscription, Renewal of website and Anti-Virus | LASUBEB/NP/NM/035/22 | 18000000 | Plan
Actual
36 | Monitoring of LGEAs Data Roll-out | LASUBEB/NP/NM/036/22 | 1500000 | Plan
Actual
37 | Preparation of Schools, LGEAs and Board's activities monthly report | LASUBEB/NP/NM/037/22 | 300000 | Plan
Actual
38 | Preparation of Medium Term Basic Education Strategic Plan | LASUBEB/NP/NM/038/22 | 19685600 | Plan
Actual
39 | Preparation, Defence of Budget and Quarterly Appraisal | LASUBEB/NP/NM/039/22 | 24000000 | Plan
Actual
40 | Schools Status Report | LASUBEB/NP/NM/040/22 | 12000000 | Plan
Actual
41 | Preparation and bilaterial discusion/ Departmental Work Plans Retreat | LASUBEB/NP/NM/041/22 | 12000000 | Plan
Actual
42 | Monitoring of 2nd & 3rd Terms Unified Examination for Pupils In Primary Schools | LASUBEB/NP/NM/042/22 | 3000000 | Plan
Actual
43 | Conduct of Promotion (Structured Training Programme) Exercise for Teaching & Non-teaching staff | LASUBEB/NP/NM/043/22 | 20907000 | Plan
Actual
44 | Conduct of AP&D for Discipline, Conversion & Regularization | LASUBEB/NP/NM/044/22 | 1000000 | Plan
Actual
45 | Preparation of Y2022 Personnel Cost Budget | LASUBEB/NP/NM/045/22 | 500000 | Plan
Actual
46 | Conduct of Promotion Oral Interview forTeaching and Non-Teaching staff | LASUBEB/NP/NM/046/22 | 4500000 | Plan
Actual
47 | Conversion Interview Exercise | LASUBEB/NP/NM/047/22 | 2000000 | Plan
Actual
48 | Duty Post Examination | LASUBEB/NP/NM/048/22 | 2000000 | Plan
Actual
49 | Recruitment of new Teachers Expenses | LASUBEB/NP/NM/049/22 | 10000000 | Plan
Actual
50 | Estabilishment matter Expenses | LASUBEB/NP/NM/050/22 | 20000000 | Plan
Actual
51 | Basic Education Quality Assurance (BEQA) Expenses | LASUBEB/NP/NM/051/22 | 45000000 | Plan
Actual
52 | Social Mobilization Expenses | LASUBEB/NP/NM/052/22 | 20000000 | Plan
Actual
53 | School Services | LASUBEB/NP/NM/053/22 | 32000000 | Plan
Actual
54 | School Projects monitoring | LASUBEB/NP/NM/054/22 | 12000000 | Plan
Actual
55 | Preparation of Budget/ Departmental WorkPlan for the 20 LGEAs | LASUBEB/NP/NM/055/22 | 5000003 | Plan
Actual
56 | Preparation of Medium Term Basic Education Strategic Plan | LASUBEB/NP/NM/056/22 | 11885600 | Plan
Actual
57 | Carrying out Advocacy/LGEA Forum at (20 LGEAs) | LASUBEB/NP/NM/057/22 | 8000000 | Plan
Actual
58 | Support Annual Merit Award Service for Teaching & Non-Teaching Staff at LGEAs Level (20LGEAs | LASUBEB/NP/NM/058/22 | 8000000 | Plan
Actual
59 | Conduct of MTBESP & BESDA School Census | LASUBEB/NP/NM/059/22 | 72669000 | Plan
Actual
60 | Preparation of Senority list /Personnel Budget | LASUBEB/NP/NM/060/22 | 2400000 | Plan
Actual
61 | Pension Matter | LASUBEB/NP/NM/061/22 | 2000000 | Plan
Actual
62 | Promotion Matter | LASUBEB/NP/NM/062/22 | 2500000 | Plan
Actual
63 | Advocacy Programme on Child's Right Protection | LASUBEB/NP/NM/063/22 | 3000000 | Plan
Actual
64 | Conduct of Mobile Counselling and Parental Education in all LGEAs | LASUBEB/NP/NM/064/22 | 6000000 | Plan
Actual
65 | Child Abuse Related Matters | LASUBEB/NP/NM/065/22 | 3000000 | Plan
Actual
66 | Monitoring of Home grown School feeding programme | LASUBEB/NP/NM/066/22 | 4500000 | Plan
Actual
67 | Monitoring of School Farm and Garden programme | LASUBEB/NP/NM/067/22 | 1650000 | Plan
Actual
68 | Pre-retirement Empowerment Programme for retiring officers | LASUBEB/NP/NM/068/22 | 21120000 | Plan
Actual
69 | Sensitisation of Teachers, PDOs & HOS on Pension Matters | LASUBEB/NP/NM/069/22 | 19560000 | Plan
Actual
654183195

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LASUBEB
BUDGET YEAR: Y2022
S/N | Description of Training/Workshop/ Conference | Project Package | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training of Junior Staff | LASUBEB/S-WTC/SS/001/22 |  | 4 |  | Plan |  |  |  |  | 8500000
Actual
2 | Workshop and Training for Librarian | LASUBEB/S-WTC/SS/002/22 |  | 3 |  | Plan |  |  |  |  | 1200000
Actual
3 | Workshop and Training for Sport and Game Masters | LASUBEB/S-WTC/SS/003/22 |  | 3 |  | Plan |  |  |  |  | 1200000
Actual
4 | Workshop & Training for Pension Desk Officers | LASUBEB/S-WTC/SS/004/22 |  | 3 |  | Plan |  |  |  |  | 1200000
Actual
5 | Workshop & Training for School Support Officers | LASUBEB/S-WTC/SS/005/22 |  |  |  | Plan |  |  |  |  | 2400000
|  |  |  | 3 |  | Actual
6 | Workshop & Training for A&HR Officers | LASUBEB/S-WTC/SS/006/22 |  | 3 |  | Plan |  |  |  |  | 1200000
Actual
7 | Workshop & Training for Secretariat, Welfare & Social Officers | LASUBEB/S-WTC/SS/007/22 |  | 3 |  | Plan |  |  |  |  | 2400000
Actual
8 | Workshop for EMIS Desk Officers | LASUBEB/S-WTC/SS/008/22 |  | 2 |  | Plan |  |  |  |  | 5000000
Actual
9 | Training and Workshop Expenses of Executive cadre Officers | LASUBEB/S-WTC/SS/009/22 |  | 1 |  | Plan |  |  |  |  | 3000000
Actual
10 | Training for Basic Education Quality Assurance Officers | LASUBEB/S-WTC/SS/010/22 |  | 1 |  | Plan |  |  |  |  | 5000000
[6 empty] | Actual |  |  |  |  | 773333.3333
11 | Training of Budget Officers | LASUBEB/S-WTC/SS/011/22 |  | 1 |  | Plan |  |  |  |  | 4000000
Actual
Actual
12 | Training of Food Vendors | LASUBEB/S-WTC/SS/012/22 |  | 1 |  | Plan |  |  |  |  | 750000
Actual
13 | Training of Internal Auditors | LASUBEB/S-WTC/SS/013/22 |  | 1 |  | Plan |  |  |  |  | 400000
Actual
14 | Workshop for Board members & Directors and House of Assembly Committee Members on Education | LASUBEB/S-WTC/SS/014/22 |  | 5 |  | Plan |  |  |  |  | 30000000
Actual
15 | Induction training for newly recruited Teachers and Care givers | LASUBEB/S-WTC/SS/015/22 |  | 1 |  | Plan |  |  |  |  | 15000000
Actual
16 | Trainning of Management Staff | LASUBEB/S-WTC/SS/016/22 |  | 3 |  | Plan |  |  |  |  | 6000000
Actual
17 | Workshop & Training for Account Officers | LASUBEB/S-WTC/SS/017/22 |  | 1 |  | Plan |  |  |  |  | 1000000
Actual
18 | Workshop &Trainning for Secretaries | LASUBEB/S-WTC/SS/018/22 |  | 1 |  | Plan |  |  |  |  | 2400000
Actual
19 | Workshop & Training for Procurement Officers | LASUBEB/S-WTC/SS/019/22 |  | 1 |  | Plan |  |  |  |  | 1200000
Actual
20 | Workshop & Training for Social Mobilisation Officers | LASUBEB/S-WTC/SS/020/22 |  | 1 |  | Plan |  |  |  |  | 5000000
Actual
21 | Training of Education Secretaries | LASUBEB/S-WTC/SS/021/22 |  | 1 |  | Plan |  |  |  |  | 4000000
Actual
22 | Training of officers at NIEPA | LASUBEB/S-WTC/SS/022/22 |  | 1 |  | Plan |  |  |  |  | 7479480
Actual
23 | Retrainning of Food Vendors | LASUBEB/S-WTC/SS/023/22 |  | 1 |  | Plan |  |  |  |  | 3000000
Actual
24 | Training of Special Education Teachers | LASUBEB/S-WTC/SS/024/22 |  | 1 |  | Plan |  |  |  |  | 20340000
Actual
25 | Training on Intra-Net, Pesonnel Records Management System | LASUBEB/S-WTC/SS/025/22 |  | 1 |  | Plan |  |  |  |  | 100000000
Actual
26 | ICT Training | LASUBEB/S-WTC/SS/026/22 |  | 1 |  | Plan |  |  |  |  | 102320000
Actual
27 | Training of Guidiance & Counselling Teachers | LASUBEB/S-WTC/SS/027/22 |  | 1 |  | Plan |  |  |  |  | 14000000
Actual
28 | Training of Teachers in Basic Science | LASUBEB/S-WTC/SS/028/22 |  | 1 |  | Plan |  |  |  |  | 14000000
Actual
29 | Training of Library Teachers | LASUBEB/S-WTC/SS/029/22 |  | 1 |  | Plan |  |  |  |  | 7500000
Actual
30 | Training of ECCDE Teachers | LASUBEB/S-WTC/SS/030/22 |  | 1 |  | Plan |  |  |  |  | 14000000
Actual
31 | Literacy and Numeracy Trainning for Classroom Teachers | LASUBEB/S-WTC/SS/031/22 |  | 1 |  | Plan |  |  |  |  | 46960000
Actual
32 | Training of PHE Teachers | LASUBEB/S-WTC/SS/032/22 |  | 1 |  | Plan |  |  |  |  | 40680000
Actual
33 | Training of Vocational Teachers | LASUBEB/S-WTC/SS/033/22 |  | 1 |  | Plan |  |  |  |  | 20300000
Actual
34 | Retreat & Training for School Support | LASUBEB/S-WTC/SS/034/22 |  | 1 |  | Plan |  |  |  |  | 6400000
Actual
35 | Trainning on Instructional Materials Preparation | LASUBEB/S-WTC/SS/035/22 |  | 1 |  | Plan |  |  |  |  | 72500000
Actual
36 | Schools Mangers/Classroom Teacher Improvement Programme | LASUBEB/S-WTC/SS/036/22 |  | 1 |  | Plan |  |  |  |  | 277080000
Actual
37 | International Training of School Managers | LASUBEB/S-WTC/SS/037/22 |  | 1 |  | Plan |  |  |  |  | 263240000
Actual
38 | School Based Deworming Training | LASUBEB/S-WTC/SS/038/22 |  | 1 |  | Plan |  |  |  |  | 10000000
Actual
39 | Training of Teachers on Safe-Guard | LASUBEB/S-WTC/SS/039/22 |  | 1 |  | Plan |  |  |  |  | 10000000
Actual
40 | Training of Teachers on Home Grown School Feeding | LASUBEB/S-WTC/SS/040/22 |  | 1 |  | Plan |  |  |  |  | 10000000
Actual
1141422813.33

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTANCY
MINISTRY/ AGENCY: LASUBEB
BUDGET YEAR: Y2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Replacement of broken / damaged doors, keys and locks; Window Blinds and accessories; Toilet Closests and accessories ;repair of electrical fittings | LSUBEB/S-NC/FB/001/22 |  |  | 2049600 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Carry out Monthly Environmental Sanitation Exercise; Clearing of blocked pipes and evacuation of Septic Tanks; Refuse Disposal; Funmigation of Office and Maintenance of SUBEB Hall | LSUBEB/S-NC/FB/002/22 |  |  | 2640000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Maintenance and servicing of Air Condition | LSUBEB/S-NC/FB/003/22 |  |  | 2282000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Maintenance of CCTV camera and Intercom | LSUBEB/S-NC/FB/004/22 |  |  | 600000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Maintenance of office Furniture | LSUBEB/S-NC/FB/005/22 |  |  | 2496000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Servicing and Repairs of Vehicles bi- monthly and Repair of Car Air Condition | LSUBEB/S-NC/FB/006/22 |  |  | 7590000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Renewal of Vehicle Tracking Devices | LSUBEB/S-NC/FB/007/22 |  |  | 1300000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Repairs/ Servicing/ Replacement of faulty parts of 350KVA Milkano Generator | LSUBEB/S-NC/FB/008/22 |  |  | 6000000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Registration of Pupils into ECCCDE/Pry One, Transfer of Pupils into Primaries 2- 5 and Placement of Primary Six Pupils into JSS I Related expenses | LSUBEB/S-NC/FB/009/22 |  |  | 4500000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Lagos SUBEB In-view on Television | LASUBEB/S-NC/FB/010/22 |  |  | 24000000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Airing of SUBEB Activities on Television | LASUBEB/S-NC/FB/011/22 |  |  | 9000000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Airing of IRI (KO-KO-KA) programme on Radio | LASUBEB/S-NC/FB/012/22 |  |  | 12000000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Advertisement & Jingles on ECCDE/ Primary One Registration in 4 languages | LASUBEB/S-NC/FB/013/22 |  |  | 1500000 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Maintenance/repair of computer system, CCTV, Photocopiers | LASUBEB/S-NC/FB/014/22 |  |  | 10200000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Developing Co-Curricular Activities in Schools and 20 LGEA Level | LASUBEB/S-NC/FB/015/22 |  |  | 56000000 | <100M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Provision of Mid-Day Meal for pupils in 31 Inclusive Units | LASUBEB/S-NC/FB/016/22 |  |  | 27027000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Operation of Speed Boats in Riverine Schools for186 days (50 litres per day/boat) | LASUBEB/S-NC/FB/017/22 |  |  | 12000000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Conduct of Annual Merit Award for Teachers | LASUBEB/S-NC/FB/017/22 |  |  | 20400000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
End-of-the-year welfare for Teaching and non teaching staff | LASUBEB/S-NC/FB/017/22 |  |  | 35460000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Long Service Award for Teaching & Non-Teaching Staff | LASUBEB/S-NC/FB/017/22 |  |  | 35000000 | <50M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
Printing of Envelopes | LASUBEB/S-NC/FB/018/22 |  |  | 3693900 | <10M | Fixed Budget | Plan | Post | Post | 13/1/22 | 2022-03-02 | 17/02/22 | 24/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | Plan |  |  |  | 20/04/22 | 2022-04-05 | 18/05/22
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 275738500

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LASUBEB
BUDGET YEAR: Y2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | External Auditor Fee | LASUBEB/S-C/FB/001/22 | Fixed Budget | Lump sum | 2500000 | Post | Plan | 2022-02-03 | 2022-09-03 | 23/3/22 | 30/3/22 | 13/4/22 | 2022-11-05 | 25/5/22 | 2022-08-06 | 15/06/22 | 22/07/22 | 2022-06-07 | 22/07/22 | 2022-06-07 |  | 2000000 | 27/07/22 | 2022-03-08 | 17/08/22 | 31/08/22 | 2021-07-09 | 2500000
Actual
2 | Audit of the financial Statement of the Board & Schools | LASUBEB/S-C/FB/002/22 | Fixed Budget | Lump sum | 2500000 | Prior | Plan | 2022-02-03 | 2022-09-03 | 23/3/22 | 30/3/22 | 13/4/22 | 2022-11-05 | 25/5/22 | 2022-08-06 | 15/06/22 | 22/07/22 | 2022-06-07 | 22/07/22 | 2022-06-07 |  | 2000000 | 27/07/22 | 2022-03-08 | 17/08/22 | 31/08/22 | 2021-07-09 | 2500000
Actual
3 | Classroom in your Home | LASUBEB/S-C/DC/001/22 | Direct Contract | Lump sum | 36000000 | Prior | Plan | 2022-02-03 | 2022-09-03 | 23/3/22 | 30/3/22 | 13/4/22 | 2022-11-05 | 25/5/22 | 2022-08-06 | 15/06/22 | 22/07/22 | 2022-06-07 | 22/07/22 | 2022-06-07 |  | 2000000 | 27/07/22 | 2022-03-08 | 17/08/22 | 31/08/22 | 2021-07-09
Actual
4 | EKO Excel Fees based on estimted 436,920 pupils enrolment@ N15,219 per child for 2020/2021 Academic Session i.e N2,216,499,226.33 each for Terms I, II & II. | LASUBEB/S/SS/001/19 | Single Source | Lump sum | 6649497679 | Prior | Plan | [14 empty] | 2000000 | ON GOING
Actual
6690497679

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LASUBEB
BUDGET YEAR: Y2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Provision of Motor bike for Dispatch | LASUBEB/G/NS/001/22 |  |  | 1300000 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
2 | Provision of Office furniture for SUBEB and LGEA offices | LASUBEB/G/NS/002/22 |  |  | 40080000 | <50M | National Shopping | Post | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
3 | Upgrading and Revamping of ICT Facilities at LGEAs | LASUBEB/G/NCB/001/22 |  |  | 139399164 | <500M | National Compititive Bidding | Post | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
4 | Provision of Cameras/ Laptops/ Tablets for SUBEB and LGEAs | LASUBEB/G/NS003/22 |  |  | 93500000 | <100M | National Shopping | Prior | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
5 | Replacement of 57 Vehicles tyres; Batteries(100AH - solite) ; Jack and Fittings | LASUBEB/G/NS/004/22 |  |  | 9430000 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
6 | Provision of Computer and Photocopier Tonner Ink for LGEAs & SUBEB HQ and Replacement of computer accessories | LASUBEB/G/NS/005/22 |  |  | 13200000 | <50M | National Shopping | Post | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
7 | Provision of Procurement Folders | LASUBEB/G/NS/006/22 |  |  | 125000 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
8 | Provision of Uniforms for Drivers, Guards, cleaners, Store & Cateen officers, Clinic Staff | LASUBEB/G/NS/007/22 |  |  | 5000000 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
9 | Instructional Materials for special schools | LASUBEB/G/NS/008/22 |  |  | 5000000 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
10 | Provision of school records and registers | LASUBEB/G/NS/009/22 |  |  | 2550000 | <10M | National Shopping | Prior | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
11 | Instructional Materials for ECCD & Primary Schools | LASUBEB/G/NS/010/22 |  |  | 15000000 | <50M | National Shopping | Post | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
12 | Procurement of Printer Toner Ink | LASUBEB/G/NS/011/21 |  |  | 3600000 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
13 | Provision of consumable items and learning materials to vocational centres | LASUBEB/G/NS/012/22 |  |  | 15000000 | <50M | National Shopping | Post | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
14 | Replacement of Feeding Bottles | LASUBEB/G/NS/013/22 |  |  | 17000000 | <50M | National Shopping | Prior | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
15 | Fuelling of vehicles and 350KVA Milkano Generator | LASUBEB/G/NCB/002/22 |  |  | 74168400 | <100M | National Shopping | Prior | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
16 | Stationery and Printings Items and Provision of Account Books | LASUBEB/G/NS/014/22 |  |  | 20904000 | <50M | National Shopping | Prior | Prior | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
17 | Procurement of Two (2) Mini Buses Y 2020 Intervention Fund | LASUBEB/G/NS/015/22 |  |  | 3555727.48 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
18 | Procurement of Air Conditioners | LASUBEB/G/NS/016/22 |  |  | 4327500 | <10M | National Shopping | Post | Post | Plan | 2022-12-05 | 26/05/22 | 2022-02-06 | 16/06/22 | 13/07/22 | 20/07/22 | 27/7/22 |  |  | 2022-08-10 | 17/8/2022 | 2022-09-09
Actual
1 | Completion of 6,415 pairs of Pupils Furniture | LASUBEB/NCB/G/048/20 |  |  | 88300000 | <500M | National Compititive Bidding | Post | Prior | Plan | ON GOING (OUTSTANDING LIABILITY)
Actual
551439791.48

## works (ONGOING)
PROCUREMENT PLAN FOR WORKS (LIABILITY)
MINISTRY: LASUBEB
BUDGET YEAR: Y2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  |  | (1 wk) | (1-2 wks) | (2-4wks)
1 | Rehabilitation of a Block of 12 Classrooms with Office and Toilet at Methodist Primary School, Oke Eletu |  |  | 2958298.5 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING
Actual
2 | Rehabilitation of a Block of 6 Classrooms with Office and Toilets at Community Primary School, Surulere, Alimosho | LASG/LSUBEB/NS-10/W-REHAB/9/2016 | 10 | 1649999.5 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 16499995
Actual
3 | Rehabilitation of 17 + 1 Classrooms with Office and Toilets at ZI School I and II, Alaba, Amuwo Odofin | LASG/LSUBEB/NS-19/W-REHAB/9/2016 | 19 | 3649998.8 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 36499988
Actual
4 | Construction of a Block of 6 Classrooms with H/T Office, Assistant H/T Office, Store and Toilets (Special Raft Foundation) Riverine at Community Primary School, Iba-Oloja, Ibeju-Lekki |  |  | 13800000 | <50M | NCB | BOQ | POST | Plan | POST | ONGOING
Actual
5 | Construction of 350m Fence, Gate and Gate House (Raft Foundation) at Fazil Omar Ahamadiya Primary School, Okokomaiko, Ojo | LASG/LSUBEB/NS-53/W-CON/9/2016 | 53 | 5697990 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 18993300
Actual
6 | Construction 480m fence at UPE Primary School, Ajegbende, Epe | LASG/LSUBEB/NS-59/W-CON/9/2016 | 59 | 1271290 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING
Actual
7 | Rehabilitation of a Block of 18 Classrooms, office and Toilets at Victoria Island primary School, Eti-Osa, |  |  | 2280016 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING
Actual
8 | Rehabilitation of 12 Classrooms with Toilets at Army Children Primary School, Badagry | LASG/LSUBEB/NS-22/W-REHAB/9/2016 | 22 | 1479149.75 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 29582995
Actual
9 | Construction of a Block of 13 + 1 Classrooms with H/T Office, Assistant H/T Office, Store and Toilets (Raft Foundation) at L. G. Central Primary School, Epe | LSUBEB/2018/INFRAST-DEV/NS/W/05/18 | 5 | 41308500.237 | <50M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 137695000.79
Actual
10 | Construction of 20 classrooms with office and Toilets at Anglican Primary School,Isawo, Ikorodu |  |  | 6194081 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING
Actual
11 | Construction of 13 classrooms at Community Primary School, Abule Eko, Ijede | LASG/LSUBEB/NS-01/WC/9/2016 | 1 | 4246400 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING
Actual
12 | Rehabilitation of 17 +1 Block of Classrooms, office and Toilets at Akoka Primary School, Lagos Mainland | LASG/LSUBEB/NS-29/REH/9/2016 | 29 | 1824998 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 36499970
Actual
13 | Construction of 480m Fence, Gate and Gate House (Raft Foundation) at UPE Primary School, Ajegbende, Epe | LASG/LSUBEB/NS-59/CON/9/2016 |  | 1271795 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 25435900
Actual
14 | Construction of 410m Fence, Gate and Gate House (Raft Foundation) at Community Primary School, Ijedodo | LASG/LSUBEB/NS-54/CON/9/2016 | 54 | 1098340 | <10M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 21966800
Actual
15 | Completion of SUBEB Data Centre | LASUBEB/S-C/QCBS/OO1/20 |  | 16000000 | <50M | NCB | BOQ | POST | Plan | POST | ONGOING | [7 empty] | 181201206
Actual
104730856.79

## Works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LASUBEB
BUDGET YEAR: Y2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  |  | (1 wk) | (1-2 wks) | (2-4wks)
1 | Rehabilitation of BEQA Annex Offices | LASUBEB/W/NS/001/22 |  | 25000000 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
2 | Construction of new block of 6 classroom at Methodist Primary School, Oke Eletu | LASUBEB/W/NS/002/22 |  | 75000000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
3 | Construction of 6 classrooms with office Toilets and Fence at Anglican Primary School, Ijede, Ikorodu | LASUBEB/W/NS/003/22 |  | 75000000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
4 | Construction of 6 classrooms with office Toilets and Fence at Anglican Primary School, Sekungba, Epe | LASUBEB/W/NS/004/22 |  | 75000000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
5 | Construction of SUBEB Permanent Headquarters Office at Emmanuel Primary Schools Complex, Ogudu, Kosofe | LASUBEB/W/NCB/001/22 |  | 244351296 | <500M | NCB | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
6 | Rehabilitation of a block of 10 Classrooms with Toilets at Olukotun Primary School, Alimosho | LASUBEB/W/NS/005/22 |  | 45600350 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
7 | Rehabilitation of 44 classrooms with offices and toilets at Premier Day primary School, Surulere | LASUBEB/W/NS/006/22 |  | 71051831 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
8 | Construction of a block of 13 Classrooms at L. A. Primary School, Sagbokoji Amuwo-Odofin | LASUBEB/W/NCB/002/22 |  | 150000000 | <500M | NCB | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
9 | Rehabilitation of a block of 13 Classrooms at Olowo Ira Primary School, Kosofe | LASUBEB/W/NS/007/22 |  | 46541196 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
10 | Rehabilitation of a block of 13 Classrooms at Oke-Ira Primary School, Aguda Tuntun Ogba, Ikeja | LASUBEB/W/NS/008/22 |  | 46541196 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
11 | Construction of a block of 13 Classrooms at Darocha Primary School, Agege | LASUBEB/W/NS/009/22 |  | 63500000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
12 | Construction of a block of 6 Classrooms at Ayodele Primary School, Ajeromi/Ifelodun | LASUBEB/W/NS/010/22 |  | 34000000 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/22 | 2022-03-03 | 2022-10-03 | 17/3/22 | 2022-07-04 | 13/04/22 | 20/04/22 |  |  | 2022-11-05 | 18/05/22 | 2022-01-06 | 13/12/22 | 2023-03-01
Actual
13 | Construction of a block of 13 Classrooms at African Model Nur/Primary School, Alagbado Alimosho | LASUBEB/W/NS/011/22 |  | 60001000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
14 | Emergency Repairs on Primary Schools | LASUBEB/W/NS/012/22 |  | 30000000 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
15 | Clearing of Bushy and Cleaning of Schools Environment for resumption of Academic Activities | LASUBEB/W/NS/013/22 |  | 51000000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
15 | Repair of Septic Tanks/Evacuation & clearing of blocked toilet pipes | LASUBEB/W/NS/014/22 |  | 71190000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
16 | Repair of Broken Schools' Furniture | LASUBEB/W/NS/015/22 |  | 50700000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
17 | Rescreeding of damaged classroom | LASUBEB/W/NS/016/22 |  | 59640000 | <100M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
18 | Reparing and fixing of broken classroom doors and windows | LASUBEB/W/NS/017/22 |  | 30300000 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
19 | Replacement damage ceilings and leaking classroom Roofs/Sheet | LASUBEB/W/NS/018/22 |  | 30920000 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
20 | Mending School Fence | LASUBEB/W/NS/019/22 |  | 31250000 | <50M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
21 | Flooding & Erosion | LASUBEB/W/NS/020/22 |  | 2500000 | <10M | NS | BOQ | POST | Plan | PRIOR | 25/02/21 | 2021-03-03 | 2021-10-03 | 17/3/21 | 2021-07-04 | 13/04/21 | 20/04/21 |  |  | 2021-11-05 | 18/05/21 | 2021-01-06 | 2022-07-02 | 28/2/23
Actual
1369086869