## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY: LAGOS STATE PRINTING CORPORATION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Transport & Travel | LSPC/NP/NM/01/2022 | 5000000 | Plan | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 5000000
Actual
2 | Utility | LSPC/NP/NM/02/2022 | 3000000 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3000000
Actual
3 | Miscellaneous | LSPC/NP/NM/03/2022 | 15000000 | Plan | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
Actual
4 | Insurance | LSPC/NP/NM/04/2022 | 2000000 | Plan | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 166666.6667 | 2000000
Actual
5 | Commercial Activities | LSPC/NP/NM/05/2022 | 10000000.08 | Plan | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 833333.34 | 10000000.08
Actual
6 | Audit Fees | LSPC/NP/NM/06/2022 | 2000000 | Plan |  |  |  | 666666.6667 |  |  |  | 666666.6667 |  |  |  | 666666.6667 | 2000000
Actual
7 | Bank Charges | LSPC/NP/NM/07/2022 | 1000000 | Plan | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 1000000
Actual
8 | Special Duties Expenses | LSPC/NP/NM/08/2022 | 15000000 | Plan | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
|  |  |  | Actual |  | ,
9 | Placement of Advertisement & Billboards | LSPC/NP/NM/09/2022 | 4800000 | Plan | 1600000 |  |  |  | 1600000 |  |  |  | 1600000 |  |  |  | 4800000
Actual
10 | Imprest | LSPC/NP/NM/10/2022 | 6000000 | Plan | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 6000000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY: LAGOS STATE PRINTING CORPORATION
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training and Staff Development | LSPC/S-WTC/NS/01/2022 |  |  |  | Plan |  |  |  |  | 6000000
Actual
2 | Confrence and Seminar | LSPC/S-WTC/NS/02/2022 |  |  |  | Plan |  |  |  |  | 10000000
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY: LAGOS STATE PRINTING CORPORATION
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance of Office Building | LSPC/S-NC-F/DC/01/2022 | 1 | 1 | 30000000 | <10M | DC | Plan | Post | Prior | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | Plan | 2022-03-09 | 2022-03-11 |  | 2022-04-08 | 2022-04-22 | 2022-05-06
[7 empty] | Actual | [9 empty] | Actual
Maintenance and Repair of Motor Vehicles | LSPC/S-NC-F/DC/O2/2022 | 1 | 1 | 15000000 | <10M | DC | Plan | Post | Prior | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | Plan | 2022-03-10 | 2022-03-12 |  | 2022-04-09 | 2022-04-23 | 2022-05-07
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Plants Machinery | LSPC/S-NC-F/DC/O3/2022 | 1 | 1 | 30000000 | >10M | DC | Plan | Post | Prior | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | Plan | 2022-03-13 | 2022-03-15 |  | 2022-04-12 | 2012-04-26 | 2022-05-10
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Generating Set | LSPC/S-NC-F/DC/04/2022 | 1 | 1 | 4000000 | <10M | DC | Plan | Post | Post | 2022-01-13 | 20/01/23 | 27/01/23 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | Plan | 2022-03-09 | 2022-03-11 |  | 2022-04-08 | 2022-04-22 | 2022-05-06
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Office Furniture and Equipments | LSPC/S-NC-F/DC/05/2022 | 1 | 1 | 15000000 | <10M | DC | Plan | Post | Prior | 2022-01-14 | 2022-01-27 | 2022-02-03 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | Plan | 2022-03-10 | 2022-03-12 |  | 2022-04-09 | 2022-04-23 | 2022-05-07
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Computers | LSPC/S-NC-F/DC/06/2022 | 1 | 1 | 4000000.08 | >10M | DC | Plan | Post | Post | 2022-01-17 | 2022-01-30 | 2022-02-06 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | Plan | 2022-03-13 | 2022-03-15 |  | 2022-04-12 | 2012-04-26 | 2022-05-10
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY: LAGOS STATE PRINTING CORPORATION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Consultancy Service on Printing Production | LSPC/C/CQS/01/2022 | CQS | Lump Sum | 1000000 | Post | Plan | 13/01/22 | 20/01/22 | 27/01/22 | 2022-10-02 | 17/02/22 | 24/02/22 | 17/03/22 | 24/03/22 | 31/03/22 | 2022-07-04 | 14/04/22 | 21/04/22 | 28/04/22 | 2022-02-05 |  | 2022-09-05 | 23/05/22 | 2022-06-05 | 13/05/22 | 20/05/22
Actual
2 | [6 empty] | Plan
Actual
3 | [6 empty] | Plan
Actual
4 | [6 empty] | Plan
Actual
5
6
7
8
9
10
11
12

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE PRINTING CORPORATION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Stationery | LSPC/G-F/NS/01/2022 | 1 | 1 | 5000000 | <50M | NS | 0 | Post | Plan | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 | 2022-04-19
Actual
2 | Procurement of Motor Vehicle Fuel | LSPC/G-F/NS/02/2022 | 1 | 1 | 20000000.04 | <50M | NS | Post | Prior | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-08 |  | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-20
Actual
3 | Procurement of Uniforms | LSPC/G/NS/01/2022 | 1 | 1 | 2000000 | <50M | NS | Post | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-11 |  | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-15 | 2022-04-23
Actual
4 | Procurement of Diesel and Other Lubricants | LSPC/G-F/NS/03/2022 | 1 | 1 | 30000000 | <50M | NS | Post | Post | Plan | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 | 2022-04-19
Actual
5 | Procurement of Papers, Plates, Inks and Lithographics Chemicals for Printing | LSPC/G/ICB/01 /2022 | 4 | 1 | 3439000000 | >500M | ICB | Pre | Prior | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-08 |  | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-20
Actual
6 | Procurement of drugs, injections, tesk kits and other equipments for staff clinic | LSPC/G/NS/02/2022 | 1 | 1 | 2000000 | <50M | NS | Pre | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-11 |  | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-15 | 2022-04-23
Actual
7 | Procurement of Newspapers | LSPC/G-F/NS/04/2022 | 1 | 1 | 3200000 | <50M | NS | Post | Prior | Plan | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 | 2022-04-19
Actual
8 | Procurement and Installation of 5-Colour Printing machine | LSPC/G/ICB/02/2022 | 1 | 1 | 742000000 | >500M | NCB | Pre | Prior | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-08 |  | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-20
Actual
9 | Procurement of Machines | LSPC/G/ICB/03/2022 | 5 | 1 | 923950000 | >500M | NCB | Pre | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-11 |  | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-15 | 2022-04-23
Actual
10 | Procurement of Automatic Knife Sharpener with PLC controlled operation | LSPC/G/NS/03/2022 | 1 | 1 | 29800000 | <50M | NS | Post | Post | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-08 |  | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-20
Actual
11 | Procurement of Office Equipments | LSPC/G/NS/04/2022 | 1 | 1 | 15000000 | <50M | NS | Pre | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-11 |  | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-15 | 2022-04-23
Actual
12 | Procurement of Office Furnitures | LSPC/G/NS/05/2022 | 1 | 1 | 25000000 | <50M | NS | Pre | Prior | Plan | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 | 2022-04-19
Actual
13 | Procurement of Motor Vehicle | LSPC/G/NS/06/2022 | 1 | 1 | 40000000 | <50M | NS | Post | Prior | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-08 |  | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-20
Actual
14 | Procurement of 500KVA Generator | LSPC/G/NS/07/2022 | 1 | 1 | 15000000 | <50M | NS | Pre | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-11 |  | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-15 | 2022-04-23
Actual
15 | Procurement of Computer, Laptop and Peripherals for MIS | LSPC/G/NS/08/2022 | 1 | 1 | 10000000 | <50M | NS | Post | Prior | Plan | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 | 2022-04-19
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE PRINTING CORPORATION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of New Admin Block | LSPC/W/NCB/01/2022 | 1 | 250000000 | >50M | NCB | Bill of Quantity | Pre | Plan | Prior | 2022-01-13 | 20/01/22 | 27/01/22 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-07 |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 | 2022-04-19
Actual
2 | Facility Management | LSPC/W-F/NCB/01/2022 | 1 | 54625000 | >50M | NCB | Bill of Quantity | Post | Plan | Prior | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-08 |  | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-20
Actual
Plan
Actual

## Sheet4
LAGOS STATE GOVERNMENT LAGOS STATE PRINTING CORPORATION Y2022 DRAFT PROCUREMEMT PLAN