## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: GENERAL HOSPITAL MUSHIN,LAGOS
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVEL & TRANSPORT | GHM/NP/NM/001/22 | 600000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
|  |  |  | Actual | [12 empty] | 0
2 | ELECTRICITY BILL | GHM/NP/NM/002/22 | 4800000 | Plan | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 4800000
|  |  |  | Actual | [12 empty] | 0
3 | PROMOTION EXERCISE | GHM/NP/NM/003/22 | 300000 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
|  |  |  | Actual | [12 empty] | 0
4 | GENERAL UTILITY:1)Telephone bills hospital family lines for 10 HOD's for officers on calls make Recharge 10 phone on monthly bill | GHM/NP/NM/004/22 | 300,000.00 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
|  |  |  | Actual | [12 empty] | 0
5 | SPECIAL DUTIES ( Social Welfare) | GHM/NP/NM/005/22 | 10499556 | Plan | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 874963 | 10499556
|  |  |  | Actual | [12 empty] | 0
6 | MISCELLANOUS:one set Servicing of various meetings (management, procurement, reconcilation, meeting head of admin , account, Monday round meeting discipinary meeting. | GHM/NP/NM/006/22 | 360000 | Plan | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 360000
|  |  |  | Actual | [12 empty] | 0
7 | GENERAL UTILITY:Procurement of 7 news papers for Directors and HOD,s a week (7 a month)(2)Procurement of Medical Gas from Boc gases | GHM/NP/NM/007/22 | 360000 | Plan | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 360000
Actual
8 | PROVISION FOR DIESEL FOR GENERATOR, ELECTRICITY BILL AND SPECIAL EXPENSES. | GHM/NP/NM/008/22 | 4299556 | Plan | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 358296.3333 | 4299556
Actual
|  | TOTAL |  | Plan | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 1793259.3333 | 21519112
|  |  |  | Actual | [12 empty] | 0

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: Mushin Genral Hospital
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | CONFERENCE /SEMINAR FOR STAFF | GHM/S-WTC/SS/001/22 | Contemporary Auditing Governance, Forensics and Ethical Conduct. | 6 Participants | 4 Days | Plan | Abuja, Nigeria | 879999.9996 | 600000 | 720000 | 2199999.9996
Actual
2 | COWLSO / TRAINING | GHL/S-WTC/SS/002/22 | COWLSO | 5 Participants | 3 Days | Plan |  | 250000 | 100000 | 50000 | 400000
Actual
|  |  |  | TOTAL |  | Plan |  | 1129999.9996 | 700000 | 770000 | 2599999.9996
[6 empty] | Actual |  | 0 | 0 | 0 | 0

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: GENERAL HOSPITAL MUSHIN
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | GHM/S-NC/NS/001/22 |  |  | 240000 | <10M | N/S | Plan | POST | POST | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-11 | 2022-04-18 | 2022-04-19 | 2022-04-26 | Plan | N/A | N/A |  | 2022-04-21 | N/A | 2022-04-28 | 2022-04-28
[7 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE MAINTENANCE AND REPAIRS:Servicing and repairs of the hospital ambulances | GHM/S-NC-F/NS/001/22 |  |  | 420000 | <10M | N/S | Plan | POST | POST | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-11 | 2022-04-18 | 2022-04-19 | 2022-04-26 | Plan | N/A | N/A |  | 2022-04-21 | N/A | 2022-04-28 | 2022-04-28
| TOTAL |  |  | 660000

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: GENERAL HOSPITAL MUSHIN,LAGOS
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF UNIFORMS & PROTECTIVE OUTFITS;protective for various departments (lab coat) DOCTOR( CONSULTANT) 2)medical Lab 40 staffs@5000 each =200,000,3)40 doctors@ 5000=200,000,4)40pharmacist/technician @5000=200,000,5)40 nos radiographers and tecnicians @5000=200000 6)40 dental offcers/ therapist@5000=200000 |  | GHM/G-F/NS/001/22 |  |  | 1500000 | <10M | N/S | POST | POST | Plan | 03/O1/2022 | 10/O1/2022 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 07/O2/2022 | N/A | N/A |  | 21/O2/2022 | 07/O3/2022 | N/A | 14/O3/2022 | 21/O3/2022
Actual
2 | PROCUREMENT OF STATIONERIES:printing of letter heads papers purchase of computer toners for different users in different departments nos 14 per quarter 2)administrative consumables reams of paper,tonner ink ,for photocopier and servicing monthly replacement of 10,UPS with various systems in the departments other accessories (biro staplers file jackets) |  | GHM/G-F/NS/002/22 |  | 12 | 360000 | <10M | N/S | POST | POST | Plan | 03/O1/2022 | 2022-01-10 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 2022-02-07 | N/A | N/A |  | 2022-02-21 | 2022-03-07 | N/A | 2022-04-26 | 2022-04-26
Actual
3 | FUEL CONSUMPTION;purhase of fuel for the 2 ambulance for 170 per litre and 2 cars(60)litres a week for each months |  | GHM/G-F/NS/003/22 |  | 12 | 720000 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
[11 empty] | Actual | [14 empty] | 44599
4 | FUEL PLANT /HEAVY EQUIPMENT ;purhase of Diesel for the 4 Generators 10,000 litres for 250 per litre for 12months |  | GHM/G-F/NS/004/22 |  | 12 | 20000000 | >10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
5 | PROCUREMENT/PRINTING OF MEDICAL FORMS AND CARDS; Printing of 1,000 folders and 1,000 continuation sheets 1,000 cards and 1,000 various investigation forms etc quarterly bases. |  | GHM/G-F/NS/005/22 |  | 12 | 500000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
6 | DRUGS (ANAESTHESIA) |  | GHM/G-F/NS/006/22 |  | 12 | 111833333.3333 | >100M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
7 | LABORATORY (CONSUMABLES) |  | GHM/G-F/NS/007/22 |  | 12 | 51333333.3333 | <50M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
8 | X-RAY (FILMS & CHEMICALS) |  | GHM/G-F/NS/008/22 |  | 12 | 6355555.5556 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
9 | SUT/DRES (CONSUMABLES) |  | GHM/G-F/NS/009/22 |  | 12 | 4888888.8889 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
10 | DIET (IN-PATIENTS) |  | GHM/G-F/NS/010/22 |  | 12 | 12100000 | <20M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
11 | ACCOMODATION (CONSUMABLES) |  | GHM/G-F/NS/011/22 |  | 12 | 11000000 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-10 | 2022-01-20 | 2022-01-27 | 2022-02-07 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
12 | DELIVERY PACK (CONSUMABLES) |  | GHM/G-F/NS/012/22 |  | 12 | 12894444.4444 | <20M | N/S | POST | POST | Plan | 03/O1/2022 | 10/O1/2022 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 07/O2/2022 | N/A | N/A |  | 21/O2/2022 | 07/O3/2022 | N/A | 14/O3/2022 | 21/O3/2022
Actual
13 | ADMISSION PACK (CONSUMABLES) |  | GHM/G-F/NS/013/22 |  | 12 | 7333333.3333 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
14 | MEDICAL REPORT (OUT-PATIENTS) |  | GHM/G-F/NS/014/22 |  | 12 | 3483333.3333 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
15 | ULTRA-SCAN (CONSUMABLES) |  | GHM/G-F/NS/015/22 |  | 12 | 11000000 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
16 | CLINICAL MEETING (OUT-PATIENTS) |  | GHM/G-F/NS/016/22 |  | 12 | 1833333.3333 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
17 | RBS/CON (CONSUMABLES) |  | GHM/G-F/NS/017/22 |  | 12 | 3483333.3333 | <10M | N/S | POST | POST | Plan | 03/O1/2022 | 10/O1/2022 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 07/O2/2022 | N/A | N/A |  | 21/O2/2022 | 07/O3/2022 | N/A | 14/O3/2022 | 21/O3/2022
Actual
18 | FOLDER (OUT-PATIENTS) |  | GHM/G-F/NS/018/22 |  | 12 | 14666666.6667 | <20M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
19 | OBSERVATION (CONSUMALES) |  | GHM/G-F/NS/019/22 |  | 12 | 5500000 | <10M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
20 | DELIVERY FEES (ONSUMABLES) |  | GHM/G-F/NS/020/22 |  | 12 | 5500000 | <10M | N/S | POST | POST | Plan | 03/O1/2022 | 10/O1/2022 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 07/O2/2022 | N/A | N/A |  | 21/O2/2022 | 07/O3/2022 | N/A | 14/O3/2022 | 21/O3/2022
Actual
21 | DENTAL (CONSUMABLES) |  | GHM/G-F/NS/021/22 |  | 12 | 7944444.4444 | <10M | N/S | POST | POST | Plan | 03/O1/2022 | 10/O1/2022 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 07/O2/2022 | N/A | N/A |  | 21/O2/2022 | 07/O3/2022 | N/A | 14/O3/2022 | 21/O3/2022
Actual
22 | OPERATION (CONSUMABLES) |  | GHM/G-F/NS/022/22 |  | 12 | 57016666.6667 | <100M | N/S | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | N/A | N/A |  | 2022-03-15 | 2022-03-15 | N/A | 2022-03-22 | 2022-03-22
Actual
23 | NHIS (OUT-PATIENTS) |  | GHM/G-F/NS/023/22 |  | 12 | 1833333.3333 | <100M | N/S | POST | POST | Plan | 2022-03-29 | 2022-05-04 | 2022-12-04 | 2022-04-19 | 2022-04-26 | 2022-03-05 | 2022-10-05 | 2022-05-17 |  | 24/05/2022 | 2022-05-31 | N/A | 2022-07-06 | 2022-07-06
Actual
24 | PROCUREMENT OF DESKTOP COMPUTER SYSTEM FOR THE PREPARATION, PRODUCTION OF DOCUMENTS (2 PCS), LAPTOP (2 PCS) AND UPS |  | GHM/G-F/NS/024/22 |  | 2 | 1150000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
25 | PROCUREMENT OF COMPUTER TABLES AND CHAIRS |  | GHM/G-F/NS/025/221 |  | 1 | 100000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
26 | PROCUREMENT OF PHOTOCOPY MACHINE |  | GHM/G-F/NS/026/22 |  | 1 | 120000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
27 | PROVISION FOR END OF THE YEAR STAFF WELFARE |  | GHM/G-F/NS/027/22 |  | 1 | 2500000 | <10M | N/S | POST | POST | Plan | 03/O1/2022 | 10/O1/2022 | 10/O1/2022 | 24/O1/2022 | 31/O1/2022 | 07/O2/2022 | N/A | N/A |  | 21/O2/2022 | 07/O3/2022 | N/A | 14/O3/2022 | 21/O3/2022
Actual
28 | PROVISION FOR SERVICING, REFILLING AND RECHARGING OF FIRE EXTINGUISHER OF DIFFERENT KILOGRAMS AND EQUIPMENTS |  | GHM/G-F/NS/028/22 |  | 2 | 1700000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
29 | PROVISION FOR FUMIGATION AND DERATIZATION OF THE HOSPITAL |  | GHM/G-F/NS/029/22 |  | 1 | 2000000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
30 | PROCUREMENT UNIFORM & PROTECTIVES. Procurement of uniform & protectives for 100 staffs of various department. |  | GHM/G-F/NS/030/22 |  |  | 1500000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
31 | PLANNING UNITS EXPENSES |  | GHM/G-F/NS/031/22 |  |  | 2200000 | <10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
32 | FUEL FOR PLANT / HEAVY EQUIPMENT |  | GHM/G-F/NS/032/22 |  |  | 20000000 | >10M | N/S | POST | POST | Plan | 2022-01-24 | 2022-01-31 | 04-02-2022 | 2022-02-14 | 2022-02-14 | 04-03-2022 | 11-03-2022 | 2022-03-17 |  | 15/03/2022 | 2022-03-15 | N/A | 29-03-2022 | 29-03-2022
Actual
|  | GRAND TOTAL |  |  |  | 384350000

## Works (hidden)
PROCUREMENT PLAN FOR WORKS.
MINISTRY/AGENCY: GENERAL HOSPITAL MUSHIN,LAGOS
BUDGET YEAR: 2021
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | RENOVATION OF HOSPITAL KITCHEN |  | GHM/G-F/NS/001/21 |  | 125 | 1700000 | <10M | N/S | POST | POST | Plan | 01/O2/2021 | 8/O2/2021 | 15/O2/2021 | 1/O3/2021 | 15/O3/2021 | 22/O3/2021 | N/A | N/A |  | 29/O3/2021 | 5/O4/2021 | N/A | 12/O4/2021 | 12/O4/2021
[11 empty] | Actual | [8 empty] | 2,000.000.00
2 | RENOVATION OF HOSPITAL BUILDING |  | GHM/G-F/NS/002/21 |  |  | 30000000 | <10M | N/S | POST | POST | Plan | 15/O2/2021 | 22/2 /2021 | 1/O3/2021 | 15/O3/2021 | 29/O3/2021 | 5/04/20121 | N/A | N/A |  | 2021-12-04 | 19/04/2021 | N/A | 26/4/2021 | 26/4/2021
Actual
3 | PROVISION AND INSTALLATION OF WATER PROOF SECURITY LIGHT |  | GHM/G-F/NS/003/21 |  |  | 3750000 | <10M | N/S | POST | POST | Plan | 2021-01-03 | 2021-08-03 | 15/03/2021 | 29/03/2021 | 2021-12-04 | 19/04/2021 | N/A | N/A |  | 26/04/2021 | 2021-03-05 | N/A | 2021-10-05 | 2021-10-05
[11 empty] | Actual | [14 empty] | #VALUE!
4 | PROVISION OF AIR-CONDITIONERS 2HP SPLITS (40 PCS) |  | GHM/G-F/NS/004/21 |  |  | 14000000 | >10M | N/S | POST | POST | Plan | 2021-01-03 | 2021-08-03 | 15/03/2021 | 29/03/2021 | 2021-12-04 | 19/04/2021 | N/A | N/A |  | 26/04/2021 | 2021-03-05 | N/A | 2021-10-05 | 2021-10-05
Actual
5 | RECONSTRUCTION OF GENERATOR HOUSE FOR 275KVA & 150 KVA GENERATOR SET |  | GHM/G-F/NS/005/21 |  |  | 2850000 | <10M | N/S | POST | POST | Plan | 29/3/2021 | 2021-05-04 | 2021-12-04 | 19/04/2021 | 26/04/2021 | 2021-03-05 | 2021-10-05 | 17/05/2021 |  | 24/05/2021 | 31/05/2021 | N/A | 2021-07-06 | 2021-07-06
Actual
6 | ROOFING OF THEATRE WALK WAY TO THE WARDS |  | GHM/G-F/NS/006/21 |  |  | 9000000 | <10M | N/S | POST | POST | Plan | 29/3/2021 | 2021-05-04 | 2021-12-04 | 19/04/2021 | 26/04/2021 | 2021-03-05 | 2021-10-05 | 17/05/2021 |  | 24/05/2021 | 31/05/2021 | N/A | 2021-07-06 | 2021-07-06
Actual
|  | GRAND TOTAL |  |  |  | 61300000