## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE EXAMINATIONS BOARD
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | PROCUREMENT OF GENERAL UTILITY SERVICES | LSEB/NP/001/22 | 2,500,000.00 | Plan |  |  |  | 500000 | 500000 | 500000 | 500000 | 500000
Actual
2 | PROCUREMENT OF TRAVEL & TRANSPORT (LOCAL) | LSEB/NP/002/22 | 12,000,000.00 | Plan |  |  | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
Actual
3 | ENTERTAINMENT & HOSPITALITY | LSEB/NP/003/22 | 3000000 | Plan |  |  | 1000000 |  |  | 1000000 |  |  | 1000000
Actual
4 |  |  |  | Plan
Actual
5 |  |  |  | Plan
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE EXAMINATION BOARD
BUDGET YEAR:
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | CONFERENCES (CIPM) | EXPANDING POSIBILITIES | 5 | 4 DAYS | Plan | ABUJA | 100,000 * 5 | 55,000*5 | 13,000 * 5 | 827000
Actual
2 | CONFERENCES (CIPSMN) | PROCUREMENT ADUIT AS A TOOL FOR CONTROL AND PERFORMENT | 1 | 4 DAYS | Plan | ABUJA | 60000 | 55000 | 46,000 * 4 | 312000
Actual
3 | CONFERENCES (COWLSO) | UNLEARN, LEARN & RELEARN | 2 | 3 DAYS | Plan | LAGOS | 100000 | 30000 | 30,000 * 2 | 190000
Actual
4 | CONFRENCES (MCPD) | CHALLENGES AND LANDMARK ISSUES IN ACCOUNTING | 3 | 4 DAYS | Plan | LAGOS | 105000 | 138000 | 23,000*3 | 312000
Actual
5 | CONFRENCES (ANAN) | 2022 MANADATORY CONTINUING | 1 | 4 DAYS | Plan | OSUN | 35,000 *2 | 40,000 *2 | 69000 | 248000
[5 empty] | Actual |  |  |  | TOTAL | 1889000
6 |  |  |  |  | Plan
Actual
7 |  |  |  |  | Plan
Actual
8 |  |  |  |  | Plan
Actual
9 |  |  |  |  | Plan
Actual
10 |  |  |  |  | Plan
Actual
11 |  |  |  |  | Plan
Actual
12 |  |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE EXAMINATIONS BOARD
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
PROCUREMENT OF MOTOR VEHICLE REPAIRS & MAINTANANCE | LSEB/G-F/NS/001/22 |  | 6 | 2000000 | <5M | NS | Plan | POST | POST | 13/02/2022 | NA | 17/02/2022 | 19/02/2022 | 21/02/2022 | 24/02/2022 | NA | Plan | 01/03/2022 | NA | 0 | 04/03/2022 | NA | 18/03/2022 | 19/03/2022
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE EXAMINATIONS BOARD
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | ITEM WRITING, MODERATION, SUPERVISION AND CBT CENTRES FOR SCREENING TEST INTO MODEL COLLEGES | LSEB/G-F/NS/001/22 | NC |  | 37000000 | POST | Plan | 10/02/2022 | 17/02/2022 | 19/02/2022 | 21/02/2022 | 24/02/2022 | 24/02/2022 | 01/03/2022 | 04/03/2022 | 18/03/2022 | 10/02/2022 | 17/02/2022 | 19/02/2022 | 21/02/2022 | 24/02/2022 |  | 01/03/2022 | 04/03/2022 | 18/03/2022 | 10/03/2022 | 10/04/2022
Actual
2 | ITEM WRITING,MODERTION,PROOF READING,SUPERVISION AND CBT CENTERS FOR PUBLIC SERVICE EXAMINATIONS | LSEB/G-F/NS/002/22 | NC |  | 9750000 | POST | Plan | 10/02/2022 | 17/02/2022 | 19/02/2022 | 21/02/2022 | 24/02/2022 | 24/02/2022 | 01/03/2022 | 04/03/2022 | 18/03/2022 | 10/02/2022 | 17/02/2022 | 19/02/2022 | 21/02/2022 | 24/02/2022 |  | 01/03/2022 | 04/03/2022 | 18/03/2022 | 10/03/2022 | 10/04/2022
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE EXAMINATIONS BOARD
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF PRINTING EXAMINATIONS QUESTIONS AND ANSWERS SHEETS FOR PLACEMENT INTO JUNIOR SECONDARY SCHOOLS | LSEB/G-F/NS/001/22 |  | VARIOUS | 5000000 | <10M | NS | POST | POST | Plan | 05/08/2022 | 15/05/2022 | 22/05/2022 | 29/05/2022 | 06/12/2022 | 19/06/2022 |  |  |  | 26/06/2022 |  | 17/7/2022
[10 empty] | Actual | 27/07/2022
2 | PROCUREMENT OF PRINTING EXAMINATIONS QUESTIONS AND ANSWERS SHEETS FOR BASIC EDUCATION CERTIFICATE EXAMINATIONS | LSEB/G-F/NS/002/22 |  | VARIOUS | 138000000 | <100M | NS | POST | PRIOR | Plan | 16/04/2022 | 23/04/2022 | 30/04/2022 | 05/07/2022 | 21/05/2022 | 28/05/2022 |  |  |  | 06/04/2022 |  | 25/06/2022
[10 empty] | Actual | 15/07/2022
3 | PROCUREMENT OF PRINTING CUSTOMISED OMR FOR ALL EXAMINATIONS | LSEB/G-F/NS/003/22 |  | VARIOUS | 100000000 | <100M | NS | POST | PRIOR | Plan | 23/03/2022 | 04/06/2022 | 13/04/2022 | 20/04/2022 | 05/04/2022 | 05/11/2022 |  |  |  | 18/05/2022 |  | 06/01/2022
[10 empty] | Actual | 15/04/2022
4 | PROCUREMENT OF PURCHASE DIESEL FOR GENERATOR | LSEB/G-F/NS/004/22 |  | VARIOUS | 10250000 | <50M | NS | POST | POST | Plan | 23/03/2022 | 04/06/2022 | 13/04/2022 | 20/04/2022 | 05/04/2022 | 05/11/2022 |  |  |  | 18/05/2022 |  | 06/01/2022
Actual
5 | PROCUREMENT OF MOTOR VEHICLE FUEL CONSUMPTION | LSEB/G-F/NS/005/22 |  | VARIOUS | 2500000 | <5M | NS | POST | PRIOR | Plan | 02/04/2022 | 03/11/2022 | 20/03/2022 | 04/04/2022 | 18/04/2022 | 23/04/2022 |  |  |  | 14/05/2022 |  | 01/06/2022
[10 empty] | Actual | 04/03/2022
6 | PROCUREMENT OF STATIONARIES | LSEB/G-F/NS/006/22 |  | VARIOUS | 2000000 | <5M | NS | POST | PRIOR | Plan | 02/04/2022 | 03/11/2022 | 20/03/2022 | 04/04/2022 | 18/04/2022 | 23/04/2022 |  |  |  | 24/05/2022 |  | 01/06/2022
[10 empty] | Actual | 04/03/2022
7 | PROCUREMENT OF PRINTING OF QUESTION PATER FOR BASIC EDUCATION CERTIFICATE EXAMINATION | LSEB/G-F/NS/007/22 |  | VARIOUS | 44025000 | <50M | NS | POST | PRIOR | Plan | 23/03/2022 | 04/06/2022 | 13/04/2022 | 20/04/2022 | 05/04/2022 | 05/11/2022 |  |  |  | 18/05/2022 |  | 06/01/2022
[10 empty] | Actual | 15/04/2022
8 | ITEM WRITING, MODERATION, SUPERVISION AND CBT FOR SCREENING TEST INTO MODEL/UUPGRADED JUNIOR SEC. SCHOOL | LSEB/G-F/NS/008/22 |  | VARIOUS | 20500000 | <50M | NS | POST | PRIOR | Plan | 23/03/2022 | 04/06/2022 | 13/04/2022 | 20/04/2022 | 05/04/2022 | 05/11/2022 |  |  |  | 18/05/2022 |  | 06/01/2022
[10 empty] | Actual | 15/04/2022
9 | PROCUREMENT OF PRINTING OF QUESTION PAPER FOR CAS/PLACEMENT TEST INTO JSS 1 | LSEB/G-F/NS/009/22 |  | VARIOUS | 6800000 | <10M | NS | POST | PRIOR | Plan | 02/04/2022 | 03/11/2022 | 20/03/2022 | 04/04/2022 | 18/04/2022 | 23/04/2022 |  |  |  | 14/05/2022 |  | 01/06/2022
[10 empty] | Actual | 04/03/2022
10 | ITEM WRITING, MODERATION, SUPERVISION AND CBT FOR COMPULSORY EXAM FOR ADMIN & EXECUTIVE OFFICER | LSEB/G-F/NS/010/22 |  | VARIOUS | 3945000 | <5M | NS | POST | PRIOR | Plan | 23/03/2022 | 04/06/2022 | 13/04/2022 | 20/04/2022 | 05/04/2022 | 05/11/2022 |  |  |  | 18/05/2022 |  | 06/01/2022
[10 empty] | Actual | 15/04/2022
11 | ITEM WRITING, MODERATION, SUPERVISION AND CBT FOR EXTERNAL SECRETARIAL EXAM CONFIDENTIAL SECRETARY | LSEB/G-F/NS/011/22 |  | VARIOUS | 1497720 | <5M | NS | POST | PRIOR | Plan | 23/03/2022 | 04/06/2022 | 13/04/2022 | 20/04/2022 | 05/04/2022 | 05/11/2022 |  |  |  | 18/05/2022 |  | 06/01/2022
Actual
12 | ITEM WRITING, MODERATION, SUPERVISION AND CBT FOR TRADE TEST FOR ARTISANS | LSEB/G-F/NS/012/22 |  | VARIOUS | 868000 | <5M | NS | POST | PRIOR | Plan | 02/04/2022 | 03/11/2022 | 20/03/2022 | 04/04/2022 | 18/04/2022 | 23/04/2022 |  |  |  | 14/05/2022 |  | 01/06/2022
[10 empty] | Actual | 04/03/2022
|  |  |  | TOTAL | 335385720
| MR. GBADEGESIN S.S |  | ARAGBADA,B.0
| DIRECTOR: LAGOS STATE EXAMINATION BOARD |  | H.O.D ADMIN
| MR. OYENIRAN S.B |  | MRS. SENAYON WHENU O.N
| H.O.D SCREENING TEST |  | H.O.D ACCOUNT
| MRS. OYEDELE |  | MR. OGUNLEYE
| H.O.D BASIC EDUCATION CERTIFICATE EXAMINATION (BECE) |  | H.O.D PLANNING & BUDGET
| MR. ANDERO S.O |  | MR. ADEJORIN A.A
| H.O.D PUBLIC SERVICE EDUCATION |  | H.O.D I.C.T
MR. KUYE D.O
H.O.D PLACEMENT TEST

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual