## Non-Proc items
MINISTRY / AGENCY AJEROMI GENERAL HOSPITAL AJEGUNLE
BUDGET YEAR: 2022
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
| TRAVEL & TRANSPORT: PAYMENT OF LOCAL TRANSPORT ALLOWANCES | AGHA/NP/NM/001/2022 | 800,000.00 | Plan | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 66.,666.6 | 800000
1 |  |  |  | Actual
2 | MISCELLANEOUS : PAYMENT FOR COURIER SERVICES & SERVICING OF MEETINGS | AGHA/NP/NM/002/2022 | 200000 | Plan | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 200000
Actual
3 | GENERAL UTILITY SERVICES : PROVISION OF GAS,RECHARGED CARDS & COMUNICATION | AGHA/NP/NM/003/2022 | 200000 | Plan | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 16667 | 750000
Actual
4 | PAYMENT OF ELECTRICITY BILL | AGHA/NP/NM/004/2022 | 9,000,000.00 | Plan | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000
Actual
5 | HOSPITAL EXPENSES : PAYMENT FOR DSTV AND INTERNET SUBCRIPTION | AGHA/NP/NM/05/2022 | 750000 | Plan | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 750000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: AJEROMI GENERAL HOSPITAL AJEGUNLE
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | SPONSORSHIP OF 2 NOS DENTIST TO NIGERIAL DENTAL ASSOCIATION ANNUAL CONFRENCE | AGHA/S-WTC/SS/001/2022 |  | 14 | 1 WEEKS | Plan | LAGOS STATE | 328760.72 |  |  | 4602650
Actual
2 | CONFERENCE FOR HEAD OF NURSING SERVICES IN NIGERIA | AGHA/S-WTC/SS/002/2022 |  | 1 | 1 WEEKS | Plan | LAGOS STATE | 725075 |  |  | 725075
Actual
3 | ANNUAL SCIENTIFIC MEETING FOR MEDICAL WOMEN (3) NOS | AGHA/S-WTC/SS/04/2022 |  | 3 | 1 WEEKS | Plan | LAGOS STATE | 220675 |  |  | 662025
Actual
4 | ANNUAL CONERENCE OF WIVES OF LAGOS STATE OFFICIAL (8) NOS(COWSO) | AGHA/S-WTC/SS/003/2022 |  | 8 | 1 WEEK | Plan | LAGOS STATE | 133981.25 |  |  | 1071850
Actual
5 | REFRESHER COURSE FOR 6 NOS OF NURSES | AGHA/S-WTC/SS/004/2022 |  | 6 | 2 WEEKS | Plan | LAGOS STATE | 136608.3 |  |  | 819650
Actual
[6 empty] | Plan |  |  |  |  | 7881250
Actual
Note on B6: Procurement:

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
MINISTRY/AGENCY:AJEROMI GENERAL HOSPITAL AJEGUNLE
BUDGET YEAR: 2022
NONCONSULULTING SERVICES
|  | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | MAINTENANCE OF OFFICE BUILDING | AGHA/NC/NS/001/2022 | 1 |  | 700000 | <10M | NS | Plan | POST | POST | 4/3/2022 | N/A | 18/4/2022 | *2/5/2022 | *9/5/2022 | 16/5/2022 | N/A | Plan | 30/5/2022 | N/A | 0 | 13/6/2022 | 27/6/2022 | 2022-11-07 | 25/7/2022
[8 empty] | Actual | [9 empty] | Actual
2 | MAINTENANCE & REPAIR OF PLANT & MACHINERY | AGHA/NC/NS/002/2022 | 1 |  | 3000000 | <10M | NS | Plan | POST | POST | *1/8/2022 | N/A | *8/8/2022 | 22/8/2022 | 29/8/2022 | *5/9/2022 | N/A | Plan | 19/9/2022 | N/A | 0 | 2022-03-10 | 17/10/2022 | 31/10/2022 | 2022-07-11
[8 empty] | Actual | [9 empty] | Actual
3 | MAINTENANCE OF SPECIALISED HOSPITAL EQUIPMENT | AGHA/NC/NS/003/2022 | 1 |  | 1750000 | <10M | NS | Plan | POST | POST | *8/8/2022 | N/A | *15/8/2022 | 29/8/2022 | *5/9/2022 | *12/9/2022 | N/A | Plan | *26/9/2022 | N/A | 0 | 10/10/2022 | 24/10/2022 | 2022-07-11 | 14/11/2022
[8 empty] | Actual | [9 empty] | Actual
4 | PRINTING OF HOSPITAL FORMS | AGHA/NC/NS/004/2022 | 1 |  | 2500000 | <10M | NS | Plan | POST | POST | 15/8/2022 | N/A | *22/8/2022 | *5/9/2022 | *12/9/2022 | *19/9/2022 | N/A | Plan | *3/10/2022 | N/A | 0 | 17/10/2022 | 31/10/2022 | 14/11/2022 | *21/11/2022
[8 empty] | Actual | [9 empty] | Actual
5 | MAINTANANCE AND REPAIR OF PLANT AND MACHINERY | AGHA/NC/NS/05/2022 | 1 |  | 30000 | <10M | NS | Plan | POST | POST | *22/8/2022 | N/A | *29/8/2022 | *12/9/2022 | 19/9/2022 | 26/9/2022 | N/A | Plan | *10/10/2022 | N/A | 0 | 24/10/2022 | *7/11/2022 | 21/11/2022 | *28/11/2022
[8 empty] | Actual | [9 empty] | Actual
[6 empty] | <10M | NS | Plan |  |  |  | N/A |  |  |  |  | N/A | Plan |  | N/A
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR NON CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
6 | [6 empty] | Plan
Actual
7

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY:AJEROMI GENERAL HOSPITAL AJEGUNLE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual |  |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) |  | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF STATIONERY ITEMS | AGHA/G-F/NS/001/2022 | 1 |  | 220000 | <10M | N/S | POST | POST | Plan |  | N/A | 24/1/2022 | 2022-07-02 | 14/2/2022 | N/A | 21/2/2022 | N/A | 0 | 28/2/2022 | 7/3/2022 | 14/3/2022 | 21/3/2022 | 28/3/2022
Actual
2 | PROCUREMENT OF DIESEL | AGHA/G-F/NS/002/2022 | 1 |  | 3000000 | >10M | N/S | POST | POST | Plan | 24/1/2022 | N/A | 31/1/2022 | 14/2/20222 | 21/2/2022 | N/A | 28/2/2022 | N/A | 0 | 2022-07-03 | 14/3/2022 | 21/3/2021 | 28/3/2022 | 2022-04-04
Actual
3 | MOTOR VEHICLE FUEL CONSUPTION | AGHA/G-F/NS/003/2022 | 1 |  | 320000 | <10M | N/S | POST | POST | Plan | 31/1/2022 | N/A | 2022-07-02 | 21/2/2022 | 28/2/2022 | N/A | 2022-07-03 | N/A |  | 14/3/2022 | 21/3/2022 | 28/3/2022 | 2022-04-04 | 2022-11-05
Actual
4 | PROCUREMENT OF MEDICAL GAS | AGHA/G-F/NS/004/2022 | 1 |  | 20500000 | <10M | N/S | POST | POST | Plan | 2022-07-02 | N/A | 14/2/2022 | 28/2/2022 | 2022-07-03 | N/A | 14/3/2022 | N/A | 0 | 21/3/2022 | 28/3/2022 | 4/4/2022 | 2022-11-04 | 18/4/2022
Actual
4 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFIT (DOCTORS, HEALTH ATTENDANT) | AGHA/G-F/NS/005/2022 | 1 |  | 3000000 | <10M | N/S | POST | POST | Plan | 14/2/2022 | N/A | 28/2/2022 | 14/3/2022 | 28/3/2022 | N/A | 2022-04-04 | N/A | 0 | 2022-11-04 | 18/4/2022 | 25/4/2022 | 2022-02-05 | 2025-09-05
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods igr
PROCUREMENT PLAN FOR GOODS (IGR)
MINISTRY/AGENCY:AJEROMI GENERAL HOSPITAL AJEGUNLE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual |  |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) |  | (1 wk) | (1-2 wks) | (2-4wks)
1 | ACCOMONDATTION | AGHA/G-F/NS/IGR/001/2022 | 1 |  | 913000 | <10M | N/S | POST | POST | Plan | 17/01/2022 | N/A | 24/1/2022 | 2022-07-02 | 14/2/2022 | N/A | 21/2/2022 | N/A | 0 | 28/2/2022 | 7/3/2022 | 14/3/2022 | 21/3/2022 | 28/3/2022
Actual
2 | DENTAL | AGHA/G-F/NS/IGR/002/2022 | 1 |  | 913000 | >10M | N/S | POST | POST | Plan | 24/1/2022 | N/A | 31/1/2022 | 2022-07-02 | 31/2/2022 | N/A | 2022-07-03 | N/A | 0 | 14/3/2022 | 21/3/2022 | 28/3/2021 | 2022-04-04 | 2022-11-04
Actual
3 | LABORATORY FEE | AGHA/G-F/NS/IGR/003/2022 | 1 |  | 3278000 | <10M | N/S | POST | POST | Plan | 31/1/2022 | N/A | 2022-07-02 | 14/2/2021 | 21/2/2022 | N/A | 28/2/2022 | N/A | 0 | 2022-07-03 | 14/3/2022 | 21/3/2022 | 28/3/2022 | 2022-04-04
Actual
4 | EYE | AGHA/G-F/NS/IGR/004/2022 | 1 |  | 1023000 | <10M | N/S | POST | POST | Plan | 2022-07-02 | N/A | 14/2/2022 | 21/2/2022 | 28/2/2022 | N/A | 2022-07-03 | N/A | 0 | 14/3/2022 | 21/3/2022 | 28/3/2022 | 2022-04-04 | 2022-11-05
Actual
5 | DIET/CANTEEN | AGHA/G-F/NS/IGR/005/2022 | 1 |  | 1, 023,000.00 | <10M | N/S | POST | POST | Plan | 14/2/2022 | N/A | 21/2/2022 | 28/2/2022 | 2022-07-03 | N/A | 14/3/2022 | N/A | 0 | 21/3/2022 | 28/3/2022 | 4/4/2022 | 2022-11-04 | 18/4/2022
Actual
6 | DRESS PACK | AGHA/G-F/NS/IGR/006/2022 | 1 |  | 363000 | <10M | N/S | POST | POST | Plan | 21/2/2022 | N/A | 28/2/2022 | 2022-07-03 | 14/3/2022 | N/A | 21/3/2022 | N/A |  | 28/3/2022 | 2022-04-04 | 2022-11-04 | 18/4/2022 | 25/4/2022
[10 empty] | Actual | [8 empty] | 0
7 | ADMISSION PACK | AGHA/G-F/NS/IGR/007/2022 | 1 |  | 748000 | <10M | N/S | POST | POST | Plan | 28/2/2022 | N/A | *7/3/2022 | 14/3/2022 | 21/3/2022 | N/A | 28/3/2022 | N/A | 0 | 2022-04-04 | 2022-11-04 | 18/4/2022 | 25/4/2022 | 2022-02-05
Actual
8 | SCAN | AGHA/G-F/NS/IGR/008/2022 | 1 |  | 1133000 | <10M | N/S | POST | POST | Plan | 2022-07-03 | N/A | 14/3/2022 | 21/3/2022 | 28/3/2022 | N/A | 2022-04-04 | N/A | 0 | 2022-11-04 | 18/4/2022 | 25/4/2022 | 2022-02-05 | 2022-12-05
Actual
9 | SUTURING PACK | AGHA/G-F/NS/IGR/009/2022 | 1 |  | 693000 | >10M | N/S | POST | POST | Plan | 14/3/2022 | N/A | 21/3/2022 | 28/3/2022 | 2022-04-04 | N/A | 2021-11-04 | N/A | 0 | 18/4/2022 | 25/4/2022 | 2022-02-05 | 2022-12-05 | 19/5/2022
Actual
10 | O & G | AGHA/G-F/NS/IGR/10/2022 | 1 |  | 1793000 | <10M | N/S | POST | POST | Plan | 21/3/2022 | N/A | 28/2/2021 | 2022-04-04 | 2022-11-05 | N/A | 18/4/2022 | N/A | 0 | 25/4/2022 | *2/5/2022 | 2022-12-05 | 19/5/2022 | 26/5/2022
Actual
11 | RADIOLOGY | AGHA/G-F/NS/IGR/11/2022 | 1 |  | 693000 | <10M | N/S | POST | POST | Plan | 28/3/2022 | N/A | 2022-04-04 | 2022-11-04 | 18/4/2022 | N/A | 25/4/2022 | N/A | 0 | 2022-02-05 | *12/5/2022 | 19/5/2922 | 26/5/2922 | 2022-01-06
Actual
12 | ECG | AGHA/G-F/NS/IGR/12/2022 | 1 |  | 374000 | <10M | N/S | POST | POST | Plan | *4/4/2022 | N/A | *11/4/2022 | 18/4/2022 | 25/4/2022 | N/A | 2022-02-05 | N/A | 0 | 2022-12-05 | 19/5/2022 | 26/5/2022 | *1/6/2022 | 2022-07-06
Actual
13 | NHIS | AGHA/G-F/NS/IGR/13/2022 | 1 |  | 1958000 | <10M | N/S | POST | POST | Plan | *11/4/2022 |  | 18/4/2022 | 25/4/2022 | 2022-02-05 | N/A | 2022-12-05 | N/A | 0 | 19/5/2022 | 26/5/2022 | 2022-01-06 | *7/6/2022 | 14/6/2022
Actual
14 | BLOOD BANK | AGHA/G-F/NS/IGR/14/2022 | 1 |  | 693000 | <10M | N/S | POST | POST | Plan | 18/4/2022 | N/A | 25/4/2022 | 2022-02-05 | 2022-12-05 | N/A | 19/5/2022 |  |  | 26/5/2022 | 2022-01-06 | 2022-07-06 | 14/6/2022 | 23/6/2022
[10 empty] | Actual | [8 empty] | 0
15 | SDRF | AGHA/G-F/NS/IGR/15/2022 | 1 |  | 12298000 | >10M | N/S | POST | PRI0R | Plan | 25/4/2022 | N/A | *2/5/2022 | 2022-12-05 | 19/5/2022 | N/A | 26/5/2022 | N/A |  | 2022-01-06 | 7/3/2022 | 14/3/2022 | 23/6/2022 | 30/6/202
Actual
14 | GYAENE MISC | AGHA/G-F/NS/IGR/16/2022 | 1 |  | 1243000 | <10M | N/S | POST | POST | Plan | 2022-02-05 | N/A | 2022-12-05 | 19/5/2022 | 26/5/2022 |  | 2022-01-06 | N/A | 0 | 2022-07-03 | 14/3/2022 | 23/6/2022 | 30/6/2022 | 2022-07-07
Actual
16 | PHARMACY CONSUMABLE | AGHA/G-F/NS/IGR/17/2022 | 1 |  | 693000 | <10M | N/S | POST | POST | Plan | *12/5/2022 | N/A | 19/5/2022 | 26/5/2022 | 2022-01-06 | N/A | 2022-07-06 | N/A | 0 | 14/6/2022 | 21/6/2022 | 28/6/2022 | *5/7/2022 | 2022-12-07
[6 empty] | <10M | N/S | POST | POST | Plan | 19/5/2022 | N/A | 26/5/2022 | 2022-01-06 | 2022-07-06 | N/A | 14/6/2022 | N/A | 0 | 21/6/2022 | 28/6/2021 | 2022-05-07 | *12/7/2022 | 19/7/2021
17 | SANITARY PACK | AGHA/G-F/NS/IGR/18/2022 | 1 |  | 583000 |  |  |  |  | Actual
[6 empty] | <10M | N/S | POST | POST | Plan | 26/7/2022 | N/A | *1/6/2022 | 2022-07-06 | 14/6/2022 | N/A | 21/6/2022 | N/A | 0 | 28/6/2022 | 2022-05-07 | 2022-12-07 | 19/7/2022 | 26/3/2022
18 | THEATER PACK | AGHA/G-F/NS/IGR/19/2022 |  |  | 2,88,000.00 |  |  |  |  | Actual
[6 empty] | <10M | N/S | POST | POST | Plan | *1/6/2022 | N/A | *7/6/2022 | 14/6/2022 | 21/6/2022 | N/A | 28/6/2022 | N/A | 0 | 2022-05-07 | 2022-12-07 | 19/7/2022 | 26/7/2022 | 2022-02-08
19 | DELIVERY PACK | AGHA/G-F/NS/IGR/20/2022 |  |  | 737000 |  |  |  |  | Actual
[6 empty] | <10M | N/S | POST | POST |  | *7/6/2022 | N/A | 14/6/2022 | 21/6/2022 | 28/6/2022 | N/A | 2022-05-07 | N/A | 0 | 2022-12-07 | 19/7/2022 | 26/7/2022 | *2/8/2022 | 2022-09-08
20 | ANAESTHESIA | AGHA/G-F/NS/IGR/21/2022 |  |  | 1738000 |  |  |  |  | Actual
[6 empty] | <10M | N/S | POST | POST | Plan | 14/6/2022 | N/A | *21/6/2022 | 28/6/2022 | 2022-05-07 | N/A | 2022-12-07 | N/A | 0 | 19/7/2022 | 26/7/2022 | 2022-02-08 | *9/8/2022 | 16/8/2022
21 | ADMISSION MISC | AGHA/G-F/NS/IGR/22/2022 |  |  | 968000 |  |  |  |  | Actual
[6 empty] | <10M | N/S | POST | POST | Plan | 21/6/2022 | N/A | *28/6/2022 | 2022-05-07 | 2022-12-07 | N/A | 19/7/2022 | N/A | 0 | 26/7/2022 | 2022-02-08 | 2022-09-08 | 16/8/2022 | 23/8/2022
22 | OBSERVATION | AGHA/G-F/NS/IGR/23/2022 |  |  | 253000 |  |  |  |  | Actual
[6 empty] | >10M | N/S | POST | PRI0R | Plan | 28/6/2022 | N/A | 2022-05-07 | 2022-12-07 | 19/7/2022 |  | 26/7/2022 | N/A | 0 | 2022-02-08 | 2022-09-08 | 16/8/2022 | 23/8/2022 | 30/9/2022
23 | RE- IMBURSEMENT | AGHA/G-F/NS/IGR/24/2022 |  |  | 37752000 |  |  |  |  | Actual