## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: Alimosho General Hospital
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | family planning(allowance for family planning officials) | ALGH/NP /NM/001/22 | 4,500,000.00 | Plan | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 4500000
Actual
2 | Social Work (financial support for social service work) | ALGH/NP /NM/002/22 | 4,000,000.00 | Plan | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 333333.33 | 4000000
Actual
3 | travel/transport(allowance for dispatching official letters) | ALGH/NP /NM/003/22 | 500,00.00 | Plan | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 41666.66 | 500000
Actual
4 | general utility service(payment for official phone calls for head of dept) | ALGH/NP /NM/004/22 | 300,000.00 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
Actual
5 | special duties(expenses incured on emergency) | ALGH/NP /NM/005/22 | 8,000,000.00 | Plan | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 8000000
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: Alimosho General Hospital
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | package number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Cowslo and professional conferences and seminars |  | professional women empowerment | 10 | 3 days | Plan | Lagos | 65000 | 15000 | 20000 | 1000000
|  | ALGH/S-WTC/001/22 |  |  |  | Actual
2 | Training and staff development all cadres |  | To enhance productivity | 645 | 2days | Plan | Lagos | 8000 |  | 5500 | 8000000
|  | ALGH/S-WTC/002/22 |  |  |  | Actual
3 | [5 empty] | Plan
Actual
4 | [5 empty] | Plan
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
printing of medical stationery | ALGH/S-NC-F/NS/001/22 |  |  | 6000000 | <50M | NS | Plan | POST | POST | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | NA | 2022-11-04 | Plan | 18/4/2022 | 20/4/2022 | NA | 2022-02-05 | NA | 16/5/2022 | 18/5/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of office Building | ALGH/S-NC-F/NS/002/22 |  |  | 300000 | <50M | NS | Plan | POST | POST | 2022-03-21 | 2022-03-28 | 2022-04-18 | 2022-05-18 | 2022-05-14 | NA | 2022-04-25 | Plan | 2022-04-26 | 2022-04-27 | NA | 2022-05-30 | NA | 2022-05-21 | 2022-07-04
[7 empty] | Actual | [9 empty] | Actual
Maintenance and repair of other equipment | ALGH/S-NC-F/NS/003/22 |  |  | 3000000 | <50M | NS | Plan | POST | POST | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | NA | 2022-11-04 | Plan | 18/4/2022 | 20/4/2022 | NA | 2022-02-05 | NA | 16/5/2022 | 18/5/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Environment | ALGH/S-NC-F/NS/004/22 |  |  | 6500000 | <50M | NS | Plan | POST | POST | 2022-05-03 | 2022-04-17 | 2022-04-21 | 2022-05-07 | 2022-05-21 | NA | 2022-09-26 | Plan | 2022-06-13 | 2022-06-16 | NA | 2022-05-23 | NA | 2022-06-13 | 2022-06-27
[7 empty] | Actual | [9 empty] | Actual
MTCE of Generating set and Air conditioner | ALGH/S-NC-F/NS/005/22 |  |  | 6000000 | <50M | NS | Plan | POST | POST | 2022-07-18 | 2022-07-25 | 2022-02-08 | 2022-08-22 | 2022-08-23 | NA | 2022-06-13 | Plan | 2022-09-26 | 2022-09-28 | NA | 2022-10-10 | NA | 2022-10-17 | 2022-10-24
[7 empty] | Actual | [9 empty] | Actual
Motor vehicle maintenance and repairs | ALGH/S-NC-F/NS/006/22 |  |  | 500000 | <50M | NS | Plan | POST | POST | 2022-03-07 | 2022-03-14 | 2022-03-21 | 28//2022 | 2022-04-04 | NA | 2022-11-04 | Plan | 25/4/2022 | 27/4/2022 | NA | 2022-11-05 | NA | 2022-01-06 | 29/6/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Specialised equipment vehicle | ALGH/S-NC-F/NS/007/22 |  |  | 10000000 | <50M | NS | Plan | POST | POST | 2022-05-03 | 2022-04-17 | 2022-04-21 | 2022-05-07 | 2022-05-21 | NA | 2022-09-26 | Plan | 2022-06-13 | 2022-09-16 | NA | 2022-09-23 | NA | 2022-10-13 | 2022-11-27
[7 empty] | Actual | [9 empty] | Actual
[5 empty] | <50M | NS | Plan | POST | POST | [5 empty] | NA |  | Plan | 2022-09-06 | 2022-11-06 | NA | 2022-01-06 | NA | 15/6/2022 | 14/7/2022
[7 empty] | Actual | [9 empty] | Actual
[5 empty] | <50M | NS | Plan | POST | POST | [5 empty] | NA |  | Plan | 2022-09-06 | 2022-11-06 | NA | 2022-01-06 | NA | 15/6/2022 | 14/7/2022
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: Alimosho General Hospital
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of stationery items | ALGH /G-F/NS/001/22 |  |  | 300000 | <10m | NS | Post | Postl | Plan | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-04 | 2022-04-11 | N/S | 2022-04-26 | 2022-04-26 | N/S | N/S | N/S | N/S | 2022-05-02 | 2022-05-09
Actual
2 | Procurement of domestic cleaning items such as Izal, mopping stick, disinfectant etc | ALGH /G-F/NS/002/22 |  |  | 300000 | <10m | NS | Post | Postl | Plan | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-04 | 2022-04-11 | N/S | 2022-04-26 | 2022-04-26 | N/S | N/S | N/S | N/S | 2022-05-02 | 2022-05-09
Actual
3 | Fueling of Generating set | ALGH /G-F/NS/003/22 |  |  | 5000000 | <50M | NS | Post | Postl | Plan | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-04 | 2022-04-11 | N/S | 2022-05-02 | 2022-05-03 | N/S | N/S | N/S | N/S | 2022-05-02 | 2022-05-09
Actual
4 | Procurement of uniform and protective | ALGH /G-F/NS/004/22 |  |  | 8,000,000. 00 | <10m | NS | Post | Postl | Plan | 2022-05-21 | 2022-03-28 | 2022-04-04 | 2022-04-18 | 2022-05-04 | N/S | 2022-05-02 | 2022-05-03 | N/S | N/S | N/S | N/S | 2022-05-23 | 2022-05-30
Actual
5 | Procurement of Medical Gas | ALGH /G-F/NS/005/22 |  |  | 20086285 | <50M | NS | Post | Prior | Plan | 2022-05-21 | 2022-03-28 | 2022-04-04 | 2022-04-18 | 2022-05-04 | N/S | 2022-06-13 | 2022-06-14 | N/S | N/S | N/S | N/S | 2022-05-23 | 2022-05-30
Actual
6 | Procurement of planning, research and statistics unit items | ALGH /G-F/NS/006/22 |  |  | 4500000 | <10m | NS | Post | Postl | Plan | 2022-05-21 | 2022-03-28 | 2022-04-04 | 2022-04-18 | 2022-05-04 | N/S | 2022-06-13 | 2022-06-14 | N/S | N/S | N/S | N/S | 2022-06-06 | 2022-06-13
Actual
7 | Procurement of Chemical reagents for various Laboratory | ALGH /G-F/NS/007/22 |  |  | 16000000 | <50M | NS | Post | Prior | Plan | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-05-02 | 2022-05-16
Actual
8 | Procurement of kitchen and refectory consumables for house officers on training | ALGH /G-F/NS/008/22 |  |  | 10500000 | <50M | NS | Post | Prior | Plan | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-05-02 | 2022-05-16 | N/S | 2022-08-22 | 2022-08-22 | N/S | N/S | N/S | N/S | 2022-06-06 | 2022-06-13
Actual
9 | Motor vehicle consumption /incidental. | ALGH /G-F/NS/009/22 |  |  | 500000 | <10m | NS | Post | Postl | Plan | 2022-07-18 | 2022-07-25 | 2022-07-04 | 2022-07-18 | 2022-07-30 | N/S | 2022-08-22 | 2022-08-22 | N/S | N/S | N/S | N/S | 2022-10-19 | 2022-10-26
Actual
10 | [8 empty] | Postl | Plan | [5 empty] | N/S |  |  | N/S | N/S | N/S | N/S
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual