## GOODS
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan vs Actual | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION (DATES)
Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Govenor Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Complete Delivery/Istall | Inspection and Final Acceptance
|  |  |  | 0 | 0 |  |  |  | Plan | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | (1-4 wks) | 48Hours | 0 | 1WK | 1-2 wks | 2-4 wks
Actual
Procurement of Computer peripheral Devices & Accessories | CBD/G/NS/001/22 | NA | NA | 3,110,004.00 | <10M | NS | POST | POST | Plan | 2022-01-03 |  | 2022-08-03 | 15/03/2022 | 29/3/2022 |  | 2022-05-04 | 2022-03-05 |  | 2022-05-05 | 2022-12-05 | 19/5/2022 | 26/5/2022 | 2022-02-06
Actual
Procuremet of Specialised Office tools for different units | CBD/G/NS/002/22 | NA | NA | 14,500,000.00 | <50M | NS | PRE | PRIOR | Plan | 2022-01-03 |  | 2022-08-03 | 15/03/2022 | 29/3/2022 |  | 2022-05-04 | 2022-03-05 |  | 2022-05-05 | 2022-12-05 | 19/5/2022 | 26/5/2022 | 2022-02-06
Actual
Procurement of Stationery | CBD/G/NS/003/22 | NA | NA | 870000 | <10M | NS | POST | POST | Plan | 30/03/2022 | 27/4/2022 | 2022-04-05 | 18/5/2022 | 25/5/2022 | 2022-01-06 | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/7/2022 | 22/07/2022 | 29/7/2022 | 2022-05-08
Actual
Fueling of Enforcement Vehicles for Ikeja & Lagos Island CBD | CBD/G-F/NS/004/22 | NA | NA | 24670000 | <50M | NS | POST | POST | Plan
Actual
TOTAL |  |  |  | 43150004
[5 empty] | #VALUE! |  |  |  | Actual | [8 empty] | #VALUE!
| Mr. Musa Olawale M Permanent Secretary (COS/CBD)/CHAIRMAN | [5 empty] | Mr. Onafowokan, B. L Director , ADM & HR |  |  | Mrs. Adewoju, O. O Deputy Director Finance & Account |  |  | Mrs. Alliu Funmilayo Noimot Asst. Director, Procurement |  |  | Mrs. Alliu Funmilayo Noimot Asst. Director, Procurement |  |  |  | Mr. Olaoye Segun Asst. Director,Publuc Affairs
[7 empty] | Engr. Musa Quadri Assistant Chief Electrical Engineer |  |  |  | Miss. Disu Omobolanle Principal Planning Officer |  |  |  |  | Mrs. Oyebisi O. Senior Auditor

## WORKS
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS | [9 empty] | NA: MEANS NOT APPLICABLE
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  | APPORVAL |  | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Avail | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Mr. Governor Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
|  |  | 0 | 0 |  |  |  | Plan |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | 1-4WKS | 48Hours | 0 | 1WK | 4-6 wks | 2-4 wks
Actual
Installation of Iron Railings at Apongbon Lagos Island CBD | CBD/W/NS/001/22 | NA | 49,985,824.39 | <50M | NS | BOQ | PRE | Plan | PRIOR | 2021-03-03 | 24/32021 | 31/03/2021 | 07/04/2021 | 21/4/2021 | 28/04/2021 | 05/05/2021 | 02/06/2021 |  | 2021-04-06 | 11/06/2021 | 18/06/2021 | 25/6/2021 | 2/7/2021
Actual
Installation of Iron Railings from Kodesoh road to Ikeja Local Government on both side to Simbiat Abiola road Ikeja | CBD/W/NS/002/22 | NA | 70000000 | <50M | NS | BOQ | PRE | Plan | PRIOR | 2021-03-03 | 24/32021 | 31/03/2021 | 07/04/2021 | 21/4/2021 | 28/04/2021 | 05/05/2021 | 02/06/2021 |  | 2021-04-06 | 11/06/2021 | 18/06/2021 | 25/6/2021 | 2/7/2021
Actual
Installation of Portal Carbin for Police rest room and local store in Ikeja including accessories | CBD/W/NS/003/22 | NA | 24428361.55 | <50M | NS | BOQ | PRE | Plan | PRIOR | 2022-01-03 |  | 2022-08-03 | 15/03/2022 | 29/3/2022 |  | 2022-05-04 | 2022-03-05 |  | 2022-05-05 | 2022-12-05 | 19/5/2022 | 26/5/2022 | 2022-02-06
Actual
Ongoing | CBD/W/NS/004/18 | NA | 10,221,697.33 | <50M | NS | BOQ | PRE | Plan | PRIOR | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Oustanding payment on Beautification and Construction of Water Fountain at Onikan Roundabout, CBD | [7 empty] | Actual
Ongoing | CBD/W/NS/005/18 | NA | 6,282,635.00 | <50M | NS | BOQ | PRE | Plan | PRIOR | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Oustanding payment on Beautification and Construction of Water Fountain at Flag House | [7 empty] | Actual
Ongoing | CBD/W/NS/006/2020 | NA | 1325586.05 | <50M | NS | BOQ | PRE | Plan | PRIOR | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Outstanding Payment for the construction of water fountain at king Ado,Onikan | [7 empty] | Actual
Total Cost |  |  | 162244104.32 | #VALUE! |  |  |  | Plan | [9 empty] | #VALUE!
|  |  | #VALUE! | #VALUE! |  |  |  | Actual | [9 empty] | #VALUE!
| Mr. Musa Olawale M Permanent Secretary (COS/CBD) |  |  |  | Mr. Onafowokan, B. L. Dir. , ADM & HR |  |  |  |  | Mrs. Adewoju, Olusola Olayinka Dep. Dir. Finance & Account |  |  |  |  | Mr. Olaoye Segun Asst.Dir.Publuc Affairs Officer |  |  |  | Mrs. Alliu Funmilayo Noimot Asst. Director, Procurement
|  |  |  | Engr. Musa Quadri Assistant Chief Electrical Engineer | [5 empty] | Miss Disu Omobolanle Principal Planning Officer | [6 empty] | Mrs. Oyebibi Oluwatobi Senior Internal Auditor

## NCS
PROCUREMENT PLAN FOR NON - CONSULTANCY SERVICES
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS
BUDGET YEAR: 2022
|  |  | BASIC DATA | [10 empty] | BIDS EVALUATION (DATES) |  |  |  | APPROVAL |  | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | No. Unit | Budget Avail | Approval Threshold | Procurement Method | Plan vs. Actual | Pre-or Post Qualification | Prior or Post Review | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | Minutes of Negotiation | PPA Issues Certificate of Compliance | Plan vs. Actual | Mr. Governor Approval | Register Mr. Governor's approval with PPA | Contract Amount in N'000 | Date Contract signature 1-6 wk | Mobilization/ Advance Payment | Complete Delivery/Install 2-8wks | Inspection and Final Acceptance
|  |  |  | 0 | 0 |  | Plan |  |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | (1 wk) | 1-2 wks | Plan | 1-4wks | 48Hours | 0 | 1wk | 2-4 wks
[7 empty] | Actual | [9 empty] | Actual
Refurbishment of 20 CBD operational vehicles | CBD/S-NC/NS/001/22 | NA | NA | 7,531,367.00 | <10M | NS | Plan | POST | POST | 2022-06-04 | 13/04/2022 | 21/4/2022 | 2022-04-05 | 2022-11-05 | 18/05/2022 | 25/05/2022 | Plan | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/07/2022 | 29/07/2022 | 2022-05-08
[7 empty] | Actual | [9 empty] | Actual
Stakeholders Summits | CBD/S-NC/NS/002/22 | NA | NA | 15,500,000.00 | <50M | NS | Plan | PRE | PRIOR | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
[7 empty] | Actual | [9 empty] | Actual
Publicity advocacy and Press Coverage | CBD/S-NC/NS/003/22 | NA | NA | 5,000,000.00 | <10M | NS | Plan | POST | POST | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
[7 empty] | Actual | [9 empty] | Actual
Quarterly Stakeholders Forum with plaza owners, market leaders, Transport Unions & Security Agencies | CBD/S-NC/NS/004/22 | NA | NA | 12,000,000.00 | <50M | NS | Plan | PRE | PRIOR | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
[7 empty] | Actual | [9 empty] | Actual
Biannual Meeting with Formal Sector | CBD/S-NC/NS/005/22 | NA | NA | 4,000,000.00 | <10M | NS | Plan | POST | POST | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
[7 empty] | Actual | [9 empty] | Actual
Yulitide Sensitization on fire outbreak and Security issues within Lagos Island CBD | CBD/S-NC/NS/006/22 | NA | NA | 10,000,000.00 | <50M | NS | Plan | PRE | PRIOR | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Office Building | CBD/S-NC/NS/007/22 | NA | NA | 3,500,000.00 | <10M | NS | Plan | POST | POST | 2022-06-04 | 13/04/2022 | 21/4/2022 | 2022-04-05 | 2022-11-05 | 18/05/2022 | 25/05/2022 | Plan | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/07/2022 | 29/07/2022 | 2022-05-08
[7 empty] | Actual | [9 empty] | Actual
Motor Vehicle Repairs & Maintenance | CBD/S-NC/NS/008/22 | NA | NA | 5,960,000.00 | <10M | NS | Plan | POST | POST | 2022-06-04 | 13/04/2022 | 21/4/2022 | 2022-04-05 | 2022-11-05 | 18/05/2022 | 25/05/2022 | Plan | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/07/2022 | 29/07/2022 | 2022-05-08
[7 empty] | Actual | [9 empty] | Actual
Provision for Last Day in Office/sendforth | CBD/S-NC/NS/009/22 | NA | NA | 6,000,000.00 | <10M |  | Plan | POST | POST | 2022-06-04 | 13/04/2022 | 21/4/2022 | 2022-04-05 | 2022-11-05 | 18/05/2022 | 25/05/2022 | Plan | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/07/2022 | 29/07/2022 | 2022-05-08
Actual
Sewing / branding of Uniforms and Proctetcive Outfits | CBD/S-NC/NS/010/22 | NA | NA | 1,200,000.00 | <10M |  | Plan | POST | POST | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
Actual
Retreat for CBD Staff | CBD/S-NC/NS/011/22 | NA | NA | 10,000,000.00 | <50M |  | Plan | PRE | PRIOR | 2022-06-04 | 13/04/2022 | 21/4/2022 | 2022-04-05 | 2022-11-05 | 18/05/2022 | 25/05/2022 | Plan | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/07/2022 | 29/07/2022 | 2022-05-08
Actual
Beautification of flower pots within Lagos Island CBD | CBD/S-NC/NS/012/22 | NA | NA | 29428362.22 | <50M |  | Plan | PRE | PRIOR | 2022-04-05 | 2022-11-05 | 18/5/2022 | 2022-01-06 | 2022-08-06 | 15/06/2022 | 22/06/2022 | Plan | 29/06/2022 | 27/7/2022 |  | 29/07/2022 | 2022-05-08 | 2022-12-08 | 19/8/2022
Actual
Maintenance and Repairs of Photocopier machine and Generator | CBD/S-NC/NS/013/22 | NA | NA | 250000 |  |  | Plan | POST | POST | 2022-06-04 | 13/04/2022 | 21/4/2022 | 2022-04-05 | 2022-11-05 | 18/05/2022 | 25/05/2022 | Plan | 2022-08-06 | 2022-06-07 |  | 2022-08-07 | 15/07/2022 | 29/07/2022 | 2022-05-08
Actual
Total Cost |  |  |  | 110369729.22 | #VALUE! |  | Plan | [9 empty] | Plan |  |  | #VALUE!
|  |  |  | #VALUE! | #VALUE! |  | Actual | [9 empty] | Actual |  |  | #VALUE!
S/N NAME DESIGNATURE SIGNATURE
1. Mr. Musa Olawale M Permanent Secretary (COS/CBD)/CHAIRMAN
2. Mr. Onafowokan, B. L Director , ADM & HR
3. Mrs. Adewoju, O. O Deputy Director Finance & Account
4. Mr. Olaoye Segun Asst. Director,Publuc Affairs
5. Mrs. Alliu F. N Asst. Director, Procurement
6. Engr. Musa Quadri Assistant Chief Electrical Engineer
7. Adeagbo Kehinde Adeyemo Asst. Chief Data Processing Officer
8. Miss. Disu Omobolanle Principal Planning Officer
9. Elebiju, Bamidele Senior Auditor

## WORKSHOP
PROCUREMENT PLAN FOR CONFERENCE/SEMINAR
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS
BUDGET YEAR: 2022
S/N | Description of Workshop/Conference | Package Number | Objective of Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | LEADERSHIP & EXECUTIVE MANAGEMENT |  | Resilient Leadership for High Performing Organisations | 1 | 4 days | Plan | Abuja | 200000 | 158000 | 383000 | 741000
Actual
2 | FINANCE & ACCOUNTING |  | The effective financial controller Managing Financial functions and improvement opportunities | 1 | 4 days | Plan | Abuja | 110000 | 125000 | 306400 | 541400
Actual
3 | INSTITUTE OF CHARTERED MEDIATORS AND CONCILIATORS |  | MEDIATION SKILLS ACCREDITATION AND CERTIFICATION TRAINING | 1 |  | Plan | P/HARCOURT | 150000 | 125000 | 306400 | 581400
Actual
4 | NIPR |  | NEW STRATEGIES IN PUBLIC RELATIONS AND CORPORATE COMMUNICATION PRACTICE | 1 |  | Plan | ABUJA | 110000 | 125000 | 306400 | 541400
Actual
5 | OYERINDE |  |  | 1 |  | Plan | ABUJA | 300000 |  |  | 992700
Actual
6 | HUMAN RESOURCES & ADMIN |  | EFFECTIVE TEAM LEADERS "GUIDE TO TEAMWORK AND TEAM BUILDING" | 1 |  | Plan | ABUJA | 150000 | 125000 | 306400 | 581400
Actual
7 | HUMAN RESOURCES & ADMIN |  | TIME MANAGEMENT, PLANNING, ORGANIZING AND GOAL SETTING | 1 |  | Plan | P/HARCOURT | 150000 | 125000 | 306400 | 581400
Actual
8 | CIA |  | ADMINISTRATION IN A DYNAMIC ENVIRONMENT: TIME AND CHALLENGES AND STRATEGIES FOR RESULT-ORIENTED PERFORMANCE | 1 |  | Plan | UYO AKWA-IBOM | 80000 | 116000 | 87300 | 283300
Actual
9 | HUMAN RESOURCES & ADMIN |  | MASTERING PEOPLE MANAGEMENT AND TEAM LEADERSHIP | 1 |  | Plan | ABUJA | 150000 | 125000 | 306400 | 581400
Actual
10 | HUMAN RESOURCES & ADMIN |  | EFFECTIVE TEAM LEADERS "GUIDE TO TEAMWORK AND TEAM BUILDING" | 1 |  | Plan | ABUJA | 150000 | 125000 | 306400 | 581400
Actual
11 | HUMAN RESOURCES & ADMIN |  | PRACTICAL TOOLS FOR EFFECTIVE LEADERSHIP | 1 |  | Plan | P/HARCOURT | 150000 | 125000 | 306400 | 581400
Actual
12 | CIPSMN |  | PUBLIC PRIVATE PARTNERSHIP (3PS) THE PANACEA FOR TIMELY AND SUSTAINABLE PROJECT DELIVERY BY GOVERNMENT AT ALL LEVELS. | 1 |  | Plan | ABUJA | 180000 | 125000 | 306400 | 611400
Actual
13 | LEADERSHIP AND EXECUTIVE MANAGEMENT |  | POLITICS AND THE MODERN WORLD | 1 |  | Plan | ABUJA | 190000 | 125000 | 306400 | 621400
Actual
14 | FINANCE & ACCOUNTING |  | ADVANCED FINANCIAL MANAGEMENT PLANNING, IMPLEMENTATION, REPORTING AND ANALYSIS FOR CORPORATE ORGANIZATION | 1 |  | Plan | P/HARCOURT | 110000 | 125000 | 306400 | 541400
Actual
15 | HUMAN RESOURCES & ADMIN |  | PUBLIC RELATIONS AND CORPORATE COMMUNICATIONS SKILLS FOR HR MANAGERS | 1 |  | Plan | KADUNA | 150000 | 123500 | 231000 | 504500
Actual
16 | HUMAN RESOURCES & ADMIN |  | INNOVATION IN WORKFORCE PLANNING AND ORGANIZATIONAL DEVELOPMENT | 1 |  | Plan | KADUNA | 150000 | 123500 | 231000 | 504500
Actual
17 | CIA |  | ADMINISTRATION IN A DYNAMIC ENVIRONMENT: TIME AND CHALLENGES AND STRATEGIES FOR RESULT-ORIENTED PERFORMANCE | 1 |  | Plan | UYO AKWA IBOM | 80000 | 119000 | 117150 | 316150
Actual
18 | ANAN |  | MCPD | 2 |  | Plan | ABUJA | 65,000.00 + 60,000.00 =125,000.00 | 250000 | 612800 | 987800
Actual
19 | AHR |  | 9TH ANNUAL NATIONAL CONFERENCE OF ASSOCIATION OF HUMAN RESOURCE PRACTITIONER OF NIGERIA | 9 |  | Plan | ABUJA | 120,000.00 x 9=1,080,000.00 | 162,500.00+ 500,000.00(125,000.00 x 4) + 238,000.00 (119,000x2) + 158,000.00 + 123,500.00=1,182,000.00 | 666,500.00 + 416,000.00 (368,000x4) + 368,000.00 (184,000x2) +475,000.00 + 278,400.00 = 2,203,900.00 | 5591500
Actual
S/N NAME DESIGNATURE SIGNATURE
1. Mr. Musa Olawale M Permanent Secretary (COS/CBD)/CHAIRMAN
2. Mr. Onafowokan, B. L Director , ADM & HR
3. Mrs. Adewoju, O. O Deputy Director Finance & Account
4. Mr. Olaoye Segun Asst. Director,Publuc Affairs
5. Mrs. Alliu F. N Asst. Director, Procurement
6. Engr. Musa Quadri Assistant Chief Electrical Engineer
7. Adeagbo Kehinde Adeyemo Asst. Chief Data Processing Officer
8. Miss. Disu Omobolanle Principal Planning Officer
9. Elebiju, Bamidele Senior Auditor

## NON PROCURABLE
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS
| BUDGET YEAR: 2022 | [16 empty] | CONTRACT FINALIZATION
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Upkeep and Maintenance Allowance for CBD Ad-hoc Officers | CBD/NP/NM/001/22 | 112,980,000.00 | Plan | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 9415000 | 112,980,000.00
Actual
2 | Provision for other expenses | CBD/NP/NM/002/22 | 2,500,000.00 | Plan | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 2,500,000.00
Actual
3 | Monitoring and Evaluation Expenses for Enforcement /Taskforce | CBD/NP/NM/003/22 | 2,000,000.00 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 2,000,000.00
Actual
4 | Travel & Transport - Local | CBD/NP/NM/004/22 | 1740000 | Plan | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 145000 | 1740000
Actual
5 | Payment of Recharge cards and Newspaper (General Utility) | CBD/NP/NM/005/22 | 2090000 | Plan | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 174166.67 | 2090000
Actual
6 | Payment of support for financial assistance to bereavement (Miscellaneous) | CBD/NP/NM/006/22 | 480000 | Plan | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 480000
Actual
7 | Personnel Cost | CBD/NP/NM/007/22 | 60662429 | Plan | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 5055202.42 | 60662429
Actual
8 | Payment of C-ways water refill (General Utility) | CBD/NP/NM/008/22 | 302000 | Plan | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 25166.67 | 302000
Actual
9 | Payment of DSTV Subscription (General Utility) | CBD/NP/NM/009/22 | 168000 | Plan | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 14000 | 168000
Actual
10 | Payment for PMB, Management Meetings etc (Miscellaneous) | CBD/NP/NM/010/22 | 1970000 | Plan | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 164166.67 | 1970000
Actual
| TOTAL |  | 184892429 | [13 empty] | 184892429
| Mr. Musa Olawale M Permanent Secretary (COS/CBD)/CHAIRMAN |  |  | Mr. Onafowokan, B. L Director , ADM & HR |  |  | Mrs. Adewoju, O. O Deputy Director Finance & Account |  |  |  | Mrs. Alliu Funmilayo Noimot Asst. Director, Procurement |  |  |  | Mr. Olaoye Segun Asst. Director,Publuc Affairs
|  | Engr. Musa Quadri Assistant Chief Electrical Engineer | [5 empty] | Miss. Disu Omobolanle Principal Planning Officer | [5 empty] | Mrs. Oyebisi O. Senior Auditor

## Sheet1
ITEMS LINE | FIGURE (#)
GOODS | 43150004
WORKS | 162244104.32
NCS | 110369729.22
NP | 184892429
WORKSHOP | 20000000
TOTAL FIGURE | 520656266.54

## TRAINING
PROCUREMENT PLAN FOR TRAINING
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS
BUDGET YEAR: 2022
OVERSEAS TRAINING CALENDER
S/N | Department | Description of Training & Venue | Participants | Designation | Plan vs Actual | Duration | Tuition Fee | Transport Fare | Allowance/Estacode | Visa Fee | Total Cost
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
[5 empty] | Plan | [5 empty] | 0
[5 empty] | Actual | [5 empty] | 0
| PLAN TOTAL |  |  |  | Plan | [5 empty] | 0
| ACTUAL TOTAL |  |  |  | Actual | [5 empty] | 0

## SERVICES
PROCUREMENT PLAN FOR CONSULTANCY SERVICES
MINISTRY/ AGENCY: CENTRAL BUSINESS DISTRICTS
BUDGET YEAR: 2022
PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) (DATES) |  | SHORTLISTING (DATES) |  |  | REQUEST FOR PROPOSALS (DATES) |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) (DATES) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION (DATES) |  |  |  |  | CONTRACT IMPLEMENTATION (DATES)
Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor Approval | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
|  |  |  | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-4 wks | 1-4wk | 48Hours | 0 | 1 wk | 2 wk | 2wks | 1-2 wks | 2-4 wks |  |  | 0
Actual
Total Cost | [5 empty] | Plan | [22 empty] | #VALUE!
|  |  |  | #VALUE! |  | Actual | [14 empty] | #VALUE! | [7 empty] | #VALUE!