## NCS
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2022
S/N | Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Subsription for internet facility | LASCOPA/NCS/001/22 | 1 |  | 1440000 |  | Least-cost selection method | Plan | Pre Qualification | Prior Review | 2022-01-05 | 2022-02-03 | 2022-02-10 | 2022-02-24 | 2022-03-03 | 2022-03-10 | 2022-03-17 | Plan | 2022-04-14 | 2022-04-15 | 1440000 | 2022-05-05 | 2022-05-19 | 2022-06-02
Actual
2 | Management / board members retreat | LASCOPA/NCS/002/22 | 1 |  | 15000000 |  | Quality -and Cost Based Selection Method | Plan | Pre Qualification | Prior Review | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-31 | 2022-06-08 | 2022-06-15 | 2022-06-29 | Plan | 2022-07-27 | 2022-07-28 | 15000000 | 1-Sep-2022 | 2022-09-15 | 20-Sep-2022
Actual
3 | Stakeholders Forum on Food Safety | LASCOPA/NCS/003/22 | 1 |  | 4000000 |  | Least-cost selection method | Plan | Pre Qualification | Prior Review | 2022-01-05 | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | Plan | 2022-07-29 | 2022-07-30 | 4000000 | 3-Sep-2022 | 2022-09-17 | 22-Sep-2022
Actual
4 | Seminar with stakeholders on products and Consumers Right | LASCOPA/NCS/004/22 | 1 |  | 4000000 |  | Least-cost selection method | Plan | Pre Qualification | Prior Review | 2022-01-05 | 2022-02-05 | 2022-02-12 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | Plan | 2022-07-31 | 2022-08-01 | 4000000 | 5-Sep-2022 | 2022-09-19 | 24-Sep-2022
Actual
5 | Consumer Protection week/road show in 5 IBILE divisions of Lagos | LASCOPA/NCS/005/22 | 1 |  | 12084300 |  | Least-cost selection method | Plan | Pre Qualification | Prior Review | 2022-01-05 | 2022-02-06 | 2022-02-14 | 2022-02-28 | 2022-03-06 | 2022-03-14 | 2022-03-20 | Plan | 2022-08-02 | 2022-08-03 | 12084300 | 7-Sep-2022 | 2022-09-21 | 26-Sep-2022
Actual
6 | Retreat & Summit | LASCOPA/NCS/006/22 | 1 |  | 15000000 |  | Least-cost selection method | Plan | Pre Qualification | Prior Review | 2022-01-05 | 2022-02-07 | 2022-02-15 | 2022-03-01 | 2022-03-07 | 2022-03-15 | 2022-03-26 | Plan | 2022-08-04 | 2022-08-05 | 15000000 | 9-Sep-2022 | 2022-09-23 | 28-Sep-2022
Actual
| TOTAL |  |  |  | 51524300 | [15 empty] | 51524300

## GOODS
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | General maintenance & Repairs of office building. | LASCOPA/G/NS/001/22 | 1 |  | 2000000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-01-10 | N/A | 24/01/22 | 14/02/22 | 2022-02-28 | N/A | 28/03/22 | 29/03/22 | 2000000 | 2022-04-05 | 2022-04-12 | 2022-04-26
2 | Motor Vehicle Fuel Consumption | LASCOPA/G/NS/002/22 | 1 |  | 5070000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-01-17 | N/A | 31/01/22 | 2022-02-28 | 2022-03-14 | N/A | 2022-04-04 | 2022-04-05 | 5070000 | 2022-04-12 | 2022-04-19 | 2022-05-03
3 | Procurement of Staff development items | LASCOPA/G/NS/003/22 | 1 |  | 1280000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-02-01 | N/A | 15/2/22 | 22/2/22 | 2022-03-01 | N/A | 2022-04-05 | 2022-04-06 | 1280000 |  | 2022-04-13 | 2022-04-20
4 | Procurement of Furnitures & Equipment From Capital | LASCOPA/G/NS/004/22 | 1 |  | 13041000 | >10,000,000 | National shopping | Post | Prior | Plan | 2022-02-08 | N/A | 22/2/22 | 2022-03-01 | 2022-03-08 | N/A | 2022-04-12 | 2022-04-13 | 13041000 |  | 2022-04-20 | 2022-04-27
5 | Procurement of Setting up of offices in LGA`s From Capital | LASCOPA/G/NS/005/22 | 1 |  | 12200000 | >10,000,000 | National shopping | Post | Prior | Plan | 2022-03-01 | N/A | 2022-03-15 | 2022-03-22 | 2022-03-29 | N/A | 2022-04-26 | 2022-04-27 | 12200000 | 2022-05-04 | 2022-05-11 | 2022-05-25
6 | Procurement of stationery | LASCOPA/G/NS/006/22 | 1 |  | 6000000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-03-08 | N/A | 2022-03-22 | 2022-03-29 | 2022-04-05 | N/A | 2022-05-03 | 2022-05-04 | 6000000 | 2022-05-11 | 2022-05-18 | 2022-06-01
7 | Procurement of Management Information System items(Toner, ink etc) | LASCOPA/G/NS/007/22 | 1 |  | 1560000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-03-15 | N/A | 2022-03-29 | 2022-04-05 | 2022-04-12 | N/A | 2022-05-10 | 2022-05-11 | 1560000 | 2022-05-18 | 2022-05-25 | 2022-06-08
8 | Procurement of raincoats, boots (rubber & leather), nose guard, gloves customized T- shirt and jacket with cap for 10 officers | LASCOPA/G/NS/008/22 | 1 |  | 1300000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-04-05 | N/A | 2022-04-19 | 2022-05-10 | 2022-05-24 | N/A | 2022-06-21 | 2022-06-22 | 1300000 | 2022-06-29 | 2022-07-06 | 2022-07-20
9 | Procurement of office consumables for complaint and mediation department | LASCOPA/G/NS/009/22 | 1 |  | 1240000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-04-12 | N/A | 2022-04-26 | 2022-05-17 | 2022-05-31 | N/A | 2022-06-28 | 2022-06-29 | 1240000 | 2022-07-06 | 2022-07-13 | 2022-07-27
10 | Procureemnt of Agency digital signboard for Public Affair Unit | LASCOPA/G/NS/010/22 | 1 |  | 850000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-04-19 | N/A | 2022-05-10 | 2022-05-24 | 2022-06-07 | N/A | 2022-07-05 | 2022-07-06 | 850000 | 2022-07-13 | 2022-07-20 | 2022-08-03
11 | Procurement of Uniforms and protectives for 80 officers from special duties expenses | LASCOPA/G/NS/011/22 | 1 |  | 760000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-07-06 | N/A | 21/6/22 | 2022-05-07 | 2022-12-07 | N/A | 2022-09-08 | 2022-10-08 | 760000 | 17/8/22 | 24/8/22 | 2022-07-09
12 | Procurement of drivers uniform for 4 officers from special duties expenses. | LASCOPA/G/NS/012/22 | 1 |  | 120000 | <10,000,000 | National shopping | Post | Post | Plan | 14/6/22 | N/A | 28/6/22 | 2022-12-07 | 19/7/22 | N/A | 16/8/22 | 17/8/22 | 120000 | 24/8/22 | 31/8/22 | 14/9/2022
13 | Procurement of bulk Consumables from special duties expenses | LASCOPA/G/NS/013/22 | 1 |  | 2000000 | <10,000,000 | National shopping | Post | Post | Plan | 21/6/22 | N/A | 2022-05-07 | 19/7/22 | 26/7/22 | N/A | 23/8/22 | 24/8/22 | 2000000 | 31/8/22 | 2022-07-09 | 21/9/2022
14 | Procurement of ICT equipment | LASCOPA/G/NS/014/22 | 1 |  | 1000000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-05-07 | N/A | 19/7/22 | 2022-02-08 | 2022-09-08 | N/A | 2022-06-09 | 2022-07-09 | 1000000 | 14/9/22 | 21/9/22 | 2022-05-10
15 | Procurement of legal unit books and other working tool | LASCOPA/G/NS/015/22 | 1 |  | 2000000 | <10,000,000 | National shopping | Post | Post | Plan | 2022-12-07 | N/A | 26/7/22 | 2022-09-08 | 16/8/22 | N/A | 13/9/22 | 14/9/22 | 2000000 | 21/9/22 | 28/9/22 | 2022-12-10
| TOTAL |  |  |  | 50421000 | [13 empty] | 50421000
100842000

## TRAIN & CONF
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Nigeria Bar Association, Abuja. | LASCOPA/S/WTC/001/22 | For Capacity Develpoment | 6 | 54 | Plan | Abuja | 900000 | 454000 | 2581500 | 3110000
2 | CIPM Conference, Abuja. | LASCOPA/S/WTC/002/22 | For Capacity Develpoment | 1 | 4 | Plan | Abuja | 100000 | 65000 | 192000 | 347000
3 | ANAN conference, Abuja | LASCOPA/S/WTC/003/22 | For Capacity Develpoment | 3 | 15 | Plan | Abuja | 165000 | 191000 | 595500 | 952000
4 | NIM Conference, Abuja. | LASCOPA/S/WTC/004/22 | For Capacity Develpoment | 3 | 12 | Plan | Abuja | 225000 | 187000 | 385000 | 797000
5 | Procurement Confence | LASCOPA/S/WTC/005/22 | For Capacity Develpoment | 1 | 5 | Plan | PH | 50000 | 64000 | 178500 | 292500
6 | Computer Conference, Uyo. | LASCOPA/S/WTC/006/22 | For Capacity Develpoment | 1 | 4 | Plan | Uyo | 70000 | 82000 | 216000 | 368000
7 | Comp.Professionals Reg.Council of Nig. Conf. Imo | LASCOPA/S/WTC/007/22 | For Capacity Develpoment | 1 | 4 | Plan | Imo | 73500 | 64000 | 144000 | 281500
8 | Public Relations National Conf. | LASCOPA/S/WTC/008/22 | For Capacity Develpoment | 1 | 4 | Plan | PH | 75000 | 64000 | 144000 | 283000
9 | ICAN Conf. Abuja | LASCOPA/S/WTC/009/22 | For Capacity Develpoment | 2 | 12 | Plan | Abuja | 220000 | 143000 | 497500 | 860500
10 | Admin. & HR Practioners Conf. Abuja | LASCOPA/S/WTC/010/22 | For Capacity Develpoment | 2 | 8 | Plan | Abuja | 200000 | 147000 | 408000 | 755000
11 | Govt. Legal Adviser Course | LASCOPA/S/WTC/011/22 | For Capacity Develpoment | 1 | 4 | Plan | Abuja | 150000 | 80000 | 218000 | 448000
12 | Contemporary Law & Practice | LASCOPA/S/WTC/012/22 | For Capacity Develpoment | 1 | 4 | Plan | Abuja | 150000 | 65000 | 192000 | 407000
13 | Dispute Mgt. & Negotiation Skills (NIALS) | LASCOPA/S/WTC/013/22 | For Capacity Develpoment | 6 | 30 | Plan | Abuja | 840000 | 165000 | 891000 | 1961000
14 | Team Building &Synergy for Peak Perf. (NIMR) | LASCOPA/S/WTC/014/22 | For Capacity Develpoment | 3 | 15 | Plan | Ibadan | 225000 | 45000 | 541500 | 811500
15 | Mgt Control | LASCOPA/S/WTC/015/22 | For Capacity Develpoment | 1 | 4 | Plan | PH | 110000 | 65000 | 192000 | 367000
16 | Team Building &Synergy for Peak Perf. (NIMR) | LASCOPA/S/WTC/016/22 | For Capacity Develpoment | 2 | 10 | Plan | Sango-Otta | 150000 | 24000 | 242000 | 416000
17 | Mandatory Proficiency Prof. In Supply Chain CIPSMN | LASCOPA/S/WTC/017/22 | For Capacity Develpoment | 2 | 8 | Plan | Abuja | 100000 | 125000 | 288000 | 513000
18 | Information Technology Project Mgt | LASCOPA/S/WTC/018/22 | For Capacity Develpoment | 1 | 6 | Plan | Abuja | 195000 | 64000 | 213000 | 472000
19 | Training for Board Members | LASCOPA/S/WTC/019/22 | For Capacity Develpoment | 5 | 20 | Plan | Abuja | 600000 | 350000 | 1080000 | 2090000
20 | Effective budgeting and Budgetary Control in Private and Public sector | LASCOPA/S/WTC/020/22 | For Capacity Develpoment | 1 | 4 | Plan | Abuja | 65000 | 61000 | 96500 | 222500
21 | Alternative Dispute Resolution. 6th-10th July, 2021 (ICMC) | LASCOPA/S/WTC/021/22 | For Capacity Develpoment | 2 | 10 | Plan | Sango | 190000 | 20000 | 181500 | 391500
22 | Auditing the Governance, Risk Mgt and compliance (GRC) function | LASCOPA/S/WTC/022/22 | For Capacity Develpoment | 1 | 4 | Plan | PH | 120000 | 61000 | 96500 | 277500
23 | Environmental management | LASCOPA/S/WTC/023/22 | For Capacity Develpoment | 1 | 5 | Plan | Abeokuta | 80000 | 10000 | 90,750,00 | 180750
24 | Negotiation and Influential skills | LASCOPA/S/WTC/024/22 | For Capacity Develpoment | 4 | 20 | Plan | Abeokuta | 380000 | 30000 | 242000 | 652000
25 | Environmental management | LASCOPA/S/WTC/025/22 | For Capacity Develpoment | 1 | 5 | Plan | Abeokuta | 80000 | 7500 | 60500 | 148000
26 | Financial Accounting & Reporting- A Strategy for Service Delivery (ICAN) | LASCOPA/S/WTC/026/22 | For Capacity Develpoment | 1 | 5 | Plan | Abeokuta | 100000 | 7500 | 60500 | 148000
27 | Data Processing and Analysis using SPSS/PC+ | LASCOPA/S/WTC/027/22 | For Capacity Develpoment | 1 | 5 | Plan | Sango | 110000 | 7500 | 60500 | 178000
28 | Advanced Management Clerical Skills (Best Needs) | LASCOPA/S/WTC/028/22 | For Capacity Develpoment | 1 | 5 | Plan | Ibadan | 88500 | 7500 | 60500 | 156500
29 | Driver Training | LASCOPA/S/WTC/029/22 | For Capacity Develpoment |  |  | Plan | Sango | 77500 | 5000 | 30750 | 113250
| TOTAL | [6 empty] | 5889500 | 10088750 | 10088750 | 18000000
32
33
34
35
36
37
38
39
40

## NON PROC ITEMS
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE CONSUMER PROTECTION AGENCY
BUDGET YEAR: Y2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel allowance for dispatch of 27 mails weekly @2,500x4=270,000 x 12= 3,240,000. | LASCOPA/NP/NM/001/22 | 3,240,000 | Plan | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 270000 | 3240000
Actual
2 | Court Summons, Execution & matters relating to Consumer court | LASCOPA/NP/NM/002/22 | 1,516,000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 158000 | 158000 | 1516000
Actual
3 | Motor Vehicles repairs & maintenance | LASCOPA/NP/NM/003/22 | 1200000 | Plan | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 1200000
Actual
4 | Payment of DSTV Subscription for GM,Board Secretary & Admin Offices | LASCOPA/NP/NM/004/22 | 540,000 | Plan | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 540000
Actual
5 | Payment of DSTV Subscription for 3 other offices | LASCOPA/NP/NM/005/22 | 144,000 | Plan | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 12000 | 144000
Actual
6 | Payment of DSTV Subscription for SIRD & PAO Offices | LASCOPA/NP/NM/006/22 | 255,600 | Plan | 22800 | 22800 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 21000 | 255600
Actual
7 | Miscellaneous- Corp Members allowance | LASCOPA/NP/NM/007/22 | 1,020,000 | Plan | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 1020000
Actual
8 | Miscellaneous- unforeseen expenses | LASCOPA/NP/NM/008/22 | 2,444,000 | Plan | 207000 | 203000 | 203000 | 203000 | 203000 | 203000 | 203000 | 203000 | 204000 | 204000 | 204000 | 204000 | 2444000
Actual
9 | Consumer Education | LASCOPA/NP/NM/009/22 |  | Plan
Actual
* | Trade Fairs & (LSMSME, NSSI,INDUSTRIAL DAY & INTERNATIONAL FAIR) |  | 500,000 | Plan | [12 empty] | 500000
* | Enlightment at grassroots (6 CDAs, Motor parks & 8 tradesmen & artisan associations) |  | 2,020,000 | Plan | [12 empty] | 2020000
* | 6 Public Schools & 4 Private Schools Advocacy. |  | 4,000,000 | Plan | [12 empty] | 4000000
* | Continuation of Public Seminars (4 LGAs & 4 LCDAs) |  | 1,900,000 | Plan | [12 empty] | 1900000
10 | Handling & Complaints for Complaint & Mediation Dept | LASCOPA/NP/NM/010/22 | 2400000 | Plan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 2400000
Actual
11 | Survelance | LASCOPA/NP/NM/011/22 | 1800000 | Plan | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 1800000
Actual
12 | Honourarium fror 2 mopol officers | LASCOPA/NP/NM/012/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
13 | General Investigation | LASCOPA/NP/NM/013/22 | 2500000 | Plan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 250000 | 250000 | 2500000
Actual
14 | Publicity & Press Coverage | LASCOPA/NP/NM/014/22 |  | Plan
Actual
* | Media Appearance |  | 3000000 | Plan | [12 empty] | 3000000
| Newspaper & Publicity |  | 2000000 | Plan | [12 empty] | 2000000
| Press Interview / Hon./Exclu. Talktoria Video |  | 2500000 | Plan | [12 empty] | 2500000
| Production/ Placement |  | 4000000 | Plan | [12 empty] | 4000000
| Media Tour/ Parley/ Briefing |  | 1600000 | Plan | [12 empty] | 1600000
| Prod. Of Info-graphics Mat/ Social Media |  | 500000 | Plan | [12 empty] | 500000
| Prod. Of Documentary in LTV |  | 1800000 | Plan | [12 empty] | 1800000
15 | World Consumer Day | LASCOPA/NP/NM/015/22 | 2000000 | Plan | [12 empty] | 2000000
Actual
16 | World Counterfeit Day | LASCOPA/NP/NM/016/22 | 1000000 | Plan | [12 empty] | 1000000
Actual
17 | Allowances for Ad-Hoc/ Volunteers | LASCOPA/NP/NM/017/22 | 6000000 | Plan | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 6000000
Actual
18 | Staff welfare | LASCOPA/NP/NM/018/22 | 10385200 | Plan | 867600 | 867600 | 865000 | 865000 | 865000 | 865000 | 865000 | 865000 | 865000 | 865000 | 865000 | 865000 | 10385200
Actual
19 | Annual tagging & coding of office equipment & furniture | LASCOPA/NP/NM/019/22 | 200000 | Plan | [12 empty] | 200000
Actual
20 | Planning Research & Statistics Expenses | LASCOPA/NP/NM/020/22 | 1255816.76 | Plan | 107908.38 | 107908.38 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 104000 | 1255816.76
Actual
21 | Audit Unit Expenses | LASCOPA/NP/NM/021/22 | 1000000 | Plan | 80000 | 80000 | 80000 | 80000 | 100000 | 80000 | 100000 | 80000 | 80000 | 80000 | 80000 | 80000 | 1000000
Actual
22 | External Auditor's Fees | LASCOPA/NP/NM/022/22 | 500000 | Plan | [12 empty] | 500000
Actual
23 | Procurement Unit Expenses | LASCOPA/NP/NM/023/22 | 1000000 | Plan | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 100000 | 100000 | 80000 | 80000 | 1000000
Actual
24 | Research & Development | LASCOPA/NP/NM/024/22 |  | Plan
Actual
i | Investigation & Research(Routine Laboratory analysis due to complaints on products by consumers on consumables and non-consumables |  | 2500000 | Plan | 210000 | 208000 | 210000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 208000 | 2500000
Actual
ii | Anti-counterfeiting program on fast moving consumer goods (FCMG) & capacity building on unwholesome sales of Ready to Eat (RTE) products in selected markets i.e 3markets |  | 2250000 | Plan | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 187000 | 190000 | 190000 | 2250000
Actual
iii | Annual Business conduct for supermarkets and groceries stores program on proper handling, packaging and storage of products |  | 1500000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
Actual
25 | Servicing of meetings | LASCOPA/NP/NM/025/22 | 2000000 | Plan | 170000 | 170000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 166000 | 2000000
Actual
26 | Board members allowance | LASCOPA/NP/NM/026/22 | 3250000 | Plan | [12 empty] | 3250000
Actual
27 | Rent expenses | LASCOPA/NP/NM/027/22 | 28520500 | Plan | [12 empty] | 28520500
Actual