## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE ELECTRICITY BOARD
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Personnel Cost | LSEB/NP/NM/001/22 | 6850000 | Plan | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 569547.44 | 6834569.28
Actual
2 | Overhead Expenses | LSEB/NP/NM/002/22 | 239941956.5 | Plan | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 19995163.04 | 239941956.48
Actual
3 | Payment of Electricity Supply by Ikeja DISCO | LSEB/NP/NM/S/001/22 | 850000000 | Plan | 70833333.34 | 70833333.34 | 70833333.34 | 70833333.34 | 70833333.33 | 70833333.33 | 70833333.33 | 70833333.33 | 70833333.33 | 70833333.33 | 70833333.33 | 70833333.33 | 850000000
Actual
4 | Monthly Payment to IPPs | LSEB/NP/NM/S/002/22 | 7864256781.49 | Plan | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.8 | 655234731.75 | 655234731.74 | 7862816781.49
Actual
| Outstanding Liabilities for Year 2022 |  |  | Plan
Actual
5 | Illumination of Venue of ‘One Lagos Fiesta’ Concert at Agege, Badagry, Epe, Ikorodu & Lagos- Year 2017 | LSEB/NP/NM/003/22 | 66276157.5 | Plan
Actual
6 | Illumination of Venue of "One Lagos Fiesta" Concert at Agege, Badagry, Epe, Ikorodu & Lagos- Year 2018 | LSEB/NP/NM/004/22 | 24244027.5 | Plan
Actual
7 | Rehabilitation of Streetlights on Lagos-Abeokuta Road (Abule-Egba to Sango Toll-gate) | LSEB/NP/NM/005/22 | 118691100 | Plan |  |  |  | 0
Actual
8 | Illumination of MKO Garden -Gani Fawehinmi Park & the Environ, Ojota, Lagos | LSEB/NP/NM/006/22 | 86647440 | Plan
Actual
9 | Operations and Maintenance of Public Lighting Infrastructure in Lagos State for the month of July - October, 2021 | LSEB/NP/NM/007/22 | 2450792694.6 | Plan
Actual
10 | Payment of Security component of the Streetlight Operation and Maintenance for the month of July - October, 2021 | LSEB/NP/NM/008/22 | 129600000 | Plan
Actual
11 | Payment for the Replacement of vandalised High Voltage distribution Cable from Anthony bridge to TREM bridge | LSEB/NP/NM/009/22 | 102994800 | Plan
Actual
| TOTAL |  | 11940294957.59 | Plan | 746632775.62 | 746632775.62 | 746632775.62 | 746632775.62 | 746632775.61 | 746632775.61 | 746632775.61 | 746632775.61 | 746632775.61 | 746632775.61 | 746632775.56 | 746632775.55 | 8959593307.25
Actual
|  |  | Mr. L. D. Shitta |  | Engr. K. T. Shoberu |  | Engr. H. Y. Omotayo |  | Engr. A. M. Babalola |  | Mrs. Adetokubo Ladega |  | Ms. A. R. Adeniji
|  |  | Deputy Director (A&HR) |  | Asst. Director (Electrical) |  | Asst. Director (Electrical) |  | Asst. Director (Electrical) |  | Asst. Director (Legal) |  | Asst. Director (Geologist)
|  |  |  | Mr. D. Oluwawunmi |  | Engr. J. O. Kafisewon |  | Engr. S. A. Akinsanya |  | Mrs. E. T Ogunnorin |  | Mrs. E. O. Adesokan
|  |  |  | Asst. Director (Scientific) |  | Asst. Director (ICT) |  | Chief Electrical Engineer |  | Chief Finance & Accounts Officer |  | Chief Procurement Officer
[5 empty] | Mrs. M. A. Adekoya |  | Mrs. M. A. Abudu |  | Mrs. A. A. Ariyo |  | Engr. L. A. Orunsolu
[5 empty] | Cheif Internal Officer (Audit) |  | Asst. Chief Statistician |  | Asst. Chief Public Affairs Officer |  | Asst. Chief Electrical Engineer
Mr. Mukhtaar Tijani
General Manager
0

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2021
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
[7 empty] | Plan | Pre | Post | NA | NA | NA | NA | NA | NA | NA | Plan | NA | NA | NA | NA | NA | NA
[7 empty] | Actual | Pre | Post | [7 empty] | Actual
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY:
BUDGET YEAR:
S/N | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 |  |  |  |  | Plan
Actual
2 |  |  |  |  | Plan
Actual
3 |  |  |  |  | Plan
Actual
4 |  |  |  |  | Plan
Actual
5 |  |  |  |  | Plan
Actual
6 |  |  |  |  | Plan
Actual
7 |  |  |  |  | Plan
Actual
8 |  |  |  |  | Plan
Actual
9 |  |  |  |  | Plan
Actual
10 |  |  |  |  | Plan
Actual
11 |  |  |  |  | Plan
Actual
12 |  |  |  |  | Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE ELECTRICITY BOARD
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Energy Audit of Lagos State Government Facilities, across the State | LSEB/S-C-F/QCBS/001/22 | QCBS | Lump Sum | 39570930 | Prior | Plan | 2022-01-04 | 01-Feb-2022 | 15-Feb-2022 | 22-Feb-2022 | 22-Mar-2022 | 05-Apr-2022 | 19-Apr-2022 | 31-May-2022 | 14-Jun-2022 | 28-Jun-2022 | 12-Jul-2022 | 26-Jul-2022 | 09-Aug-2022 | 06-Sep-2022 |  | 08-Sep-2022 | 15-Sep-2022 | 29-Sep-2022 | 13-Oct-2022 | 27-Oct-2022
Actual
2 | Energy Audit of Twenty (20) Local Communities with the Aim of Introducing Mini Grids to the Communities | LSEB/S-C-F/QCBS/002/22 | QCBS | Lump Sum | 55121472 | Prior | Plan | 2022-01-04 | 01-Feb-2022 | 15-Feb-2022 | 22-Feb-2022 | 22-Mar-2022 | 05-Apr-2022 | 19-Apr-2022 | 31-May-2022 | 14-Jun-2022 | 28-Jun-2022 | 12-Jul-2022 | 26-Jul-2022 | 09-Aug-2022 | 06-Sep-2022 |  | 08-Sep-2022 | 15-Sep-2022 | 29-Sep-2022 | 13-Oct-2022 | 27-Oct-2022
Actual
3 | Energy Audit of Twenty (20) Markets in Preparation for Lagos Informal Economy Electrification Project | LSEB/S-C-F/QCBS/003/22 | QCBS | Lump Sum | 83842290 | Prior | Plan | 2022-01-04 | 01-Feb-2022 | 15-Feb-2022 | 22-Feb-2022 | 22-Mar-2022 | 05-Apr-2022 | 19-Apr-2022 | 31-May-2022 | 14-Jun-2022 | 28-Jun-2022 | 12-Jul-2022 | 26-Jul-2022 | 09-Aug-2022 | 06-Sep-2022 |  | 08-Sep-2022 | 15-Sep-2022 | 29-Sep-2022 | 13-Oct-2022 | 27-Oct-2022
Actual
4 | Energy Audit of Alausa Secretariat | LSEB/S-C-F/QCBS/004/22 | QCBS | Lump Sum | 55121472 | Prior | Plan | 2022-01-04 | 01-Feb-2022 | 15-Feb-2022 | 22-Feb-2022 | 22-Mar-2022 | 05-Apr-2022 | 19-Apr-2022 | 31-May-2022 | 14-Jun-2022 | 28-Jun-2022 | 12-Jul-2022 | 26-Jul-2022 | 09-Aug-2022 | 06-Sep-2022 |  | 08-Sep-2022 | 15-Sep-2022 | 29-Sep-2022 | 13-Oct-2022 | 27-Oct-2022
Actual
5 | Safety Management System/ Implementation, Technical Safety Training/ Workplace Training and Re-training for all Staff and Quality Monitoring to ensure Compliance to Project Standard and Safety Measures | LSEB/S-C-F/QCBS/005/22 | QCBS | Lump Sum | 15200015.9 | Prior | Plan | 2022-01-04 | 01-Feb-2022 | 15-Feb-2022 | 22-Feb-2022 | 22-Mar-2022 | 05-Apr-2022 | 19-Apr-2022 | 31-May-2022 | 14-Jun-2022 | 28-Jun-2022 | 12-Jul-2022 | 26-Jul-2022 | 09-Aug-2022 | 06-Sep-2022 |  | 08-Sep-2022 | 15-Sep-2022 | 29-Sep-2022 | 13-Oct-2022 | 27-Oct-2022
Actual
| TOTAL |  |  |  | 248856179.9 |  | Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE ELECTRICITY BOARD
BUDGET YEAR: YEAR 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira (₦) | Approval Threshold (₦) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount (₦) | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Cables and Electrical components for IPP Development |  |  |  |  | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Rehabilitation & Reconnection of IPP high voltage distribution network from Airforce Substation to Bolade Substation along Agege Motor Road | LSEB/G-F/NCB/001/22 | 1 |  | 213359641.25 | >100m | NCB | Pre | Prior | Plan | 1O11:S11/4/2022 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of CMD Road Streetlight Substation to Alausa Power Plant | LSEB/G-F/NS/001/22 | 2 |  | 29867192.81 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Oba Elegushi & 1st Avenue Streetlight Substation to Island Power Plant | LSEB/G-F/NCB/002/22 | 3 |  | 112163782.47 | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Ikeja Bus Terminal, Ikeja Fire Station, Kodesho Senior Staff Quarters, Kodesho Streetlighting Substation and Medical Road Streetlighting Substation to Mainland Power Plant | LSEB/G-F/NCB/003/22 | 4 |  | 143762474.74 | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Ikoyi Waterworks to Peninsula Integrated Power Plant | LSEB/G-F/NS/002/22 | 5 |  | 39109645.86 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Ilupeju Fire Station to Viathan Power Plant | LSEB/G-F/NS/003/22 | 6 |  | 21430055.31 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Maroko Fire Station to Peninsula Integrated Power Plant | LSEB/G-F/NS/004/22 | 7 |  | 29815055.31 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Installation of new meters/replacement of burnt and damaged meters | LSEB/G-F/NS/005/22 | 8 |  | 21787025 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Ojodu Berger Interchange Streetlight Substation to Alausa Power Plant | LSEB/G-F/NCB/004/22 | 9 |  | 65095835.86 | >50m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Polo Club Streetlight Substation to Peninsula Integrated Power Plant | LSEB/G-F/NCB/005/22 | 10 |  | 72811420.69 | >50m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Connection of Sura Primary Health Care and MVAA Office to Island Power Plant | LSEB/G-F/NS/006/22 | 11 |  | 21923647.78 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
2 | Procurement and Installation of Fifteen (15 Nos) 500KVA, 33/11/0.415KV transformers to various communities in the State. |  |  |  |  | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Electrification Intervention at Ilefunfun, Ilogbo Eremi CDA | LSEB/G-F/NS/007/22 | 1 |  | 15029730.96 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Electrification Intervention at Ashafa Tijani CDA | LSEB/G-F/NS/008/22 | 2 |  | 13198086.74 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Nuraini Yusuf CDA | LSEB/G-F/NS/009/22 | 3 |  | 17255461.11 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Igboye CDA | LSEB/G-F/NS/010/22 | 4 |  | 16434382.68 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intgervention at Oke Sabo/ Idegun CDA | LSEB/G-F/NS/011/22 | 5 |  | 17594396.28 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Imopelufa CDA | LSEB/G-F/NS/012/22 | 6 |  | 12848168.48 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Akanni Seriki Crescent CDA | LSEB/G-F/NS/013/22 | 7 |  | 14955174.58 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Sea Side CDA | LSEB/G-F/NS/014/22 | 8 |  | 17631595.28 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Adeyanlu CDA | LSEB/G-F/NS/015/22 | 9 |  | 19342281.74 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Lakowe CDA | LSEB/G-F/NS/016/22 | 10 |  | 20142166.54 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Taluku Okegun- Odofin CDA | LSEB/G-F/NS/017/22 | 11 |  | 19296542.46 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Okuju Imeke CDA | LSEB/G-F/NS/018/22 | 12 |  | 24439196.11 | >50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Ore Oke Akute CDA | LSEB/G-F/NS/019/22 | 13 |  | 18896759.16 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Peaceland Ogombo CDA | LSEB/G-F/NS/020/22 | 14 |  | 15902544.22 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
| Electrification Intervention at Shodeke Egba CDA | LSEB/G-F/NS/021/22 | 15 |  | 15989475.06 | >10m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
3 | Procurement of Solar spares and Electrical Components for the Operation and Maintenance of the 213 Solar Electrification installed in 175 Schools, incudes 32 Boarding Schools and 11 Primary Health Centers | LSEB/G-/NCB/009/22 |  |  | 57282507.9425 | <100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
[10 empty] | Actual | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
4 | Replacement of Damaged Facial Board hosting Inverters. Combiners, Charge controllers etc | LSEB/G-F/NS/022/22 |  |  | 11471416.375 | <50m | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
5 | Procurement and Re-installation of 320 Nos. of 305W Solar PV Panels in Badagry, Ikorodu, Ibeju Lekki and Epe hubs | LSEB/G-F/NCB/010/22 |  |  | 55976669.5375 | >50m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
6 | Procurement and Installation of Solar Panel Steel Structures and reinstallation of 608 Nos. Photo-voltaic modules at Ilado Primary Health Centres (PHC) and Ajara Primary Health Centres (PHC), Badagry | LSEB/G-F/NCB/011/22 |  |  | 59602568.75 | >50m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
7 | Procurement of Poles, Cables and Electrical Components for the Installation of Streetlights across the State |  |  |  |  | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Installation of Streetlights along Peter Agah, Ejigbo | LSEB/G-F/NCB/012/22 | 1 |  | 62397246.14 | <100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| Streetlight Installation on Odusami, NOB-Oluwa, Erinola Salako and Abisogun Leigh Streets, Ogba | LSEB/G-F/NCB/013/22 | 2 |  | 67712183.64 | <100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| 4 | LSEB/G-F/NCB/014/22 | 3 |  | 102425039.6 | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| The Installation of Streetlights on Oniru Palace Road, and the adjoining street, Victoria Island | LSEB/G-F/NCB/015/22 |  |  |  | <100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| The Installation of Streetlights on Lekki Zone 10 Alternative Roads, Lekki | LSEB/G-F/NCB/016/22 | 5 |  |  | >100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| The Installation of Streetlights at Kareem Ikotun and Olosa Street, Victoria Island | LSEB/G-F/NCB/017/22 | 6 |  |  | <100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
8 | Purchase of Energy Analizer 435 II | LSEB/G-F/NS/023/22 |  | 5 nos. | 17714418.6 | <100m | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-29 | 2022-03-12 | 2022-03-26 | 2022-04-09 | 2022-05-07 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-29
Actual
| TOTAL |  |  |  | 1251304147.815 |  |  |  |  | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE ELECTRICITY BOARD
BUDGET YEAR: YEAR 2022
| CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira (₦) | Approval Threshold | Procurement Method |  | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Operations and Maintenance of Streetlight Infrastructure within the State | LSEB/W/FA/001/22 | Across the State | 4012800000 | >500m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
2 | Direct Labour Component for the Operation and Maintenance of the 213 Solar electrification installed in 175 Schools, includes 32 Boarding Schools and 11 Primary Health Centers | LSEB/W/FA/002/22 | Across the State | 37386164.92 | <50m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
3 | Repayment of Retrofitting of existing Public Streetlights in the State | LSEB/W/NCB/001/21 | Across the State | 7701908671.56 | >500m | NCB | BEME | Pre | Plan | Prior | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2022-04-19 | 2022-05-03
Actual
4 | Direct Labour Component for IPP Development - Connection to IPP Power Plants - Connection of various Government Facilities to IPP | LSEB/W/FA/003/22
| Direct Labour Component for the Rehabilitation & Reconnection of IPP high voltage distribution network from Airforce Substation to Bolade Substation along Agege Motor Road |  | 1 | 27003896.25 | <50m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of CMD Road Streetlight Substation to Alausa Power Plant |  | 2 | 8038508.07 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Oba Elegushi & 1st Avenue Streetlight Substation to Island Power Plant |  | 3 | 14665913.23 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Ikeja Bus Terminal, Ikeja Fire Station, Kodesho Senior Staff Quarters, Kodesho Streetlighting Substation and Medical Road Streetlighting Substation to Mainland Power Plant |  | 4 | 16108323.41 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Ikoyi Waterworks to Peninsula Integrated Power Plant |  | 5 | 7793986.38 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Ilupeju Fire Station to Viathan Power Plant |  | 6 | 4424455.57 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Maroko Fire Station to Peninsula Integrated Power Plant |  | 7 | 6182670.57 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Installation of new meters/replacement of burnt and damaged meters |  | 8 | 1322811.13 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Ojodu Berger Interchange Streetlight Substation to Alausa Power Plant |  | 9 | 10022800.79 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Polo Club Streetlight Substation to Peninsula Integrated Power Plant |  | 10 | 16513700.19 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Component for the Connection of Sura Primary Health Care and MVAA Office to Island Power Plant |  | 11 | 2507724.33 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
5 | Direct Labour Components for the Procurement and Installation of Fifteen (15 Nos) 500KVA, 33/11/0.415KV transformers to various communities in the State. | LSEB/W/FA/004/22
| Direct Labour Components for Electrification Intervention at Ilefunfun, Ilogbo Eremi CDA |  | 1 | 3757433.74 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Ashafa Tijani CDA |  | 2 | 3299522.68 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Nuraini Yusuf CDA |  | 3 | 4313865.29 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Igboye CDA |  | 4 | 4108595.67 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intgervention at Oke Sabo/ Idegun CDA |  | 5 | 4398599.07 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Imopelufa CDA |  | 6 | 3212042.12 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Akanni Seriki Crescent CDA |  | 7 | 3738793.67 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Sea Side CDA |  | 8 | 4407898.82 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Adeyanlu CDA |  | 9 | 4835570.43 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Lakowe CDA |  | 10 | 5035541.63 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Taluku Okegun- Odofin CDA |  | 11 | 4824135.61 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Okuju Imeke CDA |  | 12 | 6109799.03 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Ore Oke Akute CDA |  | 13 | 4724189.79 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Peaceland Ogombo CDA |  | 14 | 3975636.06 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for Electrification Intervention at Shodeke Egba CDA |  | 15 | 3997368.76 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
6 | Painting and Repair of Solar Corroded PV Mounting Structures across Solar Hubs | LSEB/W/FA/005/22 |  | 29495069.12 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
7 | Replacement of Damaged Facial Board hosting Inverters. Combiners, Charge controllers etc | LSEB/W/FA/006/22 |  | 11789641.64 | <5m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
8 | Bi-annual Routine Maintenance (Washing of PV Modules, Solar Cabin Interior and Exterior) and Prevention of Rain Water into the Cabin Interior | LSEB/W/FA/007/22 |  | 12388998.75 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
9 | Direct Labour Components for the Re-installation of 320 Nos. of 305W Solar PV Panels in Badagry, Ikorodu, Ibeju Lekki and Epe hubs | LSEB/W/FA/008/22 |  | 13076979.45 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
10 | Reconstruction/Installation of Direct Labour Components for the Solar Panel Steel Structures and Re-installation of 608 Nos. Photo-voltaic modules at Ilado Primary Health Centres (PHC) and Ajara Primary Health Centres (PHC), Badagry | LSEB/W/FA/008/22 |  | 14984635.34 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
11 | Operation and Maintenance of the Solar Systems installed in 5-Phase 1 Oxygen Kiosk Sites | LSEB/W/FA/009/22 |  | 26322450 | <50m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
12 | Routine Maintainance of LSEB owned IPP distribution networks | LSEB/W/FA/007/22 |  | 15000000 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
13 | Installation of Twenty- One (21Nos.) Donated transformers yet to be installed for the Local Government and Local Council Development Areas of the State. | LSEB/W/FA/009/22
| Installation of Donated Transformer at Irewole Obawole CDA, Ifako-Ijaiye |  | 1 | 8605742.62 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer ar Town Hall CDA, Eredo |  | 2 | 7856449.6 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer ar Mojoda CDA, Eredo |  | 3 | 7502500.8 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Bar-beach CDA, Eti-Osa |  | 4 | 12305468.23 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Dolphin Estate CDA, Eti-Osa |  | 5 | 9771131.45 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Ogbe Agbowa CDA, Ketu-Ejirin |  | 6 | 14158803.97 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Liadi CDA, Ikorodu North |  | 7 | 10399812.87 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Omojoda CDA, Ikorodu North |  | 8 | 8777201.45 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Alarumaku Ifelodun Agura CDA, Ikorodu |  | 9 | 8350260.5 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Obalende Police Barracks CDA, Eti-Osa |  | 10 | 5649444.27 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Kayode Adeyeri CDA, Kosofe |  | 11 | 5649908.64 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Ajagannabe CDA, Epe |  | 12 | 5978555.6 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Papa Olusosun CDA, Oregun |  | 13 | 6217378.99 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Mechanic Village CDA, Ikeja |  | 14 | 9129100.82 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Imeke CDA, Olorunda |  | 15 | 8137645.87 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Eyindi CDA, Epe |  | 16 | 6651880.15 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Ilo-Awela CDA, Ojokoro |  | 17 | 8645842.99 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Ilo-Agbegbemi CDA, Ojokoro |  | 18 | 7606193.12 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Thomas Olaniyan CDA, Agboyi-Ketu |  | 19 | 8408577.76 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Adenaike Odo-Ogun CDA, Agboyi-Ketu |  | 20 | 8251574.28 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Installation of Donated Transformer at Zion CDA, Agboyi-Ketu |  | 21 | 8251574.28 | <10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
15 | Direct Labour Components for the Installation of New Streetlights | LSEB/W/FA/011/22
| Direct Labour Components for the Installation of Streetlights along Peter Agah, Ejigbo |  | 1 | 11279500 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for the Streetlight Installation on Odusami, NOB-Oluwa, Erinola Salako and Abisogun Leigh Streets, Ogba |  | 2 | 15097500 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for the Streetlight Installation on Post Office, Agbado-Ijaiye Road |  | 3 | 14128000 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for The Installation of Streetlights on Oniru Palace Road, and the adjoining street, Victoria Island |  | 4 | 74034707.96 | >50m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for The Installation of Streetlights on Lekki Zone 10 Alternative Roads, Lekki |  | 5 | 153161409.65 | >100m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| Direct Labour Components for The Installation of Streetlights at Kareem Ikotun and Olosa Street, Victoria Island |  | 6 | 11279500 | >10m | Force Account | BEME | Pre | Plan | Prior | 2022-01-04 | 2022-01-18 | 2022-02-01 | 2022-03-15 | 2022-03-29 | 2022-04-12 |  |  |  | 2022-04-19 | 2022-05-03 | 2022-05-31
Actual
| TOTAL |  |  | 12509762058.94 |  |  |  |  | Plan
Actual