## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR:2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | IMPLEMENTATION OF THE LAGOS STATE ELECTRICITY POLICY- Creation of Institutions/ Agencies- Set up cost | MEMR/NP/NM/001/22 | 316018060.07 | Plan |  |  | 79004515.02 |  |  | 79004515.02 |  |  | 79004515.02 |  |  | 79004515.02 | 316018060.07
Actual
2 | Legal Unit expenses | MEMR/NP/NM/002/22 | 3500000 | Plan |  |  |  | 1750000 |  |  |  |  | 1750000 |  |  |  | 3500000
Actual
3 | Publicity and Press Coverage(Honorarium) | MEMR/NP/NM/003/22 | 5200000 | Plan |  |  |  | 1733333.34 |  |  |  | 1733333.34 |  |  |  | 1733333.34 | 5200000
Actual
4 | Monitoring & Evaluation Expenses | MEMR/NP/NM/004/22 | 15600000 | Plan |  |  | 3750000 |  |  | 3750000 |  |  | 3750000 |  |  | 3750000 | 15000000
Actual
5 | Special Duties Expenses | MEMR/NP/NM/005/22 | 27550000 | Plan |  |  | 6887500 |  |  | 6887500 |  |  | 6887500 |  |  | 6887500 | 27000000
Actual
6 | Audit duties expenses | MEMR/NP/NM/006/22 | 2000000 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 2000000
Actual
7 | Planning Research & Statistic Expenses | MEMR/NP/NM/007/22 | 4000000 | Plan |  |  |  | 1333333.34 |  |  |  | 1333333.34 |  |  |  | 1333333.34 | 4000000
Actual
8 | Procurement Unit Expenses | MEMR/NP/NM/008/22 | 2000000 | Plan |  |  | 500000 |  |  | 500000 |  |  | 500000 |  |  | 500000 | 2000000
Actual
9 | Energy Studies Initiatives | MEMR/NP/NM/009/22 | 4000000 | Plan |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 | 4000000
Actual
10 | Registration & Documentation of oil & Gas Facilities: Printing of 500 application forms @ N2,000 each, Printing of 500 nos objection consent form @ N2,000 each, Printing of 500 sealed notice stickers @ N2,000 each, Printing of 500 Annual State Registration application forms @ N2,000 each | MEMR/NP/NM/010/22 | 4000000 | Plan |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 |  |  | 1000000 | 4000000
Actual
11 | Provision for Mineral Resources and Environmental Management Committee (MIREMCO) Operations | MEMR/NP/NM/011/22 | 35088588.6 | Plan |  |  |  | 11696196.2 |  |  |  | 11696196.2 |  |  |  | 11696196.2 | 35088588.6
Actual
12 | Expenses for Monitoring of Petroleum Products Facilities | MEMR/NP/NM/012/22 | 30345000 | Plan |  |  | 756250 |  |  | 7586250 |  |  | 7586250 |  |  | 7586250 | 30345000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY:
BUDGET YEAR:2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | HONOURABLE COMMISSIONER & PS | MEMR/S-WTC/SS/001/22 |  | 2 |  | Plan |  |  |  |  | 2000000
Actual
2 | OFFICE OF THE HC &PS | MEMR/S-WTC/SS/002/22 |  | 4 |  | Plan
Actual
3 | ADVANCED INTERNAL AUDITING ORGANISED BY ICAN | MEMR/S-WTC/SS/003/22 | CAPACITY BUILDING | 1 | 6 DAYS | Plan | ENUGU | 129990 | 125000 | 453000 | 707990
Actual
4 | STRATEGIC ISSUES IN REVENUE GENERATION, COLLECTION AND FRAUD PREVENTION ORGANISED BY ICAN | MEMR/S-WTC/SS/004/22 | CAPACITY BUILDING | 4 | 6 DAYS | Plan | ENUGU | 439960 | 464000 | 680400 | 1584360
Actual
5 | GEOGRAPHIC INFORMATION SYSTEM TRAINING | MEMR/S-WTC/SS/005/22 | CAPACITY BUILDING | 5 | 6 DAYS | Plan | IBADAN | 225000 | 71250 | 32250 | 328500
Actual
6 | EFFECTIVELY MANAGING & LEADING PEOPLE BY CIPM | MEMR/S-WTC/SS/006/22 | CAPACITY BUILDING | 2 | 3DAYS | Plan | OGUN | 190000 | 36000 | 238800 | 464800 | 0
Actual
7 | PRIORITY MANAGEMENT, OPTIMIZING TIME, WORK FLOW & PRODUCTIVITY BY CIPM | MEMR/S-WTC/SS/007/22 | CAPACITY BUILDING | 6 | 3DAYS | Plan | OGUN | 570000 | 71250 | 526050 | 1167300
Actual
8 | DESIGNING LIQUIFIED PETROLEUM GAS (LPG) RETICULATION PIPING SYSTEM FOR HOUSING ESTATE &SMART CITIES. | MEMR/S-WTC/SS/008/22 | CAPACITY BUILDING | 4 | 3DAYS | Plan | ABUJA | 200000 | 486500 | 845300 | 1531800
Actual
9 | LEVERAGING IT FOR NATIONAL SECURITY & ECONOMIC STABILITY | MEMR/S-WTC/SS/009/22 | CAPACITY BUILDING | 2 | 3 DAYS | Plan | ABUJA | 200000 | 235000 | 204450 | 639450
Actual
10 | INTERNATIONAL PROTOCOL & PUBLIC RELATIONS | MEMR/S-WTC/SS/010/22 | CAPACITY BUILDING | 1 | 5 DAYS | Plan | ABUJA | 86000 | 119000 | 190750 | 395750
Actual
11 | CHARTERED INSTITUTE OF PURCHASING AND SUPPLY MANAGEMENT OF NIGERIA | MEMR/S-WTC/SS/011/22 | CAPACITY BUILDING | 1 | 4 DAYS | Plan |  | 100000 | 123500 | 231000 | 454500
Actual
12 | NATIONAL BAR ASSOCIATION (NBA) CONFERENCE | MEMR/S-WTC/SS/012/22 | CAPACITY BUILDING | 1 | 6 DAYS | Plan |  | 140000 | 123500 | 342000 | 605500
Actual
13 | SURVEY UNIT | MEMR/S-WTC/SS/013/22 | CAPACITY BUILDING | 1 |  | Plan |  |  |  |  | 400000
Actual
14 | EMOTIONAL INTELLIGENCE IN THE WORK PLACE | MEMR/S-WTC/SS/014/22 | CAPACITY BUILDING | 2 | 3 DAYS | Plan |  | 70000 | 232000 | 176600 | 476600
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: MINISTRY OF ENERGY AND MINERAL RESOURCES
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Conversion of Generators to pool generators (Min of Health) | MEMR/S-NC/NS/001/22 | 1 |  | 1500000 | <10M | NS | Plan | POST | POST | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 |  | 2022-06-04 | 2022-08-04
Actual
Overhauling of 2 nos generating set | MEMR/S-NC/NS/002/22 | 2 |  | 3500000 | <10M | NS | Plan | POST | POST | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-01-04 | 2022-08-04 |  | 15/04/22 | 17/04/22
Actual
Repair/Fixing of 4 nos Generators | MEMR/S-NC/NS/003/22 | 3 |  | 4250000 | <10M | NS | Plan | POST | POST | 14/02/22 | 21/02/22 | 28/02/22 | 14/3/2022 | 21/03/22 | 28/03/22 | 2022-04-04 |  | 2022-11-04 | 13/4/2022
Actual
Servicing of 43 nos Generator | MEMR/S-NC/NS/004/22 | 4 |  | 13430605 | <50M | NS | Plan | POST | Prior | 15/02/22 | 22/02/22 | 2022-01-03 | 15/3/2022 | 22/3/22 | 29/3/22 | 2022-05-04 |  | 2022-12-04 | 14/4/22
Actual
REFURBISHMENT OF OPERATIONAL VEHICLES | MEMR/S-NC/NS/005/22 | 5 |  | 10631075.16 | <50M | NS | Plan | POST | Prior | 16/02/22 | 23/02/22 | 2022-02-03 | 16/3/2022 | 23/03/22 | 30/03/22 | 2022-06-04 |  | 13/04/22 | 15/04/22
Actual
Installation of wired Network Infrastructure for Ground floor | MEMR/S-NC/NS/006/22 | 6 |  | 5000000 | <10M | NS | Plan | POST | POST | 17/02/22 | 24/02/22 | 2022-03-03 | 17/3/2022 | 24/03/22 | 31/03/22 | 2022-07-04 |  | 14/04/22 | 16/04/22
Actual
Maintenance of Office Building | MEMR/S-NC/NS/007/22 |  |  | 2123040 | <10M | NS | Plan | POST | POST | 18/02/22 | 25/02/22 | 2022-04-03 | 18/3/2022 | 25/03/22 | 2022-01-04 | 2022-08-04 |  | 15/04/22 | 18/04/22
Actual
Motor Vehicle Repair & Maintenance | MEMR/S-NC/NS/008/22 |  |  | 7203042 | <10M | NS | Plan | POST | POST | 21/02/22 | 28/02/22 | 2022-07-03 | 21/03/22 | 28/03/22 | 2022-04-04 | 2022-11-04 |  | 18/04/22 | 20/04/22
Actual
Janitorial Services | MEMR/S-NC/NS/009/22 |  |  | 5000000 | <10M | NS | Plan | POST | POST | 17/02/22 | 24/02/22 | 2022-03-03 | 17/3/2022 | 24/03/22 | 31/03/22 | 2022-07-04 |  | 14/04/22 | 18/04/22
Actual
Annual Retreat for Staff | MEMR/S-NC/NS/010/22 |  |  | 26294977.22 | <50M | NS | Plan | POST | prior | 14/02/22 | 21/02/22 | 28/02/22 | 14/3/2022 | 21/03/22 | 28/03/22 | 2022-04-04 |  | 2022-11-04 | 13/4/2022
Actual
Maintenance of dashboard /payment toll gate | MEMR/S-NC/NS/011/22 |  |  | 8200000 | <10M | NS | Plan | POST | POST | 14/02/22 | 21/02/22 | 28/02/22 | 14/3/2022 | 21/03/22 | 28/03/22 | 2022-04-04 |  | 2022-11-04 | 13/4/2022
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Consultancy services for Centralization of Power distribution | MEMR/QCBS/001/22 | QCBS | LUMP SUM | 156245199.9 | PRIOR | Plan | 10/02/22 | 17/02/22 | 24/02/22 | 10/03/22 | 17/03/22 | 24/03/22 | 14/04/22 | 21/04/22 | 28/04/22 | 5/05/22 | 12/05/22 | 19/05/22 | 26/05/22 | 30/05/22 |  | 6/06/22 | 20/06/22 | 4/07/22 | 11/07/22 | 18/07/22
Actual
2 | Consultancy services for upgrade of Operational Command Centre | MEMR/QCBS/002/22 | QCBS | LUMPSUM | 326600000.02 | PRIOR | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
3 | FEASIBILITY STUDY TO DETERMINE POWER NEEDS OF LASG UTILITY FACILITIES | MEMR/QCBS/003/22 | QCBS | LUMPSUM | 14936515.76 | PRIOR | Plan | 14/2/22 | 21/2/22 | 28/2/22 | 14/3/22 | 21/3/22 | 28/3/22 | 18/4/22 | 25/4/22 | 2/5/22 | 9/5/22 | 16/5/22 | 23/5/22 | 30/5/22 | 1/6/22 |  | 8/6/22 | 22/6/22 | 6/7/22 | 13/7/22 | 20/7/22
Actual
4 | LAGOS STATE GEOCHEMICAL MAPPING/GEOCHEMICAL BASELINE STUDIES (LAGOS WEST SENATORIAL DISTRICT) | MEMR/QCBS/004/22 | QCBS | LUMPSUM | 26638500 |  | Plan | 10/02/22 | 17/02/22 | 24/02/22 | 10/03/22 | 17/03/22 | 24/03/22 | 14/04/22 | 21/04/22 | 28/04/22 | 5/05/22 | 12/05/22 | 19/05/22 | 26/05/22 | 30/05/22 |  | 6/06/22 | 20/06/22 | 4/07/22 | 11/07/22 | 18/07/22
Actual
5 | FEASIBILITY FOR CLAY BENEFICIATION AND DEVELOPMENT | MEMR/QCBS/005/22 | QCBS | LUMPSUM | 19950669 | PRIOR | Plan | 14/2/22 | 21/2/22 | 28/2/22 | 14/3/22 | 21/3/22 | 28/3/22 | 18/4/22 | 25/4/22 | 2/5/22 | 9/5/22 | 16/5/22 | 23/5/22 | 30/5/22 | 1/6/22 |  | 8/6/22 | 22/6/22 | 6/7/22 | 13/7/22 | 20/7/22
6 | PRELINIMINARY STUDY TO INVESTIGATE THE LEVEL OF EXPOSURE TO GEODYNAMICS ACTIVITIES IN THE STATE | MEMR/QCBS/006/22 | QCBS | LUMPSUM | 11287500 | PRIOR | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
7 | Geological Investigation of Wastewater Treatment Plant Sites in Lagos State for Groundwater and Enviromental Contamination | MEMR/QCBS/007/22 | QCBS | LUMPSUM | 34400000 |  | Plan | 10/02/22 | 17/02/22 | 24/02/22 | 10/03/22 | 17/03/22 | 24/03/22 | 14/04/22 | 21/04/22 | 28/04/22 | 5/05/22 | 12/05/22 | 19/05/22 | 26/05/22 | 30/05/22 |  | 6/06/22 | 20/06/22 | 4/07/22 | 11/07/22 | 18/07/22
Actual
8 | LAGOS STATE AGRICULTURAL ZONE (GIZ )MAPPING LAGOS EAST (Phase 1) | MEMR/QCBS/008/22 | QCBS | LUMPSUM | 110379843.08 |  | Plan | 14/2/22 | 21/2/22 | 28/2/22 | 14/3/22 | 21/3/22 | 28/3/22 | 18/4/22 | 25/4/22 | 2/5/22 | 9/5/22 | 16/5/22 | 23/5/22 | 30/5/22 | 1/6/22 |  | 8/6/22 | 22/6/22 | 6/7/22 | 13/7/22 | 20/7/22
Actual
9 | SET UP FOR LAGOS GEOLOGICAL & MINING COMPANY: State Owed Enterprise(fully or partially owned) | MEMR/QCBS/009/22 | QCBS | LUMPSUM | 86000000 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
10 | ACQUISITION OF AERO MAGNETIC DATA ON MINERAL RESOURCES THAT FALLS WITHIN & ALONG THE STATE BOUNDARY | MEMR/QCBS/010/22 | QCBS |  | 39000000 |  | Plan | 10/02/22 | 17/02/22 | 24/02/22 | 10/03/22 | 17/03/22 | 24/03/22 | 14/04/22 | 21/04/22 | 28/04/22 | 5/05/22 | 12/05/22 | 19/05/22 | 26/05/22 | 30/05/22 |  | 6/06/22 | 20/06/22 | 4/07/22 | 11/07/22 | 18/07/22
Actual
11 | FEASIBILITY STUDY FOR THE ESTABLISHMENT LAGOS ENERGY HUB (BADAGRY) Development of Outline Business case | MEMR/QCBS/011/22 | QCBS |  | 75000000 |  | Plan | jhjkk | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 2022-06-07 | 2022-06-14 | 28/06/22 | 5/07/22 | 12/07/22
Actual
12 | CONSULTANCY SERVICES FOR PROMOTION OF USE OF CLEAN ENERGY (LPG,CNG) FOR VEHICULAR /POWER PURPOSE (IN LINE WITH NATIONAL GAS EXPANSION PROJECT) | MEMR/QCBS/012/22 | QCBS |  | 55600000 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
13 | CONSULTANCY SERVICES FOR REGULATION OF GAS (DECANTERS) | MEMR/QCBS/013/22 | QCBS |  | 53000000 |  | Plan | 10/02/22 | 17/02/22 | 24/02/22 | 10/03/22 | 17/03/22 | 24/03/22 | 14/04/22 | 21/04/22 | 28/04/22 | 5/05/22 | 12/05/22 | 19/05/22 | 26/05/22 | 30/05/22 |  | 6/06/22 | 20/06/22 | 4/07/22 | 11/07/22 | 18/07/22
Actual
14 | Consultancy services for the Creation Of Petroleum Product Truck Park with Modern Facilities (Phase 1) | MEMR/QCBS/014/22 | QCBS |  | 181784796.61 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
15 | GEOLOGICAL INVESTIGATION OF LANDFILLS FOR GROUNDWATER & ENVIRONMENTAL CONTAMINATION (Olososun, Abule Egba, & Isolo Landfill & Environs) | MEMR/QCBS/015/22 |  |  | 53011381.25 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
16 | GEOLOGICAL INVESTIGATION OF LANDFILLS FOR GROUNDWATER & ENVIRONMENTAL CONTAMINATION ( Epe & Ewu Elepe-landfill sites & environs) | MEMR/QCBS/016/22 | QCBS |  | 57272775 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
17 | GEOLOGICAL INVESTIGATION OF LANDFILLS FOR GROUNDWATER & ENVIRONMENTAL CONTAMINATION (Solous & Badagry landfill sites & environs) | MEMR/QCBS/017/22 | QCBS |  | 69510843.75 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
18 | INVESTIGATION OF POSSIBLE SOURCE OF HYDROCARBON LEAKAGE AT Onikan Area of Lagos using ground penetrating radar. | MEMR/QCBS/018/22 | QCBS |  | 7500000 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
19 | SALTWATER INTRUSION INVESTIGATION IN LAGOS COASTAL COMMUNITIES (Amuwo Odofin/Ajegunle/Ikotun- Satelite Town/Festac/Epe/Ejirin/Kosofe/Ajegunle/ Oworonsoki/Somolu/Ojodu/ Iseri-Olofin /Olowoira) | MEMR/QCBS/019/22 | QCBS |  | 140689000 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual
20 | LAGOS STATE GEOCHEMICAL MAPPING/GEOCHEMICAL BASELINE STUDIES (LAGOS EAST SENATORIAL DISTRICT) | MEMR/QCBS/020/22 | QCBS |  | 22016000 |  | Plan | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | 2022-05-31 |  | 7/06/22 | 21/06/22 | 5/07/22 | 12/07/22 | 19/07/22
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR: 2021
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1
|  | ELECTRICITY INFRASTRUCTURE IMPROVEMNET WITHIN ALAUSA SECRETARIAT & LASG AGENCIES | [7 empty] | Plan | Prior
Actual
| 1 | Rehabilitation of low voltage power distribution facilities at the Digital Village | MEMR/W/NS/001/01-22 | 1 | 35252781.07 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-04-08 | 2022-04-15 | 2022-04-29
Actual
| 2 | Replacement of Vandalized Earthing within alausa seretariat & LASG Agencies | MEMR/W/NS/001-02/22 | 2 | 10139800 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 3 | Replacement of 800A at Civil service Commission | MEMR/W/NS/001-03/22 | 3 | 7737320.89 | <10M | N/S | BOQ | POST | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-06-04 |  | 2022-04-13 | 2022-04-20 | 2022-04-05
Actual
| 4 | Replacement of Damaged Cable Powering @ Adeyemi Bero Hall | MEMR/W/NS/001-04/22 | 4 | 29460539.9 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-04-08 | 2022-04-15 | 2022-04-29
Actual
| 5 | Automated Feeder Pillar within the sercretariat | MEMR/W/NS/001-05/22 | 5 | 10973875 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 6 | Fencing of 12 nos Substation around the Lagos State Secretariat | MEMR/W/NS/001-06/22 | 6 | 21464190 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-06-04 |  | 2022-04-13 | 2022-04-20 | 2022-04-05
Actual
| 7 | Replacement of damaged cable at Ministry Establishment, Training & Pension | MEMR/W/NS/001-07/22 | 7 | 15500000 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-04-08 | 2022-04-15 | 2022-04-29
Actual
| 8 | Replacement of damaged cable at safety Commission | MEMR/W/NS/001-08/22 | 8 | 19831546.88 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 13 | [8 empty] | Plan
| 9 | Replacement of 1X500mm2 PVC & 4X95mm2 cable at Min. of Agric,PPA & Civic Engagement | MEMR/W/NS/001-09/22 | 9 | 25597324.4 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-04-08 | 2022-04-15 | 2022-04-29
Actual
| 10 | Replacement of Damaged cable at Min. of Justice | MEMR/W/NS/001-10/22 | 10 | 18120000 | <50M | N/S | BOQ | POST | plan | Prior | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-06-04 |  | 2022-04-13 | 2022-04-20 | 2022-04-05
actual
| 11 | Electrification of Lagos State Senior Model College, Badore | MEMR/W/NS/002-01/22 | 1 | 18842947.92 | <50M | N/S |  | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
[8 empty] | BOQ |  | Actual
| 12 | Electrification of Unity Estate, Off Ijede Road, Ikorodu |  | 2 | 45779554.81 | <50M | N/S | BOQ | POST | plan | Prior | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-04-08 | 2022-04-15 | 2022-04-29
|  |  | MEMR/W/NS/002-03/22 | [6 empty] | actual
| 13 | Electrification of Education Resources Centres, Ojodu | MEMR/W/NS/002-04/22 | 3 | 22250000 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 14 | Electrification of Lagos State Cooperative, Oko Oba | MEMR/W/NS/002-05/22 | 4 | 21550000 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-04-08 | 2022-04-15 | 2022-04-29
Actual
| 15 | Upgrade of electrical facilities in lagos state Fire stations | MEMR/W/NS-002/06/22 | 5 | 34964025.07 | <50M | N/S | BOQ | POST | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-06-04 |  | 2022-04-13 | 2022-04-20 | 2022-04-05
Actual
| 16 | Electrification of Ibeju Lekki area and community | MEMR/W/NCB/003/22 |  | 1000000000 | >1B | NCB | BOQ | POST | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-06-04 |  | 2022-04-13 | 2022-04-20 | 2022-04-05
Actual
|  | HOSPITALS ELECTRIFICATION INTERVENTION (ELECTRICITY INFRASTRUCTURE IMPROVEMENT OF LASG GENERAL HOSPITALS. Phase (1 & 2) | [18 empty] | 2022-04-13 | 2022-04-20 | 2022-04-05
| 17 | Upgrade of power distribution facilities for Surulere MCC | MEMR/W/NCB/004-001/22 | 1 | 129734458.2 | <500M | NCB | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 18 | Upgrade of power distribution facilities for Apapa General Hospital | MEMR/W/NCB/004-002/22 | 2 | 102964672.86 | <500M | NCB | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 19 | Upgrade of power distribution facilities of Ibeju Lekki General Hospital | MEMR/W/NCB/004-003/22 | 3 | 184704212.5 | <500M | NCB | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 20 | Upgrade of power distribution facilities of Epe General Hospital | MEMR/W/NCB/004-004/22 | 4 | 160736025.97 | <500M | NCB | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 21 | Renewable Energy solutions for Agbowa MCC | MEMR/W/NS/004-005/22 | 5 | 49026239.18 | <50M | NS | BOQ | POST | Plan | Prior | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 22 | Electrification of Ajeromi /Ifelodun General Hospital | MEMR/W/NCB/004-006/22 | 6 | 49026239.18 | <50M | NS | BOQ | POST | Plan | Post | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 23 | Renewable Energy solutions for Isolo General Hospital | MEMR/W/NS/004-007/22 | 7 | 49026239.18 | <50M | NS | BOQ | POST | Plan | Post | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 24 | Upgrade of power distribution facilities for Amuwo Odofin General Hospital | MEMR/W/NS/004-008/22 | 8 | 49026239.18 | <50M | NS | BOQ | POST | Plan | Post | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-03
Actual
| 25 | Relocation of Power cable and property situated at Block 69A,26,27 & 28 and Admiralty Lekki Pennisula scheme1 in Lagos state | MEMR/W/DC/001/22 |  | 220000000 | <500M | DC | BOQ | POST | Plan | Post | 2022-11-02 | 18/02/22 | 25/02/22 | 2022-11-03 | 18/03/22 | 2022-03-25 | 2022-04-01 | 2022-04-05
Actual
| 26 | The Connection of Imota Rice Mill to Existing 33KV Distribution line | MEMR/W/DC/002/22 |  | 190000000 | <500M | DC | BOQ | POST | Plan | Post | 2022-11-03 | 18/02/23 | 25/02/23 | 2022-11-04 | 18/03/23 | 2022-03-25 | 2022-04-01 | 2022-04-05
Actual
| 27 |  | MEMR/W/DC/001/24 |  | 220000002 | <500M | DC | BOQ | POST | Plan | Post | 2022-11-04 | 18/02/24 | 25/02/24 | 2022-11-05 | 18/03/24 | 2022-03-25 | 2022-04-01 | 2022-04-05
Actual

## goods
| PROCUREMENT PLAN FOR GOODS. | [11 empty] | 0
MINISTRY/AGENCY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Purchase of 60 nos Batteries of different capacities | MEMR/G/NS/001/22 |  | 60 | 8100000 | <10M | N/S | POST |  | Plan | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-08-04 | 15/4/22 | 29/4/22
[9 empty] | POST | Actual
2 | Electrification of 66 comunities (Transformers & accessories) | MEMR/G/NCB/001/22 |  |  | 1203413224.74 | > 1B | NCB | POST |  | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 |  | 2022-04-07 | 2022-04-14 | 2022-04-28
[9 empty] | PRIOR | Actual
3 | PROVISION OF OFFICE FURNITURE & EQUIPMENT | MEMR/G/NS/002/22 |  |  | 36000000 | <50M | NS |  |  | Plan | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-07 |  | 2022-04-14 | 2022-04-21 | 2022-05-05
[9 empty] | PRIOR | Actual
4 | PROCUREMENT OF COMPUTER HARDWARE | MEMR/G/NS/003/22 |  |  | 30000000 | <50M | NS |  |  | Plan | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-08-04 | 15/4/22 | 29/4/22
[9 empty] | PRIOR | Actual
5 | SURVEY EQUIPMENT | MEMR/G/NS/004/22 |  |  | 3500000 | <10M | NS |  |  | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 |  | 2022-04-07 | 2022-04-14 | 2022-04-28
[9 empty] | POST | Actual
6 | Stationery | MEMR/G/NS/005/22 |  |  | 3273041 | <10M | NS |  |  | Plan | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-07 |  | 2022-04-14 | 2022-04-21 | 2022-05-05
[9 empty] | POST | Actual
7 | Procurement of computer consumables | MEMR/G/NS/006/22 |  |  | 4500000 | <10M | NS |  |  | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-03-31 |  | 2022-04-07 | 2022-04-14 | 2022-04-28
[9 empty] | POST | Actual
8 | Fuelling of Heavy Duty Plants & Equipment | MEMR/G/NS/007/22 |  |  | 16000000 | <50M | NS |  |  | Plan | 2022-09-02 | 16/02/22 | 23/02/22 | 2022-09-03 | 16/03/22 | 23/03/22 | 30/03/22 | 2022-01-04 |  | 2022-08-04 | 15/4/22 | 29/4/22
[9 empty] | PRIOR | Actual
9 | Fuelling for 3 vehicles for 20 trips/month for 10mnths @ 8,500 each (Oil &n Gas dept) | MEMR/G/NS/008/22 |  |  | 5100000 | <10M | NS |  |  | Plan | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-07 |  | 2022-04-14 | 2022-04-21 | 2022-05-05
[9 empty] | PRIOR | Actual
10 | Motor Vehicle Fuel Consumption | MEMR/G/NS/009/22 |  |  | 8703040.9994 | <10M | NS |  |  | Plan | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-07 |  | 2022-04-14 | 2022-04-21 | 2022-05-05
Actual

## Consultancy (On-Going)
PROCUREMENT PLAN FOR CONSULTING SERVICES (ONGOING)
MINISTRY/ AGENCY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Operation Command Centre for Remote Monitoring of critical energy infrastructure | MEMR/CS/NP/001/21 | NP |  | 422125888.3 | Prior | Plan | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 11/6/2021 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 9/7/2021 | 16/7/2021 | 23/7/2021 | 26/7/2021 | 418000000 | 27/7/2021 | 10/8/2021 | 24/8/2021 | 31/8/2021 | 7/9/2021
Actual
2 | Development of Data Base for oil & Gas facilities | MEMR/CS/QBS/011/21 | QCBS |  | 59100000 | Prior | Plan | 12/2/2021 | 19/2/2021 | 26/2/2021 | 12/3/2021 | 19/3/2021 | 26/3/2021 | 16/4/2021 | 23/4/2021 | 30/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 28/5/2021 | 1/6/2021 | 41500000 | 8/6/2021 | 22/6/2021 | 6/07/2021 | 13/07/2021 | 20/07/2021
Actual
3 | CONSULTANCY FOR MEDIUM AND LOW VOLTAGE INFRASTRUCTURE WITHIN ALAUSA DISTRIBUTION NETWORK | MEMR/S-C/QCBS/018/21 | QCBS |  | 19000000 | Prior | Plan | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 11/6/2021 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 9/7/2021 | 16/7/2021 | 23/7/2021 | 26/7/2021 | 19000000 | 27/7/2021 | 10/8/2021 | 24/8/2021 | 31/8/2021 | 7/9/2021
Actual
4 | ENGAGEMENT OF A CONSULTANT FOR REVIEW OF PROPOSED POWER SOLUTIONS FOR 5MW POWER SUPPLY FOR IMOTA RICE MILL IMOTA LAGOS | MEMR/S-C/SSS/001/21 | SSS |  | 7500000 | Prior | Plan | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 11/6/2021 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 9/7/2021 | 16/7/2021 | 23/7/2021 | 26/7/2021 | 7500000 | 27/7/2021 | 10/8/2021 | 24/8/2021 | 31/8/2021 | 7/9/2021
Actual
5 | : ENGAGEMENT OF THE CONSORTIUM OF MESSRS TECHNOCRAT CONSULT AND IT SYSTEMS LIMITED/CLOSED USER NETWORK LIMITED TO ACHIEVE EFFECTIVE PROJECT MANAGEMENT AND FULL PROJECT IMPLEMENTATION OF THE OPERATION COMMAND CENTRE (OCC | MEMR/S-C/SSS/002/21 | SSS |  | 10000000 | Prior | Plan | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 11/6/2021 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 9/7/2021 | 16/7/2021 | 23/7/2021 | 26/7/2021 | 10000000 | 27/7/2021 | 10/8/2021 | 24/8/2021 | 31/8/2021 | 7/9/2021
Actual
6 | : ENGAGEMENT OF CONSULTANT FOR THE DEPLOYMENT OF OPTIMISATION SOLUTIONS FOR PROJECT EFFICIENCY | MEMR/S-C/SSS/003/21 | SSS |  | 39000000 | Prior | Plan | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 11/6/2021 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 9/7/2021 | 16/7/2021 | 23/7/2021 | 26/7/2021 | 39000000 | 27/7/2021 | 10/8/2021 | 24/8/2021 | 31/8/2021 | 7/9/2021
Actual
7 | Consultancy Services for the Development of a gas Based Policy for emissions reduction in Lagos State | MEMR/CS/QBS/008/21 | QBS |  | 33200000 | Prior | Plan | 18/5/2021 | 25/5/2021 | 2021-06-01 | 15/6/2021 | 22/6/2021 | 29/06/2021 | 20/7/2021 | 27/7/2021 | 2021-08-03 | 2021-10-08 | 17/8/2021 | 24/8/2021 | 31/8/2021 | 2021-09-01 | 44500000 | 2021-09-08 | 22/9/2021 | 6/07/2021 | 13/07/2021 | 20/07/2021
Actual
8 | ENVIRONMENTAL AND SOCIAL IMPACT ASSESSMENTFOR THE LIGHT UP LAGOS PHASE 1 COMMUNITY ELECTRICITY DISTRIBUTION INTERVENTION | MEMR/CQBS//019/21 | QCBS |  | 52032000 | Prior | Plan | 9/4/2021 | 16/4/2021 | 23/4/2021 | 7/5/2021 | 14/5/2021 | 21/5/2021 | 11/6/2021 | 18/6/2021 | 25/6/2021 | 2/7/2021 | 9/7/2021 | 16/7/2021 | 23/7/2021 | 26/7/2021 |  | 27/7/2021 | 10/8/2021 | 24/8/2021 | 31/8/2021 | 7/9/2021
Actual

## Works (On-Going)
|  | PROCUREMENT PLAN FOR WORKS | (ONGOING)
MINISTRY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR: 2022
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
|  | Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1
| 1 | Upgrade of the distribution infrastructure across Eleko-Ajah-Lekki Business District and Magbon Phase 1A | MEMR/W/DC/003-01/21 | 1 | 499946980 | <500M | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 499946980 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 2 | Upgrade of the distribution infrastructure across Eleko-Ajah-Lekki Business District and Magbon Phase 1B | MEMR/W/DC/003-02/21 | 2 | 499100000 | <500M | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 499100000 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 3 | Distribution upgrade and meter installation at Alimosho-Orelope | MEMR/W/DC/004-01/21 | 3 | 497108764 | <500M | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 497108764 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 4 | Distribution upgrade and meter installation at Alimosho-Okunola and Agege-Oko Oba | MEMR/W/DC/004-02/21 | 4 | 495395884 | <500M | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 495395884 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 5 | RENOVATION OF BLOCK 6, GROUND FLOOR AND PART OF FIRST FLOOR OF MININTRY OF ENERGY AND MINERAL RESOURCES | MEMR/W/DC/002/21 |  | 64329267.56 | <100m | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 63899244.31 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 6 | Electrification of Ebute Metta General Hospital | MEMR/W/NCB-O07/001/21 | 1 | 112854340.0001 | <500m | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 162853879.95 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 7 | Electrification of Randle General Hospital Surulere | MEMR/W/NCB-007/003/21 | 3 | 42704212.5 | <50m | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 158053852.45 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 8 | Electrification of MCC Eti-Osa | MEMR/W/NCB-007/004/21 | 4 | 56275040.496 | <50m | NCB | BOQ | Post | Plan | Post | 2021-09-02 | 16/02/2021 | 23/02/2021 | 2021-09-03 | 16/03/2021 | 23/03/2021 | 24/03/2021 | 2021-06-04 | 119890078.13 | 13/04/2021 | 27/04/2021 | 2021-11-05
Actual
| 13 | [8 empty] | Plan

## Goods (On-Going
| PROCUREMENT PLAN FOR GOODS. (ONGOING) | [11 empty] | 0
MINISTRY/AGENCY: MINISTRY OF ENERGY AND MINERAL RESOURCES
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Pilot Solar Solution for General Hospitals | MEMR/G/DC/001/21 |  |  | 42217070.52 | <50m | N/S | Post | Prior | Plan | 24/06/2021 | 2021-01-07 | 2021-07-08 | 25/07/2021 | 2021-01-08 | 2021-08-09 | 17/8/2021 | 20/8/2021 | 42217070.52 | 2021-05-04 | 2021-04-12 | 26/04/2021
Actual