## Sheet1
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: EPE GENERAL HOSPITAL
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PPROCUREMENT OF SPARE PART FOR MOTOR VEHICLES |  | EGH/G-F/NS/01/22 | 1 | 1 | 478000 | <10M | NS | POST | POST | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 478000 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25 | 2022-11-22
Actual
2 | PROCUREMENT OF CONSUMABLES FOR PATIENTS ADMISSION |  | EGH/G-F/NS/02/22 | 2 | 1 | 18900000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-06 | 04/20/2022 | 2022-05-04 | 2022-06-06 | 2022-06-20 | 2022-06-27 | 2022-07-11 | 2022-07-13 | 18900000 | 07-20-22 | 2022-07-27 | 2022-08-10 | 2022-11-01 | 2022-12-02
Actual
3 | PROCUREMENT OF CONSUMABLES FOR MAJOR AND MINOR OPERATION |  | EGH/G-F/NS/02/22 | 2 | 2 | 19887500 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-08 | 04/22/2022 | 2022-05-06 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-15 | 19887500 | 07-22-2022 | 2022-07-29 | 2022-08-12 | 2022-11-09 | 2022-12-07
Actual
4 | PROCUREMENT OF ANAESTHESIA CONSUMABLES |  | EGH/G-F/NS/02/22 | 2 | 3 | 30860000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-11 | 2022-04-25 | 2022-05-09 | 2022-06-10 | 2022-06-24 | 2022-07-01 | 2022-07-15 | 2022-07-18 | 30860000 | 2022-07-25 | 2022-08-01 | 2022-08-15 | 2022-11-15 | 2022-12-13
Actual
5 | PROCUREMENTOF DRESSING & INJ.CONSUMABLES AT G.O.P.D |  | EGH/G-F/NS/02/22 | 2 | 4 | 8970000 | <10M | NS | POST | POST | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 8970000 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25 | 2022-11-22
Actual
6 | PROCUREMENT OF CONSUMABLES FOR MORTUARY SERVICES |  | EGH/G-F/NS/02/22 | 2 | 5 | 4782000 | <10M | NS | POST | POST | Plan | 2022-04-06 | NA | 2022-05-04 | 2022-06-06 | 2022-06-20 | NA |  |  | 4782000 | 07-20-22 | 2022-07-27 | 2022-08-10 | 2022-11-01 | 2022-12-02
Actual
7 | PROCUREMENT OF CONSUMABLES FOR DENTAL SERVICES |  | EGH/G-F/NS/02/22 | 2 | 6 | 12465000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-08 | 04/22/2022 | 2022-05-06 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-15 | 12465000 | 07-22-2022 | 2022-07-29 | 2022-08-12 | 2022-11-09 | 2022-12-07
Actual
8 | PROCUREMENTOF MEDICAL CONSUMABLES(PACKS) |  | EGH/G-F/NS/02/22 | 2 | 7 | 11900000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-11 | 2022-04-25 | 2022-05-09 | 2022-06-10 | 2022-06-24 | 2022-07-01 | 2022-07-15 | 2022-07-18 | 11900000 | 2022-07-25 | 2022-08-01 | 2022-08-15 | 2022-11-15 | 2022-12-13
Actual
9 | PROCUREMENT OF GENERAL MEDICAL CONSUMABLES FOR HOSP. USE |  | EGH/G-F/NS/02/22 | 2 | 8 | 6436300 | <10M | NS | POST | POST | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 6436300 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25 | 2022-11-22
Actual
10 | PROCUREMENT OF LAB. REAGENTS & SCREENING TEST KIT |  | EGH/G-F/NS/03/22 | 3 | 10 | 62730000 | <100M | NS | PRIOR | PRIOR | Plan | 2022-04-06 | 04/20/2022 | 2022-05-04 | 2022-06-06 | 2022-06-20 | 2022-06-27 | 2022-07-11 | 2022-07-13 | 62730000 | 07-20-22 | 2022-07-27 | 2022-08-10 | 2022-11-01 | 2022-12-02
Actual
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: EPE GENERAL HOSPITAL
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  | 2022-06-20: BID EVALUATION (DATES); 2022-07-11: APPROVAL | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
11 | PROCUREMENT OFX-RAY/SCAN & ECG MATERIALS AND CONSUMABLES |  | EGH/G-F/NS/04/22 | 4 | 11 | 23622200 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-08 | 04/22/2022 | 2022-05-06 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-15 | 23622200 | 07-22-2022 | 2022-07-29 | 2022-08-12 | 2022-11-09 | 2022-12-07
Actual
12 | PROCUREMENT OF PHYSIOTHERAPHY MATERIALS AND CONSUMABLES |  | EGH/G-F/NS/05/22 | 5 | 12 | 4475000 | <10M | NS | POST | POST | Plan | 2022-04-11 | NA | 2022-05-09 | 2022-06-10 | 2022-06-24 | NA |  |  | 4475000 | 2022-07-25 | 2022-08-01 | 2022-08-15 | 2022-11-15 | 2022-12-13
Actual
13 | PROCUREMENT OF MATERIALS FOR MED. REPORT/DEATH CERT. AND FOLDERS |  | EGH/G-F/NS/06/22 | 6 | 13 | 16950000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 16950000 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25 | 2022-11-22
Actual
14 | PROCUREMENT OF EYE CLINIC AND MATERIALS CONSUMABLES |  | EGH/G-F/NS/07/22 | 7 | 14 | 30930000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-06 | 04/20/2022 | 2022-05-04 | 2022-06-06 | 2022-06-20 | 2022-06-27 | 2022-07-11 | 2022-07-13 | 30930000 | 07-20-22 | 2022-07-27 | 2022-08-10 | 2022-11-01 | 2022-12-02
Actual
13 | PROCUREMENT OF MEDICAL MATERIALS FOR NHIS CLIENTS(DRUGS |  | EGH/G-F/NS/08/22 | 8 | 15 | 89495000 | <100M | NCB | PRIOR | PRIOR | Plan | 2022-04-08 | 04/22/2022 | 2022-05-06 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-15 | 89495000 | 07-22-2022 | 2022-07-29 | 2022-08-12 | 2022-11-09 | 2022-12-07
Actual
14 | PROCUREMENT OF MATERIALS FOR EMERGENCY RESPONSE IN CASUALTY |  | EGH/G-F/NS/09/22 |  | 16 | 11198000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-11 | 2022-04-25 | 2022-05-09 | 2022-06-10 | 2022-06-24 | 2022-07-01 | 2022-07-15 | 2022-07-18 | 11198000 | 2022-07-25 | 2022-08-01 | 2022-08-15 | 2022-11-15 | 2022-12-13
Actual
15 | PROCUREMENT OF MATERIAL FOR CONT.MED.EDUCATION PROG. |  | EGH/G-F/NS/10/22 |  | 17 | 5,475.000.00 | <10M | NS | POST | POST | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 5,475.000.00 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25 | 2022-11-22
Actual
16 | PROCUREMENTOF MATERIALS FOR THE PROVISION OF SERVICE FOR NHIS |  | EGH/G-F/NS/11/22 |  | 18 | 35844500 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-06 | 04/20/2022 | 2022-05-04 | 2022-06-06 | 2022-06-20 | 2022-06-27 | 2022-07-11 | 2022-07-13 | 35844500 | 07-20-22 | 2022-07-27 | 2022-08-10 | 2022-11-01 | 2022-12-02
Actual
17 | PROCUREMENT OF DELIVERY PACK,GYNEA SERVICES AND ADMISSION |  | EGH/G-F/NS/12/22 |  | 19 | 52866000 | <100M | NS | PRIOR | PRIOR | Plan | 2022-04-08 | 04/22/2022 | 2022-05-06 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-15 | 52866000 | 07-22-2022 | 2022-07-29 | 2022-08-12 | 2022-11-09 | 2022-12-07
Actual
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: EPE GENERAL HOSPITAL
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  | 2022-06-22: BID EVALUATION (DATES); 2022-07-13: APPROVAL | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
18 | PROCUREMENT OF PATIENTS PYJAMAS |  | EGH/G-F/NS/13/22 |  | 20 | 6940000 | <10M | NS | POST | POST | Plan | 2022-04-11 | NA | 2022-05-09 | 2022-06-10 | 2022-06-24 | NA |  |  | 6940000 | 2022-07-25 | 2022-08-01 | 2022-08-15 | 2022-11-15 | 2022-12-13
Actual
19 | PROCUREMENTOF ORTOPAEDIC SERVICES RENDERED |  | EGH/G-F/NS/15/22 |  | 21 | 9090000 | <10M | NS | POST | POST | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 9090000 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25 | 2022-11-22
Actual
20 | PROCUREMENT OF SPARE PART FOR SERVICES OF MEDICAL EQUIPMENTS |  | EGH/G-F/NS/16/22 |  | 22 | 3000000 | <10M | NS | POST | POST | Plan | 2022-04-06 | NA | 2022-05-04 | 2022-06-06 | 2022-06-20 | NA |  |  | 3000000 | 07-20-22 | 2022-07-27 | 2022-08-10 | 2022-11-01 | 2022-12-02
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: EPE GENERAL HOSPITAL
BUDGET YEAR: 2022
OVER HEAD MONITOR
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  | 2022-06-22: BID EVALUATION (DATES); 2022-07-13: APPROVAL | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | FUEL FOR MOTOR VEHICLE ,PLANTS AND HEAVY EQUIPMENTS |  | EGH/G-F/NS/01/22 |  |  | 17267369 | <50M | NS | PRIOR | PRIOR | Plan | 2022-04-08 | 04/22/2022 | 2022-05-06 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-15 | 17267369 | 2022-06-05 | 2022-05-17 | 2022-06-13 | 2022-11-15 | 2022-12-13
Actual
2 | PROCUREMENTOF STATIONARIES FOR THE USE OF HOSPITAL |  | EGH/G-F/NS/02/22 |  |  | 2049000 | <10M | NS | POST | POST | Plan | 2022-04-11 | NA | 2022-05-09 | 2022-06-10 | 2022-06-24 | NA |  |  | 2049000 | 28/4/2022 | 2022-05-09 | 2022-06-02 | 2022-10-25 | 2022-11-22
Actual
3 | PROCUREMENT OF MEDICAL SUPPLIES AND CONSUMABLE |  | EGH/G-F/NS/03/22 |  |  | 2893600 | <10M | NS | POST | POST | Plan | 2022-04-04 | NA | 2022-05-02 | 2022-06-02 | 2022-06-16 | N/A |  |  | 2893600 | MAY-02-2022 | 2022-05-11 | 2022-06-07 | 2022-11-01 | 2022-12-02
Actual
4 | PROCUREMENT OF UNIFORMS AND PROTECTIVES MATERIALS |  | EGH/G-F/NS/04/22 |  |  | 2355000 | <10M | NS | POST | POST | Plan | 2022-04-06 | NA | 2022-05-04 | 2022-06-06 | 2022-06-20 | NA |  |  | 2355000 | MAY-04-2022 | 2022-05-13 | 2022-06-09 | 2022-11-09 | 2022-12-07
Actual
5 | [10 empty] | Plan
Actual
6 | [10 empty] | Plan
Actual
7 | [10 empty] | Plan
Actual
8 | [10 empty] | Plan
Actual
9 | [10 empty] | Plan
Actual
10 | [10 empty] | Plan
Actual
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: EPE GENERAL HOSPITAL
BUDGET YEAR: 2022
OVERHEAD
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  | 2022-06-22: BID EVALUATION (DATES); 2022-07-13: APPROVAL | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Sheet2
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: GENERAL HOSPITAL EPE
BUDGET YEAR: 2022
Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
LOCAL TRAVEL AND TRANSPORT | EGH/NP/NM/01/22 | 463000 | Plan | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 463000
STAFF TO ALAUSA AND HSC |  |  | Actual
GENERAL UTILITY | EGH/NP/NM/02/22 | 463000 | Plan | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 38583 | 463000
SERVICES |  |  | Actual
PAYMENT FOR EMERGENCY | EGH/NP/NM/03/22 | 443584 | Plan | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 36965 | 443584
NEEDS AND ENTERTAINMENTS |  |  | Actual
PAYMENT FOR ELECTRICITY | EGH/NP/NM/04/22 | 6,360,000.00 | Plan | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 530000 | 6360000
BILL |  |  | Actual
GIFT TO RETIREES AND | EGH/NP/NM/05/22 | 6,726,871.49 | Plan | NOVEMBER: 6726871.49 | 6726871.49
OTHER STAFF |  |  | Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
|  | 14456455.49 | Plan | [12 empty] | 14456455.49
Actual

## Sheet3
PROCUREMENT PLAN FOR WORKS
MINISTRY: GENERAL HOSPITAL EPE
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[10 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
[8 empty] | Plan | POST
Actual
[8 empty] | Plan | POST
Actual
[8 empty] | Plan | POST
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Sheet4
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: GENERAL HOSPITAL EPE
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | 2022 ANNUAL SCIENTIFIC CONFERENCE OF THE NIGERIAL INSTITUTE OF MEDICAL RESEARCH, YABA | EGH/S-WTC/01/22 |  | 4 | 2 DAYS | Plan | LAGOS | 400000 |  |  | 1600000
Actual
2 | OCCUPATIONAL HEALTH AND SAFETY MANAGEMENT | EGH/S-WTC/02/22 |  | 2 | 3 DAYS | Plan | ABUJA | 500000 |  |  | 1000000
Actual
3 | ANNUAL CONFERENCE FOR HEAD OF ACCOUNT | EGH/S-WTC/03/22 |  | 1 | 5 DAYS | Plan | ABUJA | 400000 |  |  | 400000
Actual
4 | 2022 NATIONAL CONFERENCE FOR NURSE | EGH/S-WTC/09/22 |  | 10 | 1 DAYS | Plan | LAGOS | 5000 |  |  | 50000
Actual
5 | THORACIC LUMBER SPINE : PATHOLOGIES TREATMENT | EGH/S-WTC/08/22 |  | 15 | 3 DAYS | Plan | LAGOS | 50000 |  |  | 750000
Actual
6 | TEAM WORK AND ATTITUDINAL CHANGE | EGH/S-WTC/06/22 |  | 40 | 5 DAYS | Plan | KWARA | 200000 |  |  | 200000
Actual
7
8
9
10
11
12 | [5 empty] | Plan |  |  |  |  | 4000000
Actual

## Sheet5
BUDGET YEAR: 2022 NON-CONSULTANCY SERVICES G.H.EPE 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | PROVISION OF FOOD FOR THE INPATIENTS | EGH/S-NC-F/NS/01/22 | 1 | 1 | 17408000 | <50M | NS | Plan | PRIOR | PRIOR | 2022-04-04 | 04/20/2022 | 2022-05-02 | 2022-06-02 | 2022-06-16 |  | 2022-06-24 | Plan | 2022-07-11 | 2022-07-13 | 17408000 | 08-17-22 | 2022-08-31 | 2022-10-10 | 2022-11-01
[8 empty] | Actual | [9 empty] | Actual
2 | PROVISION OF FOOD STUFFS MATERIALS FOR DEMONSTRATION CLASS | EGH/S-NC-F/NS/02/22 | 1 | 2 | 3925000 | <10M | NS | Plan | POST | POST | 2022-04-06 | NA | 2022-05-04 | 2022-06-06 | 2022-06-20 |  |  | Plan |  |  | 3925000 | 07-22-2022 | 2022-07-29 | 2022-08-12 | 2022-11-09
[8 empty] | Actual | [9 empty] | Actual
3 | MAINTAINANCE OF BUILDING | EGH/S-NC-F/NS/03/22 | 1 | 3 | 655000 | <10M | NS | Plan | POST | POST | 2022-04-08 | NA | 2022-05-06 | 2022-06-08 | 2022-06-22 |  |  | Plan |  |  | 655000 | 2022-07-25 | 2022-08-01 | 2022-08-15 | 2022-11-15
[8 empty] | Actual | [9 empty] | Actual
4 | PRINTING OF TREATMENT& INDEX CARD AND FOLDER | EGH/S-NC-F/NS/04/22 | 1 | 4 | 2000000 | <10M | NS | Plan | POST | POST | 2022-04-11 | NA | 2022-05-09 | 2022-06-10 | 2022-06-24 |  |  | Plan |  |  | 2000000 | 06-23-2022 | 2022-06-30 | 2022-07-14 | 2022-10-25
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[5 empty] | 534303924 |  |  | Plan | [9 empty] | Plan |  |  | 23988000
[8 empty] | Actual | [9 empty] | Actual