## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: GENERAL HOSPITAL 1FAKO IJAIYE
BUDGET YEAR: 2022 (NON - PROCURABLE ).
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | PAYMENT OF LOCAL TRANSPORT ALLOWANCE | GHII/NP-F/NS/001/22 | 840000 | Plan | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 840000
Actual
2 | SERVICING OF Y2022 | GHII/NP-F/NS/002/22 | 1000000 | Plan | [5 empty] | 1000000 | [6 empty] | 1000000
Actual
3 | FINANCIAL SUPPORT FOR ADVOCACY ON CHILD ABUSE | GHII/NP-F/NS/003/22 | 800000 | Plan | 66666 | 66666 | 66666 | 66666 | 66666 | 66666 | 66666 | 66666 | 66666 | 66666 | 66666 | 66674 | 800000
Actual
4 | ALLOWANCE FOR SPECIAL DUTIES | GHII/NP-F/NS/004/22 | 1,250,000 | Plan | 104166 | 104166 | 104166 | 104166 | 104166 | 104166 | 104166 | 104166 | 104166 | 104166 | 104166 | 104174 | 1250000
Actual
5 | STIPENDS FOR SPECIAL DUTIES ASSIGNMENT | GHII/NP-F/NS/005/22 | 840,000 | Plan | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | 840000
Actual
6 | ADVOCACY PROGRAMME ON GENDER BASED VIOLENCE | GHII/NP-F/NS/006/22 | 500,000 | Plan | 41666 | 41666 | 41666 | 41666 | 41666 | 41666 | 41666 | 41666 | 41666 | 41666 | 41666 | 41674 | 500000
Actual
7 | ENTERTAINMENT OF VISITORS ON OFFICIAL ASSIGNMENT.(MISCELLANEOUS) | GHII/NP-F/NS/007/22 | 600,000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
8 | PAYMENT OF ELECTRICITY BILLS | GHII/NP-F/NS/008/22 | 32,400,000 | Plan | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 32400000
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: GENERAL HOSPITAL IFAKO IJAIYE
BUDGET YEAR: 2021
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | COWLSO | GHII/G-T/NS/001/21 | Increase productivity and performance | Doctor Apex Administrator | 3 | Plan |  | 830000 |  |  | 830000
Actual
2 | WORKSHOP AND TRAINING FOR ALL STAFF | GHII/G-T/NS/002/21 | Increase productivity and performance | Doctors Nursing Admin Laboratory Accounts |  | Plan |  | 830000 |  |  | 830000
Actual
3 | TRAVEL AND TRANSPORT | GHII/G-T/NS/004/21 | Increase productivity and performance | MEMBERS OF STAFF |  | Plan |  | 840000 |  |  | 840000
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | GHII/NC-F/NS/001/22 | 1 |  | 540000 | <10M | NS | Plan |  | POST | 2022-01-02 | N/A | 2022-07-02 | 2022-04-04 | 2022-11-04 | 18-04-2022 | 2022-02-05 | Plan | N/A | N/A | 540000 | 2022-03-02 | 17/2/2022 | 2022-02-12 | 2022-09-12
[7 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE MAINTENANCE AND REPAIRS | GHII/NC-F/NS/002/22 |  |  | 480000 | <10M | NS | Plan |  | POST |  | N/A | [5 empty] | Plan | N/A | N/A | 480000 | 2022-04-03 | 2022-05-04 | 28/10/2022 | 2022-08-12
[7 empty] | Actual | [9 empty] | Actual
PRINTING OF FOLDER | GHII/NC-F/NS/003/22 |  |  | 4408123 | <10M | NS | Plan |  |  | 2022-02-08 | N/A | 2022-02-15 | 2022-02-22 | 2022-03-01 |  | 2022-03-15 | Plan | N/A | N/A | 4408123 | 2022-03-22 | 2022-04-05 | 2022-11-15 | 2022-11-22
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF LAUNDRY EQUIPMENT | GHII/NC-F/NS/004/22 |  |  | 1000000 | <10M | NS | Plan |  |  | 2022-02-22 | N/A | 2022-03-02 | 2022-03-09 | 2022-03-16 |  | 2022-03-23 | Plan | N/A | N/A | 1000000 | 2022-03-30 | 2022-04-13 | 2022-10-26 | 2022-11-02
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE & REPAIR OF PLANTS & MACHINE/X-RAY MACHINE | GHII/NC-F/NS/005/22 |  |  | 4500000 | <10M | NS | Plan |  |  | 2022-02-01 | N/A | 2022-02-08 | 2022-02-15 | 2022-02-22 |  | 2022-03-01 | Plan | N/A | N/A | 4500000 | 2022-03-15 | 2022-03-22 | 2022-11-01 | 2022-11-15
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: GENERAL HOSPITAL IFAKO IJAIYE
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | CONFERENCE AND SEMINAR | GHII/S-WTC/001/22 | NS |  | 6000000 | POST | Plan
Actual
2 | WORKSHOP AND TRAINING | GHII/S-WTC/002/22 | NS |  | 1000000 | POST | Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: GENERAL HOSPITAL IFAKO IJAIYE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | MOTOR VEHICLE FUEL CONSUMPTION | GHII/G-F/NS/001/22 | 1 | 2 | 360000 | <10M | NS |  | POST | Plan | 2022-01-03 | N/A | 2022-01-17 | 2022-01-31 | 2022-02-07 | N/A | N/A | N/A |  | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-08 | 2022-03-11
Actual
2 | GENERAL UTILITY SERVICE | GHII/G-F/NS/002/22 | 1 |  | 180000 | <10M | NS |  | POST | Plan | 2022-01-17 | N/A | 2022-01-24 | 2022-02-01 | 2022-02-08 | N/A | N/A | N/A |  | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-09 | 2022-03-10
Actual
3 | PROCUREMENT OF STATIONERY ITEMS | GHII/G-F/NS/003/22 | 1 |  | 600000 | <10M | NS |  | POST | Plan | 2022-01-15 | N/A | 2022-01-22 | 2022-02-04 | 2022-02-18 | N/A | N/A | N/A |  | 2022-02-25 | 2022-03-04 | 2022-03-18 | 2022-03-25 | 2022-03-28
Actual
4 | MEDICAL REPORT | GHII/G-F/NS/004/22 | 1 |  | 1456000 | <10M | NS |  | POST | Plan |  | N/A |  |  |  | N/A | N/A | N/A
Actual
5 | DIESEL FUEL FOR PLANT AND HEAVY EQUIPMENT | GHII/G-F/NS/005/22 | 1 |  | 12000000 | <50M | NS |  | POST | Plan | 2022-01-29 | N/A | 2022-02-07 | 2022-02-21 | 2022-02-28 | N/A | N/A | N/A |  | 2022-03-07 | 2022-03-14 | 2022-03-28 | 2022-04-11 | 2022-04-12
Actual
6 | DRUGS (SDRF) | GHII/G-F/NS/006/22 | 1 |  | 172287000 | <200M | NS |  | POST | Plan |  | N/A |  |  |  | N/A | N/A | N/A
Actual
7 | LABORATORY | GHII/G-F/NS/007/22 | 1 |  | 104000000 | <150M | NS |  | POST | Plan | 2022-02-07 | N/A | 2022-02-14 | 2022-02-21 | 2022-02-28 | N/A | N/A | N/A |  | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-25
Actual
8 | PROCUREMENT OF UNIFORMS AND PROTECTIVE OUTFITS | GHII/G-F/NS/008/22 | 1 |  | 2000000 | 4 | NS |  | POST | Plan | 2022-02-04 | N/A | 2022-02-11 | 2022-02-25 | 2022-03-04 | N/A | N/A | N/A |  | 2022-03-11 | 2022-03-18 | 2022-03-31 | 2022-04-14 | 2022-04-15
Actual
9 | PROCUREMENT OF FOODS AND ITEMS | GHII/G-F/NS/009/22 | 1 |  | 850000 | <10M | NS |  | POST | Plan | 2022-02-07 | N/A | 2022-02-14 | 2022-02-28 | 2022-03-07 | N/A | N/A | N/A |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-18 | 2022-04-19
Actual
10 | BLOOD TRANSFUSION SERVICE | GHII/G-F/NS/010/22 | 1 |  | 37350000 | <50M | NS |  | POST | Plan |  | N/A |  |  |  | N/A | N/A | N/A
Actual
11 | ADMISSION PACK | GHII/G-F/NS/011/22 | 1 |  | 1300000 | <10M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
12 | ECG | GHII/G-F/NS/012/22 | 1 |  | 6480000 | <10M | NS |  | POST |  | Plan |  | N/A |  |  |  | N/A | N/A | N/A
Actual
13 | DRESSING PACK | GHII/G-F/NS/013/22 | 1 |  | 9000000 | <10M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
14 | DELIVERY PACK | GHII/G-F/NS/014/22 | 1 |  | 14850000 | <50M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
15 | DELIVERY FEES | GHII/G-F/NS/015/22 | 1 |  | 54000000 | <100M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
16 | THEATRE PROCEDURE | GHII/G-F/NS/016/22 | 1 |  | 101700000 | <200M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
17 | DIET | GHII/G-F/NS/017/22 | 1 |  | 22500000 | <50M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
18 | CLINICAL PRESENTATION | GHII/G-F/NS/018/22 | 1 |  | 1035000 | <10M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
19 | PHYSIOTHERAPHY | GHII/G-F/NS/019/22 | 1 |  | 7646000 | <10M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
20 | EYE CLINIC | GHII/G-F/NS/020/22 | 1 |  | 4000000 | <10M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
21 | DENTAL CLINIC | GHII/G-F/NS/021/22 | 1 |  | 6696000 | <10M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
22 | X-RAY/SCAN(RADIOLOGY) | GHII/G-F/NS/022/22 | 1 |  | 24950000 | <50M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
23 | FOLDER | GHII/G-F/NS/023/22 | 1 |  | 13500000 | <50M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
24 | LAGOS STATE HEALTH SCHEME | GHII/G-F/NS/024/22 | 1 |  | 42750000 | <50M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A
25 | ADMISSION FEES | GHII/G-F/NS/025/22 | 1 |  | 22500000 | <50M | NS |  | POST |  |  |  | N/A |  |  |  | N/A | N/A | N/A

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual