## Non-Proc
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: IBILE OIL AND GAS CORPORATION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Lot No. | Budget Available (=N=) | Approval Threshold | Procurement Method | Plan/Actual | Prior or Post review | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | MISCELLANEOUS | IOGC/NP/NM/001/2022 |  | 3500000 | <10M | National Shopping | Plan | Post | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 291666.6667 | 3500000
Actual
2 | BOARD MEMBERS ALLOWANCES | IOGC/NP/NM/002/2022 |  | 17000000 | <10M | National Shopping | Plan | Post | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 1416666.6667 | 17000000
Actual
3 | SPONSORSHIPS | IOGC/NP/NM/003/2022 |  | 1000000 | <10M | National Shopping | Plan | Post | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 83333.3333 | 1000000
Actual
4 | TRAVEL AND TRANSPORT | IOGC/NP/NM/004/2022 |  | 4140000 | <10M | National Shopping | Plan | Post | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 345000 | 4140000
Actual
5 | GENERAL UTILITY SERVICES | IOGC/NP/NM/005/2022 |  | 5000000 | <10M | National Shopping | Plan | Post | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 5000000
Actual

## Non-Cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2022
S/Nr. | Contract Description | BASIC DATA | [8 empty] | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | Budget Available (=N=) | Approval Threshold | Procurement Method | Plan Vs Actual | Prior or Post review | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | PUBLICITY AND PRESS COVERAGE | IOGC/NC/NCB/001/2022 |  | 2000000 | <10M | National Shopping | Plan | Post | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-21 | 2022-04-28 | 2022-05-05 | Plan |  | 2022-05-26 | 2022-06-16 | 2022-07-14 | 2022-07-21
[7 empty] | Actual | [10 empty] | Actual
2 | JANITORIAL SERVICES | IOGC/NC/NCB/002/2022 |  | 3500000 | <10M | National Shopping | Plan | Post | 2022-02-09 | 2022-02-10 | 2022-02-24 | 2022-03-10 | 2022-03-24 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-19 | Plan |  | 2022-06-02 | 2022-06-23 | 2022-07-21 | 2022-07-28
[7 empty] | Actual | [10 empty] | Actual
3 | BOARD EXPENSES | IOGC/NC/NCB/003/2022 |  | 1500000 | <10M | National Shopping | Plan | Post | 2022-02-09 | 2022-02-10 | 2022-02-24 | 2022-03-10 | 2022-03-24 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-19 | Plan |  | 2022-06-02 | 2022-06-23 | 2022-07-21 | 2022-07-28
[7 empty] | Actual | [10 empty] | Actual
4 | MAINTENANCE AND REPAIR OF GEN SETS | IOGC/NC/NCB/004/2022 |  | 3114981.18 | <10M | National Shopping | Plan | Post | Plan | Post | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | Plan |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28
[7 empty] | Actual |  | Actual | [8 empty] | Actual
5 | MAIINTENANCE OF OFFICE BUILDING | IOGC/NC/NCB/005/2022 |  | 4112050.56 | <10M | National Shopping | Plan | Post | Plan | Post | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | Plan |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28
[7 empty] | Actual |  | Actual | [8 empty] | Actual
6 | MOTOR VEHICLE REPAIR AND MAINTENANCE | IOGC/NC/NCB/006/2022 |  | 2875000 | <10M | National Shopping | Plan | Post | Plan | Post | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | Plan |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28
[7 empty] | Actual |  | Actual | [8 empty] | Actual

## Consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: IBILE OIL AND GAS CORPORATION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  |  | Plan vs. Actual | APPROVAL |  | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lump sum or Time-Based | Estimated Amount in N '000 | Approval Threshold | Prior/ Post Review |  | Mr. Governor's approval. | Register Approval with PPA | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
1 | ENLIGHTENMENT AND CAMPAIGN | IOGC/S-C/CQS/001/2022 |  | Lump sum | 2000000 | <10M | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-03 | 2022-03-10 | 2022-03-24 | 2022-04-07 | 2022-04-21 | 2022-05-12 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-07-14 |  | 2022-07-21 | 2022-08-04 | 2022-08-18 | 2022-09-01 | 2022-09-15
Actual
2 | AUDIT EXPENSES | IOGC/S-C/CQS/002/2022 |  | Lump Sum | 4600000 | <10M | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-03 | 2022-03-10 | 2022-03-24 | 2022-04-07 | 2022-04-21 | 2022-05-12 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-07-14 |  | 2022-07-21 | 2022-08-04 | 2022-08-18 | 2022-09-01 | 2022-09-15
Actual
3 | SPECIALISED TRAINING | IOGC/S-C/CQS/003/2022 |  | Lump Sum | 4700000 | <10M | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-03 | 2022-03-10 | 2022-03-24 | 2022-04-07 | 2022-04-21 | 2022-05-12 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-07-14 |  | 2022-07-21 | 2022-08-04 | 2022-08-18 | 2022-09-01 | 2022-09-15
Actual
4 | ANNUAL RETREAT | IOGC/S-C/CQS/004/2022 |  | Lump Sum | 8800000 | <10M | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-03 | 2022-03-10 | 2022-03-24 | 2022-04-07 | 2022-04-21 | 2022-05-12 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-07-14 |  | 2022-07-21 | 2022-08-04 | 2022-08-18 | 2022-09-01 | 2022-09-15
Actual
5 | CONFERENCES AND SEMINARS | IOGC/S-C/CQS/005/2022 |  | Lump Sum | 4000000 | <10M | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-03 | 2022-03-10 | 2022-03-24 | 2022-04-07 | 2022-04-21 | 2022-05-12 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-07-14 |  | 2022-07-21 | 2022-08-04 | 2022-08-18 | 2022-09-01 | 2022-09-15
Actual

## Goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: IBILE OIL AND GAS CORPORATION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | APPROVAL |  |  |  | BID EVALUATION (DATES) |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | MOTOR VEHICLE FUEL CONSUMPTION | IOGC/G/NS/001/2022 |  |  | 4025000 | <10M | National Shopping | Post | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual
2 | STATIONERY | IOGC/G/NS/002/2022 |  |  | 3400000 | <10M | National Shopping | Post | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual
3 | UNIFORMS AND PROTECTIVE OUTFIT | IOGC/G/NS/003/2022 |  |  | 1000000 | <10M | National Shopping | Post | Post | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual
4 | ICT CONSUMABLES | IOGC/G/NS/004/2022 |  |  | 14749445.43 | <50M | National Shopping | Prior | Prior | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual
5 | PURCHASE OF 30NOS. H9WO6EA HP ELITEBOOK FOLIO 1040 G6 LAPTOPS @ N500,000 EACH - | IOGC/G/NS/005/2022 |  |  | 15000000 | <50M | National Shopping | Prior | Prior | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual
6 | OFFICE EQUIPMENT AND IT | IOGC/G/NS/006/2022 |  |  | 15000000 | <50M | National Shopping | Prior | Prior | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual
7 | PURCHASE OF 6NOS. GAS DELIVERY TRUCKS | IOGC/G/NCB/007/2022 |  |  | 275742000 | <500M | National Shopping | Prior | Prior | Plan | 2022-02-01 | 2022-02-03 | 2022-02-17 | 2022-03-10 | 2022-03-24 | 2022-04-07 |  | 2022-04-14 | 2022-04-28 | 2022-05-12 | 2022-06-02 | 2022-06-08
Actual

## Works
PROCUREMENT PLAN FOR WORKS
AGENCY: IBILE OIL AND GAS CORPORATION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | APPROVAL |  | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | CONSTRUCTION OF 2NOS. RETAIL FILLING STATIONS | IOGC/W/NCB/001/2022 |  | 430000000 | <500M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
4 | RENOVATION AND PARTITIONING | IOGC/W/NCB/004/2022 |  | 30000000 | <50M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
6 | CONSTRUCTION OF 17NOS. 20 MT GAS PLANTS | IOGC/W/NCB/006/2022 |  | 4080563360 | >500M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
7 | CONSTRUCTION OF 10NOS. CO-LOCATED GAS STATIONS FOR AUTO GAS | IOGC/W/NCB/0071/2022 |  | 797050041 | >500M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
8 | CONSTRUCTION OF 5NOS. STAND-ALONE GAS STATIONS | IOGC/W/NCB/008/2022 |  | 1617485000 | >500M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
9 | CONSTRUCTION OF 1NO. 240MT GAS STORAGE FACILITY | IOGC/W/NCB/009/2022 |  | 505154793 | >500M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
10 | CONSTRUCTION OF 4NOS. AUTO GAS CONVERSION CENTRES/WORKSHOPS | IOGC/W/NCB/010/2022 |  | 2788791528 | >500M | National Competitive Bidding | BOQ | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
12 | WHITE PRODUCT OFFTAKE FROM NIGERIAN NATIONAL PETROLEUM CORPORATION (NNPC) - REVOLVING FUND | IOGC/W/NCB/012/2022 |  | 904000000 | >500M | National Competitive Bidding | Lump Sum | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
13 | LPG OFFTAKE FROM NIGERIA LIQUIFIED NATURAL GAS LTD (NLNG) | IOGC/W/NCB/013/2022 |  | 622690020 | >500M | National Competitive Bidding | Lump Sum | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual
14 | EXPANSION OF LUBRICANTS BUSINESS | IOGC/W/NCB/014/2022 |  | 100000000 | <500M | National Competitive Bidding | Lump Sum | Pre | Plan | Prior | 7th Feb 2022 | 10th Feb 2022 | 2022-03-03 | 2022-03-17 | 2022-03-31 | 2022-04-28 | 2022-05-12 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-07-07 | 2022-07-28 | 2022-08-04
Actual