## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
| MINISTRY/ AGENCY: |  | ISOLO GENERAL HOSPITAL
| BUDGET YEAR: |  | 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | DIET-payment for cooking ingredients for in-patients,doctors on call and officers on night dutiies. | ISGH/NP/NM/001/22 | 2,261,347.91 | Plan | 188445.65 | 188445.65 | 188445.65 | 188,445.65 | 188445.65 | 188445.65 | 188445.65 | 188,445.65 | 188445.65 | 188445.65 | 188445.65 | 188445.65 | 2,261,347.91
Actual
2 | Accomodation(payment of cleaning outfits.zealand mgt consultancy ltd,purchase of gowns. | ISGH/NP/NM/002/22 | 4,571,347.83 | Plan | 380,945.65 | 380945.65 | 380945.65 | 380,945.65 | 380945.65 | 380,945.65 | 380,945.65 | 380,945.65 | 380945.65 | 380945.65 | 380945.65 | 380945.65 | 4,571,347.83
Actual
3 | miscellenous(photocopies of official documents,entertainment and other needs in the hospital) | ISGH/NP/NM/003/22 | 679,120 | Plan | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 56593.33 | 679,120.00
Actual
4 |  |  |  | Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: ISOLO GENERAL HOSPITAL
BUDGET - 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | committee of wives of lagos state officers{COWLSO} | ISGH/S-WTC/001/22 |  | 5 | 3 days | Plan | lagos | 150000 | 120000 | 120000 | 1950000
Actual
2 | Association of National Accountants of Nigeria (ANAN) Annual conference | ISGH/S-WTC/002/22 | National building and sustainable; challenges and prospects | 1 | 5 days | Plan | Abuja | 190000 | 200000 | 390000 | 780000
Actual
3 | chartered institute of purchase and supply mgt of nig mandatory programe | ISGH/S-WTC/003/22 | Aligning the strategic public procuerment and supply chain mgt practice with good corporate government towards attaining the next level of government. | 2 | 3 days | Plan | lagos | 140000 | 130000 | 130000 | 800000
Actual
4 | chartered institute of purchase and supply mgt of nigmembers proficiency | ISGH/S-WTC/004/22 | Procurement planning for works, goods and services in MDAs and private sector. | 1 | 3 days | Plan | Abuja | 150000 | 1`50,000 | 170000 | 470000
Actual
5 | charterd institute of personel management | ISGH/S-WTC/005/22 |  | 1 | 3 days | Plan | lagos | 195000 | 205000 | 200000 | 600000
Actual
6 | Annual Nurses conference | ISGH/S-WTC/006/22 |  | 1 | 5 days | Plan | lagos | 100000 | 120000 | 180000 | 400000
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2022 NON-CONSULTING SERVICES
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance/repair of office building | ISGH/S-NC-F/SS/001/22 |  |  | 380000 | <10m | SS | Plan | Post | post | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-05-04 | 2022-04-11 | N/A | N/A | Plan | 2022-04-25 | 2022-04-27 | N/A | 2022-05-09 | N/A | 2022-05-02 | 2022-07-04
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Motor vehicle repair | ISGH/S-NC-F/SS/002/22 |  |  | 620000 | <10m | SS | Plan | post | post | 2022-03-21 | 2022-03-28 | 2022-04-18 | 2022-05-18 | 2022-05-14 | N/A | N/A | Plan | 2022-05-02 | 2022-05-04 | N/A | 2022-05-16 | N/A | 2022-05-30 | 2022-06-07
[7 empty] | Actual | [9 empty] | Actual
Maintenance of computers and official laptops | ISGH/S-NC-F/SS/003/22 |  |  | 5000000 | <10m | SS | Plan | post | post | 2022-05-03 | 2022-04-17 | 2022-06-21 | 2022-04-07 | 2022-05-21 | N/A | N/A | Plan | 2022-06-13 | 2022-06-16 | N/A | 2022-05-23 | N/A | 2022-06-13 | 2022-06-27
[7 empty] | Actual | [9 empty] | Actual
Special duties(unbudgeted expenses)-staff welare | ISGH/S-NC-F/SS/004/22 |  |  | 4735003 | <10m | SS | Plan | post | post | 2022-07-18 | 2022-07-25 | 2022-02-08 | 2022-08-08 | 2022-08-22 | N/A | N/A | Plan | 2022-09-26 | 2022-09-28 | N/A | 2022-10-10 | N/A | 2022-10-17 | 2022-10-24
[7 empty] | Actual | [9 empty] | Actual
planning unit expenses(designed by budget officers. | ISGH/S-NC-F/SS/005/22 |  |  | 2000000 | <10m | SS | Plan | post | post | 2022-05-03 | 2022-04-17 | 2022-06-21 | 2022-03-07 | 2022-05-21 | N/A | N/A | Plan | 2022-06-13 | 2022-06-16 | N/A | 2022-05-23 | N/A | 2022-05-13 | 2022-06-27
[7 empty] | Actual | [9 empty] | Actual
Maintenance of house officers quarter | ISGH/S-NC-F/SS/006/22 |  |  | 4000000 | <10m | SS | Plan | Post | post | 2022-07-18 | 2022-07-25 | 2022-02-08 | 2022-08-08 | 2022-08-22 | N/A | N/A | Plan | 2022-09-26 | 2022-09-28 |  | 2022-10-10 |  | 2022-10-17 | 2022-10-24
[7 empty] | Actual | [9 empty] | Actual |  |  | N/A |  | N/A
Medical director's Expenses | ISGH/S-NC-F/SS/007/22 |  |  | 2500000 | <10m | SS | Plan | Post | post | 2022-05-03 | 2022-04-17 | 2022-06-21 | 2022-08-07 | 2022-08-21 | N/A | N/A | Plan | 2022-06-13 | 2022-06-16 |  | 2022-10-23 |  | 2022-10-13 | 2022-10-27
[7 empty] | Actual | [9 empty] | Actual |  |  | N/A |  | N/A
Eye(servicing of eye surgical machine and cosumables) | ISGH/S-NC-F/SS/008/22 |  |  | 1161348 | <10m | SS | Plan | Post |  | 2022-05-03 | 2022-04-17 | 2022-06-21 | 2022-08-07 | 2022-08-21 | N/A | N/A | Plan | 2022-06-13 | 2022-06-16 | N/A | 2022-10-23 |  | 2022-10-13 | 2022-10-27
[7 empty] | Actual |  | post | [7 empty] | Actual |  |  |  |  | N/A
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
|  | 5 |  |  |  |  | Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: ISOLO GENERAL HOSPITAL
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of fuel for plant set for gen and heavy equipment/motor vehicle fuel. | ISGH/G-F/NS/001/22 |  |  | 20380880 | <50m | NS | post | Prior | Plan | 2022-03-07 | 14TH MAR 22 | 21ST MAR 22 | 4TH APR 22 | 11TH APRI 22 | N/A | 25TH APRI 22 | 26TH APRI 22 | N/A | N/A | N/A | N/A | 2ND MAY 22 | 9TH MAY 22
Actual
2 | laboratory[procurement of hormonal assey,investigation,reagents,micro biology reagents) | ISGH/G-F/NS/002/22 |  |  | 5799669.02 | <10m | NS | post | post | Plan | 2022-03-21 | 28TH MAR 22 | 4TH APRI 22 | 18TH APRI 22 | 4TH APRI 22 | N/A | 2ND MAY 22 | 3RD MAY 22 | N/S | N/A | N/A | N/A | 23RD MAY 22 | 30TH MAY 22
Actual
3 | procurement of stationery | ISGH/G-F/NS/OO3/22 |  |  | 520000 | <10m | NS | post | post | Plan | 4TH APRI 22 | 11TH APRI 22 | 18TH APRI 22 | 2ND MAY 22 | 16TH MAY 22 | N/A | 25TH APRI 22 | 14TH JUN 22 | N/S | N/A | N/A | N/A | 6TH JUN 22 | 13TH JUN 22
Actual
4 | procurement of cooking& medical gas(general utility service) | ISGH/G-F/NS/004/22 |  |  | 440000 | <10m | NS | post | post | Plan | 18TH JUL 22 | 25TH JUL 22 | 4TH JUL 22 | 18TH JUL 22 | 30TH JUL 22 | N/A | 22ND AUG 22 | 23ND AUG 22 | N/S | N/A | N/A | N/A | 19TH OCT 22 | 26TH SEPT 22
Actual
5 | operation(procurement of oxygen gas and surgical gloves) | ISGH/G-F/NS/005/22 |  |  | 4946557.46 | <10m | NS | post | post | Plan | 18TH JUL 22 | 25TH JUL 22 | 4TH JUL 22 | 18TH JUL 22 | 30TH JUL 22 | N/A | 22ND AUG 22 | 23RD AUG 22 | N/S | N/A | N/A | N/A | 19TH OCT 22 | 26TH OCT 22
Actual
6 | dental(procurement of dental consumables) | ISGH/G-F/NS/006/22 |  |  | 1002934.72 | <10m | NS | post | post | Plan | 18TH JUL 22 | 25TH JUL 22 | 4TH JUL 22 | 18TH JUL 22 | 30TH JUL 22 | N/A | 2ND MAY 22 | 23RD AUG 22 | N/S | N/S | N/S | N/S | 19TH OCT 22 | 30TH MAY 22
Actual
7 | Delivery(procurement for delivery packs,admission pack and c/s pack) | ISGH/G-F/NS/007/22 |  |  | 4216359.27 | <10m | NS | post | post | Plan | 18TH JUL 22 | 11TH APRI 22 | 4TH JUL 22 | 18TH JUL 22 | 30TH JUL 22 | N/A | 2ND MAY 22 | 23RD AUG 22 | N/S | N/S | N/S | N/S | 23RD MAY 22 | 9TH MAY 22
Actual
8 | Physiotherapy(procurement of infared bulbs,payment for supply of bandages) | ISGH/G-F/NS/008/22 |  |  | 501348.7 | <10m | NS | post | post | Plan | 18TH JUL 22 | 25TH JUL 22 | 4TH JUL 22 | 18TH JUL 22 | 30TH JUL 22 | N/A | 2ND MAY 22 | 26TH APRI 22 | N/S | N/S | N/S | N/S | 19TH OCT 22 | 30TH MAY 22
Actual
9 | Medical records(procurement of ECG paper) | ISGH/G-F/NS/009/22 |  |  | 348520.61 | <10m | NS | post | post | Plan | 18TH JUL 22 | 11TH APRI 22 | 4TH JUL 22 | 18TH JUL 22 | 30TH JUL 22 | N/A | 25TH APRI 22 | 3RD MAY 22 | N/S | N/S | N/S | N/S | 23RD MAY 22 | 9TH MAY 22
Actual
10 | Radiology(procurement of radiology film and radiology gel) | ISGH/G-F/NS/0010/22 |  |  | 1839977.88 | <10m | NS | post | post | Plan | 18TH JUL 22 | 11TH APRI 22 | 21ST MAR 22 | 18TH APRI 22 | 30TH JUL 22 | N/A | 25TH APRI 22 | 3RD MAY 22 | N/S | N/S | N/S | N/S | 19TH OCT 22 | 9TH MAY 22
Actual
11 | Surgery(procurement for supply of vicryl and consumables) |  |  |  | 1271347.96 | <10m | NS | Post | post |  | 4TH APRI 22 | 11TH APRI 22 | 21ST MAR 22 | 18TH APRI 22 | 16TH MAY 22 | N/A | 2ND MAY 22 | 3RD MAY 22 | N/S | N/S | N/S | N/S | 19TH OCT 22 | 13TH JUN 22
12 | Medicine(procurement of check test script) |  |  |  | 358348.09 |  | NS | post | post |  | 4TH APRI 22 | 11TH APRI 22 | 4TH JUL 22 | 18TH APRI 22 | 16TH MAY 22 |  | 2ND MAY 22 | 26TH APRI 22 | N/S | N/S | N/S | N/S | 23RD MAY 22 | 30TH MAY 22
13 | ENT(procurement of wooden tongue depressor) |  |  |  | 295892.54 | <10m | NS | post | post |  | 4TH APRI 22 | 11TH APRI 22 | 4TH JUL 22 | 18TH APRI 22 | 16TH MAY 22 | N/A | 25TH APRI 22 | 26TH APRI 22 | N/S | N/S | N/S | N/S | 23RD MAY 22 | 13TH JUN 22

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual