## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | General Manager, Deputy G.M (OPS), Deputy GM (SS) | LMB/S-WTC/SS/001/21 | Management Development programme for senior executive | 3 | 4Days |  | Abuja | 450000 | 450000 | 900000 | 1800000
2 | Debuty Director CA & HR | LMB/S-WTC/SS/002/21 | Leadership and team Building for government Officals GL 15 | 1 | 4Days | Plan | Abuja | 100000 | 150000 | 200000 | 450000
Actual
3 | Asst Dir. Accounting Officer & Chief Exe. Audit Officer | LMB/S-WTC/SS/003/21 | ANAN MCPD | 2 | 4 Days | Plan | Akure | 220000 | 200000 | 310000 | 730000
Actual
4 | Asst. Dir. Procurement Officer | LMB/S-WTC/SS/004/21 | Mandatory Proficiency Programe in Supply Chain Management | 1 | 4 Days | Plan | Abuja | 100000 | 100000 | 200000 | 400000
Actual
5 | Asst. Dir.Communication Pubic Affairs | LMB/S-WTC/SS/005/21 | Managing Communication Intricacies in human capital Dev. And Sustainability | 1 | 4 Days | Plan | Jos | 100000 | 100000 | 200000 | 400000
Actual
6 | Company Secritary (Consolidated) | LMB/S-WTC/SS/006/21 | Performance and Productivity improvement for Legal Officers | 1 | 3Days | Plan | Abuja | 80000 | 90000 | 167000 | 337000
Actual
8 | Chief Exc Satistician | LMB/S-WTC/SS/008/21 | International Statistical Conference | 2 | 3Days | Plan | Lagos | 115000 | 24000 | 26000 | 150000
Actual
7 | COWLSO | LMB/S-WTC/SS/009/21 | The role of women in achieveing the THEME Goal | 5 | 5Days | Plan | EkoHotel Victoria Island | 250000 | 55000 | 180000 | 485000
Actual
8 | GL01-03 | LMB/S-WTC/SS/010/21 | Work ethics and organisational Productivity GL01-03 | 10 | 1Days | Plan | Lagos | 200000 | 20000 | 50000 | 270000
Actual
9 | GL 04-06 | LMB/S-WTC/SS/011/21 | Work ethics and organisational Productivity GL04-06 | 10 | 3Days | Plan | Lagos | 400000 | 96000 | 60000 | 556000
Actual
10 | GL 08-09 | LMB/S-WTC/SS/012/21 | Work ethics and organisational Productivity GL 08-09 | 12 | 3Days | Plan | Lagos | 672000 | 120000 | 120000 | 912000
Actual
11 | GL10-12 | LMB/S-WTC/SS/013/21 | Essential Skills for HR professional GL10-12 | 5 | 2 Days | Plan | Lagos | 375000 | 75000 | 50000 | 500000
Actual
|  |  | GRAND TOTAL | [7 empty] | 7000000

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: LAGOS MORTGAGE BOARD: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Facility Expenses: ( Satakehplder Forum and Safety) | LMB/NP/NM/001/21 | 1 | N/A | 30000000 | >50 | IC | Plan | N/A | POST | 31/4/2022 | 26/3/2022 | 6/4/2022 | 24/4/2022 | N/A | 8/5/2022 | N/A | Plan | 10/6/2022 | 12/6/2022 |  | 10/7/2022 | 24/7/2022 | 7/8/2022 | 10/8/2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Office Building: Repairs of office Furnitures at Customer Service Point, General office Maintenance for thev year, Repairs & Maintenance of photocopy Machines, Servicing of AC, Quarterly Funmigation of Office Building - Non consulting | LMB/NP/NM/001/21 | 1 | N/A | 4320000 | >10 | IC | Plan | N/A | POST | 31/4/2022 | 26/3/2022 | 6/4/2022 | 24/4/2022 | N/A | 8/5/2022 | N/A | Plan | 10/6/2022 | 12/6/2022 |  | 10/7/2022 | 24/7/2022 | 7/8/2022 | 10/8/2022
[7 empty] | Actual | [9 empty] | Actual
34320000

## Consultancy 2
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS MORTGAGE BOARD
| BUDGET YEAR: 2021 |  | 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
| Technology Dissemination |  |  |  | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Audit Exercise | LMB/CS/IC/001/2022 | IC | Lumpsum | 3300 | POST | Plan | N/A | N/A | N/A | N/A | N/A | 6/3/2022 | 27/3/2022 | N/A | N/A | N/A | 24/3/2022 | N/A | 29/3/2022 | 1/5/2022 | NIL | 8/5/2022 | 22/5/2022 | N/A | 5/6/2022 | 19/6/2022 | NIL
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS MORTGAGE BOARD
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Stationaries : Files,700*1,500=1,050,000, Cartons of A4 Papers13,500*150=2,025,000, Cartons of Official Evelop4,500*20=90,000,Minuting Sheet@10,500*30=315,000, Giant Staple Pin@1,400*20=28,000,Giant Stapler Pin@13,500*5=67,500,seal, biro, Stamp ink Pad, Colour Legal Foolscap Paper, White Legal Foolscap etc. |  | LMB/G-F/NS/001/21 | 1 | N/A | 4320000 | <10M | N.S. | Post | POST | Plan | 2/3/2021 | 9/3/2021 | 16/3/2021 | 23/3/2021 | N/A | N/A | 22/4/2021 | 24/4/2021 | NIL | 8/5/2021 | 22/5/2021 | NIL | 5/6/2021 | 8/6/2021
Actual
2 | Fueling:Procurement of Fuel for 2 Nissan Buses @165*9,097Ltrs=1,537,500, Purchase of Fuel for 2 Hilux Jeep@ 165*6,159Ltrs=1,016,250 , Purchase of Fuel for Toyota Corolla Pool Car @165* Ltrs.Gac Truck@165*6,159=1,016,250 |  | LMB/G/NS-F/002/21 | 1 | N/A | 3570000 | <10M | N.S. | Post | POST | Plan | 4/3/2021 | 11/3/2021 | 18/3/2021 | 25/3/2021 | N/A | N/A | 24/4/2021 | 28/4/2021 | NIL | 5/5/2021 | 19/5/2021 | NIL | 2/6/2021 | 4/6/2021
Actual
3 | Purchase of Office Furniture Equipment and Rebranding of Customer Care Room |  | LMB/G/NS-F/003/20 | 1 | N/A | 29500000 | <50M | N.S. | Post | POST | Plan | 2/3/2021 | 9/3/2021 | 16/3/2021 | 23/3/2021 | N/A | N/A | 22/4/2021 | 24/4/2021 | NIL | 8/5/2021 | 22/5/2021 | NIL | 5/6/2021 | 8/6/2021
Actual
4 | Purchase of Fire Extinguishers for (5) schemess of LMB |  | LMB/G/NS-F/003/20 | 1 | N/A | 113000000 | <50M | N.S. | Post | POST | Plan | 2/3/2021 | 9/3/2021 | 16/3/2021 | 23/3/2021 | N/A | N/A | 22/4/2021 | 24/4/2021 | NIL | 8/5/2021 | 22/5/2021 | NIL | 5/6/2021 | 8/6/2021
Actual
5 | Procurement of Laptop Computers for Management Staff:Purchase of 4 Laptops480*5=2,400,000, Desk Top Computer 380,000*4=1,520,000Smart Tv@356,000*2=712,000Cabinet 325,000*8=2,600,000, PA Syetem=68,000, |  | LMB/G/NS-F/004/21 | 1 | N/A | 7500000 | <10M | N.S. | Post | POST | Plan | 3/3/2021 | 10/3/2021 | 17/3/2021 | 24/3/2021 | N/A | N/A | 23/4/2021 | 27/4/2021 | NIL | 4/5/2021 | 18/5/2021 | NIL | 29/9/2021 | 2/6/2021
Actual
6 | Mianagement Information System:Procurement of HP 80A Toner @35,000*30=1,050,000, Purchase of 4 in 1 Colour Black Ink for General office@75,000*8=600,,000,Colour Green Ink for General office@75,000*8=600,000,Purchase of 4 in 1 Yellow ink@ 75,00*8=600,000, purchase 4 in 1Colour Red ink@ 75,000*8 =600,000and Maintenance of MIS = 550,000, |  | LMB/G/NS-F/006/21 | 1 | N/A | 4000000 | <10M | N.S. | Post | POST | Plan | 2/3/2021 | 9/3/2021 | 16/3/2021 | 23/3/2021 | N/A | N/A | 22/4/2021 | 24/4/2021 | NIL | 8/5/2021 | 22/5/2021 | NIL | 5/6/2021 | 8/6/2021
Actual
|  | GRAND TOTAL |  |  |  | 161890000

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Non Proc Item 2
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS MORTGAGE BOARD
BUDGET YEAR: 2022
Non Procurable Items
Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
Payment for Car Park Usage for Staff and Customers |  | 480,000.00 | Plan | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 38000 | 37000 | 480000
Actual
Monthly Running cost for Staff & corp Members | LMB/S-NC-F/003/21 | 4200000 | Plan | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 4200000
Actual
Allowance for transport for official assignment within and outside Lagos | LMB/S-NC-F/004/21 | 1,800,000.00 | Plan | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 1800000
Actual
Miscellaneous (Payment of Adhoc Staff410,000*12=4,920,000 , Journal Annual Subscription, Key Handing over ceremony@500,000, Ministerial Press briefing Twice Yearly=400,000, Servicing of mgt, General Meeting with Allotee@615,000, Cleaning Materials). | LMB/S-NC-F/005/21 | 6,480,000.00 | Plan |  |  | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 6,480,000.00
Actual
General Unility Services (DSTV Subscription@16715*12=200,580, Gotv Subscription,Recharge Card for Customer Care line@30,000*12=360,000, Waste Disposal@10,000*12=120,000, Other Expenses 982,520,Refilling of water Dispenser@24,000*12=288,000, Payment of Electricity Bill@350,000*12=4,200,000,News Paper@20,000*12=240,000) | LMB/S-NC-F/006/21 | 6,480,000.00 |  |  |  | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 648000 | 6,480,000.00
Actual
Lagos HOMS Mortgage and arbtration | LMB/S-NC-F/007/21 | 12,000,000.00 | Plan | MARCH: 3000000; JUNE: 3000000; SEPTEMBER: 3000000; DECEMBER: 3000000 | 12000000
Actual
Office Rent | LMB/S-NC-F/008/21 | 11,500,000.00 | Plan | MARCH: 11500000 | 11500000
Actual
Service Charter Expenses: | LMB/S-NC-F/009/21 | 1000000 | Plan | JUNE: 500000; OCTOBER: 500000 | 1000000
Actual
Planning,Research and Satistics (Provision for Annual Summit for Planners, budget Preparation) | LMB/S-NC-F/011/21 | 500000 | Plan | JULY: 500000 | 500000
Actual
Publicity and Press Coverage( Quarterly Payment for Documentary, Adertisment Coverage and Publicity on Rent- To- Own programme) | LMB/S-NC-F/012/21 | 4,800,000.00 | Plan | MARCH: 1200000; MAY: 1200000; JUNE: 1200000; JULY: 1200000 | 4800000
Actual
Maintenance of Portal Content and Websites Administrative fees | LMB/S-NC-F/013/21 | 7000000 | Plan | APRIL: 7000000 | 7000000
Actual
Provision of Bandwidth increase service of Rent To Own | LMB/S-NC-F/014/21 | 8000000 | Plan | APRIL: 8000000 | 8000000
Actual
Motor Vehicle Repair and Maintenance: (Quarterly Provision for General servicing of official Vehicles, Renewal of Vehicle Licenses, Purchase of Vechicle Tyres, Maintenance of Vehicle AC & Diagnostic service, Brake Pads, Change of Shock Absorbers) | LMB/S-NC-F/015/21 | 4350000 | Plan | MARCH: 1087500; JUNE: 1087500; SEPTEMBER: 1087500; DECEMBER: 1087500 | 4350000
Actual
Procurement Unit ( Purchase of Material Inks and Paper) | LMB/S-NC-F/015/21 | 300000 | Plan | SEPTEMBER: 300000 | 300000
Actual
Service Charge on Rent: (Quarterly Provision for General servicing, Maintenance) | LMB/S-NC-F/015/21 | 5700000 | Plan | MARCH: 1425000; JUNE: 1425000; SEPTEMBER: 1425000; DECEMBER: 1425000 | 5700000
Actual
Debt Recovery: | LMB/S-NC-F/015/21 | 3300000 | Plan | MARCH: 825000; JUNE: 825000; SEPTEMBER: 825000; DECEMBER: 825000 | 3300000
Actual
Annual Retreat: | LMB/S-NC-F/015/21 | 2980243 | Plan | JUNE: 2980243 | 2980243
Actual
GRAND TOTAL |  | 82190243 | [13 empty] | 80870243