## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/AGENCY: LAGOS STATE VALUATION OFFICE
Yea 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | AWARDS AND REWARDS | LSVO/NP/NM/001/22 | 3, 000,000 | Plan |  |  | 3000000
Actual
2 | MISCELLENANIOUS ( To cater for payments of IT Students/Temporary Staffs) | LSVO/NP/NM/002/22 | 2500000 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
Actual
3 | TRAVEL AND TRANSPORT | LSVO/NP/NM/003/22 | 550000 | Plan | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000 | 55000
Actual
4 | GENERAL UTILITY SERVICE | LSVO/NP/NM/004/22 | 250000 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
Actual
5 | Site Visitation Allowance for 25 Valuation Officers/Staff @v #20000 x 6 months. | LAVO/NP/NM/005/22 | 9930000 | Plan |  |  |  | 566666.67 | 566666.67 | 566666.67 | 566666.67 | 566666.67 | 566666.67
Actual
6 | Engagement of 30 Temporary Staff s @ #60,000 x6 months. | LSVO/NP/NM/006/22 | 35748000 | Plan |  |  |  | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000
Actual
7 | Engagement of 8 Temporary data processing and collation Staff s @ #60,000 x6 months. | LSVO/NP/NM/007/22 | 9532800 | Plan |  |  |  | 480000 | 480000 | 480000 | 480000 | 480000 | 480000
Actual
8 | Lagos State Fixed Assets Management Policy. | LSVO/NP/NM/0008/22 | 50000000 | Plan |  |  |  | 50000000
Actual
9 | Updating of Assets Register | LSVO/NS/NM/009/22 | 41645352 | Plan |  |  |  |  | 41645352
Actual
10 | External Study, Tour to similar Agencies/Offices in order clinmes by 12 Officers from various MDA's (LASVO, LAHA. Min of Local Government, Min 0f Establisment). | LASVO/NS/NM/010/22 | 70000000 | Plan | [6 empty] | 70000000
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE VALUATION OFFICE LASVO
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | NIESV | PPA/S-WTC/SS/001/22 |  |  |  | Plan | ABUJA
Actual
2 | CIPM | PPA/S-WTS/SS/002/22 |  |  |  | Plan | ABUJA
Actual
3 | ANAN | PPA/S-WTC/SS/003/22 |  |  |  | Plan | ABUJA
Actual
4 | NITAD | PPA/S-WTC/SS/004/22 |  |  |  | Plan | ABUJA
Actual
5 | ICAN | PPA/S-WTC/SS/005/22 |  |  |  | Plan | ABUJA
Actual
6 | CIPMNS | PPA/S-WTC/SS/006/22 |  |  |  | Plan | ABUJA
Actual
7 | COREN/NSE | PPA/S-WTC/SS/007/22 |  |  |  | Plan | ABUJA
Actual
8 | NSA | PPA/S-WTC |  |  |  | Plan | ABUJA
Actual
9 | ICAD | PPA/S-WTC/SS/009/22 |  |  |  | Plan | LAGOS
Actual
10 | NIPR | PPA/S-WTC/SS/010/22 |  |  |  | Plan | LAGOS
Actual
11
12
13
14
15
16

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
YEAR: 2022 | [10 empty] | LAGOS STATE VALUATION OFFICE LASVO
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Aprroval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature(4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Maintenance and repairs of Office Equipment. | LSVO/S-NC/NS/001/22 |  | various | 2350000 | <10 M | NS | Plan | POST | POST | 2022-01-01 | 2022-01-14 | 2022-01-21 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | Plan | 2022-03-10 | 2022-03-12 | 2350000 | 2022-03-26 | 2022-04-08 | 2022-04-17 | 2022-04-18
[7 empty] | Actual | [9 empty] | Actual
Maintenance and repairs of Office Equipment | LSVO/S-NC/NS/002/22 |  | various | 3000000 | <10 M | NS | Plan | POST | POST | 2022-01-01 | 2022-01-14 | 2022-01-21 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | Plan | 2022-03-10 | 2022-03-12 | 3000000 | 2022-03-26 | 2022-04-08 | 2022-04-17 | 2022-04-18
[7 empty] | Actual | [9 empty] | Actual
Motor Vehicle Repairs and Maintenance to cater for 4 Vehicles and 2 Motor Cycles. | LSVO/S-NC-F/NS/003/22 |  | various | 3400000 | <10 M | NS | Plan | POST | POST | 2022-01-01 | 2022-01-07 | 2022-01-14 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | Plan | 2022-02-28 | 2022-03-02 | 3400000 | 2022-03-16 | 2022-03-30 | 2022-04-13 | 2022-04-14
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [8 empty] | 2019-03-26 | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:LAGOS STATE VALUATION OFFICE
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Engagement of 12 Lead consultants and Valuation Firms ( For valuation of Fixed Asset) @ =N=20,283,182 each. | LSVO/S-C/QCBS/01/2022 | QCBS | TIME BASE | 243398178 | PRIOR | Plan | 1 JAN 22 | 7 JAN 22 | 14 JAN 22 | 23 JAN 22 | 6 FEB 22 | 13 FEB 22 | 27 FEB 22 | 4 MAR 22 | 11 MAR 22 | 18 MAR 22 | 25 MAR 22 | 1 APR 22 | 8 APR 22 | 10 APR 22 | 243398178 | 17 APR 22 | 27 APR 22 | 8 MAY 22 | 15 MAY 22 | 22 MAY 22 | 243,398,178.
Actual
2 | Bar Coding,Asset tagging and data capture using digitized oracle capture.Bar Coding,Asset tagging and data capture using digitized oracle capture. | LSVO/S-C/QCBS/02/2022 | QCBS | TIME BASE | 220000000 | PRIOR | Plan | 1 JAN 22 | 7 JAN 22 | 14 JAN 22 | 28 JAN 22 | 3 FEB 22 | 10 FEB 22 | 24 FEB 22 | 3 MAR 22 | 10 MAR 22 | 17 MAR 22 | 24 MAR 22 | 31 MAR 22 | 4 APR 22 | 9 APR 22 | 220000000 | 16 APR 22 | 23 APR 22 | 7 MAY 22 | 12 MAY 22 | 19 MAY 22 | 220,000,000.
Actual
Plan
Actual
Plan
Actual
5 | [6 empty] | Plan
Actual
6
6 | [6 empty] | Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
| MINISTRY/AGENCY: |  | LAGOS STATE VALUATION OFFICE.
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description |  | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  |  | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[13 empty] | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Computer /Management Information System. 10th Generation Intel Core 15, 8GRAM 256SSD, Wifi Win10Ms Office Antivirus 15.6,Win10 Procurement of Laptop. |  | LSVO/G/NS/001/22 |  | 26 | 16500000 | <50M | NS | POST | POST | Plan | 2022-02-01 | 2022-02-09 | 2022-02-16 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 28 apr 22 | 2 May 22 | 16500000 | 2022-05-09 | 2022-05-16 | 2022-05-30 | 2022-06-27 | 2022-06-28
Actual
2 | Procurement of 12 AC OutLets Basic Rack. |  | LSVO/G/NS/002/22 |  | 1 | 250000 | <5M | NS | POST | PRIOR | Plan | 2022-03-01 | N/A | 2022-03-22 | 29- Mar 22 | 2022-04-04 | 2022-04-11 | 11 May 22 | N/A | 250000 | 2022-05-20 | 2022-05-27 | 2022-06-08 | 2022-07-08 | 2022-06-28
Actual
3 | Procurement of Dji Mavic Air fly more Combo Drone |  | LASVO/G/NS/003/22 |  | 2 | 1700000 | <5 M | NS | POST | POST | Plan | 2022-01-03 | N/A | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-03-14 | 2022-03-16 | 1700000 | 2022-03-23 | 2022-03-30 | 2022-04-18 | 2022-05-09 | 2022-05-10
Actual
4 | Procurement of 5KW Pure Sine Wave with chargecontroller. |  | LASVO/G/NS/004/22 |  | 1 | 450000 | <5 M | NS | POST | POST | Plan | 2022-04-01 | N/A | N/A | N/A | N/A | N/A | 2022-05-01 | N/A | 450000 | 2022-05-23 | 2022-06-30 | 18-Jul- 22 | 9-Aug-22 | 2022-09-10
Actual
5 | Procurement of Personal Protective Equipments |  | LASVO/G/NS/005/22 |  |  | 5000000 | <5 M | NS | POST | POST | Plan | 2022-01-10 | N/A | 2022-01-24 | 2022-02-07 | 14-FEB -22 | 2022-02-21 | 2022-03-21 | 2022-03-23 | 5000000 | 2022-03-30 | 2022-04-06 | 2022-04-20 | 2022-05-11 | 2022-05-12
Actual
6 |  | Procurement of Operational Vehicle Materials. E.g procurement of 1 No of Toyota Hiace Engine | LASVO/G/NS/006/22 |  | 33 | 4000000 | <5M | NS | POST | POST | Plan | 2022-01-10 | N/A | 2022-01-24 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-03-21 | 2022-03-23 | 4000000 | 2022-03-30 | 2022-04-06 | 2022-04-20 | 2022-05-11 | 2022-05-12
Actual
7 | Procurement of Furniture and Office Equipments. Eg. Procurement of 1 no of Industrial Wireless Photocopy Machine, Procurement of 10 No of Office Table. Etc |  | LASVO/G/NS/007/22 |  | 51 | 10500000 | <50M | NS | POST | POST | Plan | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-03-14 | 2022-03-16 | 1700000 | 2022-03-23 | 2022-03-30 | 2022-04-18 | 2022-05-09 | 2022-05-10
Actual
[11 empty] | Plan | [13 empty] | 2022-05-10
Actual
[11 empty] | Plan | [13 empty] | 2022-05-10
Actual
[11 empty] | Plan | [13 empty] | 2022-05-10 | `````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````
Actual
[11 empty] | Plan | [13 empty] | 2022-05-10
Actual
[11 empty] | Plan | [13 empty] | 2022-08-20
Actual
[11 empty] | Plan | [13 empty] | 2022-05-10
Actual
[11 empty] | Plan | [13 empty] | 2022-07-16
Actual
[11 empty] | Plan | [13 empty] | 2022-07-16
Actual
[11 empty] | Plan | [13 empty] | 2022-07-16
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE VALUATION OFFICE
YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual