## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE BUILDING CONTROL AGENCY
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | MISCELLANEOUS | LASBCA/NP/NM/001/22 | 1000000 | Plan | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 8929 | 1000000
Actual
2 | UPKEEP OF LASBCA DISTRICT OFFICES(ALLOWANCES) | LASBCA/NP/NM/002/22 | 15,000,000.00 | Plan | 1250000 | 1250000 | 1250000 |  | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 15000000
Actual
3 | ENFORCEMENT & COMPLIANC(ALLOWANCES) | LASBCA/NP/NM/003/22 | 28,000,000.00 | Plan | 2333333 | 2333333 | 2,333,333,00 | 2333333 | 2333333 | 2333333 | 2333333 | 2333333 | 2333333 | 2333333 | 2333333 | 2333333 | 28000000
Actual
4 | GENERAL UTILITY EXPENSES | LASBCA/NP/NM/004/22 | 3000000 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3000000
Actual
2 | PROCUREMENT EXPENSES | LASBCA/NP/NM/005/22 | 500,000.00 | Plan | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 500000
Actual
6 | AUDIT UNIT EXPENSES | LASBCA/NP/NM/006/22 | 500,000.00 | Plan | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 500000
Actual
7 | LEGAL EXPENSES | LASBCA/NP/NM/007/22 | 500,000.00 | Plan | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 500000
Actual
8 | ICT UNIT EXPENSES | LASBCA/NP/NM/008/22 | 500,000.00 | Plan | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 500000
Actual
9 | SPECIAL DUTY EXPENSES | LASBCA/NP/NM/009/22 | 8,700,000.00 | Plan | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 725000 | 8700000
Actual
10 | PLANNING & RESEARCH UNIT EXPENSES | LASBCA/NP/NM/010/22 | 500000 | Plan | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41667 | 41,667,00 | 41667 | 41667 | 41667 | 41667 | 500000
Actual
11 | MAINTENANCE OF OFFICE BUILDING(ALLOWANCE) | LASBCA/NP/NM/011/22 | 3,500.000.00 | Plan | 291667 | 291667 | 291667 | 291667 | 291667 | 291.667.00 | 291667 | 291667 | 291667 | 291667 | 291667 | 291667 | 3500000
Actual
12 | TRAVEL & TRANSPORT | LASBCA/NP/NM/012/22 | 5000000 | Plan | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 416667 | 5000000
Actual
13 | MONITORING OF DISTRESS BUILDING | LASBCA/NP/NM/013/22 | 18000000 | Plan | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 18000000
Actual
| TOTAL |  | 84700000 | Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/AGENCY:LAGOS STATE BUILDING CONTROL AGENCY
BUDGET/YEAR:2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP & TRAINING EXPENSES | PPA/S-WTC/SS/001/22 | TO IMPROVE THE SKILLS OF STAFFS OF THE PROFESSONAL CADRES | ALL STAFFS OF PROFESSIONAL CADRES |  | Plan | LAGOS/ABUJA |  |  |  | 10000000
Actual
2 | CONFERENCES & SEMINARS | PPA/S-WTC/SS/001/22 | TO UPDATE THE PROFESSIONAL OFFICERS OF ICAN,ANAN,COREN,CIPM,NITP,ETC | PROFESSIONAL OFFICERS |  | Plan | LAGOS/ABUJA |  |  |  | 10000000
Actual
3 | [5 empty] | Plan
Actual
4 | [5 empty] | Plan
Actual
5 | TOTAL |  |  |  |  | Plan |  |  |  |  | 20000000
Actual
6 | [5 empty] | Plan
Actual
7
8
9
10
11
12

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
MINISTRY/AGENCY: -LASBCA | [9 empty] | 2022 |  | NON -CONSULTING SERVICES
MINISTRY/AGENCY:LASBCA
Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
RETREAT | LASBCA/S-NC/NS/001/22 |  |  |  | 25000000 | <50M | NS | Plan | Post | Post | 2022-02-15 | 22-02-2022 | 01-03-2022 | 08-03-2022 | 22-03-2022 | 04-04-2022 | 11-04-2022 | Plan | 25-04-2022 | 09-05-2022 | 0 | 07-06-2022 | 28-06-2022 | 11-07022 | 29-07-2022
[8 empty] | Actual | [9 empty] | Actual
REFURBISHMENT OF OPERATIONAL VEHICLES | LASBCA/S-NC/NCB/002/22 |  |  | 5 | 35000000 | >50M | NS | Plan | Pre | Prior | 25-04-2022 | 16-05-2022 | 30-05-2022 | 13-06-2022 | 04-07-2022 | 18-07-2022 | 25-07-2022 | Plan | 08-08-2022 | 22-08-2022 | 0 | 12-09-2022 | 03-10-2022 | 17-10-2022 | 28-10-2022
[8 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF TRACTOR &HEAVY EQUIP | LASBCA/S-NC/NS/003/22 |  |  | 1 | 36750000 | >50M | NS | Plan | Pre | Prior | 11-04-2022 | 09-05-2022 | 23-05-2022 | 06-06-2022 | 27-06-2022 | 11-07-2022 | 18-07-2022 | Plan | 25-07-2022 | 08-08-2022 | 0 | 15-08-2022 | 05-09-2022 | 16-09-2022 | 29-09-2022
[8 empty] | Actual | [9 empty] | Actual
MAINTENANCE & REPAIR OF MOTOR VEHICLES | LASBCA/S-NC/NS/004/22 |  |  |  | 8000000 | >10M | NS | Plan | Post | Post | 11-04-2022 | 09-05-2022 | 23-05-2022 | 06-06-2022 | 27-06-2022 | 11-07-2022 | 18-07-2022 | Plan | 25-07-2022 | 08-08-2022 | 0 | 15-08-2022 | 27-09-2022 | 16-09-2022 | 29-09-2022
[8 empty] | Actual | [9 empty] | Actual
REFURBISHMENT OF OPERATIONAL VEHICLES | LASBCA/S-NC/NS/005/22 |  |  |  | 35000000 | >10M | NS | Plan | Pre | Prior | 11-04-2022 | 09-05-2022 | 23-05-2022 | 06-06-22 | 27-06-2022 | 11-07-2022 | 18-07-2022 | Plan | 25-07-2022 | 08-08-2022 | 0 | 15-08-2022 | 20-08-2022 | 16-09-2022 | 29-09-2022
[8 empty] | Actual | [9 empty] | Actual
PRINTING OF STATUTORY NOTICES | LASBCA/S-NC/NS/006/22 |  |  |  | 25000000 | >10M | NS | Plan | Pre | Prior | 07-02-2022 | 28-02-2022 | 07-03-2022 | 14-03-2022 | 04-04-2022 | 20-04-2022 | 27-04-2022 | Plan | 11-05-2022 | 01-06-2022 | 0 | 29-06-2022 | 28-07-2022 | 18-08-2022 | 31-08-2022
[8 empty] | Actual | [8 empty] | . | Actual
PRINTING OF STATISTICAL PUBLICTION | LASBCA/S-NC/NS/007/22 |  |  |  | 750000 | <10M | NS | Plan | Post | Post | 07-02-2022 | 28-02-2022 | 07-03-2022 | 14-03-2022 | 04-04-2022 | 20-04-2022 | 27-04-2022 | Plan | 11-05-2022 | 01-06-2022 | 0 | 29-06-2022 | 28-07-2022 | 18-08-2022 | 31-08-2022
[8 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  |  | 165500000 |  |  | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan |  |  |  | 25-03-2022 | 08-04-2022 | 22-04-2022 | 20-05-2022 | 03-06-2022 | 08-06-2022 | Plan | 22-06-2022 | 21-07-2022 | 0 | 22-07-2022 | 26-08-2022 | 16-09-2022 | 31-10-2022
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan |  |  |  | 25-03-2022 | 08-04-2022 | 22-04-2022 | 20-05-2022 | 03-06-2022 | 08-06-2022 | Plan | 22-06-2022 | 21-07-2022 | 0 | 22-07-2022 | 26-08-2022 | 16-09-2022 | 31-10-2022
[8 empty] | Actual | [9 empty] | Actual
0
w

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LASBCA
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | INFORMATION TECH/DATABASE(ELECTRONIC MONITORING | LASBCA/S-C/IC/001/22 | IC | LUMP | 20000000 | Post | Plan | 05-04-2022 | 03-05-2022 | 17-05-2022 | 24-05-2022 | 14-06-2022 | 28-06-2022 | 12-07-2022 | 02-08-2022 | 16-08-2022 | 30-08-2022 | 06-09-2022 | 13-09-2022 | 23-09-2022 | 07-10-2022 |  | 11-10-2022 | 18-10-2022 | 01-11-2022 | 15-11-2022 | 25-11-2022 | 0.00
Actual
2 | PUBLICICITY & PRESSS COVERAGE | LASBCA/S-C/IC/002/22 | IC | LUMP | 8970728 | Post | Plan | 05-04-2022 | 03-05-2022 | 17-05-2022 | 24-05-2022 | 14-06-2022 | 28-06-2022 | 12-07-2022 | 02-08-2022 | 16-08-2022 | 30-08-2022 | 06-09-2022 | 13-09-2022 | 23-09-2022 | 07-10-2022 |  | 11-10-2022 | 18-10-2022 | 01-11-2022 | 15-11-2022 | 25-11-2022 | 0.00
Actual
3 | STAKEHOLDERS ENLIGHTEMENT CAMPAIGN FORUM | LASBCA/S-C/IC/003 /2022 | IC | LUMP | 42,681.463.00 |  | Plan | 05-04-2022 | 03-05-2022 | 17-05-2022 | 24-05-2022 | 14-06-2022 | 28-06-2022 | 12-07-2022 | 02-08-2022 | 16-08-2022 | 30-08-2022 | 06-09-2022 | 13-09-2022 | 23-09-2022 | 07-10-2022 |  | 11-10-2022 | 18-10-2022 | 01-11-2022 | 15-11-2022 | 25-11-2022 | 0.00
Actual
4 | EXTERNAL AUDITOR FEES |  |  | LUMP | 1300000 |  | Plan | 2022-03-18 | 2022-03-11 | 2022-03-25 | 2022-04-01 | 2022-04-15 | 2022-04-29 | 2022-05-13 | 2022-06-03 | 2022-06-17 | 2022-07-01 | 2022-07-08 | 2022-07-22 | 2022-08-05 | 2022-08-26 |  | 2022-08-29 | 2022-09-05 | 2022-09-19 | 2022-10-10 | 2022-10-24 | 0
Actual
Plan
Actual
| TOTAL |  |  |  | 71652191 |  | Plan
Actual

## goods
. |  | PROCUREMENT PLAN FOR GOODS.
, |  | MINISTRY/AGENCY: LASBCA
YEAR:2022
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL
|  | Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
| 1 | COMPUTER HARDWARE & ACCESSORIES | LASBCA/G/NS/001/22 |  |  | 80000000 | <50M | NS | Post | Prior | Plan | 19-04-2022 | 10-05-2022 | 24-05-2022 | 07-06-2022 | 20-06-2022 | 12-07-2022 | 27-7-2022 | 19-8-2022 | 0 | 23-8-2022 | 01-09-2022 | 2022-09-15 | 20-09-2022 | 27-9-2022
Actual
| 2 | OFFICE EQUIPMENT | LASBCA/G/NS/002/22 |  |  | 25000000 | <50M | NS | Post | Prior | Plan | 13-03-2022 | 12-04-2022 | 26-04-2022 | 10-05-2022 | 07-06-2022 | 23-06-2022 | 07-07-2022 | 08-07-2022 | 0 | 16-07-2022 | 29-07-2022 | 12-08-2022 | 19-08-2022 | 26-8-2022
Actual
| 3 | WORKSHOP EQUIPMENT | LASBCA/G/NCB/003/22 |  |  | 100000000 | >100M | NCB | Post | Prior | Plan | 13-03-2022 | 12-04-2022 | 26-04-2022 | 10-05-2022 | 07-06-2022 | 23-06-2022 | 07-07-2022 | 08-07-2022 | 0 | 16-07-2022 | 29-07-2022 | 12-08-2022 | 19-08-2022 | 26-8-2022
Actual
| 4 | SAFETY EQUIPMENT | LASBCA/G/NS/004/22 |  |  | 35000000 | <50M | NS | Post | Prior | Plan | 13-03-2022 | 12-04-2022 | 26-4-2022 | 10-05-2022 | 07-06-2022 | 23-06-2022 | 07-07-2022 | 08-07-2022 | 0 | 16-07-2022 | 29-07-2022 | 12-08-2022 | 19-08-2022 | 26-08-2022
Actual
| 5 | FIRST AID & DRUGS | LASBCA/G/NS/005/22 |  |  | 2000000 | <10M | NS | Post | Post | Plan | 19-04-2022 | 11-05-2022 | 25-05-2022 | 02-06-2022 | 23-06-2022 | 07-07-2022 | 21-07-2022 | 05-08-2022 | 0 | 09-08-2022 | 16-08-2022 | 30-08-2022 | 1 6-09-2022 | 23-09-2022
Actual
| 6 | UNIFORM AND PROTECTIVE OUTFIT | LASBCA/G/NCB/006/22 |  |  | 5000000 | >100M | NCB | Pre | Prior | Plan | 12-4-2022 | 2022-03-05 | 17-5-2022 | 31-5-2022 | 28-06-2022 | 07-07-2022 | 21-7-2022 | 05-08-2022 | 0 | 09-08-2022 | 16-08-2022 | 30-8-2022 | 17-09-2022 | 24-09-2022
Actual
| 7 | FUEL FOR MOTOR VEHICLES | LASBCA/G/NS/007/22 |  |  | 10,000,000..00 | <10M | NS | Post | 0 | Plan | 09-02-2022 | 23-03-2022 | 06-04-2022 | 19-04-2022 | 10-05-2022 | 24-05-2022 | 09-06-2022 | 10-06-2022 | 0 | 16-6-2022 | 30-6-2022 | 28-07-2022 | 04-08-2022 | 11-08-2022
Actual
| 8 | FUEL FOR HEAVY EQUIPMENT | LASBCA/G-F/NS/008/22 |  |  | 50000000 | <100M | NS | Pre | Prior | Plan | 09-02-2022 | 23-03-2022 | 06-04-2022 | 19-04-2022 | 10-05-2022 | 24-05-2022 | 09-06-2022 | 10-06-2022 | 0 | 16-6-2022 | 30-6-2022 | 28-7-2022 | 04-08-2022 | 11-08-2022
Actual
| 9 | STATIONARY | LASBCA/G-F/NS/009/22 |  |  | 4500000 | <50M | NS | Post | Post | Plan | 05-04-2022 | 26-04-2022 | 10-05-2022 | 24-05-2022 | 17-06-2022 | 01-07-2022 | 15-07-2022 | 29-07-2022 | 0 | 02-08-2022 | 09-08-2022 | 23-8-2022 | 13-09-2022 | 20-9-2022
Actual
| 10 | MGT INFORMATION SYSTEM(ICT CONSUMABLES) | LASBCA/G/NS/10/22 |  |  | 3000000 | <10M | NS | Post | Post | Plan | 05-04-2022 | 26-04-2022 | 10-05-2022 | 24-05-2022 | 17-06-2022 | 01-07-2022 | 15-07-2022 | 29-07-2022 | 0 | 02-08-2022 | 09-08-2022 | 23-08-2022 | 13-09-2022 | 20-09-2022
Actual
| 11 | CONSUMABLES(PROC,ICT,AUDIT,BUDGET,LEGAL) | LASBCA/G/NS/11/22 |  |  | 2500000 | <10M | NS | Post | Post | Plan | 19-04-2022 | 10-05-2022 | 24-05-2022 | 07-06-2022 | 20-06-2022 | 12-07-2022 | 27-07-2022 | 19-08-2022 | 0 | 23-08-2022 | 01-09-2022 | 15-09-2022 | 20-09-2022 | 27-09-2022
Actual
| 12 | TOTAL |  |  | 317000000

## works
| PROCUREMENT PLAN FOR WORKS | /YEAR 2022
MINISTRY: LAGOS STATE BUILDING CONTROL AGENCY
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
[17 empty] | 1-4wks | 48hrs
1 | CONSTRUCTION OF NEW LASBCA HQ (ON-GOING) | LASBCA/W/ST/001/21 |  | 360668803.64 |  |  |  |  | Plan | [14 empty] | ON-GOING
Actual
2 | DEMOLITION OF ILLEGAL & DISTRESS BUILDINGS | LASBCA/W/DL/001/22 |  | 15000000 | <50M | DL | BOQ | Post | Plan | Post | 15-03-2022 | 08-03-2022 | 22-04-2022 | 06-05-2022 | 27-05-2022 | 10-06-2022 | 24-06-2022 | 15-07-2022 | 0 | 18-07-2022 | 25-07-2022 | 08-08-2022 | 29-08-2022 | 12-07-2022
Actual
| TOTAL |  |  | 375668803.64 |  |  |  |  | Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual