## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel and Transport | LASIEC/NP/NM/001/22 | 27819339 | Plan | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318278 | 2318281 | 27819339
Actual
2 | Payment for Utility Services (Elecricity Bill, Waste Disposal, Recharge Card, Water Rate, Subsription for DSTV/GOTV, CUG | LASIEC/NP/NM/002/22 | 17650888 | Plan | 1470908 | 1470908 | 1470908 | 1470908 | 1470907 | 1470907 | 1470907 | 1470907 | 1470907 | 1470907 | 1470907 | 1470907 | 17650888
Actual
3 | Internet Connectivity | LASIEC/NP/NM/003/22 | 8943508 | Plan |  |  | 8943508 | [9 empty] | 8943508
Actual
4 | Statutory Commission Meeting | LASIEC/NP/NM/004/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
5 | Management Meeting | LASIEC/NP/NM/005/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
6 | Personnel Management Board Meeting | LASIEC/NP/NM/006/22 | 900000 | Plan |  |  |  | 300000 |  |  |  | 300000 |  |  |  | 300000 | 900000
Actual
7 | Senatorial District Meeting | LASIEC/NP/NM/007/22 | 1840740 | Plan |  |  |  |  | 1840740 | [7 empty] | 1840740
Actual
8 | Attendance of FOSIECON National Delegate Conference | LASIEC/NP/NM/008/22 | 2053778 | Plan |  |  |  | 1026889 | [5 empty] | 1026889 |  |  | 2053778
Actual
9 | Operational and Logistic Meetings with Electoral Officers | LASIEC/NP/NM/009/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
10 | Attendance of South West SIEC's Meetings by Chairman | LASIEC/NP/NM/010/22 | 600000 | Plan |  |  |  | 300000 | [5 empty] | 300000 |  |  | 600000
Actual
11 | Payment of Annual FOSIECON Dues | LASIEC/NP/NM/011/22 | 120000 | Plan | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 120000
Actual
12 | Newspapers |  | 337500 |  | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 28125 | 337500
13 | Press Conference by the Chairman | LASIEC/NP/NM/012/22 | 1500000 | Plan |  |  |  | 500000 |  |  |  | 500000 |  |  |  | 500000 | 1500000
Actual
14 | Payment of Commission on Turnover Value Added Tax, Police escort and Otjher Charges | LASIEC/NP/NM/013/22 | 960000 | Plan | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 960000
Actual
15 | Welfare Expenses | LASIEC/NP/NM/014/22 | 8645007 | Plan |  |  | 2161252 |  |  | 2161252 |  |  | 2161252 |  |  | 2161251 | 8645007
Actual
16 | Election Monitoring and Observation within Nigeria | LASIEC/NP/NM/015/22 | 11762503 | Plan |  | 1176250 | 1176250 | 1176253 | 1176250 | 1176250 | 1176250 | 1176250 | 1176250 | 1176250 | 1176250 |  | 11762503
Actual
17 | Organisation of Political Stakeholders Meeting For Political Parties, NOA, INEC Officials etc. | LASIEC/NP/NM/016/22 | 1115538.75 | Plan | [6 empty] | 1115538.75 | [5 empty] | 1115538.75
Actual
18 | Organisation of Security Stakeholders Meeting for Police, DSS, NCDC, Neibourghood Watch, Man O war, Boy Scout, KAI, LASTMA etc. | LASIEC/NP/NM/017/22 | 1115538.75 | Plan | [6 empty] | 1115538.75 | [5 empty] | 1115538.75
Actual
19 | Organisation of Grassroot Stakeholders Meeting at Lagos east, West and Central Senatorial District | LASIEC/NP/NM/018/22 | 2231077.5 | Plan | [6 empty] | 2231077.5 | [5 empty] | 2231077.5
Actual
20 | Organisation of Civic Populace Stakeholders Meeting | LASIEC/NP/NM/019/22 | 1115538.75 | Plan | [6 empty] | 1115538.75 | [5 empty] | 1115538.75
Actual
21 | Organisation of Media/NGOs/CBOs Stakeholders Meeting | LASIEC/NP/NM/020/22 | 1115538.75 | Plan | [6 empty] | 1115538.75 | [5 empty] | 1115538.75
Actual
22 | Sensitization of Poll Guides on Newly Deliniated Wards | LASIEC/NP/NM/021/22 | 1115538.75 | Plan | [6 empty] | 1115538.75 | [5 empty] | 1115538.75
Actual
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
23 | Organisation of Gender Sensitization Activities | LASIEC/NP/NM/022/22 | 1115538.75 | Plan | [6 empty] | 1115538.75 | [5 empty] | 1115538.75
Actual
24 | Transport Allowance For Market Survey | LASIEC/NP/NM/023/22 | 120000 | Plan | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 120000
Actual
25 | Preparation of Performance Management Report (PMR) for the Commission | LASIEC/NP/NM/024/22 | 440000 | Plan |  |  | 110000 |  |  | 110000 |  |  | 110000 |  |  | 110000 | 440000
Actual
26 | Monitoring of Projects and Elections | LASIEC/NP/NM/025/22 | 600000 | Plan |  |  | 150000 |  |  | 150000 |  |  | 150000 |  |  | 150000 | 600000
Actual
27 | Preparation of Annual Budget for the Commission | LASIEC/NP/NM/026/22 | 574932 | Plan |  | 574932 | [10 empty] | 574932
Actual
28 | Preparation and Rendition of Monthly Revenue and Expenditure to Ministry of Finance and MEPB | LASIEC/NP/NM/027/22 | 300000 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
Actual
29 | Preparation of MTSS Document for the Commission | LASIEC/NP/NM/028/22 | 456156 | Plan | [5 empty] | 456156 | [6 empty] | 456156
Actual
30 | Preparation & Printing of Bid Document | LASIEC/NP/NM/029/22 | 1704576 | Plan |  |  | 426144 |  |  | 426144 |  |  | 426144 |  |  | 426144 | 1704576
Actual
31 | Holding Ministerial Tenders' Board Meetings | LASIEC/NP/NM/030/22 | 378294 | Plan |  |  | 94573.5 |  |  | 94573.5 |  |  | 94573.5 |  |  | 94573.5 | 378294
Actual
32 | Audit Exercise for Staff | LASIEC/NP/NM/031/22 | 300000 | Plan | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000
Actual
33 | Personnel Cost (Non Oracle Staff) | LASIEC/NP/NM/032/22 | 20747060 | Plan | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728922 | 1728918 | 20747060
Actual
34 | Bye/Run-off/Re-run Elections | LASIEC/NP/NM/033/22 | 90000000 | Plan | [5 empty] | 90000000 | [6 empty] | 90000000
Actual
35 | Deliniation of Wards | LASIEC/NP/NM/034/22 | 195000000 | Plan | [5 empty] | 195000000 | [6 empty] | 195000000
Actual
36 | Monitoring and Evaluation of all Election Processes and Projects | LASIEC/NP/NM/035/22 | 7409270 | Plan |  |  | 1481854 |  | 1481854 |  | 1481854 |  | 1481854 |  | 1481854 |  | 7409270
Actual
37 | Observation and Monitoring of Elections outside Nigeria | LASIEC/NP/NM/036/22 | 32500000 | Plan | [5 empty] | 32500000 | [6 empty] | 32500000
Actual
38 | Exchange Programmes (Comparative Study Tour) | LASIEC/NP/NM/037/22 | 100000000 | Plan |  |  |  |  | 50000000 |  |  |  |  | 50000000 |  |  | 100000000
Actual
39 | Research on Voter Aparthy in Lagos State | LASIEC/NP/NM/038/22 | 30000000 | Plan |  |  |  | 30000000 | [8 empty] | 30000000
Actual
40 | Partnership Programmes with INEC on General Election | LASIEC/NP/NM/039/22 | 20000000 | Plan |  |  |  |  | 20000000 | [7 empty] | 20000000
Actual
41 | Donor Agencies/International Partnership and gender Issues' Programmes | LASIEC/NP/NM/040/22 | 15000000 | Plan |  |  |  |  | 15000000 | [7 empty] | 15000000
Actual
42 | Hosting of FOSIECON Annual General Meeting | LASIEC/NP/NM/041/22 | 70000000 | Plan | [8 empty] | 70000000 |  |  |  | 70000000
Actual
43 | Miscellaneous | LASIEC/NP/NM/038/22 | 7867129 | Plan | 655594 | 655594 | 655594 | 655594 | 655594 | 655594 | 655594 | 655594 | 655594 | 655594 | 655594 | 655595 | 7867129
Actual
| TOTAL |  | 689774990 | Plan | 100649279 | 126917009.4 | 311303001.65 | 570196406.4 | 1428131925.4 | 4889264901.65 | 274385475.4 | 130293015.4 | 1164650367.65 | 908196350.4 | 140520825.4 | 156778790.25 | 689774990
Actual

## trg conf wash
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Numbeer | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Chartered Institute of Personnel Management (CIPM) | LASIEC/S-WTC/SS/001/22 |  | 12 | 4 Days | Plan | Abuja | N100,000 x 12= N1,200,000 | N125,000 x 12= N1,464,000 | N294,400 x 12+180,000= N3,712,800 | 6556800
Actual
2 | Institute of Chartered Accountants of Nigeria (ICAN) | LASIEC/S-WTC/SS/002/22 |  | 4 | 5 Days | Plan | Abuja | N120,000 x 4= N480,000 | N125,000 x 2= N250,000 N123,500 x 2= N247,000 | N368,000 x 2 + 24,000= N760,000 N277,500 x 2+18,000= N573,000 | 2310000
Actual
3 | Chartered Institute of Purchasing & Supply Management of Nigeria (CIPSM) | LASIEC/S-WTC/SS/003/22 |  | 3 | 4 Days | Plan | Abuja | N100,000 x 3= N300,000 | N125,000 N123,500 x 2= N247,000 | N294,400+15,000=N309,400 N222,000 x 2+ 18,000= N462,000 | 1443400
Actual
4 | Nigeria Institute of Public Relation (NIPR) | LASIEC/S-WTC/SS/004/22 |  | 3 | 4 Days | Plan | Abuja | N150,000 x 3= N45 0,000 | N125,000 x 2= N250,000 N123,500 | N220,000 x 2 + 24,000= N464,000 N166,500 +9,000= N175,500 | 1463000
Actual
5 | Nigeria Institute of Management (NIM) | LASIEC/S-WTC/SS/005/22 |  | 6 | 4 Days | Plan | Abuja | N100,000 x 6= N600,000 | N125,000 x 6= N750,000 | N294,400 x 6+90,000= N1,856,400 | 3206400
Actual
6 | National Statistical Association | LASIEC/S-WTC/SS/006/22 |  | 1 | 4 Days | Plan | Abuja | N55,000 | N125,000 | N294,400 | 474400
Actual
7 | Computer Professionals of Nigeria | LASIEC/S-WTC/SS/007/22 |  | 1 | 4 Days | Plan | Abuja | N70,000 | N125,000 | N294,400 | 489400
Actual
8 | Management Trainig & Workshop by Lagos State Public Service Staff Development Center for Senior Officer | LASIEC/S-WTC/SS/008/22 |  | 45 | 3 Days | Plan | Lagos | 2895117 | 340602 | 510903 | 3746622
Actual
9 | Management Trainig & Workshop by Lagos State Public Service Staff Development Center for Junior Officer | LASIEC/S-WTC/SS/009/22 |  | 20 | 3 Days | Plan | Lagos | 1103850 | 51528 | 73590 | 1228968
Actual
10 | Total |  |  |  |  | Plan |  |  |  |  | 20918990
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Servicing of Air Conditioners | LASIEC/S-NC-F/NS/001/2022 |  | 90 | 765000 | <10Million | NS | Plan | Post | Post | 2022-02-08 | N/A | 2022-02-11 | 2022-02-18 | 2022-02-22 | 2022-02-25 | N/A | Plan | N/A | N/A |  | 2022-03-02 | 2022-03-04 | 2022-03-11 | 2022-03-11
[7 empty] | Actual | [9 empty] | Actual
Fumigation of Offices | LASIEC/S-NC-F/NS/002/2022 |  | 4 | 600000 | <10Million | NS | Plan | Post | Post | 2022-02-24 | N/A | 2022-02-28 | 2022-03-07 | 10//03/2022 | 2022-03-15 | N/A | Plan | N/A | N/A |  | 2022-03-22 | 2022-03-25 | 2022-03-28 | 2022-03-28
[7 empty] | Actual | [9 empty] | Actual
Repair and Replacement of Plumbing Fittings | LASIEC/S-NC/NS/003/2022 |  | 1 | 180000 | <10Million | NS | Plan | Post | Post | 2022-02-08 | N/A | 2022-02-11 | 2022-02-18 | 2022-02-22 | 2022-02-25 | N/A | Plan | N/A | N/A |  | 2022-03-02 | 2022-03-04 | 2022-03-11 | 2022-03-11
[7 empty] | Actual | [9 empty] | Actual
Repair of Doors and Locks | LASIEC/S-NC/NS/004/2022 |  | 5 | 1162612 | <10Million | NS | Plan | Post | Post | 2022-03-02 | N/A | 2022-03-04 | 2022-03-11 | 2022-03-16 | 2022-03-21 | N/A | Plan | N/A | N/A |  | 2022-03-28 | 2022-03-31 | 2022-04-07 | 2022-04-07
[7 empty] | Actual | [9 empty] | Actual
Repair and Servicing of Motor Vehicles | LASIEC/S-NC-F/ NS/005/2022 |  | 45 | 11724502 | <50Million | NS | Plan | Pre | Prior | 2022-03-02 | 2022-03-05 | 2022-03-08 | 2022-03-15 | 2022-03-18 | 2022-03-21 | 2022-03-23 | Plan | 2022-03-30 | 2022-04-01 |  | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-04-20
[7 empty] | Actual | [9 empty] | Actual
Engagement of Private Security Firm | LASIEC/S-NC-F/ NS/006/2022 |  | 12 | 2023968 | <10Million | NS | Plan | Post | Post | 2022-02-23 | N/A | 2022-02-25 | 2022-03-01 | 2022-03-03 | 2022-03-07 | N/A |  | N/A | N/A |  | 2022-03-14 | 2022-03-17 | 2022-03-18 | 2022-03-18
Actual
Refilling of fire Extinguisher and Servicing of Fire Alarms | LASIEC/S-NC-F/NS/007/2022 |  | 6 | 530000 | <10Million | NS | Plan | Post | Post | 2022-03-02 | N/A | 2022-03-04 | 2022-03-11 | 2022-03-16 | 2022-03-21 | N/A | Plan | N/A | N/A |  | 2022-03-28 | 2022-03-31 | 2022-04-07 | 2022-04-07
[7 empty] | Actual | [9 empty] | Actual
Servicing of CCTV and PABX Intercome | LASIEC/S-NC-F/NS/008/2022 |  | 6 | 640000 | <10Million | NS | Plan | Post | Post | 2022-02-24 | N/A | 2022-02-28 | 2022-03-07 | 10//03/2022 | 2022-03-15 | N/A | Plan | N/A | N/A |  | 2022-03-22 | 2022-03-25 | 2022-03-28 | 2022-03-28
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Heavy Duty Generating Set | LASIEC/S-NC-F/NS/009/2022 |  | 4 | 1223748 | <10Million | NS | Plan | Post | Post | 2022-02-08 | 2022-02-16 | 2022-02-22 | 2022-03-04 | 2022-03-22 | 2022-04-06 | 2022-04-13 | Plan | 2022-04-20 | 2022-05-06 |  | 2022-05-11 | 2022-06-09 | 2022-06-28 | 2022-06-30
[7 empty] | Actual | [9 empty] | Actual
Maintenance and Repairs of Photocopy Machines and computers | LASIEC/S-NC-F/NS/010/2022 |  | 242 | 6710000 | <10Million | NS | Plan | Post | Post | 2022-03-03 | N/A | 2022-03-07 | 2022-03-11 | 2022-03-14 | 2022-03-16 | N/A | Plan | N/A | N/A |  | 2022-03-21 | 2021-03-24 | 31/04/2022 | 31/04/2022
[7 empty] | Actual | [9 empty] | Actual
Engagement of Event Planner for Retreat | LASIEC/S-NC-F/NS/012/2022 |  | 172 | 17012860 | <50Million | NS | Plan | Pre | prior | 2022-10-14 | 2022-10-21 | 2022-10-24 | 2022-11-01 | 2022-11-04 | 2022-11-08 | 2022-11-11 |  | 2022-11-14 | 2022-11-21 |  | 2022-11-24 | 2022-12-01 | 2022-12-09
Actual
Engagement of Media Firm for Advertisement & Invitation to Bid | LASIEC/S-NC-F/NS/013/2022 |  | 4 | 1400000 | <10Million | NS | Plan | Post | Post | 2022-02-08 | N/A | 2022-02-11 | 2022-02-18 | 2022-02-22 | 2022-02-25 | N/A | Plan | N/A | N/A |  | 2022-03-02 | 2022-03-04 | 2022-03-11 | 2022-03-11
Actual
Repair of Casting Machine | LASIEC/S-NC-F/NS/014/2022 |  | 4 | 250887 | <10Million | NS | Plan | Post | Post | 2022-02-08 | N/A | 2022-02-11 | 2022-02-18 | 2022-02-22 | 2022-02-25 | N/A | Plan | N/A | N/A |  | 2022-03-02 | 2022-03-04 | 2022-03-11 | 2022-03-11
Actual
Engagement of Event Planners for voter Education and Public Enlightement Programme | LASIEC/S-NC/NCB/015/2022 |  | 4 | 515000000 | <10Million | NCB | Plan | Pre | prior | 2022-03-17 | 2022-03-31 | 2022-04-04 | 2022-04-11 | 2022-04-25 | 2022-05-02 | 2022-05-05 |  | 2022-05-09 | 2022-05-23 |  | 2022-05-25 | 2022-06-01 | 2022-06-15
Actual
TOTAL |  |  |  | 559223577 |  |  | Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Engagement of Legal Firm for Litigation and Court Proceedings | LASIEC/S-C/FBS/002/22 | FBS | Lump sum | 21933435 | Prior | Plan | 02/02/2022 | 08/02/22 | 16/02/22 | 23/02/22 | 08/03/22 | 16/03/22 | 25/03/22 | 19/04/22 | 28/04/22 | 11/05/22 | 17/05/22 | 24/05/22 | 02/06/22 | 17/06/22 |  | 21/06/22 | 28/06/22 | 12/07/22 | 26/07/22 | 04/08/22
Actual
2 | Engagement of Financial Audit Firm | LASIEC/S-C/QCBS/004/22 | QCBS | Lump sum | 1000000 | Post | Plan | 02/02/2022 | 08/02/22 | 16/02/22 | 23/02/22 | 08/03/22 | 16/03/22 | 25/03/22 | 19/04/22 | 28/04/22 | 11/05/22 | 17/05/22 | 24/05/22 | 02/06/22 | 17/06/22 |  | 21/06/22 | 28/06/22 | 12/07/22 | 26/07/22 | 04/08/22
Actual
| Total |  |  |  | 22933435

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Energy Saving Bulbs | LASIEC/G/F/NS/001/22 |  | 1000 | 1250000 | <10Million | NS | Post | Post | Plan | 2022-01-04 | N/A | 2022-01-06 | 2022-01-11 | 2022-01-13 | N/A | N/A | N/A |  | 2022-01-17 | 2022-01-21 | 2022-01-25 | 2022-02-27 | 2022-02-27
Actual
2 | Procurement of Toiletries and Torch Light | LASIEC/G/F/NS/002/22 |  | 3570 | 4585500 | <10Million | NS | Post | Post | Plan | 2022-01-17 | N/A | 2022-01-19 | 2022-01-26 | 2022-01-28 | N/A | N/A | N/A |  | 2022-02-01 | 2022-02-04 | 2022-02-10 | 2022-02-14 | 2022-02-14
Actual
3 | Procurement of Tyres, Fire Extinguiusher and Vehicle Accessories | LASIEC/G/F/NS/003/22 |  | 235 | 6204435 | <10Million | NS | Post | Post | Plan | 2022-01-17 | N/A | 2022-01-19 | 2022-01-26 | 2022-01-28 | N/A | N/A | N/A |  | 2022-02-01 | 2022-02-04 | 2022-02-10 | 2022-02-14 | 2022-02-14
Actual
4 | Procurement of Motor Vehicle Fuel (PMS and Diesel) | LASIEC/G/F/NCB/004/22 |  | 249,267 ltrs | 50467476 | <100Million | NCB | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-12 |  | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-15
Actual
5 | Procurement of Stationeries | LASIEC/G/F/NS/005/22 |  | 5766 | 10865801 | <50Million | NS | Pre | Prior | Plan | 2022-01-17 | N/A | 2022-01-19 | 2022-01-26 | 2022-01-28 | N/A | N/A | N/A |  | 2022-02-01 | 2022-02-04 | 2022-02-10 | 2022-02-14 | 2022-02-14
Actual
6 | Procurement of Uniform and Protectives for Drivers, Securities and Cleaners | LASIEC/G/NS/006/22 |  | 27 | 402443 | <10Million | NS | Post | Post | Plan | 2022-02-21 | N/A | 1900-02-22 | 2022-03-01 | 2021-03-03 | N/A | N/A | N/A |  | 2021-03-07 | 2022-03-11 | 2022-03-16 | 2022-03-30 | 2022-03-30
Actual
7 | Procurement of Souvenir (Branded Mugs, Key Holder etc. | LASIEC/G/NS/007/22 |  | 310 | 205000 | <10Million | NS | Post | Post | Plan | 2022-02-21 | N/A | 1900-02-22 | 2022-03-01 | 2021-03-03 | N/A | N/A | N/A |  | 2021-03-07 | 2022-03-11 | 2022-03-16 | 2022-03-30 | 2022-03-30
Actual
8 | Procurement of Printers,Toners, Computer and Accessories | LASIEC/G/NS/008/22 |  | 272 | 39371398 | <50Million | NS | Pre | Prior | Plan | 2022-02-28 | 2022-03-04 | 2022-03-08 | 2022-03-15 | 2022-03-18 | 2022-03-23 | 2022-03-30 | 2022-04-01 |  | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-04-26
Actual
9 | Procurement of Books for Commission Library | LASIEC/G/NS/012/22 |  | 42 | 543554 | <10Million | NS | Post | Post | Plan | 2022-01-04 | N/A | 2022-01-06 | 2022-01-11 | 2022-01-13 | N/A | N/A | N/A |  | 2022-01-17 | 2022-01-21 | 2022-01-25 | 2022-02-27 | 2022-02-27
Actual
10 | Procurement and Istallation of ICT Infrastructure | LASIEC/G/NCB/013/22 |  | 1 | 130000000 | <500Million | NCB | Pre | Prior | Plan | 2022-03-07 | 2022-03-14 | 2022-03-17 | 2022-03-31 | 2022-04-05 | 2022-04-07 | 2022-04-14 | 2022-04-18 |  | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-19 | 2022-05-26
Actual
14 | Procurement of Operational Vehicles | LASIEC/G/NS/014/22 |  | 1 | 20000000 | <50Million | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-12 |  | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-15
Actual
15 | Procurement of Chairs,Tables and refregerators for office at the HQ & Zonal Offices | LASIEC/G/NS/015/22 |  | 50 | 17500000 | <50Million | NS | Pre | Prior | Plan | 2022-01-04 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-12 |  | 2022-03-16 | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-15
Actual
16 | Procurement of Canopy and Chairs for Social Activities | LASIEC/G/NS/016/22 |  | 1 | 2736736 | <10Million | NS | Post | Post | Plan | 2022-01-17 | N/A | 2022-01-19 | 2022-01-26 | 2022-01-28 | N/A | N/A | N/A |  | 2022-02-01 | 2022-02-04 | 2022-02-10 | 2022-02-14 | 2022-02-14
Actual
| TOTAL |  |  |  | 284132343 |  |  |  |  | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE INDEPENDENT ELECTORAL COMMISSION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Store/Warehouse for Lagos East Senatorial District | LASIEC/W/NS/001-01/22 | 1 | 100000000 | <100Million | NS | BOQ | Pre | Plan | Prior | 2022-06-29 | 2022-07-13 | 2022-07-20 | 2022-07-27 | 2022-08-10 | 2022-08-17 | 2022-08-24 | 2022-09-07 |  | 2022-09-09 | 2022-09-16 | 2022-09-30
Actual
2 | Construction of Store/Warehouse for Lagos West Senatorial District | LASIEC/W/NS/001-02/22 | 2 | 100000000 | <100Million | NS | BOQ | Pre | Plan | Prior | 2022-06-29 | 2022-07-13 | 2022-07-20 | 2022-07-27 | 2022-08-10 | 2022-08-17 | 2022-08-24 | 2022-09-07 |  | 2022-09-09 | 2022-09-16 | 2022-09-30
Actual
| TOTAL |  |  | 200000000 |  |  |  |  | Plan
Actual

## Sheet4
LAGOS STATE INDEPENDENT ELECTORAL COMMISSION 2, BIRREL AVENUE , SABO, YABA, LAGOS YEAR 2022 PROCUREMENT PLANS SUMMARY
PROCUREMENT PLAN FOR GOODS | 284132343
PROCUREMENT PLAN FOR WORKS | 200000000
PROCUREMENT PLAN FOR CONSULTING SERVICES | 22933435
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES | 559223577
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS | 689774990
PROCUREMENT PLAN FOR TRAINING, CONFERENCES & WORKSHOPS | 20918990
TOTAL | 1776983335