## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE INFRASTRUCTURE MAINTENANCE AND REGULATORY AGENCY
BUDGET YEAR: 2022
NON PROCURABLE ITEMS
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVEL & TRANSPORT | LASIMRA/NP/NM/001/22 | N7,000,000.00 | Plan | N250,000.00 | N900,000.00 | N500,000.00 | N600,000.00 | N900,000.00 | N650,000.00 | N500,000.00 | N650,000.00 | N600,000.00 | N700,000.00 | N500,000.00 | N350,000.00 | N7,000,000.00
Actual
2 | GENERAL UTILITY SERVICE | LASIMRA/NP/NM/002/22 | N5,750,000.00 | Plan | N350,000.00 | N400,000.00 | N600,000.00 | N400,000.00 | N450,000.00 | N550,000.00 | N300,000.00 | N450,000.00 | N750,000.00 | N400,000.00 | N500,000.00 | N600,000.00 | N5,750,000.00
Actual
3 | SPECIAL DUTY EXPENSES | LASIMRA/NP/NM/003/22 | N27,500,000.00 | Plan | N2,950,000.00 | N2,300,000.00 | N2,200,000.00 | N2,550,000.00 | N2,500,000.00 | N2,850,000.00 | N1,700,000.00 | N3,000,000.00 | N1,900,000.00 | N2,500,000.00 | N2,400,000.00 | N2,850,000.00 | N27,500,000.00
Actual
4 | STAFF WELFARE | LASIMRA/NP/NM/004/22 | N16,000,000.00 | Plan | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N1,200,000.00 | N2,800,000.00 | N16,000,000.00
Actual
5 | RENT | LASIMRA/NP/NM/005/22 | N4,500,000.00 | Plan | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N375,000.00 | N4,500,000.00
Actual
7 | PUBLICITY, PUBLICATION & DOCUMENTATION | LASIMRA/NP/NM/007/22 | N20,000,000.00 | Plan | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 1,600,000.00 | N 2,400,000.00 | N 1,600,000.00 | N 1,600,000.00 | N20,000,000.00
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE INFRASTRUCTURE MAINTENANCE AND REGULATORY AGENCY
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | CONTRACT PACKAGE NO | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | WORKSHOP & TRAINING | LASIMRA/S-WTC/SS/001/22 | To improve effeciency at the workplace thereby ultimately increasing profit/revenue of the organisation | Management and Senior staff of the Agency | 1 week | Plan | Abuja | N2,500,000.00 | N600,000.00 | N1,900,000.00 | N5,000,000.00
Actual
2 | CONFERENCE & SEMINARS | LASIMRA/S-WTC/SS/002/22 | To increase exposure to current trends which will be beneficial to the performance of staff and the growth of the organisation | Management and Senior staff of the Agency | 4 weeks | Plan | Lagos and Abuja | N7,500,000.00 | N2,100,000.00 | N5,400,000.00 | N15,000,000.00
Actual
3 | [5 empty] | Plan
Actual
4 | [5 empty] | Plan
Actual
5 | [5 empty] | Plan
Actual
6 | [5 empty] | Plan
Actual
7 | [5 empty] | Plan
Actual
8 | [5 empty] | Plan
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT OF NON-CONSULTING SERVICES
MINISTRY/AGENCY: LAGOS STATE INFRASTRUCTURE MAINTENANCE AND REGULATORY AGENCY
BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
S/N |  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | MAINTENANCE OF OFFICE BUILDING | LASIMRA/S-NC/NS/001/22 |  |  | N3,500,000.00 | <N50,000,000.00 | NS | Plan | POST | POST | 2022-02-15 | NIL | 2022-02-22 | 2022-03-08 | 15/03/2022 | NIL | NIL | Plan | 22/03/2022 | 24/03/2022 |  | 21/04/2022 | 5/05/2022 | 19/05/2022 | 26/05/2022
[8 empty] | Actual | [9 empty] | Actual
2 | MOTOR VEHICLE REPAIR | LASIMRA/S-NC-F/NS/002/22 |  |  | N10,000,000 | <N50,000,000.00 | NS | Plan | POST | POST | 2021-02-15 | NIL | 2021-03-01 | 2021-03-22 | 2021-03-29 | 2021-04-06 | NIL | Plan | 2021-04-12 | 2021-04-14 |  | 2021-05-11 | 2021-05-25 | FRAME WORK AGREEMENT
[8 empty] | Actual | [9 empty] | Actual
3 | MAINTENANCE AND REPAIRS OF OFFICE EQUIPMENT | LASIMRA/S-NC/NS/004/22 |  |  | N 4,000,000.00 | <N50,000,000.00 | NS | Plan | POST | POST | 2022-03-23 | NIL | 2022-03-30 | 2022-04-13 | 2022-04-20 | 2022-04-27 | NIL | Plan | 2022-05-04 | 2022-05-06 |  | 2022-06-03 | 2022-06-17 | 2022-07-01 | 2022-07-08
[8 empty] | Actual | [9 empty] | Actual
4 | MAINTENANCE OF GENERATOR | LASIMRA/S-NC/NS/005/22 |  |  | N 3,000,000.00 | <N50,000,000.00 | NS | Plan | POST | POST | 2022-04-12 | NIL | 2022-04-19 | 2022-05-03 | 10th-May-22 | 2022-05-17 |  | Plan | 2022-05-24 | 2022-05-26 |  | 2022-06-23 | 2022-07-07 | 2022-07-21 | 2022-07-28
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES
MINISTRY/ AGENCY: LAGOS STATE INFRASTRUCTURE MAINTENANCE AND REGULATORY AGENCY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | PRE/POST QIALIFICATION | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | INSTALLATION OF COMPUTER SOFTWARE | LASIMRA/CS/SSS/001/22 | SSS | LUMPSUM | N26,500,000.00 | POST | PRIOR | Plan | 14/03/2022 | 21/3/2022 | 28/03/2022 | 11/04/2022 | 18/04/2022 | 25/04/2022 | 16/05/2022 | 23/05/2022 | 30/05/2022 | 6/06/2022 | 13/06/2022 | 20/06/2022 | 27/06/2022 | 29/06/2022 |  | 6/07/2022 | 20/07/2022 | 3/08/2022 | 10/08/2022 | 17/08/2022
Actual
2 | CONTRACT WORKS: INCREASED REVENUE GENERATION WORKS THROUGH MONITORING ENFORCEMENT CONTRACT | LASIMRA/CS/SSS/002/22 | SSS | LUMPSUM | N129,600,000.00 | POST | PRIOR | Plan | 1/04/2022 | 8/04/2022 | 15/04/2022 | 29/04/2022 | 6/05/2022 | 13/05/2022 | 3/06/2022 | 10/06/2022 | 17/06/2022 | 24/06/2022 | 1/07/2022 | 8/07/2022 | 15/07/2022 | 18/07/2022 |  | 25/07/2022 | 8/08/2022 | 22/08/2022 | 29/8/2022 | 5/9/2022
Actual
3 | CONSULTANCY FEES AND COMMISSION | LASIMRA/CS/SSS/003/22 | SSS | LUMPSUM | N 150,000,000.00 | POST | PRIOR | Plan | 2022-04-20 | 2022-04-27 | 2022-05-04 | 2022-05-18 | 2022-05-25 | 2022-06-01 | 2022-06-22 | 29/06/202 | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-07-27 | 2022-08-03 | 2022-08-05 |  | 2022-08-12 | 2022-08-26 | 2022-09-09 | 2022-09-16 | 2022-09-23
Actual
Plan
Actual
Plan
Actual

## goods
| PROCUREMENT PLAN FOR GOODS. | [23 empty] | jjkb
MINISTRY/AGENCY: LAGOS STATE INFRASTRUCTURE MAINTENANCE AND REGULATORY AGENCY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF STATIONERY FOR OFFICE USE | LASIMRA/G-F/NS/001/22 |  | VARIOUS | N6,250,000.00 | <10,000,000.00 | NS | POST | POST | Plan | 2022-02-04 | NIL | 2022-02-11 | 2022-02-25 | 2022-03-04 | NIL | 2022-03-11 | 2022-03-14 | N6,250,000.00 | 2022-03-21 | 2022-03-28 | 2022-04-11 | FRAME WORK CONTRACT AGREEMENT
Actual
2 | PROCUREMENT OF UNIFORMS & PROTECTIVE OUTFITS | LASIMRA/G-F/NS/002/22 |  | NIL | N4,800,000.00 | <10,000,000.00 | NS | POST | POST | Plan | 2022-02-16 | NIL | 2022-02-23 | 2022-03-09 | 2022-03-16 | NIL | 2022-03-23 | 2022-03-25 | N4,800,000.00 | 2022-04-01 | 08-APR-2022 | 2022-04-22 | FRAME WORK CONTRACT AGREEMENT
Actual
3 | PROCUREMENT OF OFFICE FURNITURE AND FITTING | LASIMRA/G/NS/003/22 |  | NIL | N19,887,642.00 | <50,000,000.00 | NS | POST | PRIOR | Plan | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 | 2022-05-30 | N19,887,642.00 | 2022-06-06 | 2022-06-13 | 2022-06-27 | 12-July-2022 | 2022-08-19
Actual
4 | PROCUREMENT OF TELECOCUMMUNICATION EQUIPMENT | LASIMRA/G/NS/004/22 |  | NIL | N22,658,664.00 | <50,000,000.00 | NS | POST | PRIOR | Plan | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-06-01 | 2022-06-08 | 2022-06-15 | 2022-06-22 | 2022-06-24 | N22,658,664.00 | 2022-07-01 | 2022-07-08 | 2022-07-22 | 2022-08-19 | 2022-08-26
Actual
5 | PROCUREMENT OF MOTOR VEHICLES | LASIMRA/G/NCB/005/2022 |  | NIL | N111,871,506.00 | >N100M | NCB | POST | PRIOR | Plan | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-06 | N111,871,506.00 | 2022-07-13 | 2022-07-20 | 2022-08-03 | 2022-08-17 | 2022-08-24
Actual
6 | PROCUREMENT OF FUEL (PMS) FOR MOTOR VEHICLE CONSUMPTION | LASIMRA/G-F/NS/006/22 |  | NIL | N15, 500,395.90 | <50,000,000.00 | NS | POST | PRIOR | Plan | 18-May-22 | 2022-05-25 | 2022-06-01 | 15-Jun-2022 | 2022-06-22 | 2022-06-29 | 2022-07-06 | 2022-07-08 | N15, 500,395.90 | 2022-07-15 | 2022-07-22 | 2022-08-05 | FRAME WORK CONTRACT AGREEMENT
Actual
7 | PROCUREMENT OF DIESEL TO RUN THE GENERATING SET | LASIMRA/G-F/NS/007/22 |  | NIL | N6,500,000.00 | <10,000,000.00 | NS | POST | POST | Plan | 2022-06-07 | NIL | 2022-06-14 | 2022-06-28 | 2022-07-05 | NIL | 2022-07-12 | 2022-07-14 | N6,500,000.00 | 2022-07-21 | 28-Jul-2022 | 2022-08-11 | FRAME WORK CONTRACT AGREEMENT
Actual
8 | PROCUREMENT OF GENERATING SET | LASIMRA/G/NS/008/22 |  | NIL | N10,500,000.00 | <50,000,000.00 | NS | POST | PRIOR | Plan | 2022-06-17 | 2022-06-24 | 2022-07-01 | 2022-07-15 | 2022-07-22 | 2022-07-29 | 2022-08-05 | 2022-08-08 | N10,500,000.00 | 2022-08-15 | 2022-08-22 | 2022-09-05 | 2022-09-12 | 2022-09-19
Actual
9 | PROCUREMENT OF MECHANICAL/ELECTRICAL APPLIANCES | LASIMRA/G/NS/009/22 |  | NIL | N14,750,000.00 | <50,000,000.00 | NS | POST | PRIOR | Plan | 2022-07-05 | 2022-07-12 | 2022-07-19 | 2022-08-02 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-25 | N14,750,000.00 | 2021-08-26 | 2022-09-01 | 2022-09-15 | 2022-09-22 | 2022-09-29
Actual
10 | PROCUREMENT OF MANAGEMENT INFORMATION SYSTEM CONSUMABLES | LASIMRA/G/NS/010/22 |  | NIL | N10,000,00.00 | <10,000,000.00 | NS | POST | PRIOR | Plan | 2022-07-13 | 2022-07-20 | 2022-07-27 | 2022-08-10 | 2022-08-15 | NIL | 2022-08-22 | 2022-08-24 | N10,000,00.00 | 2022-08-31 | 2022-09-07 | 2022-09-21 | 2022-09-28 | 2022-10-05
Actual
11 | PROCUREMENT OF HDD THRUST BORING MACHINES | LASIMRA/G/NS/011/22 |  | NIL | N67,811,506.80 | >50,000,000.00 | NS | POST | PRIOR | Plan | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-21 | N67,811,506.80 | 28-Sep-2022 | 2022-10-05 | 2022-10-19 | 2022-11-16 | 2022-11-23
Actual
12 | PROCUREMENT OF TOILETRIES & OTHER CONSUMABLES | LASIMRA/G/NS/012/22 |  | NIL | N6,200,000.01 | <10,000,000.00 | NS | POST | POST | Plan | 2022-08-04 | 2022-08-11 | 2022-08-18 | 2022-09-01 | 2022-09-08 | NIL | 2022-09-15 | 2022-09-19 | N6,200,000.01 | 2022-09-26 | 2022-10-03 | 2022-10-17 | 2022-10-24 | 2022-11-07
Actual
13 | COMPLAINTS & ENFORCEMENT UNIT | LASIMRA/G/NS/013/22 |  | NIL | N10,299,999.75 | <50,000,000.00 | NS | POST | PRIOR | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-01 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-07 | N10,299,999.75 | 2022-04-14 | 2022-04-21 | 2022-05-05 | 2022-05-12 | 2022-05-19
Actual
14 | PRESS AND PUBLIC RELATION UNIT | LASIMRA/G/NS/014/22 |  | NIL | N7,000,00.00 | <10,000,000.00 | NS | POST | POST | Plan | 2022-02-03 | 2022-02-10 | 2022-02-17 | 2022-03-03 | 2022-03-10 | 2022-03-31 | 2022-04-07 | 1900-04-11 | N7,000,00.00 | 2022-04-18 | 2022-04-25 | 2022-05-09 | 2022-05-16 | 2022-05-23
Actual
15 | PLANNING UNIT | LASIMRA/G/NS/015/22 |  | NIL | N9,850,000.00 | <10,000,000.00 | NS | POST | POST | Plan | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-06-03 | 2022-06-10 | 17/06/2022 | 2022-06-24 | 2022-06-28 | N9,850,000.00 | 2022-07-04 | 2022-07-11 | 2022-07-25 | 2022-08-23 | 2022-08-29
Actual
16 | PROCUREMENT UNIT | LASIMRA/G/NS/016/22 |  | NIL | N3,000,000.00 | <10,000,000.00 | NS | POST | POST | Plan | 2022-06-09 | NIL | 2022-06-16 | 2022-06-30 | 2022-07-07 | NIL | 2022-07-14 | 2022-07-18 | N3,000,000.00 | 2022-07-25 | 30-Jul-2022 | 2022-08-15 | 2022-08-26 | 2022-08-31
Actual
8 | ICT UNIT | LASIMRA/G/NS/017/22 |  | NIL | N13,000,000.00 | <50,000,000.00 | NS | POST | PRIOR | Plan | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-11 | N13,000,000.00 | 2022-08-18 | 2022-08-25 | 2022-09-08 | 2022-09-15 | 2022-09-21
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE INFRASTRUCTURE MAINTENANCE AND REGULATORY AGENCY (LASIMRA)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROVISION OF INFRASTRUCTURE FACILITY:INSTALLATION,CONSTRUCTION OF INFRASTRUCTURE AMENITIES | LASIMRA/W/NS/001/22 |  | 17654900 | <50,000,000.00 | NS | Bill of Quantity | POST | Plan | PRIOR | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-06-29 | NIL | 2022-07-06 | 2022-07-13 | 2022-07-27 | 2022-08-24 | 2022-08-31
Actual
2 | REFURBISHMENT -OFFICE BUILDING :RENOVATIONS OF OFFICE BUILDING | LASIMRA/W/NS/002/22 |  | 16900000 | <50,000,000.00 | NS | Bill of Quantity | POST | Plan | PRIOR | [8 empty] | NIL
[9 empty] | Actual |  | 2022-05-18 | 2022-05-25 | 2022-06-01 | 2022-06-15 | 2022-06-22 | 2022-06-29 | 2022-07-06 | 2022-07-08 |  | 2022-07-15 | 2022-07-22 | 2022-08-05 | 2022-09-02 | 2022-09-09
3 | CONSTRUCTION OF A COMMON UTILITY SERVICE CROSS DUCT IN UTILITIES CORRIDORS OF ROADS IN THE STATE | LASIMRA/W/NS/003/22 |  | 162188493.2 | >50,000,000.00 | NCB | Bill of Quantity | POST | Plan | PRIOR | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-07-05 | 2022-07-12 | 2022-07-19 | 2022-07-26 | 2022-07-28 | NIL | 2022-08-03 | 2022-08-10 | 2022-08-24 | 2022-09-21 | 2022-09-21
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual