## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE PARKS AND GARDENS AGENCY
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUG | SEPTEMBER | OCT | NOVEMBER | DECEMBER
1 | Special Duties Expenses(Qtly pyt of allowance to support staff @ N19,008,000.00; Fund for external Auditors N1,075,000.00 and Renewal of Insurance Premium for support staff N771,394.44) | LASPARK/NP/NM/001/22 | 77878394.44 | Plan |  | 771394.44 | 19008000 |  | 1075000 | 19008000 |  |  | 19008000 |  |  | 19008000
Actual
2 | Payment for Rent of Office Accomodation @ N30,000,000.00; Monthly electricity bill @ N214,999.99 and Annual security services @ N3,600,000.00) | LASPARK/NP/NM/002/22 | 36,180,000.00 | Plan | 514999.99 | 30733333.33 | 514999.99 | 514999.99 | 514999.99 | 514999.99 | 514999.99 | 514999.99 | 514999.99 | 514999.99 | 514999.99 | 514999.99
Actual
| TOTAL |  | 114058394.44 | Plan | 514999.99 | 30514999.99 | 19522999.99 | 514999.99 | 1589999.99 | 19522999.99 | 514999.99 | 514999.99 | 19522999.99 | 514999.99 | 514999.99 | 19522999.99
Actual
| Adewale Akinleye S |  |  |  |  | Adetoun Popoola
| Deputy Director (Procurement) |  |  |  |  | General Manager
| Lagos State Parks and Gardens Agency |  |  |  |  | Lagos State Parks and Gardens Agency
| Date: February 21, 2022 |  |  |  |  | Date: February 21, 2022
MEMBERS OF PROCUREMENT PLANNING COMMITTEE:
1 | Mrs. Adetoun Popoola (General Manager) - Chairman
2 | Mr. Adewale Akinleye S - Secretary
3 | Mr. Kareem A.B (Finance & Accounts) - Member
4 | Mrs. Abudu B (Planning & Budget) - Member
5 | Mr. Adetoye A.M (Project/Technical) - Member
6 | Mrs. Taiwo Cole (Legal) - Member
7 | Mr. Sunmoni A.O.J -Member
8 | Mrs. F. Aina - Member
9 | Mr. Shittu A.B - Member
10 | Mr. Olajide O - Member
11 | Mr. Balogun-Asako A - Member
12 | Mr. Olayemi O. U - Member

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE PARKS AND GARDENS AGENCY
BUDGET YEAR: 2022
Contract Description |  | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Quarterly maintenance of Gardens/Open Spaces and Recreational Parks |  | LASPARK/S-NC/NC-F/NCB/001/22 |  |  | 311768630.44 | <N500M | NCB | Plan | Pre | Prior | 17/01/2022 | 24/01/2022 | N/A | N/A | N/A | N/A | N/A | Plan |  |  | 311768630.44 | N/A | N/A | N/A
[8 empty] | Actual | [9 empty] | Actual
Quarterly Maintenance & Repair of Tools & Machinery |  | LASPARK/S-NC/NCB/001/22 |  |  | 2000000 | <N10M | NS | Plan | Post | Post | 17/01/2022 | 24/01/2022 | N/A | N/A | N/A | N/A | N/A | Plan |  |  | 2000000 | N/A | N/A | N/A
[8 empty] | Actual | [9 empty] | Actual
Maintenance /Pruning of trees planted Statewide |  | LASPARK/S-NC/NCB/002/21 |  |  | 8000000 | <N10M | NS | Plan | Pre | Prior | 17/01/2022 | 24/01/2022 | N/A | N/A | N/A | N/A | N/A | Plan |  |  | 8000000 | N/A | N/A | N/A
[8 empty] | Actual | [9 empty] | Actual
Maintenance of Generators/Servcing of Operational Vehicles |  | LASPARK/S-NC/NCB/003/22 |  |  | 2700000 | <N10M | NS | Plan | Pre | Prior | 17/01/2022 | 24/01/2022 | N/A | N/A | N/A | N/A | N/A | Plan |  |  | 2700000 | N/A | N/A | N/A
[8 empty] | Actual | [9 empty] | Actual
Maintenance of Horticultural Research Development Centres |  | LASPARK/S-NC/NCB/004/21 |  |  | 1000000 | <N10M | NS | Plan | Post | Post | 02/03/2022 | 09/03/2022 | N/A | N/A | N/A | N/A | N/A | Plan |  |  | 1000000 | N/A | N/A | N/A
[8 empty] | Actual | [9 empty] | Actual
Publicity and Enlighthement Campaign Programmes |  | LASPARK/S-NC/NC-F/NCB/001/22 |  |  | 10000000 | N10M | NS | Plan | Post | Post | 02/03/2022 | 09/03/2022 | N/A | N/A | N/A | N/A | N/A | Plan |  |  | 10000000 | N/A | N/A | N/A
[8 empty] | Actual | [9 empty] | Actual
|  | TOTAL |  |  | 335468630.44 |  |  | Plan | [9 empty] | Plan |  |  | 335468630.44
[8 empty] | Actual | [9 empty] | Actual
| Adewale Akinleye S |  |  |  |  | Adetoun Popoola
| Deputy Director (Procurement) |  |  |  |  | General Manager
| Lagos State Parks and Gardens Agency |  |  |  |  | Lagos State Parks and Gardens Agency
| Date: February 21, 2022 |  |  |  |  | Date: February 21, 2022
MEMBERS OF PROCUREMENT PLANNING COMMITTEE:
1 | Mrs. Adetoun Popoola (General Manager) - Chairman
2 | Mr. Adewale Akinleye S - Secretary
3 | Mr. Kareem A.B (Finance & Accounts) - Member
4 | Mrs. Abudu B (Planning & Budget) - Member
5 | Mr. Adetoye A.M (Project/Technical) - Member
6 | Mrs. Taiwo Cole (Legal) - Member
7 | Mr. Sunmoni A.O.J -Member
8 | Mrs. F. Aina - Member
9 | Mr. Shittu A.B - Member
10 | Mr. Olajide O - Member
11 | Mr. Balogun-Asako A - Member
12 | Mr. Olayemi O. U - Member

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE PARKS AND GARDENS AGENCY
BUDGET YEAR: 2022
| S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
|  | Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
| 1 | Procurement of Imternet facility, Computer hardware and toners | LASPARK/G/NS/001/22 |  |  | 7600000 | <10M | NS | POST | POST | Plan | 17/01/2022 | 24/01/2022 | 07/02/2022 | 21/02/2022 | 28/02/2022 | 7/032/2022 | 14/03/2022 | 2022-03-16 | 7600000 | 23/03/2022 | 30/03/2022 | 18/04/2022 | 2022-04-25 | 2022-04-27
Actual
| 2 | Procurement of uniforms and protective outfits( overalls and boots for gardeners; working tools for security officers; safety kits for dispatch rider) | LASPARK/G/NS/002/22 |  |  | 200000 | <10M | NS | POST | POST | Plan | 17/01/2022 | 24/01/2022 | N/A | N/A | N/A | N/A | 14/03/2022 | 2022-03-16 | 200000 | 23/03/2022 | 30/03/2022 | 18/04/2022 | 2022-04-25 | 2022-04-27
Actual
| 3 | CONTINUOUS TREE PLANTING: Procurement of plant seedlings for annual continous planting Statewide | LASPARK/G/NS/003/22 |  |  | 30000000 | <N50M | NS | Pre | Prior | Plan | 02/03/2022 | 09/03/2022 | 16/03/2022 | 06/04/2022 | 13/04/2022 | 20/04/2022 | 27/04/2022 | 2022-04-27 | 30000000 | 04/05/2022 | 11/05/2022 | 25/05/2022 | 01/06/2022 | 01/06/2022
Actual
| 4 | Procurement of Operational Tools & Equipment (CAP) | LASPARK/G-F/NCB/001/22 |  |  | 55000000 | <N100M | NCB | Pre | Prior | Plan | 17/01/2022 | 24/01/2022 | 07/02/2022 | 21/02/2022 | 28/02/2022 | 7/032/2022 | 14/03/2022 | 2022-03-16 | 55000000 | 23/03/2022 | 30/03/2022 | 18/04/2022 | 2022-04-25 | 2022-04-27
Actual
| 5 | Annual Tree Planting Day Celebrations | LASPARK/G/NS/004/22 |  |  | 10000000 | N10M | NS | POST | POST | Plan | 06/04/2022 | 13/04/2022 | 20/04/2022 | 04/05/2022 | 11/05/2022 | 18/05/2022 | 25/05/2022 | 2022-05-25 | 10000000 | 01/06/2022 | 08/06/2022 | 29/06/2022 | 06/07/2022 | 13/07/2022
Actual
| 6 | Procurement of fuel to 100Kva Generator; Specialized Tools & Equipment; Operational/Utility Vehicles | LASPARK/G-F/NS 002/21 |  |  | 6148450 | <N10M | NS | Pre | Prior | Plan | 06/01/2022 | 13/01/2022 | N/A | N/A | N/A | N/A | 27/01/2022 | 29/01/2022 | 6148450 | 2022-02-05 | 2022-02-12 | 2022-02-25 | 2022-03-08 | 2022-03-11
Actual
|  | TOTAL |  |  |  | 108948450 |  |  |  |  | Plan | [8 empty] | 108948450
Actual
| Adewale Akinleye S | [5 empty] | Adetoun Popoola
| Deputy Director (Procurement) | [5 empty] | General Manager
| Lagos State Parks and Gardens Agency | [5 empty] | Lagos State Parks and Gardens Agency
| Date: February 21, 2022 | [5 empty] | Date: February 21, 2022
MEMBERS OF PROCUREMENT PLANNING COMMITTEE:
1 | Mrs. Adetoun Popoola (General Manager) - Chairman
2 | Mr. Adewale Akinleye S - Secretary
3 | Mr. Kareem A.B (Finance & Accounts) - Member
4 | Mrs. Abudu B (Planning & Budget) - Member
5 | Mr. Adetoye A.M (Project/Technical) - Member
6 | Mrs. Taiwo Cole (Legal) - Member
7 | Mr. Sunmoni A.O.J -Member
8 | Mrs. F. Aina - Member
9 | Mr. Shittu A.B - Member
10 | Mr. Olajide O - Member
11 | Mr. Balogun-Asako A - Member
12 | Mr. Olayemi O. U - Member

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY/AGENCY: LAGOS STATE PARKS AND GARDENS AGENCY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | 1. Upgrade of existing Gardens into Parks (Agege Garden and Peace Garden) N250,000,000.00 2. Rehabilitation of Ndubuisi Kano Recreational Park; Muri Okunola Recreational Park and Dr. Finnih Recreational Park at N422,816,339.00. 3. Beautification of Lagos State Model College, Meiran; Ibadore and Agbowa at N113.082,632.00 | LASPARK/W/NCB/001/22 |  | 785898971 | >N500M | NCB | Lump Sum | Pre | Plan | Prior | 06/01/2022 | 13/01/2022 | 20/01/2022 | 03/02/2022 | 10/02/2022 | 17/02/2022 |  |  |  | 24/02/2022 | 02/03/2022 | 16/03/2022
Actual
2 | Upgrading of Horticultural Research Centres(Oko-Oba and Erikorodo) | LASPARK/W/NCB/002/22 |  | 5000000 | <N10M | NS | Lump Sum | Pre | Plan | Post | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A
Actual
| TOTAL |  |  | 790898971 |  |  |  |  | Plan
Actual
| Adewale Akinleye S |  |  |  | Adetoun Popoola
| Deputy Director (Procurement) |  |  |  | General Manager
| Lagos State Parks and Gardens Agency |  |  |  | Lagos State Parks and Gardens Agency
| Date: February 21, 2022 |  |  |  | Date: February 21, 2022
MEMBERS OF PROCUREMENT PLANNING COMMITTEE:
1 | Mrs. Adetoun Popoola (General Manager) - Chairman
2 | Mr. Adewale Akinleye S - Secretary
3 | Mr. Kareem A.B (Finance & Accounts) - Member
4 | Mrs. Abudu B (Planning & Budget) - Member
5 | Mr. Adetoye A.M (Project/Technical) - Member
6 | Mrs. Taiwo Cole (Legal) - Member
7 | Mr. Sunmoni A.O.J -Member
8 | Mrs. F. Aina - Member
9 | Mr. Shittu A.B - Member
10 | Mr. Olajide O - Member
11 | Mr. Balogun-Asako A - Member
12 | Mr. Olayemi O. U - Member

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE PARKS AND GARDENS AGENCY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Publicity and Enlightenment Campaign Programme | LASPARK/S-C-F/QCBS/001/21 | QCBS | Lump sum | 10000000 | Post | Plan | 04/05/2021 | 11/05/2021 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18/05/2021 | 20/05/2021 | 10000000 | 01/06/2021 | 15/06/2021 | 29/06/2021 | 06/07/2021 | 13/07/2021
[6 empty] | Post | Actual
Plan
Actual
| TOTAL |  |  |  | 10000000 |  | Plan | [14 empty] | 12000000
Actual
| Adewale Akinleye S | [5 empty] | Adetoun Popoola
| Deputy Director (Procurement) | [5 empty] | General Manager
| Lagos State Parks and Gardens Agency | [5 empty] | Lagos State Parks and Gardens Agency
| Date: February 21, 2022 | [5 empty] | Date: February 21, 2022
MEMBERS OF PROCUREMENT PLANNING COMMITTEE:
1 | Mrs. Adetoun Popoola (General Manager) - Chairman
2 | Mr. Adewale Akinleye S - Secretary
3 | Mr. Kareem A.B (Finance & Accounts) - Member
4 | Mrs. Abudu B (Planning & Budget) - Member
5 | Mr. Adetoye A.M (Project/Technical) - Member
6 | Mrs. Taiwo Cole (Legal) - Member
7 | Mr. Sunmoni A.O.J -Member
8 | Mrs. F. Aina - Member
9 | Mr. Shittu A.B - Member
10 | Mr. Olajide O - Member
11 | Mr. Balogun-Asako A - Member
12 | Mr. Olayemi O. U - Member