## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE WATERWAYS AUTHORITY
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Allowance for Senior Level Officers(incidental&Transport) | LASWA/NP/NM/001/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
2 | Allowance for Junior Level Officers. (Incidental & Transport) | LASWA/NP/NM/002/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
3 | Travel & Transport Allowance for Account Department -12months | LASWA/NP/NM/003/22 | 1440000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
4 | Payment of Waste Disposal - 12 Months | LASWA/NP/NM/004/22 | 240,000 | Plan | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 240000
Actual
5 | Payment VPN Subscription for waterguards - 12 months | LASWA/NP/NM/005/22 | 648,000 | Plan | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 54000 | 648000
Actual
6 | Payment of Monthly Utilities for GM & Secretary's Phone bills and Internet Subscription | LASWA/NP/NM/006/22 | 1,440,000 | Plan | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 1440000
Actual
7 | Payment for Servicing of Management meetings, Visitors and other ceremonies | LASWA/NP/NM/007/22 | 2,640,000 | Plan | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 220000 | 2640000
Actual
8 | Payment of Janitorial Service Fee | LASWA/NP/NM/008/22 | 600,000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
9 | Payment of Monthly DSTV Subscription | LASWA/NP/NM/009/21 | 264,000 | Plan | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 22000 | 264000
Actual
10 | Procurement Unit Yearly Expenses | LASWA/NP/NM/010/22 | 2,000,000 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 2000000.04
Actual
11 | Payment of salaries and allowances to all level of staff of the Agency | LASWA/NP/NM/011/22 | 143,838,820.80 | Plan | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 11986568.4 | 143838820.8
Actual
12 | Payment of External Auditors' Administrative Fee for Y2021 Financial Year Audit | LASWA/NP/NM/O12/22 | 1,200,000 | Plan | [5 empty] | 1200000 | [6 empty] | 1200000
Actual
13 | Payment of Peculiar allowance/staff pension/insurancce | LASWA/NP/NM/013/22 | 37,651,303.20 | Plan | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 3137608.6 | 37651303.2
Actual
14 | Newspapers subcription & social media campaigns . | LASWA/NP/NM/014/22 | 576,000 | Plan | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 48000 | 576000
Actual
15 | Payment of Contingency meetings & programmes | LASWA/NP/NM/015/22 | 5,845,318.42 | Plan | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.87 | 487109.86 | 487109.86 | 5845318.42
Actual
16 | Special Allowance for GM & Secretary's Offices | LASWA/NP/NM/016/22 | 1,500,000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 1500000
Actual
17 | Payment for Fueling of LASWA Patrol/Tugboats (Ibile Oil & Gas) & Pool Vehicles | LASWA/NP/NM/017/22 | 54,278,000 | Plan | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 4523166.66 | 54277999.92
Actual
18 | Payment of Legal Unit Yearly Expenses | LASWA/NP/NM/018/22 | 1,800,000 | Plan |  |  | 900000 |  |  |  |  | 900000 |  |  |  |  | 1800000
Actual
19 | Payment of Planning and Budget Unit Yearly Expenses | LASWA/NP/NM/019/22 | 2,000,000 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 2000000.04
Actual
20 | Payment of Audit Unit Incidental Expenses | LASWA/NP/NM/020/22 | 1,350,000 | Plan |  |  |  | 675000 |  |  | 675000 | [5 empty] | 1350000
Actual
21 | Payment Allowance for the attached CTU (Police Officers) to the Agency | LASWA/NP/NM/021/22 | 5,700,000 | Plan | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 5700000
Actual
22 | Payment of Pension Remitance | LASWA/NP/NM/022/22 | 2,400,000 | Plan | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 2400000
Actual
23 | Payment of Agency's Staff Life Assurance for Y2023 | LASWA/NP/NM/023/22 | 600,000 | Plan | [11 empty] | 600000 | 600000
|  |  |  | Actual | [12 empty] | 0
24 | Payment of Security Personnel at Jetties | LASWA/NP/NM/024/22 | 1,080,000 | Plan | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 90000 | 1080000
Actual
25 | Payment of Allowance to other staff, Phone Cards/Incidentals | LASWA/NP/NM/025/22 | 16,200,000 | Plan | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 1350000 | 16200000
Actual
26 | Payment of allowance to NYSC/Interns serving with the Authority | LASWA/NP/NM/O26/22 | 600,000 | Plan | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 600000
Actual
27 | Payment of insurance premium for LASWA Five Cowries Terminal Y2023 | LASWA/NP/NM/O27/22 | 700,000 | Plan | [12 empty] | 0
Actual
28 | Annual Pre-Loss Survey Exercise | LASWA/NP/NM/O28/22 | 200,000 | Plan | [11 empty] | 200000 | 200000
Actual
29 | Publication of LASWA Annual Magazine | LASWA/NP/NM/O29/22 | 3,000,000 | Plan | [11 empty] | 3000000 | 3000000
Actual
30 | Provision for the Establishment of LASWA Mobile Court | LASWA/NP/NM/O30/22 | 20,000,000 | Plan | [11 empty] | 20000000 | 20000000
Actual
31 | Training +B68:C118co-ordination, Monitoring and Inspection of officers attending training at different dates | LASWA/NP/NM/O31/22 | 800,000 | Plan | [5 empty] | 400000 | [5 empty] | 400000 | 800000
Actual
|  |  |  | Plan | [12 empty] | 311971442.42
| Total Cost |  |  | Actual | [12 empty] | #REF!

## Ongoing&Revalidated Projects
ONGOING/REVALIDATED PROJECTS OF 2020-2021
S/N | CONTRACT IDENTIFICATION | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  | BIDDING PERIOD (DATE |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement and deployment of U-Safe Remote-controlled life buoy |  | LASWA/G/DC/014/2021 |  | 33164237.7 | < 50million | DC | Lumpsum | Pre | Plan | Post
[10 empty] | Actual | [9 empty] | 110547459 | 2021-07-01 | 2021-07-02 | 2021-11-04
2 | Provision of Emergency Floating Clinic (Water Ambulance) |  | LASWA/G/DC/001-1/2021 |  | 40755285 | < 500million | DC | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 135850950 | 2021-11-02 | 2021-11-04 | 2022-01-22
3 | Procurement of Children and Adult Life Jackets |  | LASWA/G/NS/001/2020 |  | 14970000 | > 50million | NS | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 49900000 | 2020-05-29 | 2020-06-09 | 2020-05-22 | 2021-09-18 | 2022-02-12
4 | Procurement of office furniture, fittings and other accessories for 2021 |  | LASWA/G/NS/017/2021 |  | 8326948 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 8326948 | 2021-12-14 | 2021-12-15
5 | Procurement of Life rafts for LASWA Boats |  | LASWA/G/NS/016/2021 |  | 9669625 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9669625 | 2021-12-15 | 2021-12-15 |  | 2022-02-16 | 2022-02-18
6 | Procurement of New Air Conditioning Units at Five Cowries' Terminal |  | LASWA/G/NS/018/2021 |  | 9987882 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9987882 | 2021-12-23 | 2021-12-24 | 2021-12-15
7 | Removal of Two (2) Submerged Transporter Wrecks and Dredging Hose abandoned along Ipakodo Ferry Route |  | LASWA/S-NC/CQ/003-2/2021 |  | 22500000 | > 50million | CQ | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 75000000 | 2021-07-01 | 2021-07-02 | 2021-11-04
8 | Installation of Directional and Signages at Strategic Jetties |  | LASWA/S-NC/NS/011/2021 |  | 9960000 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9960000 | 2021-12-14 | 2021-12-15 | 2022-02-24
9 | Rerouting of Raw Power Supply from MTN to LASWA Head Office |  | LASWA/S-NC/NS/012/2021 |  | 9930000 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9930000 | 2021-12-23 | 2021-12-24 | 2021-12-15
10 | Installation of Sheltered Cabin at Ajido Jetty, Badagry |  | LASWA/W/NS/004/2021 |  | 9992027.18 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9992027.18 |  | 2021-11-04 |  | 2021-11-18 | 2021-11-18
11 | Installation of Sheltered Cabin at Ofin-Ibeshe Jetty |  | LASWA/W/NS/004/2021 |  | 9997402.18 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9997402.18 | 2021-12-21 | 2021-12-21
12 | Installation of Sheltered Cabin at Yafin Jetty, Badagry |  | LASWA/W/NS/004/2021 |  | 9999552.18 | < 50million | NS | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9999552.18 | 2021-12-21 | 2021-12-21
13 | Development of Waterways Monitoring and Data Center (WWMDC) |  | LASWA/CS/QCBS/005/2021 |  | 84000000 | < 500million | QCBS | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 280000000 | 2021-06-10 | 2021-06-11 | 2021-08-17
14 | Upgrade of LASWA -Search and Rescue (LASW-SAR) Unit Phase1 |  | LASWA/CS/QCBS/002/2021 |  | 75000000 | < 500million | QCBS | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 250000000 | 2021-06-10 | 2021-06-11 | 2021-08-09 | 2021-12-06 | 2021-12-06
15 | Establishment of Enhanced Aids to Navigation System (EAtoNs) |  | LASWA/CS/QCBS/009/2021 |  | 66976515.45 | < 500million | QCBS | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 223255051.5 | 2021-06-10 | 2021-06-11 | 2021-09-13
16 | Provision of System Dynamics and Enterprise Decision Support System |  | LASWA/CS/SSS/006/2021 |  | 101999851.4 | < 500million | SSS | Lumpsum | Pre | Plan | Prior
[10 empty] | Actual | [9 empty] | 254635289.16 | 2021-09-20 | 2021-09-21 | 2021-10-04
17 | Mapping and Assessment of Jetties/Terminals - Commando Jetty, Marina Badagry |  | LASWA/CS/IC/007/2021 |  | 9999440.8 | < 50million | IC | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 9999440.8 | 2021-12-02 | 2021-12-03
18 | Payment of insurance premium for LASWA Five Cowries Terminal Y2022 Oustanding |  | LASWA/NP/NM/O30/21 |  | 700000 | < 50million | NM | Lumpsum | Post | Plan | Post
[10 empty] | Actual | [9 empty] | 700000
| Total Cost |  |  |  | 527928766.89 |  |  |  |  | Plan | [9 empty] | #REF!
[10 empty] | Actual | [9 empty] | #REF!

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE WATERWAYS AUTHORITY
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration/Days | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference and Seminar | PPA/S-WTC/SS/001/22 |  | 24 |  | Plan |  | 7200000 |  |  | 7200000
Actual
2 | Retreat for Management Staff/ Water Guard Corps | PPA/S-WTC/IC/002/22 |  | 163 |  | Plan |  | 20000000 |  |  | 20000000
[6 empty] | Actual |  |  |  |  | 0
3 | International invitation to understdy Countries with viable Waterways and Attend Exhibitions/Workshop & Seminars | PPA/S-WTC/IC/003/22 |  |  |  | Plan |  | 43000000 |  |  | 43000000
Actual
4 | Bi-Annual Refresher Training Programmes for 110 water guard officers | PPA/S-WTC/SS/004/22 |  | 110 |  | Plan |  | 15000000 |  |  | 15000000
Actual
5 | Developing 21st century enterprenuership skills | PPA/S-WTC/SS/005/22 | To Improve business skills | 9 | 3 | Plan |  | 900000 | 117000 | 96000 | 1113000
Actual
6 | Managing Retirement Anxieties | PPA/S-WTC/SS/006/22 | To manage stress | 2 | 5 | Plan |  | 250000 | 32500 | 18000 | 300500
Actual
7 | Introduction to 21st Century Public Service Management | PPA/S-WTC/SS/007/22 | To improve efficiency | 3 | 5 | Plan |  | 375000 | 29250 | 20250 | 424500
Actual
8 | Project Management Workshop | PPA/S-WTC/SS/008/22 | To promote efficiency | 2 | 5 | Plan |  | 250000 | 19500 | 13500 | 283000
Actual
9 | Managing Minutes and Minutes Writing | PPA/S-WTC/SS/009/22 | To improve performance | 3 | 4 | Plan |  | 300000 | 23400 | 20250 | 343650
Actual
10 | Managing Work Place Conflicts | PPA/S-WTC/SS/010/22 | To enhance HR efficiency | 2 | 3 | Plan |  | 225000 | 15600 | 18000 | 258600
Actual
11 | Performance Enhancement Course in Store Supervision & Management | PPA/S-WTC/SS/011/22 | To improve performance | 1 | 5 | Plan |  | 125000 | 9750 | 6750 | 141500
Actual
12 | Managing to get results | PPA/S-WTC/SS/012/22 | To improve productivity | 4 | 4 | Plan |  | 400000 | 31200 | 27000 | 458200
Actual
13 | Introduction to IPSAS | PPA/S-WTC/SS/013/22 | For Accounting Proficiency | 3 | 5 | Plan |  | 375000 | 29250 | 20250 | 424500
Actual
14 | Understanding Human Behaviour and Emotional Intelligence | PPA/S-WTC/SS/014/22 | To improve personal relationships | 2 | 3 | Plan |  | 200000 | 11700 | 13500 | 225200
Actual
15 | Procurement for Non-Procurement officers | PPA/S-WTC/SS/015 | To enhance team work | 3 | 3 | Plan |  | 225000 | 17550 | 20250 | 262800
Actual
16 | Public Service Induction Course Phase II | PPA/S-WTC/SS/016 | For knowledge of public service | 3 | 5 | Plan |  | 375000 | 22750 | 15750 | 413500
Actual
17 | 21st Century Public Service Communication | PPA/S-WTC/SS/017 | To improve communication skill | 2 | 5 | Plan |  | 250000 | 19500 | 13500 | 283000
Actual
18 | Essentials of HR Management Metric & Analytics | PPA/S-WTC/SS/018 | To improve analytic skills | 1 | 3 | Plan |  | 75000 | 5850 | 6750 | 87600
Actual
19 | Stakeholder Relations Management | PPA/S-WTC/SS/019 | To improve relationships management skill | 2 | 2 | Plan |  | 100000 | 7800 | 13500 | 121300
Actual
20 | Data Management using MS-Excel | PPA/S-WTC/SS/020 | To enhance efficiency | 1 | 4 | Plan |  | 125000 | 7800 | 6750 | 139550
Actual
21 | Public Sector Audit Process | PPA/S-WTC/SS/021 | To improve efficiency | 1 | 3 | Plan |  | 75000 | 5850 | 6750 | 87600
Actual
22 | Understanding Medium Term Sector Strategy (MTSS) | PPA/S-WTC/SS/022 | To improve efficiency | 3 | 5 | Plan |  | 375000 | 22750 | 15750 | 413500
Actual
23 | Effective Speech and Report Writing | PPA/S-WTC/SS/023 | To improve productivity | 3 | 5 | Plan |  | 375000 | 19500 | 13500 | 408000
Actual
24 | Effective News Releases and Features Writing | PPA/S-WTC/SS/024 | To improve writing skills | 1 | 3 | Plan |  | 100000 | 3900 | 4500 | 108400
Actual
25 | Effective People Skills | PPA/S-WTC/SS/025 | To improve team work | 3 | 3 | Plan |  | 225000 | 11700 | 13500 | 250200
Actual
26 | Managing Work-Home Interface | PPA/S-WTC/SS/026 | To manage work stress | 7 | 3 | Plan |  | 525000 | 27300 | 31500 | 583800
Actual
27 | Managing Work Priorities | PPA/S-WTC/SS/027 | To improve productivity | 20 | 3 | Plan |  | 1500000 | 78000 | 90000 | 1668000
Actual
28 | Machine Learning for Data Analysis | PPA/S-WTC/SS/028 | To improve efficiency | 2 | 3 | Plan |  | 150000 | 7800 | 9000 | 166800
Actual
29 | Workshop on Cloud Computing | PPA/S-WTC/SS/029 | To enhance performance | 1 | 5 | Plan |  | 125000 | 6500 | 4500 | 136000
Actual
30 | Microsoft Power BI for Data Visualization | PPA/S-WTC/SS/030 | To improve efficiency | 1 | 4 | Plan |  | 75000 | 5200 | 4500 | 84700
Actual
31 | Digital Skills and Productivity Tools | PPA/S-WTC/SS/031 | To improve efficiency | 1 | 5 | Plan |  | 125000 | 6500 | 4500 | 136000
Actual
32 | Learning Analytics Workshop | PPA/S-WTC/SS/032 | To improve efficiency | 1 | 4 | Plan |  | 100000 | 5200 | 4500 | 109700
Actual
33 | Facilities Management Workshop | PPA/S-WTC/SS/033 | To improve performance | 1 | 5 | Plan |  | 125000 | 6500 | 4500 | 136000
Actual
34 | Working to get results | PPA/S-WTC/SS/034 | To improve productivity | 3 | 3 | Plan |  | 225000 | 11700 | 13500 | 250200
Actual
35 | Effective Audit Report Writing | PPA/S-WTC/SS/035 | To improve productivity | 1 | 3 | Plan |  | 75000 | 3900 | 4500 | 83400
Actual
36 | Customer service orientation and service charter delivery | PPA/S-WTC/SS/036 | To improve performance | 2 | 3 | Plan |  | 150000 | 7800 | 9000 | 166800
Actual
37 | Registry Procedure and Records Keeping | PPA/S-WTC/SS/037 | To improve productivity | 2 | 3 | Plan |  | 150000 | 7800 | 9000 | 166800
Actual
38 | Basic Communication skills | PPA/S-WTC/SS/038 | To enhance communication Skill | 5 | 3 | Plan |  | 375000 | 19500 | 22500 | 417000
Actual
39 | Equiping for an effective public service career | PPA/S-WTC/SS/039 | To improve performance | 3 | 3 | Plan |  | 225000 | 11700 | 13500 | 250200
Actual
40 | Preparing for Post-Service Life | PPA/S-WTC/SS/040 | To manage retirement anxieties | 2 | 5 | Plan |  | 250000 | 13000 | 9000 | 272000
Actual
[6 empty] | Plan |  |  |  |  | 0
Actual
[6 empty] | Plan |  | 95075000 | 682500 | 618000 | 96375500
| Total Cost |  |  |  |  | Actual |  | #REF! | #REF! | #REF! | #REF!

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE WATERWAYS AUTHORITY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
1 | Waterways Safety Initiative/Awareness Program: Water Savvy Prog. & Enlightenment | LASWA/CS/CQ/001/2022 | CQ | Lump sum | 40000000 | Prior | Plan | 2022-02-01 | 2022-02-18 | 2022-02-21 | 2022-02-28 | 2022-03-03 | 2022-03-04 | 2022-03-11 | 2022-03-14 | 2022-03-14 | 2022-03-17 | 2022-03-21 | 2022-03-24 | 2022-04-25 | 2022-04-28 |  | 2022-04-29 | 2022-05-06 | 2022-05-31 | 2022-11-15 | 2022-12-05
Actual
2 | Expansion of LASWA-Search & Rescue Unit (Additional Strategic Location) Phase II | LASWA/CS/SSS/002/2022 | SSS | Lumpsum | 150000000 | Prior | Plan | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-21 | 2022-03-28 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-04-26 | 2022-05-02 | 2022-05-06 | 2022-06-06 | 2022-06-09 |  | 2022-06-10 | 2022-06-13 | 2022-07-15 | 2022-12-15 | 2022-12-23
Actual
3 | Management and Maintenance of Waterways Control Center and LASWA-SAR | LASWA/CS/CQ/003/2022 | CQ | Lumpsum | 55000000 | Prior | Plan | 2022-03-07 | 2022-03-11 | 2022-03-15 | 2022-03-25 | 2022-03-29 | 2022-04-04 | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-29 | 2022-05-04 | 2022-05-08 | 2022-06-10 | 2022-06-15 |  | 2022-06-17 | 2022-06-21 | 2022-07-18 | 2022-12-16 | 2022-12-30
Actual
4 | Upgrade of Waterways Information and Data Centre (Marine Communications Equipment) Phase II | LASWA/CS/SSS/004/2022 | SSS | Lumpsum | 900000000 | Post | Plan | 2022-03-07 | 2022-03-11 | 2022-03-15 | 2022-03-25 | 2022-03-29 | 2022-04-04 | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-29 | 2022-05-04 | 2022-05-08 | 2022-06-10 | 2022-06-15 |  | 2022-06-17 | 2022-06-21 | 2022-07-18 | 2022-12-16 | 2022-12-30
Actual
5 | Update of Waterways Data Center Content/Databank (TIA of Ikoyi-Eti Osa-Ibeju Lekki-Epe Route) | LASWA/CS/QBS/005/2022 | QBS | Lumpsum | 264243996.21 | Prior | Plan | 2022-03-09 | 2022-03-18 | 2022-03-21 | 2022-03-23 | 2022-03-28 | 2022-04-04 | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-24 | 2022-04-26 | 2022-04-29 | 2022-05-31 | 2022-06-02 |  | 2022-06-03 | 2022-06-08 | 2022-06-30 | 2022-11-30 | 2022-12-05
Actual
6 | Conducting waterways Baseline Research intervention initiative/impact studies | LASWA/CS/QC/006/2022 | CQ | Lumpsum | 110330934.2 | Prior | Plan | 2022-02-11 | 2022-02-17 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-04-11 | 2022-04-15 | 2022-04-20 | 2022-05-30 | 2022-06-06 |  | 2022-06-07 | 2022-06-10 | 2022-06-29 | 2022-10-10 | 2022-10-21
Actual
7 | Y2022 Water Hyacinth Recycling Initiative | LASWA/CS/IC/007/2022 | IC | Lumpsum | 20000000 | Prior | Plan | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-07-06 | 2022-07-06 | 2022-07-06 | 2022-07-11 | 2022-07-14 | 2022-07-18 | 2022-08-19 | 2022-08-23 |  | 2022-08-24 | 2022-08-29 | 2022-09-15 | 2022-12-15 | 2022-12-23
Actual
8 | [5 empty] | Prior | Plan | 2022-05-16 | 2022-05-20 | 2022-05-30 | 2022-06-10 | 2022-06-14 | 2022-06-16 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-12 | 2022-07-15 | 2022-07-20 | 2022-08-19 | 2022-08-23 |  | 2022-08-24 | 2022-08-29 | 2022-09-16 | 2022-11-18 | 2022-11-25
Actual
9 | [5 empty] | Prior | Plan | 2022-05-16 | 2022-05-20 | 2022-05-30 | 2022-06-10 | 2022-06-14 | 2022-06-16 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-12 | 2022-07-15 | 2022-07-20 | 2022-08-19 | 2022-08-23 |  | 2022-08-24 | 2022-08-29 | 2022-09-16 | 2022-11-18 | 2022-11-25
Actual
10 | [6 empty] | Plan | [18 empty] | 2022-02-28 | 2022-03-07
Actual
11 | [6 empty] | Plan
Actual
12 | [6 empty] | Plan
Actual
13
14 | [6 empty] | Plan
Actual
| Total Cost |  |  |  | 1539574930.41 |  | Plan | [14 empty] | #REF!
[7 empty] | Actual | [14 empty] | #REF!

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE WATERWAYS AUNTHORITY
BUDGET YEAR: 2022
S/N | Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Repair and Replacement of parts of Five Cowries Terminal Floating Potoon | LASWA/S-NC/NS/001/2022 |  |  | 15000000 | <50million |  | Plan | Prior | Prior | 2022-02-21 | 2022-02-25 | 2022-03-01 | 2022-03-11 | 2022-03-15 | 2022-03-21 | 2022-03-25 | Plan | 2022-04-22 | 2022-04-25 |  | 2022-04-28 | 2022-05-20 | 2023-03-31 | 2023-03-31
[8 empty] | Actual | [9 empty] | Actual
2 | Annual Drydocking and replacement of parts of patrol boats | LASWA/S-NC-F/NS/002/2022 |  | 6 | 17500000 | <50million | NS | Plan | Prior | Prior | 2022-07-04 | 2022-07-08 | 2022-07-11 | 2022-07-25 | 2022-07-28 | 2022-08-02 | 2022-08-05 | Plan | 2022-09-05 | 2022-09-07 |  | 2022-09-09 | 2022-09-23 | 2022-11-21 | 2022-11-30
[8 empty] | Actual | [9 empty] | Actual
3 | Wreck Identification, Marking and Removals | LASWA/S-NC/NCB/003/2022 |  | 1 | 150000000 | >50million | NCB | Plan | Pre | Prior | 2022-03-14 | 2022-03-17 | 2022-03-21 | 2022-04-04 | 2022-04-08 | 2022-04-13 | 2022-04-18 | Plan | 2022-05-20 | 2022-05-24 |  | 2022-05-27 | 2011-06-17 | 2022-08-19 | 2022-08-26
[8 empty] | Actual | [9 empty] | Actual
4 | Maintenance of Office Building: Repairs of Acs, Electricals, Doors, Toilets Etc | LASWA/S-NC-F/NS/004/2022 |  | varied | 3355000 | <50million | NS | Plan | Post | Post | 2022-01-26 | 2022-01-28 | 2022-03-17 | 2022-04-21 | 2022-04-25 | 2022-04-29 | 2022-05-03 | Plan | 2022-05-31 | 2022-06-02 |  | 2022-06-06 | 2022-06-16 | 2022-12-21 | 2022-12-28
[8 empty] | Actual | [9 empty] | Actual
5 | Façade/Glass Cleaning | LASWA/S-NC-F/NS/005/2022 |  | 1 | 2000000 | <50million | NS | Plan | Post | Post | 2022-07-25 | 2022-07-28 | 2022-08-01 | 2022-08-05 | 2022-08-10 | 2022-08-15 | 2022-08-17 | Plan | 2022-08-26 | 2022-08-30 |  | 2022-09-02 | 2022-09-16 | 2022-11-15 | 2022-11-30
[8 empty] | Actual | [9 empty] | Actual
6 | Periodic Repair and Servicing of Patrol Boats - 1st - 4th Quarter | LASWA/S-NC-F/NS/006/2021 |  | 6 | 4200000 | <50million | NS | Plan | Post | Post | 2022-02-14 | 2022-02-17 | 2022-02-21 | 2022-03-04 | 2022-03-09 | 2022-03-14 | 2022-03-17 | Plan | 2022-04-15 | 2022-04-19 |  | 2022-04-20 | 2022-05-20 | 2022-12-23 | 2022-12-30
[8 empty] | Actual | [9 empty] | Actual
7 | Servicing and Maintenance of Official and Utility vehicles | LASWA/S-NC/NS/007/2022 |  | 5 | 2320000 | <50million | NS | Plan | Post | Post | 2022-02-07 | 2022-02-09 | 2022-02-15 | 2022-02-22 | 2022-02-24 | 2022-02-22 | 2022-02-24 | Plan | 2022-03-18 | 2022-03-22 |  | 2022-03-25 | 2022-04-15 | 2022-12-16 | 2022-12-23
[8 empty] | Actual | [9 empty] | Actual
8 | Annual Water Hyacinth Pegging and Clearing | LASWA/S-NC/NS/008/2022 |  | 1 | 70000000 | >50million | NS | Plan | Prior | Prior | 2022-05-04 | 2022-05-11 | 2022-06-15 | 2022-07-06 | 2022-07-11 | 2022-07-14 | 2022-07-18 | Plan | 2022-08-19 | 2022-08-23 |  | 2022-08-29 | 2022-09-15 | 2022-12-15 | 2022-12-23
[8 empty] | Actual | [9 empty] | Actual
9 | Projects Commissioning and Other Ceremonial Events/Programs | LASWA/S-NC/NS/009/2022 |  |  | 10000000 | <50million | NS | Plan |  |  | 2022-03-07 | 2022-03-11 | 2022-03-21 | 2022-04-04 | 2022-04-06 | 2022-04-08 | 2022-04-15 | Plan | 2022-05-20 | 2022-05-25 |  | 2022-05-30 | 2022-06-20 | 2022-11-30 | 2022-12-15
[8 empty] | Actual | [9 empty] | Actual
10 | [7 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
11 | [7 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
12 | [7 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
| Total Cost |  |  |  | 241875000 |  |  | Plan | [12 empty] | #REF!
[8 empty] | Actual | [12 empty] | #REF!

## goods
PROCUREMENT PLAN FOR GOODS
MINISTRY/AGENCY: LAGOS STATE WATERWAYS AUTHORITY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization/ Advance Payment | Substantial Completion/Installation | Inspection & Final Acceptance
1 | Procurement of 1 Unit High Performance Work Boat | LASWA/G/NCB/001/2022 |  | 1 | 78600000 | > 50million | NCB | Pre | Prior | Plan | 2022-03-01 | 2022-03-08 | 2022-03-14 | 2022-03-25 | 2022-03-29 | 2022-03-31 | 2022-04-30 | 2022-05-05 |  | 2022-05-10 | 2022-05-17 | 2022-05-31 | 2022-11-30 | 2022-12-08
Actual
2 | Procurement of 8 New Boat Engines | LASWA/G/NCB/002/2022 |  | 8 | 140000000 | < 500million | NS | Pre | Prior | Plan | 2022-03-02 | 2022-03-09 | 2022-03-15 | 2022-03-28 | 2022-03-30 | 2022-04-01 | 2022-05-02 | 2022-05-06 |  | 2022-05-11 | 2022-05-18 | 2022-06-30 | 2022-07-08 | 2022-07-11
Actual
3 | Procurement/Production of Marine Weed/Waste Harvester Machine (local Production) | LASWA/G/NCB/003/2022 |  | 1 | 300000000 | < 500million | NCB | Pre | Prior | Plan | 2022-03-04 | 2022-03-14 | 2022-03-17 | 2022-03-30 | 2022-04-04 | 2022-04-06 | 2022-05-06 | 2022-05-09 |  | 2022-05-13 | 2022-05-20 | 2022-07-01 | 2022-09-30 | 2022-10-05
Actual
4 | Production of 2,000 units Boat Number Plates (Boats Numbering System) | LASWA/G/NS/004/2022 |  | 2000 | 50000000 | < 50million | NS | Pre | Prior | Plan | 2022-04-04 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-26 | 2022-04-29 | 2022-05-31 | 2022-06-02 |  | 2022-06-06 | 2022-06-13 | 2022-07-15 | 2022-08-01 | 2022-08-05
Actual
5 | Procurement of high profile laptops for the office | LASWA/G/NS/005/2022 |  | 10 | 3800000 | < 50million | NS | Post | Post | Plan | 2022-03-07 | 2022-03-14 | 2022-03-16 | 2022-03-23 | 2022-03-25 | 2022-03-30 | 2022-04-30 | 2022-05-05 |  | 2022-05-09 | 2022-05-13 | 2022-06-14 | 2022-05-20 | 2022-05-24
Actual
6 | Procurement of office furniture, fittings and other accessories | LASWA/G/NS/006/2022 |  | varied | 14530843.24 | < 50million | NS | Post | Post | Plan | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-06-01 | 2022-06-08 | 2022-07-08 | 2022-07-13 |  | 2022-07-15 | 2022-07-22 | 2022-09-09 | 2022-08-19 | 2022-08-23
Actual
7 | Provision of Office Fittings for Water Guards Sheltered Cabins at the Jetties/Terminals | LASWA/G/NS/007/2022 |  | varied | 120000000 | <500million | NS | Post | Post | Plan | 2022-02-09 | 2022-02-16 | 2022-02-23 | 2022-03-04 | 2022-03-08 | 2022-03-14 | 2022-04-22 | 2022-04-26 |  | 2022-04-27 | 2022-05-06 | 2022-06-22 | 2022-06-03 | 2022-06-07
Actual
8 | Provision of Complete Set of Uniforms for Water Guard Officers | LASWA/G/NS/008/2022 |  | 103 | 7226000 | <50million | NS | Post | Post | Plan | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-02 | 2022-06-09 | 2022-07-11 | 2022-07-14 |  | 2022-07-16 | 2022-07-23 | 2022-10-14 | 2022-09-23 | 2022-09-30
Actual
9 | Personal Protective Equipment for waterguards | LASWA/G/NS/009/2022 |  | varied | 5000000 | <50million | NS | Post | Post | Plan | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-02 | 2022-06-09 | 2022-07-11 | 2022-07-14 |  | 2022-07-16 | 2022-07-23 | 2022-10-14 | 2022-09-23 | 2022-09-30
Actual
10 | Procurement of office toiletries, Dispenser water & tyre for utility vehicles | LASWA/G-F/NS/010/2022 |  | varied | 1140000 | < 50million | NS | Post | Post | Plan | 2022-01-13 | 2022-01-17 | 2022-01-20 | 2022-01-27 | 2022-02-03 | 2022-02-07 | 2022-02-25 | 2022-02-28 |  | 2022-03-03 | 2022-03-10 | 2022-03-29 | 2022-12-29 | 2022-12-30
Actual
11 | Procurement of Stationaries | LASWA/G-F/NS/011/2022 |  | varied | 3242000 | < 50million | NS | Post | Post | Plan | 2022-01-14 | 2022-01-18 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-07 | 2022-02-11 | 2022-02-18 |  | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-12-21 | 2022-12-23
Actual
12 | Procurement of Printer Accessories for maintenance and servicing | LASWA/G-F/NS/012/2022 |  |  | 1260000 | < 50million | NS | Post | Post | Plan | 2022-01-14 | 2022-01-18 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-07 | 2022-02-11 | 2022-02-18 |  | 2022-02-25 | 2022-03-11 | 2022-03-18 | 2022-12-21 | 2022-12-23
Actual
13 | Procurement of Clinic Accessories and Consumables for the Establishment of LASWA Clinic/Bay | LASWA/G/NS/013/2022 |  |  | 24000000 | < 50million | NS | Pre | Prior | Plan | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-25 | 2022-03-25 | 2022-03-30 | 2022-04-29 | 2022-05-04 |  | 2022-05-10 | 2022-05-12 | 2022-06-30 | 2022-07-30 | 2022-08-05
Actual
14
15
16
17
18
19
| Total Cost |  |  |  | 670198843.24 |  |  |  |  | Plan | [8 empty] | #REF!
[10 empty] | Actual | [8 empty] | #REF!

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE WATERWAYS AUTHORITY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  | BIDDING PERIOD (DATE |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
| CONSTRUCTION AND UPGRADE OF EXISTING JETTIES | [10 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Operationalization and Renovation of 25 jetties/Terminals |  | LASWA/W/NS/001/2022 |  | 10122118 | > 50million | NS | Lumpsum | Post | Plan | Post | 2022-02-07 | 2022-02-15 | 2022-02-21 | 2022-02-25 | 29/2/22 | 2022-03-02 | 2002-04-04 | 2022-04-07 |  | 2022-04-08 | 2022-04-15 | 2022-05-08 | 2022-06-08 | 2022-06-13
Actual
2 | Rehabilitation and Installation of Floating Pontoon at LASWA Annex |  | LASWA/W/NCB/002-1/2022 | 1 | 100000 | >500million | NCB | Lumpsum | Pre | Plan | Prior | 2022-03-01 | 2022-03-07 | 2022-03-14 | 2022-03-28 | 2022-03-31 | 2022-04-07 | 2022-05-09 | 2022-05-11 |  | 2022-05-13 | 2022-05-19 | 2022-06-20 | 2022-07-19 | 2022-07-27
Actual
3 | Installation of Floating Jetties/Pontoons at Etegbin Jetty |  | LASWA/W/NCB/002-2/2022 | 2 | 100000 | >500million | NCB | Lumpsum | Pre | Plan | Prior | 2022-03-01 | 2022-03-07 | 2022-03-14 | 2022-03-28 | 2022-03-31 | 2022-04-07 | 2022-05-09 | 2022-05-11 |  | 2022-05-13 | 2022-05-19 | 2022-06-20 | 2022-07-19 | 2022-07-27
Actual
4 | Installation of Floating Pontoon at Ibasa Jetty |  | LASWA/W/NCB/002-3/2022 | 3 | 100000 | >500million | NCB | Lumpsum | Pre | Plan | Prior | 2022-03-01 | 2022-03-07 | 2022-03-14 | 2022-03-28 | 2022-03-31 | 2022-04-07 | 2022-05-09 | 2022-05-11 |  | 2022-05-13 | 2022-05-19 | 2022-06-20 | 2022-07-19 | 2022-07-27
Actual
5 | Upgrade of state-owned jetties/terminals (Provision of sub-stations) Phase II |  | LASWA/W/DC/003/2022 |  | 70011018.46 | <500million | NS | Lumpsum | Pre | Plan | Prior | 2022-02-15 | 2022-02-21 | 2022-02-28 | 2022-03-08 | 2022-03-11 | 2022-03-16 | 2022-04-22 | 2022-04-26 |  | 2022-05-02 | 2022-05-09 | 2022-06-06 | 2022-08-08 | 2022-08-12
Actual
6 | [9 empty] | Plan
Actual
7 | [9 empty] | Plan
Actual
8 | [9 empty] | Plan
Actual
9 | [9 empty] | Plan
Actual
10 | [9 empty] | Plan
Actual
| Total Cost |  |  |  | 80433136.46 |  |  |  |  | Plan | [9 empty] | #REF!
[10 empty] | Actual | [9 empty] | #REF!

## Summary
SUMMARY TABLE FOR Y2022 PROCUREMENT PLAN
DESCRIPTION | PLAN/ ACTUAL | TOTAL
NON-PROCURABLE | PLAN | 311971442.42
| ACTUAL | #REF!
TRAINING/WORKSHOP/SEMINAR | PLAN | 96375500
| ACTUAL | #REF!
NON-CONSULTING SERVICES | PLAN | 241875000
| ACTUAL | #REF!
CONSULTING SERVICES | PLAN | 1539574930.41
| ACTUAL | #REF!
GOODS | PLAN | 670198843.24
| ACTUAL | #REF!
WORKS | PLAN | 80433136.46
| ACTUAL | #REF!
ONGOING/REVALIDATED 2020-2021 PROJECTS | PLAN | #REF!
| ACTUAL | 527928766.89
TOTAL | PLAN | #REF!
| ACTUAL | #REF!