## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
LAW REFORM COMMISSION
| MINISTRY/ AGENCY: LAW REFORM COMMISSION | [5 empty] | 2022
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVEL & TRANSPORT EXPENSES | LRC/NP/NM/001/2022 | 2,460,000:00 | Plan | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 205,000:00 | 2,460,000:00
Actual
2 | PAYMENT OF PROFESSIONAL FEES | LRC/NP/NM/002/2022 | 1,000,000:00 | Plan | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 83,333:33 | 1,000,000:00
Actual
3 | LEGAL PROFESSIONAL EXPENSES | LRC/NP/NM/003/2022 | 6,300,000:00 | Plan | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 525,000:00 | 6,300,000:00
Actual
4 | BANKING OPERATION EXPENSES | LRC/NP/NM/004/2022 | 2,800,000:00 | Plan | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 233,333:00 | 2,800,000:00
Actual
5 | UPKEEP & MAINTENANCE ALLOWANCE | LRC/NP/NM/005/2022 | 1,440,000:00 | Plan | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 120,000:00 | 1,440,000:00
Actual
6 | SERVICING OF MEETING (HONORARIUM) | LRC/NP/NM/006/2022 | 500,000:00 | Plan | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 41,666:67 | 500,000:00
Actual
7 | SPECIAL PROGRAMMES | LRC/NP/NM/007/2022 | 45,000,000:00 | Plan | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 3,750,000:00 | 45,000.000:00
Actual
8 | DISPOSABLE ITEMS (MISCELLANEOUS) | LRC/NP/NM/008/2022 | 1,000,000:00 | Plan
[5 empty] | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 83,333:00 | 1,000,000:00
Actual
9 | PAYMENT OF BOARD MEMBERS SITTING ALLOWANCE | LRC/NP/NM/009/2022 | 2,250,000:00
|  |  |  | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 187,500:00 | 2,250,000:00
|  |  |  | Actual | [12 empty] | 4,992,000:00
10 | PAYMENT OF GENERAL UTILITY( RECHARGE CARD & INTERNET ETC) | LRC/NP/NM/010/2022 | 4,992,000:00 | Plan | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00 | 416,000:00
Actual
|  |  | 67,742,200:00 | [13 empty] | 67,742,200:00

## Front Cover
LAGOS STATE GOVERNMENT
LAW REFORM COMMISSION
YEAR 2022
PROCUREMENT PLAN

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2022 (LAW REFORM COMMISSION)
NON CONSULTANCY
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | LRC/S-NC-F/NS/001/2022 | N/A | 1 | 678,000:00 | <N10M | NS | Plan | POST | POST | 2022-03-05 | 2022-03-12 | 2022-03-24 | 2022-04-09 | N/A | 2022-04-17 | N/A | PLAN | 22/05/22 | 23/05/22 | 678,000:00 | 2022-06-07 | 2022-07-14 | 2022-09-09 | 2022-09-26
Actual
RETREAT | LRC/S-NC/NS/002/2022 | N/A |  | 20,000,000:00 | <N20 | NS | Plan | POST | POST | 2022-04-02 | 2022-04-09 | 2022-04-19 | 2022-04-30 | N/A | 2022-05-07 | 2019-03-26 | Plan | 22/05/22 | 23/05/22 | 20,000,000:00 | 2022-05-20 | 2022-05-27 | 2022-06-11 | 2022-06-25
[7 empty] | Actual | [9 empty] | Actual
SERVICE OF MOTOR VEHICLE REPAIRS & MAINTENANCE | LRC/S-NC/NS/003/2022 | N/A | 1 |  | <N10 | NS | Plan |  | POST | 2022-04-02 | 2022-04-09 | 2022-04-19 | 2022-04-30 | N/A | 2022-05-07 | 2019-03-26 | Plan | 22/05/22 | 23/05/22 | 130,000:00 | 2022-05-20 | 2022-05-27 | 2022-06-11 | 2022-06-25
|  |  |  | 130,000:00 |  |  | Actual | [9 empty] | Actual
BUILDING RENOVATION | LRC/S-NC/NS/004/2022 | N/A |  | 14,388,092:00 | <N20 | NS | Plan |  | POST | 2022-04-02 | 2022-04-09 | 2022-04-19 | 2022-04-30 | N/A | 2022-05-07 | 2019-03-26 | Plan | 22/05/22 | 23/05/22 | 14,388,092:00 | 2022-05-20 | 2022-05-27 | 2022-06-11 | 2022-06-25
|  |  |  | 35,196,092:00 | [15 empty] | 35,196,092:00

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
| MINISTRY/ AGENCY: | [14 empty] | LAW REFORM COMMISSION
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
|  | LRC/CS/NS/001/2022 |  |  | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | INFORMATION TECHNOLOGY/DATA BASE DEVELOPMENT |  | NS |  | 3,086,200:00 | POST | Plan | 5/03/2022 | 12/03/2022 | 19/03/2022 | 9/04/2022 | 16/04/2022 | 23/04/2022 | 14/05/2022 | 21/05/2022 | 28/05/2022 | 4/06/2022 | 18/06/2022 | 25/06/2022 | 23/07/2022 | 24/07/2022 | 3.086,200:00 | N/A | N/A | 30/07/2022 | 6/08/2022
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
[5 empty] | 3,086,200:00 |  | Plan | [14 empty] | 3,086,200:00
Actual

## goods
PROCUREMENT PLAN FOR GOODS
MINISTRY/AGENCY: LAW REFORM COMMISSION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF MOTOR VEHICLE FUEL CONSUMPTIONS | LRC/G-F/NS/001/22 | N/A |  | 520,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
2 | PROCUREMENT OF STATIONERY | LRC/G-F/NS/002/22 | N/A | VARIOUS | 2,220,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
3 | PROCUREMENT OF CONSUMABLES FOR HUMAN RESOURCES DEPT | LRC/G/NS/003/22 | N/A | VARIOUS | 3,000,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
4 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFIT | LRC/G/NS/004/22 | N/A |  | 300,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
5 | PROCUREMENT OFMATERIALS & EQUIPMENT FOR ICT | LRC/G/NS/005/22 | N/A |  | 1,800,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
| PROCUREMENT OF MATERIALS &EQUIPMENT FOR PROCUREMENT UNIT | LRC/G/NS/006/22 | N/A |  | 1,800,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
6
7 | PROCUREMENT OF AUDIT TOOLS(MATERIALS & EQUIPMENTS ETC) | LRC/G/NS/007/22 | N/A |  | 1,800,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
8 | PROCUREMENT OF PUBLIC AFFAIRS TOOLS(MATERIALS & EQUIPMENTS ETC) | LRC/G/NS/008/22 | N/A |  | 1,800,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
Actual
9 | PROCUREMENT OF PLANNING RESEARCH & STATISTICS UNIT TOOLS (MATERIALS & EQUIPMENTS ETC) | LRC/G/NS/009/22 | N/A |  | 1,800,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
10 | PROCUREMENT OF PRINTING DOCUMENTS OF COMPENDIUM OF LAWS | LRC/G/NCB/0010/22 | N/A |  | 100,000,000:00 | <100M | NCB | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
11 | PROCUREMENT OF REFURBLISHMENT OF VEHICLE | LRC/G/NS/0011/22 | N/A |  | 2,500,000:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
Actual
12 | SPECIAL DUTIES EXPENSES | LRC/G/NS/0012/22 | N/A |  | 7,427,736:00 | <10M | NS | POST | POST | Plan | 1/3/2022 | 8/3/2022 | 15/3/2022 | 22/3/2022 | 29/3/2022 | 5/4/2022 | 12/4/2022 | 19/4/2022 |  | 26/4/2022 | 3/5/2022 | 2022-10-05 | 17/5/2022 | 24/5/2022
124,947,736:00

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAW REFORM COMMISSION
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | [10 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
2 | [8 empty] | Plan | POST | 2022-03-05 | 2022-03-12 | 22/3/2022 | 2022-03-04 | 2022-10-03 | 17/4/2022
[9 empty] | Actual | [11 empty] | 2022-06-04 | 2022-07-06 | 14/7/2022 | 2022-09-09
3 | [8 empty] | Plan | POST | 2022-03-05 | 2022-03-12 | 22/3/2022 | 2022-03-04 | 2022-10-03 | 17/4/2022 |  |  |  |  | 2022-06-04 | 2022-07-06 | 14/7/2022 | 2022-09-09
Actual
[9 empty] | Plan | POST | 2022-03-05 | 2022-03-12 | 22/3/2022 | 2022-03-04 | 2022-10-03 | 17/4/2022 |  |  |  |  | 2022-06-04 | 2022-07-06 | 14/7/2022 | 2022-09-09
Actual
Plan
Actual

## trg conf wsh (new)
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAW REFORM COMMISSION
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | EXECUTIVE SECRETARY 1. STRATEGIES FOR LEADERSHIP DEVELOPMENT & SUCCESSFUL SUCCESSION. | LRC/S-WTC/SS/001A/2022 | CAPACITY BUILDING | 1 | 25TH-29TH JULY 2022 | Plan | ABUJA | 115,000:00 | 158,000:00 | 427,000:00 | N700,000:00
| 2. LEADING WITH CREATIVE EDGE. | LRC/S-WTC/SS/001B/2022 | CAPACITY BUILDING | 1 | 15TH-19TH AUGUST 2022 | Plan | LAGOS | 115,000:00 | 18,000:00 | 15,000:00 | N148,000:00
| 3. NIGERIAN BAR CONFERENCE. | LRC/S-WTC/SS/00C/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER 2022 | Plan | LAGOS | 25,000:00 | 8,450:00 | 424,000:00 | N457,450:00
| 4. BEST PRACTICE DRAFTING STANDARD TERMS AND CONDITION. | LRC/S-WTC/SS/001D/2022 | CAPACITY BUILDING | 1 | 17TH-20TH MAY 2022 | Plan | LAGOS | 250,000:00 | 33,800:00 | 12,000:00 | N295,800:00
| 5. CORPORATE GOVERNANCE AND BUSINESS MANAGEMENT. | LRC/S-WTC/SS/001E/2022 | CAPACITY BUILDING | 1 | 3DAYS | Plan | ONLINE | 727,121:00 | 25,000:00 | 12,000:00 | N764,121:00
| 6. CERTIFICATE IN GOVERNANCE, RISK & COMPLIANCE | LRC/S-WTC/SS/001F/2022 | CAPACITY BUILDING | 1 | 3DAYS | Plan | ONLINE | 868,391:00 | 30,000:00 | 12,000:00 | N910,391:00
2 | DEPUTY DIRECTOR(16) 1. LAWMAKING AND LEGISLATIVE DRAFTING | LRC/S-WTC/SS/002A/2022 | CAPACITY BUILDING | 1 | 6TH-9TH SEPT. 2022 | Plan | LAGOS | 250,000:00 | 20,800:00 | 12,000:00 | N282,800:00
| 2. CURRENT TRENDS IN LEGISLATIVE DRAFTING | LRC/S-WTC/SS/002B/2022 | CAPACITY BUILDING | 1 | 25TH-28TH OCTOBER 2022 | Plan | LAGOS | 250,000:00 | 20,800:00 | 12,000:00 | N282,800:00
| 3. NIGERIAN BAR CONFERENCE. | LRC/S-WTC/SS/002/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER 2022 | Plan | LAGOS | 25,000:00 | 5,200:00 | 380,000:00 | N410,200:00
3 | DEPUTY DIRECTOR(16) 1. NIGERIAN BAR CONFERENCE | LRC/S-WTC/SS/003A/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER 2022 | Plan | LAGOS | 25,000:00 | 5,200:00 | 380,000:00 | N410,200:00
| 2. EMPLOYEE REALTIONS AND THE LAW | LRC/S-WTC/SS/003B/2022 | CAPACITY BUILDING | 1 |  | Plan | LAGOS | 250,000:00 | 20,800:00 | 12,000:00 | N282,800:00
| 3. ALTERNATIVE DISPUTE RESOLUTION STRATEGIES | LRC/S-WTC/SS/003C/2022 | CAPACITY BUILDING | 1 | 30TH -2ND SEPT 2022 | Plan | LAGOS | 250,000:00 | 20,800:00 | 12,000:00 | N282,800:00
4 | DEPUTY DIRECTOR(16) 1. CURRENT TRENDS IN LEGISLATIVE DRAFTING | LRC/S-WTC/SS/004A/2022 | CAPACITY BUILDING | 1 | 25TH-28TH OCTOBER 2022 | Plan | LAGOS | 250,000:00 | 20,800:00 | 12,000:00 | N282,800:00
| 2. NIGERIAN BAR CONFERENCE | LRC/S-WTC/SS/004B/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER 2022 | Plan | LAGOS | 25,000:00 | 5,200:00 | 380,000:00 | N410,200:00
| 3. GRIEVANCE DISCIPLINE AND DISMISSAL | LRC/S-WTC/SS/004C/2022 | CAPACITY BUILDING | 1 | 9TH-12TH AUGUST 2022 | Plan |  | 250,000:00 | 20,800:00 | 12,000:00 | N282,800:00
5 | ASSISTANT DIRECTOR (15) 1. CORPORATE GOVERNANCE AND BUSINESS MANAGEMENT | LRC/S-WTC/SS/005A/2022 | CAPACITY BUILDING | 1 | 3DAYS | Plan | ONLINE | 727,121:00 | 25,000:00 | 12,000:00 | N764,121:00
| 2. PRACTICAL TOOLS FOR EFFECTIVE LEADERSHIP | LRC/S-WTC/SS/005B/2022 | CAPACITY BUILDING | 1 | 5TH-8TH AUGUST 2022 | Plan | ALPHA PARTNERS LAGOS | 190,000:00 | 25,000:00 | 12,000:00 | N222,800:00
6 | ASSISTANT DIRECTOR (15) 1. MOTIVATIONAL LEADERSHIP: DEVELOPING INSPIRATION AND SUCCESS | LRC/S-WTC/SS/006A/2022 | CAPACITY BUILDING | 1 | 16TH -19TH NOVEMBER 2022 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 727,121:00 | 25,000:00 | 12,000:00 | N764,121:00
| 2. PRACTICAL TOOLS FOR EFFECTIVE LEADERSHIP | LRC/S-WTC/SS/006B/2022 | CAPACITY BUILDING | 1 | 4DAYS | Actual |  | 190.000:00 | 25,000:00 | 12,000:00 | N222,800:00
7 | ASSISTANT DIRECTOR (15) 1. Y2022 ANNUAL CONFERENCE OF THE ASSOCIATION OF NATIONAL ACCOUNTANT OF NIGERIAN (ANAN) | LRC/S-WTC/SS/007A/2022 | CAPACITY BUILDING | 1 | 20TH -22ND NOVEMBER, 2022 | Plan | ALPHA PARTNERS PROFESSIONAL TRAINING CONFERENCE CENTRE, LAGOS | 55,000:00 | 125,000:00 | 380,000:00 | N560,000:00
| 2. REINVENTING LEADERSHIP IN A COVID-19 WORLD | LRC/S-WTC/SS/007B/2022 | CAPACITY BUILDING | 1 | 18TH JULY 2022 | Actual |  | 357,500:00 | 20,000:00 | 12,000:00 | N389,500:00
8 | CHIEF STATE COUNSEL (14) 1. NIGERIAN BAR CONFERENCE | LRC/S-WTC/SS/008A/2022 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER 2021 | Plan | LAGOS | 25,000:00 | 3,250:00 | 276,000:00 | N313,250:00
| 2. GRIEVANCE, DISCIPLINE AND DISMISSAL | LRC/S-WTC/SS/008B/2022 | CAPACITY BUILDING | 1 | 5DAYS | Actual |  | 250,000:00 | 13,000:00 | 9,000:00 | N272,000:00
| 3. EMPLOYEE RELATION AND THE LAW | LRC/S-WTC/SS/008C/2022 | CAPACITY BUILDING | 1 | 4DAYS | Plan |  | 250,000:00 | 13,000:00 | 9,000:00 | N272,000:00
9 | CHIEF PROCUREMENT OFFICER (14) 1. PROCUREMENT PLANNING FOR WORKS, GOODS AND SERVICES IN MDAs AND PRIVATE SECTOR | LRC/S-WTC/SS/009A/2022 | CAPACITY BUILDING | 1 | 11TH-13TH MAY,2022 | Plan | ABUJA | 100,000:00 | 123,500:00 | 286,500:00 | N510,000:00
| 2. PRIORITY MANAGEMENT: OPTIMISING TIME, WORK FLOW AND PRODUCTIVITY | LRC/S-WTC/SS/009B/2022 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER 2022 | Actual | LAGOS | 190,000:00 | 13,000:00 | 9,000:00 | N212,000:00
10 | CHIEF ACCOUNTANT (14) 1. CORPORATE GOVERNANCE AND BUSINESS MANAGEMENT | LRC/S-WTC/SS/010A/2022 | CAPACITY BUILDING | 1 | 3DAYS | Plan | ONLINE | 727,121:00 | 25,000:00 | 9,000:00 | N761,121:00
11 | ASSISTANT CHIEF STATE COUNSEL (13) 1. NIGERIAN BAR CONFERENCE | LRC/S-WTC/SS/011A/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER,2022 | Plan | LAGOS | 25,000:00 | 13,000:00 | 285,000:00 | N323,000:00
| 2. EMPLOYEE REALTIONS AND THE LAW | LRC/S-WTC/SS/011B/2022 | CAPACITY BUILDING | 1 | 5DAYS |  | LAGOS | 250,000:00 | 13,000:00 | 9,000:00 | N272,000:00
| 3. NEGOTIATION AND DISPUTE MANAGEMENT STRATEGIES | LRC/S-WTC/SS/011C/2022 | CAPACITY BUILDING | 1 | 31STMAY-3RD JUNE 2022 | Actual | LAGOS | 190,000:00 | 13,000:00 | 9,000:00 | N212,000:00
12 | ASSISTANT CHIEF PLANNING OFFICER (13) 1. NIEGRIA ECONOMIC SOCIETY (NES) ANNUAL CONFERENCE | LRC/S-WTC/SS/012A/2022 | CAPACITY BUILDING | 1 | 3DAYS | Plan | LAGOS | 30,000:00 | 123,500:00 | 175,500:00 | N329,000:00
| 2. NIGERIA STATISTICAL ASSOCIATION ANNUAL CONFERENCE | LRC/S-WTC/SS/012B/2022 | CAPACITY BUILDING | 1 |  |  | LAGOS | 30,000:00 | 123,500:00 | 175,500:00 | N329,000:00
| 3. STRATEGIC PLANNING AND GOAL SETTING: SETTING BUSINESS GOALS, TARGETS AND DELIVERABLES | LRC/S-WTC/SS/012C/2022 | CAPACITY BUILDING | 1 | 10TH-13TH MAY, 2022 | Actual | L AGOS | 190,000:00 | 13,000:00 | 9,000:00 | N212,000:00
LAGOS
13 | PRINCIPAL STATE COUNSEL (12) 1. NIGERIAN BAR CONFERENCE | LRC/S-WTC/SS/013A/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER 2022 | Plan | LAGOS | 25,000:00 | 13,000:00 | 190.750:00 | N228,750:00
| 2. ALTERNATIVE DISPUTE RESOLUTION STRATEGIES | LRC/S-WTC/SS/013B/2022 | CAPACITY BUILDING | 1 | 6TH-9TH SEPT 2022 | Actual | LAGOS | 250,000:00 | 13,000:00 | 6,750:00 | N269,750:00
14 | PRINCIPAL ACCOUNTANT (12) 1. INSTITUTE OF CHARTERED ACCOUNTANT OF NIGERIA (ICAN) | LRC/S-WTC/SS/014A/2022 | CAPACITY BUILDING | 1 | 5DAYS | Plan | ABUJA | 180,000:00 | 119,000:00 | 227,550:00 | N526,550:00
| 2. PRACTICAL SAGE 50, QUICKBOOKS & FORMATTING MICROSOFT EXCEL AS ACCOUNTING PACKAGE | LRC/S-WTC/SS/014B/2022 | CAPACITY BUILDING | 1 | 3RD-7TH OCTOBER 2022 | Actual | ILORIN | 856,000:00 | 40,000:00 | 227,550:00 | N352,550:00
15 | PRINCIPAL INTERNAL AUDITOR (12) 1. Y2022 ANNUAL CONFERENCE OF THE ASSOCIATION OF NATIONAL ACCCOUNTANTS OF NIGERIA (ANAN) | LRC/S-WTC/SS/015A/2022 | CAPACITY BUILDING | 1 | 4DAYS | Plan | ABUJA | 55,000:00 | 119,000:00 | 190,000:00 | N364,750:00
| 2. WORK ATTTITUDE AND VALUE ENHANCEMENT COURSE | LRC/S-WTC/SS/015B/2022 | CAPACITY BUILDING | 1 | 28TH JUNE-1ST JULY, 2022 | Actual | LAGOS | 190,000:00 | 7,800:00 | 6,750:00 | N204,550:00
16 | PRINCIPAL PROGRAM ANALYST (12) 1. REINVENTING LEADERSHIP IN A COVID-19 WORLD | LRC/S-WTC/SS/016A/2022 | CAPACITY BUILDING | 1 | 18TH JULY 2022 | Plan | ONLINE | 357,000:00 | 15,000:00 | 6,750:00 | N379,250:00
| 2. RISK AND VULNERABILITY ASSESSMENT FOR IT SYSTEMS | LRC/S-WTC/SS/016B/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTYOBER 2022 | Actual | LAGOS | 250,000:00 | 13,000:00 | 6,750:00 | N269,750:00
17 | PRINCIPAL EXECUTIVE OFFICER II(12) 1. MANAGING AND COORDINATING TRAINING FUNCTION | LRC/S-WTC/SS/017A/2022 | CAPACITY BUILDING | 1 | 25TH-29TH OCTOBER, 2022 | Plan | NIM ABUJA | 115,000:00 | 119,000:00 | 190,750:00 | N424,750:00
| 2. WORK ATTTITUDE AND VALUE ENHANCEMENT COURSE | LRC/S-WTC/SS/017B/2022 | CAPACITY BUILDING | 1 | 4DAYS | Actual | LAGOS | 190, 000:00 | 7,800:00 | 6,750:00 | N204,550:00
18 | SENIOR ADMIN. & HR OFFICER (10) 1. MANAGING AND COORDINATING TRAINING FUNCTION | LRC/S-WTC/SS/018/2022 | CAPACITY BUILDING | 1 | 26TH-29TH OCTOBER, 2022 | Plan | NIM ABUJA | 115,000:00 | 119,000:00 | 190,750:00 | N424,750:00
19 | PROGRAM ANALYST II (08) 1. REINVENTING LEADERSHIP IN A COVID-19 WORLD | LRC/S-WTC/SS/019/2022 | CAPACITY BUILDING | 1 | 21ST NOVEMBER 2022 | Plan | ONLINE | 357,000:00 | 15,000:00 | 4,500:00 | N376,500:00
20 | CLERICAL OFFICER (07) 1. REINVENTING LEADERSHIP IN A COVID-19 WORLD | LRC/S-WTC/SS/020/2022 | CAPACITY BUILDING | 1 | 21ST NOVEMBER 2022 | Plan | ONLINE | 357,000:00 | 15,000:00 | 4,500:00 | N376,500:00
21 | CLERICAL OFFICER (07) 1. REINVENTING LEADERSHIP IN A COVID-19 WORLD | LRC/S-WTC/SS/021/2022 | CAPACITY BUILDING | 1 | 21ST NOVEMBER 2022 | Plan | ONLINE | 357,000:00 | 15,000:00 | 4,500:00 | N376,500:00
TOTAL
N17,923,325:00