## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE MUSLIM PILGRIMS WELFARE BOARD
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVEL& TRANSPORT LOCAL: DESPATCH OF LETTERS TO ALL LGs & LCDAs ON PILGRIMS MATTERS | MPWB/NP/NM/001/22 | 1,250,000.00 | Plan |  |  | 312500 |  |  | 312500 |  |  | 312500 |  |  | 312500 | 1,250,000.00
Actual
2 | GENERAL UTILITY SERVICES: FAXING OF MESSAGES TO NAHCON, TELEPHONE BILLS FOR 4NOS OFFICIAL LINES, DSTV FULL BOUQUET FOR BOARD SECRETARY, ACCOUNTANT & OPERATIONS | MPWB/NP/NM/002/22 | 1,750,000.00 | Plan |  |  | 412500 |  |  | 412500 |  |  | 412500 |  |  | 412500 | 1,750,000.00
Actual
3 | MISCELLANEOUS: SERVICING OF MEDICAL MACHINES, CMTE MEETINGS AND BANKING SERVICES | MPWB/NP/NM/003/22 | 500000 | Plan |  |  | 125000 |  |  | 125000 |  |  | 125000 |  |  | 125000 | 500000
Actual
4 | SPECIAL DUTIES EXPENSES:PAYMENT OF BOARD MEMBERS SITTING ALLOWANCE AND HAJJ SENSITISATION | MPWB/NP/NM/004/22 | 6,300,015.00 | Plan |  |  | 1,575,037,5 |  |  | 1,575,037,5 |  |  | 1,575,037,5 |  |  | 1,575,037,5 | 6,300,015.00
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE MUSLIM PILGRIMS WELARE
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Chartered Institute of Purchasing & Supply Management of Nigeria | MPWB/S-WTC/S-WTC/001/22 | The effect of covid-19 Pandemic and Amendment of the Finance Act 2020 on Public Procurement in Nigeria | 1 | 3days | Plan | Abuja | 60000 | 73000 | 207000 | 340000
Actual
2 | Institute of Chartered Accountant of Nigeria | MPWB/S-WTC/002/22 |  | 1 | 3days | Plan | Abuja | 180000 | 73000 | 276000 | 529000
Actual
3 | Nigeria Institute Statistician | MPWB/S-WTC/003/22 |  | 1 | 3days | Plan | Abuja | 45000 | 70000 | 207000 | 322000
Actual
4 | Association of National Accountants of Nigeria | MPWB/S-WTC/003/22 |  | 1 | 3days | Plan | Abuja | 45000 | 70000 | 207000 | 322000
Actual
5 | Chartered Institute of Personnel Management | MPWB/S-WTC/004/22 |  | 1 | 3days | Plan | Abuja | 80000 | 69000 | 138000 | 287000
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: LAGOS STATE MUSLIMS PILGRIMS WEFARE BOARD
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING:REPLACEMENT OF BAD DOORS, KEYS, BULBS ETC | LSPWB/S-NC/NS/001/22 |  |  | 1450000 | <10M | NS | Plan | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
[7 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE REPAIRS AND MTCE:REPAIRS, SERVICING OF DEPT. VEHICLE AND PURCHASE OF TYRES | LSPWB/S-NC/NS/002/22 |  |  | 1450000 | <10M | NS | Plan | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
[7 empty] | Actual | [9 empty] | Actual
ICT UNIT SYSTEM TROUBLESHOOTING,HARD/SOFTWARE MGT, COMPUTER MTCE AND CONSUMABLES | LSMPWB/S-NC/NS/003/22 |  |  | 350000 | <10M | NS | PLAN | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
Actual
PUBLICITY & PRESS COVERAGE: PR ACTIVITIES, INTERVIEW, ADVERT IN MEDIA HOUSES AND NEWSPAPER | LSMPWB/S-NC/NS/004/22 |  |  | 500000 | <10M | NS | PLAN | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
Actual
PLANNING UNIT: MTCE & UPDATE OF STATISTICAL / ECONOMIC DATA, ROUTINE DATA COLLECTION & ANALYSIS | LSMPWB/S-NC/NS/005/22 |  |  | 200000 | <10M | NS | PLAN | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
Actual
INTERNAL AUDIT: MONTHLT STAFF AUDIT EXERCISE, STATIONERY AND CONSUMABLE ITEMS | LSMPWB/S-NC/NS/006/22 |  |  | 600000 | <10M | NS | PLAN | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
Actual
PUBLIC RELATION EXPENSES: PRESS COVERAGE HONORARIUM, GIFT ITEMS AND MEDIA VISITS HONORARIUM | LSMPWB/S-NC/NS/007/22 |  |  | 900000 | <10M | NS | PLAN | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
Actual
PROCUREMENT UNIT: PREPARATION OF REPORT, MINUTES OF PTB AND RFQ | LSMPWB/S-NC/NS/008/22 |  |  | 355000 |  |  | PLAN | POST | POST | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-05 | 2022-04-12 |  | 2022-05-03 | 2022-05-17 | 2022-05-31 | 2022-06-01
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: LAGOS STATE MUSLIM PILGRIMS WELFARE BOARD
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  |  | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
1 | EXTERNAL AUDITOR: FOR NECESSARY ACCOUNTABILITY | MPWB/S-C/LC/001/22 | LC | Plan | 1,250,000.00 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
2 | Managing Employee Performance | MPWB/S-C/LC/002/22 | LC | Plan | 250000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
3 | Data Management Using MS-Excel | MPWB/S-C/LC/003/22 | LC | Plan | 170000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
4 | Wireless Communication and Networking Security | MPWB/S-C/LC/004/22 | LC | Plan | 360000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
5 | Effective Speech Writing and Report Writing | MPWB/S-C/LC/005/22 | LC | Plan | 220000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
6 | Effective Memo and Submission Writing | MPWB/S-C/LC/006/22 | LC | Plan | 330000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
7 | Managing to get Result | MPWB/S-C/LC/007/22 | LC | Plan | 360000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
8 | Procurement Management Practice | MPWB/S-C/LC/008/22 | LC | Plan | 220000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
9 | Understanding MTSS, Programme-Based Budgeting and Budget Profiling Report | MPWB/S-C/LC/009/22 | LC | Plan | 170000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
10 | Understanding Procurement Management (Non Procurement Officer) | MPWB/S-C/LC/010/22 | LC | Plan | 200000 | Post | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | NA | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual
11 | Monitoring and Evaluation Workshop | MPWB/S-C/LC/011/22 | LC | Plan | 220000 |  | Plan | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | S | NA | 24 May 22 | 31 May 22 | 1 Jun 22 |  | 8 Jun 22 | 22 Jun 22 | 6 Jul 22 | 13 Jul 22 | 20 Jul 22
|  |  |  | Actual |  |  | Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE MUSLIM PILGRIMS WEFARE BOARD
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF MOTOR VEHICLES FUEL CONSUMPTION | LSMPWB/G-F/NS/001/22 | NA |  | 1550000 | <10M | NS | POST | POST | Plan | 2021-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-14 |  | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-05-26
Actual
2 | PROCUREMENT OF STATIONERIES ITEMS | LSMPWB/G-F/NS/002/22 | NA |  | 1650000 | <10M | NS | POST | POST | Plan | 2021-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-14 |  | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-05-26
Actual
3 | PROCUREMENT OF UNIFORMS, PROTECTIVES AND REFLECTIVE JACKETS | LSMPWB/G/NS/003/22 | NA |  | 468738 | <10M | NS | POST | POST | Plan | 2021-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-14 |  | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-05-26
Actual
4 | AUDIT EXERCISE: MONTHLY STAFF AUDIT EXERCISE, PURCHASE OF STATIONERY AND CONSUMABLE ITEMS | LSMPWB/G/NS/004/22 | NA |  | 600000 | <10M | NS | POST | POST | Plan | 2021-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-14 |  | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-05-26
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual