## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: LAGOS STATE WASTEWATER MANAGEMENT OFFICE
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan Actual | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | TOTAL
Plan
Actual
1 | GENERAL UTILITY SERVICES | LSWMO/NP/NM/001/22 | 4,047,000 | Plan | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 337250 | 4,047,000
Actual
2 | TRAVELLING AND TRANSPORT | LSWMO/NP/NM/002/22 | 2998000 | Plan | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 249833.33 | 2998000
Actual
4 |  | LSWMO/NP/NM/004/22 | 540,000 | Plan | TOTAL: 2998000
Actual
3 | ALLOWANCE FOR (60NOS) WASTEWATER MONITORS | LSWMO/NP/NM/003/22 | 38,088,000 | Plan | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 3174000 | 38,088,000
Actual
6 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 | TOTAL |  |  | Plan
Actual
G.M …...............................
|  |  | 1) Engr. M.Adebola Matanmi |  | APR: GM ------------------------------------------------
2) Odesanya M.A D (A & HR) …………………..
3) Omojola A.O AD (Finance& Account) ………………….
4) Ayeni Kamal A.D(Legal)…………………
5) Eneh V.N Procurement ….………….……..
6 Ayeni A.O PS1(Planning & Budget) ……………………
7) Jamiu Y.O- Principal Auditor …………………….

## trg conf wsh
357000
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAGOS STATE MANAGEMENT OFFICE
BUDGET YEAR: 2022
PACKAGE NO | Description of Training/Workshop/ Conference | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
LSWMO/S-WTC/SS/001/22 | Target setting in performance management- line Manager / HR Professional Workshop |  | 5 | 3days | Plan | Abuja |  |  |  | 1500000
Actual
LSWMO/S-WTC/SS/001/22 | Motivating Team Excellence(Workshop) |  | 8 | 4 days | Plan | Lagos |  |  |  | 1900000
Actual
LSWMO/S-WTC/SS/001/20 |  |  |  |  | Plan | Abuja
Actual
LSWMO/S-WTC/SS/002/22 | Mandatory Continuing Professional Development Workshop |  | 6 | 5 days | Plan | lagos |  |  |  | 1600000
Actual
LSWMO/S-WTC/SS/003/22 | Team Building and Group Dynamics | Enhancing Building of Team and Group Dynamics | 2 | 4 days | Plan | Abuja |  |  |  | 300000
Actual
LSWMO/S-WTC/SS/004/20 |  |  |  |  | Plan
Actual
LSWMO/S-WTC/SS/005/20 |  |  |  | 5 days | Plan | Kaduna | 89000 | 65000 | 238000
Actual
LSWMO/S-WTC/SS/006/20 |  |  |  | 5 days | Plan | Abuja | 175000 | 325000 | 960000
Actual
9 |  |  |  |  | Plan
Actual
LSWMO/S-WTC/SS/007/20 |  | Enhance Entrpreneuship Business Development | 19 | 2 day | Plan | Ibadan | 950000 | 240000 | 988000
Actual
LSWMO/S-WTC/SS/008/20 |  |  | 8 | 2 day | Plan | Lagos | 240000 | 24000 | 48000
Actual
LSWMO/S-WTC/SS/009/20 |  |  | 13 | 2 day | Plan | Lagos | 390000 | 26000 | 19500
Actual
LSWMO/S-WTC/SS/010/20 |  |  | 1 | 2 day | Plan | Lagos | 30000 | 1400 | 1000
Actual
LSWMO/S-WTC/SS/004/22 | Conference for Coren Assembly, (Engineers) |  | 10 | 3 days | Plan | Kaduna | 200000 |  |  | 1800000
[5 empty] | Actual | Abuja |  |  |  | 4000000 | S
LSWMO/S-WTC/SS/012/22 | Conference & Seminars(ICAN & ANAN) for Accountants & Auditors |  | 2 | 5 days | Plan | Abuja |  |  |  | 900000
Actual
LSWMO/S-WTC/SS/013/22 | Nigeria institute of Management (NIM) Conference |  | 3 | 4 days | Plan | Abuja |  |  |  | 1600000
Actual
LSWMO/S-WTC/SS/014/22 | Conference & Seminar for procurement officer |  | 1 | 4 days | Plan | Abuja |  |  |  | 300000
Actual
LSWMO/S-WTC/SS/015/22 | Conference & Seminars for Legal Officer (BAR) |  | 1 | 7 Days | Plan | Abuja |  |  |  | 400000
Actual
LSWMO/S-WTC/SS/016/22 | Conference & Seminars for Scientific /Health officers |  | 9 | 4 days | Plan | Lagos |  |  |  | 2000000
Actual
LSWMO/S-WTC/SS/017/22 | Conference & Seminars for Planner |  | 1 | 5 Days | Plan | calabar |  |  |  | 300000
Actual
LSWMO/S-WTC/SS/01/8/22 | Conference & Seminars for ICT |  | 2 |  | Plan | lagos |  |  |  | 500000
[5 empty] | Actual |  |  |  |  | 15000000
1) Engr. M.Adebola Matanmi | G.M …...............................
2) Odesanya M.A D (A & HR) …………………..
3) Omojola A.O AD (Finance& Account) ………………….
4) Ayeni Kamal A.D(Legal)…………………
5) Eneh V.N Procurement ….………….……..
6 Ayeni A.O PS1(Planning & Budget) ……………………
7) Jamiu Y.O- Principal Auditor …………………….

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2221
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF WASTEWATER TREATMENT PLANT EQUIPMENT AND GENERATORS AT ALAUSA, OKE-AFA, ABESAN AND IPONRI . | LSWMO/S-NC-F/NS/001/22 |  |  | 14740840 | <50M | NS | Plan | POST | PRIOR | 14-1-22 | 21 /1 /22 | 7-2-22 | 25-2-22 | 4/3/22 | 10/3/22 | 2022-03-24 | Plan | 2022-04-19 | 5/5/22 |  | 14-5-22 | 30-5-22 | 2022-06-30 | 2022-12-07
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF BUILDING | [6 empty] | Plan | [9 empty] | Plan
| LSWMO/S-NC-F/NS/002/22 |  |  | 2200000 | <10M | NS | Actual | POST | POST | 2022-03-02 | NO APPLICABLE | 2022-02-17 | 2022-03-03 | 2022-03-16 | 2022-03-30 | NO APPLICABLE | Actual | 2022-04-08 | 2022-04-22 |  | 2022-05-16 | 2022-06-15 | 22-8-22 | 23-8-22
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF OUTSTATION FACILITIES | LSWMO/S-NC-F/NS/005/22 |  |  | 5000000 | <10M | NS | Plan | POST | POST | 21/1/22 | NO APPLICABLE | 2022-02-03 | 2022-02-17 | 2022-03-04 | 2022-03-18 | NO APPLICABLE | Plan | 2022-03-31 | 2022-04-08 |  | 16/5/22 | 31/5/22 | 2022-06-30 | 2022-07-04
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF MOTOR VEHICLES | LSWMO/S-NC-F/NS/006/22 |  |  | 3000000 | <10M | NS | Plan | POST | POST | 2022-03-04 | NO APPLICABLE | 2022-03-18 | 2022-03-31 | 2022-04-11 | 2022-04-25 | NO APPLICABLE | Plan | 2022-05-09 | 2022-05-23 |  | 2022-06-02 | 2022-06-16 | 2022-06-30 | 23/8/22
[7 empty] | Actual | [9 empty] | Actual
| LSWMO/S-NC-F/NS/007/22 |  | 100 | 7184462 | <50M | NS | Plan | POST | POST | 17/1/22 | NO APPLICABLE | 2022-03-31 | 2022-04-09 | 2022-04-23 | 2022-05-07 | NO APPLICABLE | Plan | 2022-05-21 | 2022-06-02 |  | 2022-06-16 | 2022-06-30 | 2022-09-08 | 2022-09-09
[7 empty] | Actual | [9 empty] | Actual
ROUNTINE MAINTENANCE CONTRACT (RETAINERSHIP | LSWMO/S-NC-F/NS/008/22 |  |  | 6400000 | <10M | NS | Plan | POST | POST | 2022-05-03 | NO APPLICABLE | 2022-03-18 | 2022-03-30 | 2022-04-08 | 2022-04-22 | NO APPLICABLE | Plan | 2022-05-05 | 2022-05-19 |  | 2022-06-06 | 13/6/22 | 2022-09-19 | 2022-09-21
[7 empty] | Actual | [9 empty] | Actual
[6 empty] | NS | Plan | POST | POST |  | NO APPLICABLE |  |  |  |  | NO APPLICABLE | Plan
[7 empty] | Actual | [9 empty] | Actual
1) Engr. M.Adebola Matanmi GM …………………..
2) Odesanya M.A D (A & HR) …………………..
3) Omojola A.O AD (Finance& Account) ………………….
4) Ayeni Kamal A.D(Legal)…………………
5) Eneh V.N Procurement ….………….……..
6 Ayeni A.O PS1(Planning & Budget) ……………………
7) Jamiu Y.O- Principal Auditor …………………….

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
| MINISTRY/ AGENCY: LAGOS STATE WASTEWATER MANAGEMENT OFFICE | [11 empty] | S
BUDGET YEAR: 2022
BASIC DATA
| PROJECT IDENTIFICATION | [5 empty] | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | CONSULTANCY SERVICE FOR VALIDATION OF DESKTOP DATA AND COMMERCEMENT OF PROCUREMENT PROCESS FOR THE PROVISION OF CONTEMPORARY WASTEWATER SYSTEM FOR AWUMO-ODOFIN AND ADJOING AREA. | LSWMO/S-C/QCBS/001/20 |  | 28,835,387 | <50M | PRIOR | Plan | 2022-05-03 | 19/3/22 | 26/3/22 | 2022-09-04 | 23/4/22 | 2022-07-05 | 28/5/22 | 2022-11-06 | 18/6/22 | 25/6/22 | 2022-02-07 | 16/7/22 | 23/7/22 | 2022-06-08 |  | 13/8/22 | 27/8/22 | 2022-10-09 | 24/9/22 | 2022-08-10
|  |  | QCBS |  |  |  | Actual
2 | CONSULTANCY SERVICE FOR COMMUNITY/STAKEHOLDERS ENGAGEMENT /VALIDATION OF DESKTOP DATA AND COMMERCEMENT OF PROCUREMENT PROCESS FOR CONSTRUCTION OF WASTEWATER TREATMENT PLANT SYSTEM IN TEN (10 NOS) LASG ESTATES | LSWMO/S-C/QCBS/002/22 | QCBS | 30,066,852 | <50M | PRIOR | Plan | 2022-05-03 | 19/3/22 | 26/3/22 | 2022-09-04 | 23/3/22 | 2022-07-05 | 28/5/20 | 2022-11-06 | 25/6/22 | 2022-02-07 | 16/7/22 | 30/7/22 | 2022-06-08 | 20/8/22 |  | 27/8/22 | 2022-09-09 | 16/11/22 | 30/11/22 | 2022-07-12
Actual
|  |  | LCS |  | <50M | PRIOR | Plan |  | 17/3/22 | 24/3/22 | 2022-07-04 | 14/4/22 | 22/4/22 | 2022-12-05 | 19/5/22
Actual
4 | CONSULTANCY SERVICE FOR DEVELOPMENT OF OUTLINE BUSINESS CASE STUDY FOR WASTEWATER INFRASTRUCTURE IN LAGOS STATE | LSWMO/S-C/QCBS/004/22 | QCBS | 335,427,068.00 | >50M&<1B | PRIOR | Plan | 2022-01-03 | 2022-08-03 | 15/3/22 | 22/3/2022 | 26/4/22 | 2022-10-05 | 30/5/22 | 14/6/22 | 28/6/22 | 2022-05-07 | 19/7/22 | 2022-09-08 | 16/8/22 | 30/8/22 |  | 2022-06-09 | 20/9/22 | 2022-11-10 | 31/10/22 | 2022-11-11
Actual
5 | CONSULTANCY SERVICE FOR GATHERING AND DEVELOPMET OF PILOT SEPTAGE MANAGEMENT PLAN IN LAGOS STATE | LSWMO/S-C/QCBS/005/22 | QCBS | 14084821 | <50M | PRIOR | Plan | [6 empty] | 2022-01-03 | 2022-08-03 | 15/3/22 | 22/3/2022 | 26/4/22 | 2022-10-05 | 30/5/22 | 14/6/22 | 28/6/22 | 2022-05-07 | 19/7/22 | 2022-09-08 | 16/8/22 | 30/8/22
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
1) Engr. M.Adebola Matanmi GM ………………….. | 1) Engr. M.Adebola Matanmi GM …………………..
2) Odesanya M.A D (A & HR) ………………….. | 2) Odesanya M.A D (A & HR) …………………..
3) Omojola A.O AD (Finance& Account) …………………. | 3) Omojola A.O AD (Finance& Account) ………………….
4) Ayeni Kamal A.D(Legal)………………… | 4) Ayeni Kamal A.D(Legal)…………………
5) Eneh V.N Procurement ….………….…….. | 5) Eneh V.N Procurement ….………….……..
6 Ayeni A.O PS1(Planning & Budget) …………………… | 6 Ayeni A.O PS1(Planning & Budget) ……………………
7) Jamiu Y.O- Principal Auditor ……………………. | 7) Jamiu Y.O- Principal Auditor …………………….

## Goods1
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOS STATE WASTEWATER MANAGEMENT OFFICE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number |  | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF DIESEL FOR WASTE WATER PLANTS(244,800 Litres) | LSWMO/G-F/NS/003/22 |  |  |  | 20436000 | <50M | NS | POST | PRIOR | Plan | 2022-04-03 | 2022-11-03 | 18/3/22 | 2022-04-04 | 19/4/22 | 25/4/22 | 2022-05-05 | 2022-10-05 |  | 17/5/2022 | 24/5/2022 | 2022-07-06 | 2022-07-11 | 14/11/2022
Actual
2 | PROCUREMENT OF NEWS PAPER, MAGAZINES AND PLACEMENT OF RADIO JUNGLES FOR WASTEWATER MANAGEMENT OFFICE | LSWMO/G/N/001/22 |  |  |  | 7000000 | <10M | NS | POST | POST | Plan | 23/3/22 | 2022-06-04 | 2022-05-05 | 2022-07-06 | 14/6/2022 | 2022-07-07 | 14/7/22 | 22/7/22 |  | 28/7/22 | 29/8/22 | 2022-12-09 | 26/9/22 | 23/12/22
Actual
3 | PROCUREMENT OF LABORATORY REGENTS CHEMICALS | LSWMO/G/NS/007/22 |  |  |  | 18000000 | <50M | NS | POST | PRIOR | Plan | 2022-05-05 | 2022-11-05 | 18/5/2022 | 25/5/2022 | 2022-02-06 | NOT APPLICABLE | 2022-09-06 | 16/6/2022 |  | 23/6/22 | 30/6/22 | 2022-05-10 | 2022-12-10 | 2022-11-11
Actual
4 | PROCUREMENT OF TOOLS | LSWMO/G/NS/008/22 |  |  |  | 1500000 | <10M | NS | POST | POST | Plan | 17/1/22 | NOT APPLICABLE | 14/2/2022 | 21-2-22 | 28-2-22 | NOT APPLICABLE | 21-3-22 | 28-3-22 |  | 2022-11-04 | 19/4/2022 | 2022-05-10 | 19/10/22 | 13/12/22
Actual
5 | PROCUREMENT OF SPECIAL DUTIES EXPENSES | LSWMO/G/NS/009/22 |  |  |  | 8314500 | <10M | NS | POST | POST | Plan | 25/2/22 | NOT APPLICABLE | 22/4/22 | 2022-09-05 | 23/5/22 | NOT APPLICABLE | 30/5/22 | 2022-04-06 |  | 13/6/2022 | 20/6/2022 | 2022-12-07 | 18/7/2022
Actual
6 | PRINTING OF INFORMATIVE LEAFFLETS FOR AWARENESS AND STAKEHOLDERS FORUM ON SEWAGE MANAGEMENT AND PROVISION FOR LOGISTIC FOR SCHOOL ADVOCACY PROGRAMME | LSWMO/G/NS/010/22 |  |  |  | 10773349 | <50M | NS | POST | PRIOR | Plan | 2022-05-02 | NOT APPLICABLE | 2022-12-03 | 22/3/22 | 27/3/22 | NOT APPLICABLE | 27/4/22 | 2022-06-05 |  | 13/5/22 | 22/5/22 | 2022-03-05 | 17/10/22 | 18/11/22
Actual
8 | PROCUREMENT OF UNIFORMS AND PROTECTIVE WEARS | LSWMO/G/NS/013/22 |  |  |  | 500000 | <10M | NS | POST | POST | Plan | 23/3/22 | NOT APPLICABLE | 22/3/2022 | 2022-06-04 | 13/4/2022 | NOT APPLICABLE | 14/5/22 | 22/5/22 |  | 28/7/22 | 27/8/22 | 2022-10-09 | 2022-05-11 | 2022-06-11
Actual
9 | PROCUREMENT OF ICT (ACCESSORIES) COMSUMABLES | LSWMO/G/NS/014/22 |  |  |  | 3184000 | <10M | NS | POST | POST | Plan | 22/3/22 | NOT APPLICABLE | 2022-08-04 | 22/4/2022 | 2022-06-05 | NOT APPLICABLE | 13/5/22 | 22/5/22 |  | 2022-02-06 | 27/8/22 | 2022-10-09 | 24/9/22 | 23/12/22
Actual
10 | PROCUREMENT OF FUEL FOR MOTOR VEHICLE IN THE OFFICE | LSWMO/G-F/NS/017/22 |  |  |  | 8951038 | <10M | NS | POST | POST | Plan | 2022-09-03 | NOT APPLICABLE | 23-3-22 | 2022-06-04 | 22/4/22 | NOT APPLICABLE | 2022-01-05 | 2022-05-05 |  | 2022-11-05 | 18/5/2022 | 25/5/22 | 2022-05-11 | 2022-06-11
Actual
11 | STATIONARIES | LSWMO/G-F/NS/018/22 |  |  |  | 7184462 | <10M | NS | POST | POST | Plan | 16/1/22 | NOT APPLICABLE | 13/2/22 | 22/2/22 | 2022-02-03 | NOT APPLICABLE | 17/3/22 | 23/3/22 |  | 30/3/22 | 2022-03-04 | 18/4/22 | 16/5/22 | 18/11/22
Actual
12 | PROCUREMENT OF OFFICE CONSUMABLES AND LOGISTICS FOR SUPPORTING UNITS IN PLANNING, ACCOUNTS, LEGAL AND INTERNAL AUDIT | LSWMO/G/NS/019/22 |  |  |  | 6600000 | <10M | NS | POST | POST | Plan | 2022-03-04 | NOT APPLICABLE | 2022-03-17 | 2022-03-31 | 2022-04-06 | NOT APPLICABLE | 13/6/22 | 16/6/22 |  | 2022-05-22 | 2022-05-27 | 2022-02-06 | 2022-06-06 | 2022-09-08
Actual
13 | PROCUREMENT OF OFFICE TOILETRIES | LSWMO/G/NS/020/22 |  |  |  | 4855500 | <10M | NS | POST | POST | Plan | 14/1/22 | NOT APPLICABLE | 13-2-22 | 22-2-22 | 27-2-22 | NOT APPLICABLE | 22-3-22 | 27-3-22 |  | 2022-10-04 | 2022-04-24 | 2022-05-10 | 17/10/22 | 13/12/22
Actual
14 | Monitoring activities and enforcement exercise by the sanitary inspectors of the Agency | LSWMO/G/NS/021/22 |  |  |  | 1000000 | <10M | NS | POST | POST | Plan | 14/1/22 | NOT APPLICABLE | 13-2-22 | 22-2-22 | 27-2-22 | NOT APPLICABLE | 22-3-22 | 27-3-22 |  | 2022-10-04 | 2022-04-24 | 2022-05-10 | 17/10/22 | 13/12/22
Actual
15 | PROCUREMENTOF BATTERIES INVERTER AND MAINTENANCE OF NETWORKS AND RADIO MASKS | LSWMO/G/NS/022/22 |  |  |  | 3500000 | <10M | NS | POST | POST | Plan | 14/1/22 | NOT APPLICABLE | 13-2-22 | 22-2-22 | 27-2-22 | NOT APPLICABLE | 22-3-22 | 27-3-22 |  | 2022-10-04 | 2022-04-24 | 2022-05-10 | 17/10/22 | 13/12/22
Actual
1) Engr. M.Adebola Matanmi GM …………………..
2) Odesanya M.A D (A & HR) ………………….. |  |  | D (ADMIN )
3) Omojola A.O AD (Finance& Account) ………………….
4) Ayeni Kamal A.D(Legal)…………………
5) Eneh V.N Procurement ….………….……..
6 Ayeni A.O PS1(Planning & Budget) ……………………
7) Jamiu Y.O- Principal Auditor …………………….

## goods2 (hidden)
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LAGOA STATE WASTEWATER MANAGEMENT OFFICE
BUDGET YEAR: 2020
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
11 | PROCUREMENT OF DIESEL FOR PLANTS AND EQUIPMENT (23,000litres) | LSWMO/G/NS/011/20 |  | 23000 | 24636000 | <50M | NS | POST | PRIOR | Plan | 15/1/20 | 30/1/20 | 13-2-20 | 20-2-19 | 27-2-20 | 13/3/20 | 20-3-20 | 27-3-20 |  | 20-3-20 | 6/4/20 | 20/4/20 | 2020-06-04 | 2020-06-05
Actual
12 | PROCUREMENT OF ICT (ACCESSORIES) COMSUMABLES | LSWMO/G/NS/012/20 |  | 250 | 2615500 | <50M | NS | POST | POST | Plan | 2020-05-04 | NOT APPLICABLE | 2020-05-19 | 2020-06-03 | 2020-06-17 | NOT APPLICABLE | 2020-06-30 | 2020-07-02 |  | 2020-07-09 | 2020-09-06 | 18/6/20 | 2020-09-07 | 2020-07-23
Actual
3 | PROCUREMENT OF FUEL FOR VECHILE (10 litres) | LSWMO/G/NS/013/20 |  | 2O | 9048000 | <50M | NS | POST | POST | Plan | 2020-02-03 | NOT APPLICABLE | 2020-02-17 | 2020-03-02 | 2020-03-09 | NOT APPLICABLE | 20-3-20 | 27-3-20 |  |  | 2020-03-16 | 2020-03-30 | 2020-05-04 | 2020-05-05
Actual
4 | PROVISION AND INSTALLATION OF DISINEFECTION SYSTEM, DOSING PUMPS MIXER AND CHEMICAL TANK | LSWMO/G/NS/014/20 | [7 empty] | Plan
Actual
5 | PROCUREMENT OF ZETAG (POLYMEROFER SEPTAGE MANAGEMENT IN LAGOS STATE | LSWMO/G/NS/015/20 |  | 10000 | 6000000 | <50M | NS | POST | POST | Plan | 10/02/2020 | NOT APPLICABLE | 2020-02-24 | 09-03-2020 | 16-03-2020 | 23/3/2020 | 2020-03-30 | 6/04/2020 | 7/04/2020 |  | 2020-04-14 | 2020-04-28 | 2020-07-06 | 2020-07-07
Actual
6 | PROCUREMENT OF LABORATORY REGENTS AND CHEMICALS | LSWMO/G/NS/016/20 |  | 10000 | 14625594 | <50M | NS | POST | PRIOR | Plan | 5/02/2020 | 12/2/2020 | 19-2-2020 | 02/4/20 | 30-6-20 | 2/7/20 | 14/7/20 | 2020-07-28 | 4/8/20 | 18/8/20 | 2020-10-02 | 2020-10-06 | 2020-11-13 | 2020-11-14
Actual
7 | PROCUREMENT OF TOOLS (KROD, DRAWING OFFICE MATERIALS | LSWMO/G/NS/017/20 |  | 117 | 2558000 | <50M | NS | POST | POST | Plan | 2020-08-04 | NOT APPLICABLE | 22/4/20 | 26/8/20 | 2020-06-08 | NOT APPLICABLE |  |  |  |  | 27/8/20 | 2020-10-09 | 24/9/20 | 2020-09-25
Actual
8 | PROCUREMENT OF PROJECT UTILITY VECHICLE | LSWMO/G/NS/018/20 |  | 2 | 14600000 | >50M&<1B | NS | POST | POST | Plan | 5/02/2020 | 12/2/2020 | 19-2-2020 | 02/4/20 | 30-6-20 | 2/7/20 | 14/7/20 | 2020-07-28 | 4/8/20 | 18/8/20 | 2020-10-02 | 2020-10-06 | 2020-11-13 | 2020-11-14
Actual
9 | [9 empty] | Plan
Actual
10 | [9 empty] | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LAGOS STATE WASTEWATER MANAGEMENT OFFICE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | REPAIRS AND REHABILITATION OF SEPTIC TANKS | LSWMO/W/NS/001/22 |  | 5000000 | <10M | NS | BOQ | PRE | Plan | PRIOR | 14/2/2022 | 28/2/22 | 2022-07-03 | 21/3/22 | 2022-11-04 | 25/4/22 | 2022-04-29 | 2022-05-05 |  | 2022-06-05 | 2022-10-05 | 24/5/22 | 2022-05-09 | 23/12/22
Actual
2 |  | LSWMO/W/NCB/002/20 |  |  | <50M | NCB | BOQ | POST | Plan | PRIOR | 2020-05-02 | 2020-12-02 | 19/2/20 | 2020-05-03 | 19/3/20 | 26/3/20 | 2020-04-03 | 2020-04-10 |  | 2020-05-04 | 2020-05-12 | 2020-05-19 | 22/7/20 | 25/10/20
Actual
3 |  | LSWMO/W/NS/002/20 |  |  |  | NS | BOQ | POST | Plan | PRIOR | 2022-05-02 | 19/2/22 | 26/2/22 | 2022-05-03 | 19/3/22 | 26/3/22 | 2022-08-04 | 22/4/2022 |  | 29/4/22 | 12/5/202`1 | 20/5/22 | 26/6/22 | 27/9/22
[5 empty] | <50M |  |  |  | Actual
4 | EVACUATION AND DISPOSAL OF SLUDGE AND SILT DEBRIS AT WWTP | LSWMO/W/NS/003/22 |  | 2400000 | <10M | NS | BOQ | PRE | Plan | PRIOR | 2022-11-01 | NOT APPLICABLE | 25/01/22 | 2022-08-02 | 22/2/22 | NOT APPLICABLE | 26/2/22 | 2022-08-03 |  | 22/3/22 | 2022-02-04 | 16/4/22 | 22/7/22 | 25/10/22
[9 empty] | Actual | POST
5 | UPGRADE AND EXPANSION OFALAUSA, ABESAN, IPONRI AND OKE-AFA WASTEWATER TREATMENT PLANT(WWTPs) | LSWMO/W/NS/004/22 |  | 173000000 | >500M | NCB | BOQ | PRE | Plan | PRIOR | 2022-11-01 | 18/1/22 | 27/1/22 | 2022-08-02 | 22/2/22 | 2022-08-03 | 22-3-22 | 28-3-22 |  | 2022-07-04 | 14/4/22 | 28/4/22 | 28/6/22 | 29/9/22
Actual
6 | DESIGN AND CONSTRUCTION OF TWO(2)TREATMENT PLANTS IN TWO COMMUNITIES IN LAGOS STATE | LSWMO/W/NS/005/22 |  | 31473927 | <50M | NS | BOQ | PRE | Plan | PRIOR | 2022-10-01 | 17/1/22 | 24/01/22 | 2022-07-02 | 22/2/22 | 2022-03-03 | 2022-03-09 | 2022-03-16 |  | 30/3/22 | 2022-02-04 | 16/4/22 | 22/7/22 | 25/10/22
Actual
7 | FENCING OF ODO-IYA-ALARO WASTEWATER TREATMENT PLANT PROJECT SITE | LSWMO/W/NS/006/22 |  | 55000000 | <50M | NS | BOQ | PRE | Plan | PRIOR | 2022-10-01 | 17/1/22 | 24/01/22 | 2022-07-02 | 22/2/22 | 14/3/2022 | 30/4/22 | 2022-12-05 |  | 19/5/22 | 2022-05-05 | 16/5/22 | 19/7/22 | 18/10/22
Actual
8 | RENOVATION OF LSWMO OFFICE | LSWMO/W/NS/007/22 |  | 20000000 | <50M | NS | BOQ | PRE | Plan | PRIOR | 2022-10-01 | 17/1/22 | 27/1/22 | 2022-07-02 | 22/2/22 | 2022-07-03 | 23/4/22 | 2022-04-05 |  | 18/5/22 | 25/5/22 | 14/6/22 | 15/8/22 | 15/11/22
Actual
9 | [8 empty] | Plan
Actual
Plan
Actual
1) M. Adebola Matanmi (Engr.) General Manager ……..
2) Odesanya M.A D (A & HR) …………………..
3) Omojola A.O AD (Finance& Account) ………………….
4) Ayeni Kamal A.D(Legal)…………………
5) Eneh V.N Procurement ….………….……..
6 Ayeni A.O PS1(Planning & Budget) ……………………
7) Jamiu Y.O- Principal Auditor …………………….
#NAME?