## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: LANDS BUREAU
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Reconstruction of Block 13 & 14, Lands Bureau(60% outstanding balance) | LB/W/NS/001/21 |  | 45176120.082 | <50M | NS | Bill of Quantities | Post | Plan | Prior | 2021-02-08 | 15/02/21 | 22/02/21 | 15/03/21 | 22/03/21 | 29/03/21 | 26/04/21 | 2021-03-27 | 75293533.47 | 2021-05-04 | 2021-05-18 | 2021-06-08 | 30/09/21 | 22/12/21
[9 empty] | Actual | [9 empty] | 45176120.08
| Perimeter Fencing at Epe(60% outstanding balance |  |  | 105000000 | >50M<1B | NCB | Bill of Quantities | Post | Plan | Prior | 2021-03-08 | 2021-03-15 | 2021-03-29 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-31 | 2021-06-01 | 179573728.46 | 2021-06-08 | 2021-06-22 | 2021-07-06 | 2021-08-17 | 2021-09-28
2 |  | LB/W/NS/002/21 | [6 empty] | Actual | [9 empty] | 105000000
3 | Paving with Interlock of External Environment(60% outstanding Balance) | LB/W/DC/003/21 |  | 15720120 | <50M | NS | Bill of Quantities | Post | Plan | Prior | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-07-12 | 2021-07-13 | 26200200 | 2021-07-20 | 2021-07-27 | 2021-08-10 | 2021-09-21 | 2021-11-02
Actual
4 | Rehabilitation of (4) Registries in the Bureau | LB/W/NCB/001/22 |  | 74804613.8 | >50M<1B | NCB | Bill of Quantities | Prior | Plan | Prior | 2022-02-15 | 2022-02-22 | 2022-01-03 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-19 | 2022-04-21 | 74804613.8 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-07-07 | 2022-08-18
Actual
5 | Installation of New Stainless Steel Remodelling of Existing Staircase Hand Rails | LB/W/NS/002/22 |  | 18000000 | <50M | NS | Bill of Quantities | Prior | Plan | Prior | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-05-10 | 2022-05-12 | 18000000 | 2022-05-19 | 2022-06-02 | 2022-06-16 | 2022-07-28 | 2022-09-08
Actual
| Renovation of Toilets | LB/W/NS/003/22 |  | 15000000 | >500<50M | NS | Bill of Quantities | Prior | Plan | Prior | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-24 | 2022-05-25 | 15000000 | 2022-06-01 | 2022-06-08 | 2022-06-22 | 2022-07-06 | 2022-07-20
6 | [8 empty] | Actual
7 | Screeding of the Office Wall,Partitioning of some Offices and Painting | LB/W/NS/004/22 |  | 10000000 | <50M | NS | Bill of Quantities | Prior | Plan | Prior | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-06-14 | 2022-06-15 | 10757238 | 2022-06-22 | 2022-06-29 | 2022-07-13 | 2022-07-27 | 2022-08-10
Actual

## Training,conference & wshop
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: LAND BUREAU
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | PROCUREMENT PLANNING FOR WORKS, GOODS AND SERVICES IN MDAs AND PRIVATE SECTOR.11-13,MAY, ABUJA | LB/S-WTC/001/22 | TO IMPROVE THE PRODUCTIVITY OF OFFICERS IN THIS CADRE | 2 | 3 DAYS | Plan | ABUJA | 200000 | 22,500 X2= 45000 | 355200 | 600200
Actual
2 | ``GLOBAL UNCERTAINTIES AND POLICY INTERVENTIONS FOR MACROECONOMIC STABILITY’’ 26th -28th, October, 2021 | LB/S-WTC/002/22 | STRATEGIG PLANNING &RECORD | 4 | 3 DAYS | Plan | ABUJA | 400000 | 90000 | 686400 | 1176400
Actual
3 | NEW TWIST AND TREND IN COMMUNICATION,REPORT ,MEMO/SPEECH WRITING MINUTES/NOTE TAKING FOR PEAK PERFORMANCE,APRIL,11-15,ENUGU | LB/S-WTC/003/22 | CRITICAL THINKING AND STRATEGIES | 2 | 5 DAYS | Plan | ENUGU | 160000 | 45000 | 355200 | 560200
Actual
4 | BASIC PRCUREMENT AUDIT 1I:PROCUREMENT AUDIT AS A TOOL FOR ECONOMIC PERFORMANCE MEASUREMENT.24-27,MAY 2022. | LB/S-WTC/SS/004/22 | TO IMPROVE THE PRODUCTIVITY OF OFFICERS IN THIS CADRE | 2 | 4 DAYS | Plan | ABUJA | 200000 | 45000 | 355200 | 600200
Actual
5 | EFFECTIVE COMMUNICATION,REPORT WRITING,PUBLIC AFFAIRS,EVENT MANAGEMENT &MEDIA RELATIONS SKILLS,4-8 JULY,ABUJA, 75,000 | LB/S-WTC/005/22 | TO INCREASE CAPABILITY OF OFFICERS IN THIS CADRE | 2 | 2 DAYS | Plan | ABUJA | 65000 | 45000 | 355200 | 465200
Actual
6 | BASIC PROCUREMENT AUDIT 3 ,19-22, JULY 2022 | LB/S-WTC/SS/006/22 | TO IMPROVE THE PRODUCTIVITY OF OFFICERS IN THIS CADRE | 2 | 4 DAYS | Plan
Actual
7 | DYNAMICS IMPACT OF CORPORATE REPORTING AND GOVERNANCE4-6 APRIL,2022,YENEGOA | LB/S-WTC/SS/007/22 | TO INCREASE CAPABILITY OF OFFICERS IN THIS CADRE | 4 | 3 DAYS | Plan | YENEGOA | 280000 | 90000 | 686400 | 1056400
Actual
8 | TECHNOLOGY IMPACT ON ACCOUNTING PRACTICE, 4-6 JULY,2022 IBADAN | LB/S-WTC/SS/008/22 | TO ENHANCE PERFORMANCE OF OFFICERS | 12 | 3DAYS | Plan | IBADAN | 720000 | 90000 | 686400 | 1496400
Actual
9 | AGROPRENEUR IN A DIGITAL ECONOMY:PATHWAY TO ECONOMIC GROWTH AND DEVELOPMENT(ICAN) 5-8,APRIL,2022 | LB/S-WTC/SS/009/22 | EVALUATION &IMPLIMENTATION STRATEGIES | 12 | 4 DAYS | Plan | OWERRI | 720000 | 270000 | 686400 | 1676400
Actual
10 | LEVERAGING IT FOR NATIONAL SECURITY AND ECONOMIC STABILITY;18-19 MAY,2002 | LB/S-WTC/010/22 | RISK MANAGEMENT STRATEGIES | 4 | 2 DAYS | Plan | ABUJA | 260000 | 90000 | 686400 | 1036400
Actual
11 | PERSONAL STRATEGIES & TECHNIQUES FOR MULTI-TASKING,INTELIGENTLY,EFFECTIVELY & SUCCESSFULLY,13-17,JUNE 2022 | LB/S-WTC/011/22 | TO IMPROVE THE PRODUCTIVITY OF OFFICERS IN THIS CADRE | 5 | 5 DAYS | Plan | ENUGU | 325000 | 112500 | 1404000 | 1841500
Actual
12 | EHANCINING MANAGERIAL COMPETENCE FOR PUBLIC OFFICERS.5-7,0CT,202 | LB/S-WTC/012/22 | STATEGIG PLANNING &RECORD KEEPING | 12 | 3 DAYS | Plan | ENUGU | 720000 | 270000 | 686400 | 1676400
Actual
13 | CORPORATE SECRETARIAL PRACTICE TRAINING FOR EXECUTIVE ASST/SECRETARIES 4TH-6TH OCTOBER. 2022 | LB/S-WTC/013/22 | TO IMPROVE THE PRODUCTIVITY OF OFFICERS IN THIS CADRE | 10 | 3 DAYS | Plan | ABUJA | 600000 | 225000 | 1668000 | 2493000
Actual
14 | CLIMATE CHANGE AND SOCIO-ECONOMIC CONSEQUENCE STATISTICS29TH AUG – 1ST SEPT, 2022 | LB/S-WTC/014/22 | TO IMPROVE THE PRODUCTIVITY OF OFFICERS IN THIS CADRE | 4 | 4 DAYS | Plan | ABUJA | 260000 | 90000 | 686400 | 1036400
Actual
15 | EFFECTIVE COACHING AND MENTORING SKILLS FOR SENIOR MANAGERS,7-9,SEPT.2022 | LB/S-WTC/015/22 | RISK MANAGEMENT STRATEGIES | 12 | 3 DAYS | Plan | ENUGU | 720000 | 270000 | 686400 | 1676400
Actual
16 | UNLOCKING REAL ESTATE POTENTIALS FOR ECONOMIC DEVELOPMENT,22-26,JUNE,2022 | LB/S-WTC/016/22 | TO INCREASE CAPABILITY OF OFFICERS IN THIS CADRE | 40 | 5 DAYS | Plan | ABUJA | 2600000 | 900000 | 6636000 | 10136000
Actual

## Non Proc
LANDS BUREAU
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: Lands Bureau
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/ Actual | JANUARY | FEBUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | Total
1 | Committee Expenses(Servicing of Stakeholders Committee Meeting) | LB/NP/NM/001/22 | 3,700,000.00 | Plan |  |  | 925000 |  |  | 925000 |  |  | 925000 |  |  | 925000
Actual
2 | Servicing of Meetings | LB/NP/NM/002/22 | 2,000,000.00 | Plan | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67 | 166666.67
Actual
3 | Dispute Resolution/ Rehabilitation Expenses for Land dispute resolution/Excision. | LB/NP/NM/003/22 | 5000000 | Plan |  |  |  |  | 2500000 | [5 empty] | 2500000
Actual
4 | Logistic for Compensation N2.5M X Quarters | LB/NP/NM/004/22 | 20,000,000.00 | Plan |  |  | 5000000 |  |  | 5000000 |  |  | 5000000 |  |  | 5000000
Actual
5 | Proposed part payment of outstanding liability to six(6) Regularization Consultant | LB/NP/NM/005/22 | 140,000,000.00 | Plan | [5 empty] | 140000000
Actual
6 | Payments of salary to75Ad - hoc staff Digitization. | LB/NP/NM/006/22 | 45000000 | Plan | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000 | 3750000
Actual
7 | Advertisement on Electronic & Print Media(Enlightenment & Camp) on the Bureau's Activities | LB/NP/NM/007/22 | 27,179,716.25 | Plan |  |  | 6103049.6 |  |  | 6103049.6 |  |  | 6103049.6 |  |  | 6103049.6
Actual
8 | Monitoring and Evaluation Excpenses | LB/NP/NM/008/22 | 20500000 | Plan | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33 | 1708333.33
Actual
9 | Servicing of e-GIS Working Committee | LB/NP/NM/009/22 | 1000000 | Plan
Actual
10 | Publication of Names of Applicant for C of O, Deemed Grant, subsequent transaction and whose properties are affected by ROW in National Newspaper | LB/NP/NM/010/22 | 14506430.4 | Plan |  |  |  |  | 7253215.2 |  |  |  |  | 7253215.2
Actual
11 | Publication of Defaulters/applications on consequent transaction, revocation and compensation noticess, executed C of O and deemed Grant and other Sundry Publications | LB/NP/011/22 | 19027152.6 | Plan | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3 | 1854465.3
Actual
12 | Pest Control Exercise | LB/NP/NM/012/22 | 1000000 | Plan |  |  | 250000 |  |  | 250000 |  |  | 250000 |  |  | 250000
Actual
13 | Payment of Outstanding Liability for Lekki Foreshore and Other Schemes | LB/NP/NM/013/22 | 19500000 | Plan |  |  | 4875000 |  |  | 4875000 |  |  | 4875000 |  |  | 4875000
Actual
14 | Payment of Compensation on Acquired Lands | LB/NP/NM/014/22 | 10263692123 | Plan |  |  | 2565923030.75 |  |  | 2565923030.75 |  |  | 2565923030.75 |  |  | 2565923030.75
Actual
15 | Acquisition of Lands (Around Train Station) | LB/NP/NM/015/22 | 4000000000 | Plan |  |  | 1000000000 |  |  | 1000000000 |  |  | 1000000000 |  |  | 1000000000
Actual
16 | Payment of Salary to Securities Personnel at Lands Bureau | LB/NP/NM/016/22 | 7680000 | Plan | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000
17 | Outstanding Payment for Y2021 maintenance of FM200 Autofire Suppression System | LB/NP/NM/017/22 | 1370000 | Actual |  |  | 1370000
18 | Payment to Montgomery vaults for back up tapes. | LB/NP/NM/018/22 | 450000 | Plan |  |  |  | 450000
Actual

## Non Cons
PROCUREMENT PLAN FOR NON CONSULTING ITEMS
MINISTRY/ AGENCY: Lands Bureau
BUDGET YEAR: 2022
S/N | Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Engagement of Janitorial Services | LB/S-NC/FB/001/22 |  |  | 11640000 | <50M | NS | Plan | Post | Prior | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | Plan | 2022-04-12 | 2022-04-14 |  | 2022-05-12 | 2022-06-03 | 2022-12-27 | 2022-01-03
[8 empty] | Actual | [9 empty] | Actual
2 | Clearing of Government Schemes | LB/S-NC/FB/002/22 |  |  | 24412198.4 | <50M | NS | Plan | Post | Prior | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-06-28 | 2022-06-04
[8 empty] | Actual | [9 empty] | Actual
3 | Annual Maintenance Agreement fee for Biometric Access control. | LB/S-NC/FB/003/22 |  |  | 400000 |  |  | Plan |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2022-06-13 | N/A |  | 2022-07-08 | N/A | 2022-12-30 | 2022-01-03
[7 empty] | NS | Actual | Post | Post | [7 empty] | Actual
4 | Maintenance of Generating Set and Inverter | LB/S-NC/FB/004/22 |  |  | 10000000 | <50M | NS | Plan | Post | Post | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-06-28 | 2022-06-04
[8 empty] | Actual | [9 empty] | Actual
5 | Proposed Repairs, Fixing, Replacements of Specific Facilities within the Land Registry | LB/S-NC/FB/005/22 |  |  |  |  | NS | Plan | Post | Post | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | Plan | 2021-05-31 | 2022-06-06 |  | 2022-06-20 | 2022-07-04 | 2022-07-18 | 2022-07-25
[5 empty] | 4461250 | <50M |  | Actual | [9 empty] | Actual
6 | Lands Retreat for staff of Lands Bureau for ease of doing business. | LB/S-NC/FB/006/22 |  |  |  |  | NS | Plan | Post | Post | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | Plan | 2022-05-17 | 2022-05-19 |  | 2022-06-16 | 2022-06-30 | 2022-06-28 | 2022-06-04
[5 empty] | 20000000 | <50M |  | Actual | [9 empty] | Actual
7 | Printing of Revenue Forms | LB/S-NC/FB/007/22 |  |  | 70750750 | >50M<1B | NS | Plan | Prior | Prior | 2022-03-15 | 2022-03-22 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | Plan | 2021-05-31 | 2022-06-06 |  | 2022-06-20 | 2022-07-04 | 2022-07-18 | 2022-07-25
[8 empty] | Actual | [9 empty] | Actual

## Consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: Lands Bureau
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
[7 empty] | Actual | [20 empty] | 6288750
1 | Preparation of New/ Updated Layout Plan in Otto-Awori Jobiti Residential Scheme &Towns-ville Private Developers' Residential Scheme(Balance Payment | LB/S-C/SSS/001/22 | SSS | Lump Sum | 6288750 | Prior | Plan | 2020-12-03 | 2020-12-10 | 2020-12-17 | 2020-12-31 | 2021-01-08 | 2021-01-15 | 2021-02-05 | 2021-02-12 | 2021-02-19 | 2021-02-26 | 2021-03-05 | 2021-03-12 | 2021-04-09 | 2021-04-12 | 6288750 | 2021-04-19 | 2021-05-03 | 2021-05-17 | 2021-05-24 | 2021-05-31
Actual
2 | Preparation of Development Guide within Lekki Axis & Existing Road Allignment | LB/S-C/QCBS/002/22 | QCBS | Lump Sum | 70250000 | Prior | Plan | 2022-02-15 | 2022-05-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-21 | 2022-06-22 |  | 2022-06-29 | 2022-07-13 | 2022-07-27 | 2022-08-10 | 2022-08-17
Actual
3 | Team Bonding initiatives for Directorates of Land Services and LUAC | LB/C/SSS/003/22 | SSS | Lump Sum | 26000000 | Prior | Plan | 2022-02-15 | 2022-05-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-21 | 2022-06-22
Actual
4 | EDMS Annual Licensing Software & Maintenance Agreement fee | LB/S-C/SSS/004/22 | SSS | Lump Sum | 72435000 | Prior | Plan | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 31/05/21 | 2022-06-07 | 2022-06-28 | 2022-06-29 |  | 2022-07-06 | 2022-07-20 | 2022-08-03 | 2022-08-10 | 2022-08-24
Actual
5 | Annual Licensing Software Maintenance fee of E-C of O | LB/C/SSS/005/22 | SSS | Lump Sum | 25000000 | Prior | Plan | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-24 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 | 2022-07-19 | 2022-07-21 |  | 2022-07-28 | 2022-08-11 | 2022-08-25 | 2022-09-08 | 2022-09-15
Actual
6 | Preparation of New Layout Plan for Moribund Schemes | LB/C/QCBS/006/22 | QCBS | Lump Sum | 38711250 | Prior | Plan | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-24 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 | 2022-07-19 | 2022-07-21 |  | 2022-07-28 | 2022-08-11 | 2022-08-25 | 2022-09-08 | 2022-09-15
Actual

## Goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: LANDS BUREAU
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Purchase of Tools and Office Needs/equipments for ongoing Digitization project | LB/NS/G/001/22 |  | Various | 20000000 | <50M | NS | Post | Prior | Plan | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-26 | 2022-03-27 |  | 2022-05-04 | 2022-05-18 | 2022-06-08 | 2022-06-22 | 2022-07-06
Actual
2 | Procurement of Industrial Photocopy Machine | LB/NS/G/002/22 |  | Various | 9000000 | <50M | NS | Post | Post | Plan | 2022-02-08 | N/A | 2022-02-22 | 2022-03-15 | 2022-03-22 | N/A | 2022-04-12 | 2022-04-20 |  | 2022-04-27 | 2022-05-04 | 2022-05-18 | 2022-06-01 | 2022-06-15
Actual
3 | Fuelling of Vehicles and Generator | LB/NS/G/003/22 |  |  | 14000000 | <50M | NS | Post | Prior | Plan | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-06 |  | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-11 | 2022-05-25
Actual
4 | Procurement of Stationeries Item | LB/NS/G/004/22 |  | Various | 30448486.73 | <50M | NS | Post | Prior | Plan | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-22 | 2022-03-29 | 2022-04-19 | 2022-04-21 |  | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-07-07 | 2022-08-18
Actual
5 | Procurement of Security paper from UK for New e - C of O | LB/ICB/G/005/22 |  | Various | 500000000 | >50M<1B | ICB | Post | Prior | Plan | 2022-03-01 | 2022-03-08 | 2022-03-22 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-06-07 | 2022-06-09 |  | 2022-06-16 | 2022-06-23 | 2022-07-07 | 2022-08-18 | 2022-09-29
Actual
6 | Procurement of Toners & Protective Binding Covers. | LB/NS/G/006/22 |  | " | 2000000 | <50M | NS | Post | Post | Plan | 2022-03-08 | N/A | 2022-03-15 | 2022-03-22 | N/A | N/A | 2022-03-12 | N/A |  | 2022-03-19 | 2022-03-26 | 2022-05-10 | 2022-05-24 | 2022-06-07
Actual
7 | Procuremnt of Equipment/Tools | LB/NS/G/007/22 |  | " | 10500000 | <50M | NS | Post | Prior | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-31 | 2022-06-01 |  | 2022-06-08 | 2022-06-22 | 2022-07-06 | 2022-08-17 | 2022-09-28
Actual
8 | Procurement of Uniform Outfit For Drivers and Cleaners | LB/NS/G/008/22 |  | Various | 1000000 | <50M | NCB | Post | Post | Plan | 2022-03-15 | N/A | 2022-03-29 | 2022-04-12 | N/A | N/A | 2022-04-26 | N/A |  | 2022-05-03 | 2022-05-10 | 2022-05-24 | 2022-06-14 | 2022-06-28
Actual
9 | Procurement of Sanitary Items | LB/NS/G/009/22 |  |  | 920000 | <50M | NS | Post | Post | Plan | 2022-03-29 | N/A | 2022-04-05 | 2022-04-12 | N/A | N/A | 2022-05-26 | N/A |  | 2022-05-03 | 2022-05-10 | 2022-05-24 | 2022-06-14 | 2022-06-28
Actual
10 | Procurement of Wooden Chairs for Planning and Index Room | LB/NS/G/010/22 |  | Various | 4988000 | <50M | NS | Post | Post | Plan | 2022-04-05 | N/A | 2022-05-19 | 2022-05-03 | N/A | N/A | 2022-06-07 | 2022-06-09 |  | 2022-06-16 | 2022-06-30 | 2022-07-14 | 2022-07-28 | 2022-08-11
Actual
11 | Procurement of Three Dimention Bold Watermark. | LB/NS/G/011/22 |  | Various | 10000000 | <50M | NS | Post | Prior | Plan | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-31 | 2022-06-02 |  | 2022-06-09 | 2022-06-16 | 2022-06-30 | 2022-07-14 | 2022-07-28
Actual
12 | Procurement and Installation of Fire Extinguishing system,200MF and | LB/NS/G/012/22 |  | " | 20000000 | >50M<1B | NS | Post | Prior | Plan | 2022-04-05 | 2022-05-12 | 2022-05-19 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-06-07 | 2022-06-09 |  | 2022-06-16 | 2022-06-30 | 2022-07-14 | 2022-07-28 | 2022-08-11
Actual
13 | Procurement of Giant Sign Post, Small Signpost | LB/NCB/G/013/22 |  | " | 50000000 | >50M<1B | NCB | Post | Prior | Plan | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-21 | 2022-06-22 |  | 2022-06-29 | 2022-07-13 | 2022-07-27 | 2022-09-07 | 2022-10-19
Actual
14 | Procurement of Computers Equipment, Software &Consumables | LB/NS/G/014/22 |  | " | 21000000 | <50M | NS | Post | Prior | Plan | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-07-12 | 2022-07-13 |  | 2022-07-20 | 2022-07-27 | 2022-08-10 | 2022-08-24 | 2022-09-07
Actual
15 | Procurement of Air Conditioners | LB/NS/G/015/22 |  | Various | 12000000 | <50M | NS | Post | Prior | Plan | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-07-12 | 2022-07-14 |  | 2022-07-21 | 2022-07-28 | 2022-08-11 | 2022-08-25 | 2022-09-08
Actual
16 | Procurement of Office Furniture | LB/NS/G/016/22 |  | " | 20000000 | <50M | NS | Post | Post | Plan | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-07-05 | 2022-07-06 |  | 2022-07-13 | 2022-07-20 | 2022-08-03 | 2022-08-17 | 2022-08-31
Actual
17 | Procurement and Installation of CCTV Cameras | LB/NS/G/017/22 |  | " | 8000000 | <50M | NS | Post | Post | Plan | 2022-05-10 | N/A | 2022-05-17 | 2022-05-31 | N/A | N/A | 2022-06-14 | N/A |  | 2022-06-21 | 2022-06-28 | 2022-07-12 | 2022-07-26 | 2022-07-09
Actual
18 | Procurement of Office Equipment for Year 2022 & Fitting for the Creation of Land Registry Court at Lands Bureau | LB/NS/G/018/22 |  | Various | 4894125 | <50M | NS | Post | Post | Plan | 2022-05-17 | N/A | 2022-05-31 | 2022-06-14 | N/A | N/A | 2022-07-26 | N/A |  | 2022-06-21 | 2022-06-28 | 2022-07-12 | 2022-07-26 | 2022-08-09
Actual
19 | Procurement of Office Furniture& Registry Cabinet | LB/NS/G/019/22 |  | " | 20000000 | <50M | NS | Post | Prior | Plan | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-14 | 2022-06-21 | 2022-06-28 | 2022-07-26 | 2022-07-28 |  | 2022-08-04 | 2022-08-11 | 2022-08-25 | 2022-09-08 | 2022-09-22
Actual
20 | Procurement of 96 Inverter Batteries | LB/NS/G/020/22 |  | Various | 19242762 | <50M | NS | Post | Post | Plan | 2022-05-24 | 2022-05-31 | 2022-06-07 | 2022-06-21 | 2022-06-28 | 2022-07-05 | 2022-06-19 | 2022-07-20 |  | 2022-07-27 | 2022-08-03 | 2022-08-17 | 2022-09-07 | 2022-09-21
Actual
21 | Procurement of Tyres and Other Parts for Operational Vehicles | LB/NS/G/021/22 |  | " | 17178510 | <50M | NS | Post | Post | Plan | 2022-06-01 | 2022-06-15 | 2022-06-29 | 2022-07-11 | 2022-07-18 | 2022-07-27 | 2022-08-17 | 2022-08-18 |  | 2022-08-25 | 2022-09-01 | 2022-09-15 | 2022-09-29 | 2022-10-14
Actual