## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: MINISTRY OF SCIENCE AND TECHNOLOGY
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Travel & Transport | MST/NP/NM/01/2022 | 3600000 | Plan | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 3600000
Actual
2 | General utility services | MST/NP/NM/02/2022 | 5000000 | Plan | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 416666.6667 | 5000000
Actual
3 | Miscellaneous | MST/NP/NM/03/2022 | 6000000 | Plan | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 6000000
Actual
4 | Committee Expenses | MST/NP/NM/04/2022 | 5722715 | Plan |  |  | 1430678.75 |  |  | 1430678.75 |  |  | 1430678.75 |  |  | 1430678.75 | 5722715
Actual
5 | Special Duties Expenses | MST/NP/NM/05/2022 | 29040000 | Plan | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 2420000 | 29040000
Actual
6 | Press/Public Relation | MST/NP/NM/06/2022 | 4000000 | Plan |  |  |  | 1333333.3333 |  |  |  | 1333333.3333 |  |  |  | 1333333.3333 | 4000000
Actual
7 | Audit Unit Expenses | MST/NP/NM/07/2022 | 2000000 | Plan |  |  | 500000 |  |  | 500000 |  |  | 500000 |  |  | 500000 | 2000000
Actual
8 | Legal Unit Expenses | MST/NP/NM/08/2022 | 1000000 | Plan | [5 empty] | 500000 | [5 empty] | 500000 | 1000000
Actual
9 | Planning, Research and Statistics Expenses | MST/NP/NM/10/2022 | 3500000 | Plan |  |  |  | 1166666.6667 |  |  |  | 1166666.6667 |  |  |  | 1166666.6667 | 3500000
Actual
10 | Procurement Unit Expenses | MST/NP/NM/11/2022 | 2500000 | Plan |  |  |  | 1500000 |  |  |  |  | 1000000 |  |  |  | 2500000
Actual
11 | Promotion Exercise Expenses | MST/NP/NM/12/2022 | 2500000 | Plan |  |  | 2500000 | [9 empty] | 2500000
Actual
12 | Science Policy, Programme & Promotion Expenses | MST/NP/NM/13/2022 | 7000000 | Plan |  |  |  | 2333333.3333 |  |  |  | 2333333.3333 |  |  |  | 2333333.3333 | 7000000
Actual
13 | Monitoring and Evaluation Expenses | MST/NP/NM/14/2022 | 3000000 | Plan |  |  |  | 1000000 |  |  |  | 1000000 |  |  |  | 1000000 | 3000000
Actual
14 | Programme Management Expenses | MST/NP/NM/15/2022 | 5000000 | Plan |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 |  |  | 1250000 | 5000000
Actual
14 | Allowance for Security and Cleaning Services | MST/NP/NM/16/2022 | 9720000 | Plan | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 810000 | 9720000
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: MINISTRY OF SCIENCE AND TECHNOLOGY
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Workshop and Trainig Expenses | MST/S-WTC/01/2022 |  |  |  | Plan |  |  |  |  | 5000000
Actual
2 | Confrence and Seminar | MST/S-WTC/02/2022 |  |  |  | Plan |  |  |  |  | 12000000
Actual
3 | State wide IT capacity Building | MST/S-WTC/03/2022 |  |  |  | Plan |  |  |  |  | 10500000
Actual
4 | Capacity Building for Oracle Application Module for MDAs | MST/S-WTC/04/2022 |  |  |  | Plan |  |  |  |  | 35000000
Actual
5 | Art of Lagos | MST/S-WTC/05/2022 |  |  |  | Plan |  |  |  |  | 130000000
Actual
6 | Retreat for ICT Professionals & Key Management | MST/S-WTC/06/2022 |  |  |  | Plan |  |  |  |  | 7500000
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 | [5 empty] | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: MINISTRY OF SCIENCE AND TECHNOLOGY
BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
S/NO |  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Subscription of ESET Antivirus | MST/S-NC/DC/01/2022 | 1 | 1 | 178900000 | >50M<1B | DC | Plan | Pre | Prior | 2022-01-05 | 2022-02-03 | 2022-02-24 | 2022-03-09 | 2022-03-23 | 2022-03-31 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-17 | 2022-06-01 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
2 | Office360 Subscription (0365e1, 0365 e2, exchange protector) | MST/S-NC/DC/02/2022 | 1 | 1 | 240100000 | >50M<1B | DC | Plan | Pre | Prior | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
3 | Subsciption of External DNS/Afrinic | MST/S-NC/DC/03/2022 | 1 | 1 | 2000000 | <50M | DC | Plan | Pre | Post | 2022-01-10 | 2022-02-08 | 2022-02-25 | 2022-03-15 | 2022-03-30 | 2022-04-04 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-24 | 2022-06-09 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
4 | Subscription of Hitachi Support | MST/S-NC/DC/04/2022 | 1 | 1 | 77000000 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
5 | Back - up site (Rack Centre) | MST/S-NC/DC/05/2022 | 1 | 1 | 70000000 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-05 | 2022-02-03 | 2022-02-24 | 2022-03-09 | 2022-03-23 | 2022-03-31 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-17 | 2022-06-01 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
6 | Microsoft License | MST/S-NC/DC/06/2022 | 1 | 1 | 134100000 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
7 | Renewal of SSL Certificate | MST/S-NC/DC/07/2022 | 1 | 1 | 6900000 | <50M | DC | Plan | Pre | Post | 2022-01-10 | 2022-02-08 | 2022-02-25 | 2022-03-15 | 2022-03-30 | 2022-04-04 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-24 | 2022-06-09 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
8 | Maintenance of Server Room Cooling & Power By First Class Group Ltd. | MST/S-NC/DC/08/2022 | 1 | 1 | 23000000 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-05 | 2022-02-03 | 2022-02-24 | 2022-03-09 | 2022-03-23 | 2022-03-31 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-17 | 2022-06-01 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
9 | Maintenance of Switches & Routers by Cisco | MST/S-NC/DC/09/2022 | 1 | 1 | 50000000 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
10 | Enterprise Network for Network Campus Infrastructure by Nesos Information & Technology Solutions | MST/S-NC/DC/10/2022 | 1 | 1 | 409416012.38 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-05 | 2022-02-03 | 2022-02-24 | 2022-03-09 | 2022-03-23 | 2022-03-31 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-17 | 2022-06-01 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
11 | Enterprise Network Security for Network Campus Infrastructure by First Class Group Limited | MST/S-NC/DC/11/2022 | 1 | 1 | 6417345.12 | >50M -100M | DC | Plan | Pre | Post | 2022-01-10 | 2022-02-08 | 2022-02-25 | 2022-03-15 | 2022-03-30 | 2022-04-04 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-24 | 2022-06-09 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
12 | Enterprise Wireless Network for Network Campus Infrastructure by Soft Alliance Limited | MST/S-NC/DC/12/2022 | 1 | 1 | 179328593.69 | >50M -100M | DC | Plan | Pre | Prior | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
13 | Support Services by Mainone | MST/S-NC/DC/13/2022 | 1 | 1 | 168000000 | >50M<1B | DC | Plan | Pre | Prior | 2022-01-05 | 2022-02-03 | 2022-02-24 | 2022-03-09 | 2022-03-23 | 2022-03-31 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-17 | 2022-06-01 | 2022-06-29
Actual
14 | Renewal of Vehicle Tracking System | MST/S-NC/DC/14/2022 | 1 | 1 | 188957375 | >50M<1B | DC | Plan | Pre | Prior | 2022-01-10 | 2022-02-08 | 2022-02-25 | 2022-03-15 | 2022-03-30 | 2022-04-04 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-24 | 2022-06-09 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
21 | Maintenance and repair of ICT Equipment | MST/S-NC/NS/01/2022 | 1 | 1 | 7573000 | <50M | NS | Plan | Pre | Post | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
22 | Motor vehicle maintance | MST/S-NC/NS/02/2022 | 1 | 1 | 6000000 | <50M | NS | Plan | Pre | Post | 2022-01-05 | 2022-02-03 | 2022-02-24 | 2022-03-09 | 2022-03-23 | 2022-03-31 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-17 | 2022-06-01 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
23 | Servicing of 4nos plant | MST/S-NC/NS/03/2022 | 1 | 1 | 2867000 | <50M | NS | Plan | Pre | Post | 2022-01-10 | 2022-02-08 | 2022-02-25 | 2022-03-15 | 2022-03-30 | 2022-04-04 | 2022-04-13 | Plan | 2022-04-28 | 2022-04-29 |  | 2022-05-24 | 2022-06-09 | 2022-06-29
[8 empty] | Actual | [9 empty] | Actual
24 | Oustanding payment for Procurement 0f Interactive Boards by Messers. Erudite | MST/S-NC/DC/20/2022 | 1 | 1 | 15000000 | <50M | DC | Plan | Pre | Prior | 2022-01-03 | 2022-02-01 | 2022-02-21 | 2022-03-07 | 2022-03-21 | 2022-03-29 | 2022-04-11 | Plan | 2022-04-26 | 2022-04-27 |  | 2022-05-16 | 2022-06-02 | 2022-06-27
[8 empty] | Actual | [9 empty] | Actual
29 | [7 empty] | Plan | Post | [8 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual
[8 empty] | Plan | [9 empty] | Plan
[8 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: MINISTRY OF SCIENCE AND TECHNOLOGY
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[8 empty] | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
1 | Consultancy Services for Mapping Digitalisation & Vectorization | MST/S-C/CQS/01/2022 | CQS | Lump Sum | 120000000 | Prior | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-17 | 2022-03-24 | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-04-30 |  | 2022-05-07 | 2022-05-21 | 2022-06-04 | 2022-06-11 | 2022-06-18
Actual
2 | Consultancy Services for Service Desk | MST/S-C/CQS/02/2022 | CQS | Lump Sum | 12700964 | Prior | Plan | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-01 |  | 2022-05-08 | 2022-05-22 | 2022-06-05 | 2022-06-12 | 2022-06-19
Actual
3 | Consultancy Service for Enterprise Security | MST/S-C/CQS/03/2022 | CQS | Lump Sum | 155000000 | Prior | Plan | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-11 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
4 | Consultancy Service for utility Service Software. | MST/S-C/CQS/04/2022 | CQS | Lump Sum | 30000000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
5 | Consultancy Service for Central Billing System | MST/S-C/CQS/05/2022 | CQS | Lump Sum | 7500000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
6 | Consultancy Service for Hosting of MDAs Application | MST/S-C/CQS/06/2022 | CQS | Lump Sum | 30000000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
7 | Consultancy Service for LASG Mapping: Data Capture Project | MST/S-C/CQS/07/2022 | CQS | Lump Sum | 110000000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
8 | Consultancy Services for the Implementation of e-GIS / Supporting equipment | MST/S-C/CQS/08/2022 | CQBS | Lump Sum | 1091975498 | Prior | Plan | 2022-01-27 | 2022-02-03 | 2022-02-10 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-30 | 2022-04-07 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | 2022-05-11 | 2022-05-13 |  | 2022-05-21 | 2022-06-04 | 2022-06-18 | 2022-06-25 | 2022-07-02
Actual
9 | Consultancy Services for Eko Vention | MST/S-C/CQS/09/2022 | CQS | Lump Sum | 20000000 | Prior | Plan | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-21 | 2022-02-28 | 2022-03-06 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-15 | 2022-06-22 | 2022-06-29
Actual
10 | Consultancy Services for OEM Support Existing Infrastructure | MST/S-C/CQBS/1/2022 | CQBS | Lump Sum | 130000000 | Prior | Plan | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-21 | 2022-02-28 | 2022-03-06 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-11 |  | 2022-05-18 | 2022-06-01 | 2022-06-15 | 2022-06-22 | 2022-06-29
Actual
11 | Start UP Lagos | MST/S-C/CQBS/2/2022 | CQBS | Lump Sum | 20000000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-03-04 | 2022-10-04 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-08-06 | 2022-06-15 | 2022-06-22
Actual
12 | Project & Mgt. Monitoring, Legal Contracting mgt, Technology & Engineering delivery, Commercial delivery and Reporting Delivery of the Lagos State Smart City Project by Messrs. Iroko Capital Partners Limited. | MST/S-C/SSS/1/2022 | SSS | Lump Sum | 551012500 | Prior | Plan | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-17 | 2022-03-24 | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-04-30 |  | 2022-05-11 | 2022-05-21 | 2022-06-04 | 2022-06-11 | 2022-06-18
Actual
13 | Implementation of Lagos Smart City Project by Messrs. Blueprint Business Technology Limited. (Phase II) | MST/S-C/SSS/2/2022 | SSS | Lump Sum | 10000000020 | Prior | Plan | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-01 |  | 2022-05-08 | 2022-05-22 | 2022-06-05 | 2022-06-12 | 2022-06-19
Actual
14 | Renewal of Oracle License and Support | MST/S-C/SSS/3/2022 | SSS | Lump Sum | 2140165378.81 | Prior | Plan | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-02 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
15 | Renewal of Annual Support of Global Computerization Project (GCP) by Soft Alliance (June 2021 - May 2022) | MST/S-C/SSS/4/2022 | SSS | Lump Sum | 450000000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-02 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
16 | Data Protection / Privacy Activities | MST/S-C/SSS/5/2022 | SSS | Lump Sum | 130520836.26 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-02 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
17 | Overhauling of ABAT Centre by First Class | MST/S-C/SSS/6/2022 | SSS | Lump Sum | 18259539.24 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-02 | 2022-05-04 |  | 2022-11-05 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
18 | Production of IT Policy & Business Process Documents | MST/S-C/SSS/7/2022 | SSS | Lump Sum | 500000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-02 | 2022-04-05 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual
19 | Smart City Expo | MST/S-C/SSS/8/2022 | SSS | Lump Sum | 151000000 | Prior | Plan | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-02 | 2022-05-04 |  | 2022-05-11 | 2022-05-25 | 2022-06-08 | 2022-06-15 | 2022-06-22
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: MINISTRY OF SCIENCE AND TECHNOLOGY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of PMS for 14nos . Vehicle and purchase of PMS for 2nos Motorcycle | MST/G-F/NS/01/2022 | 1 | 1 | 9000000 | < 50M | NS | Post | Post | Plan | 2022-01-10 | 2022-01-24 | 2022-02-14 | 2022-03-07 | 2/03/20220 | 2022-03-28 | 2022-04-04 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-02 | 2022-05-16 | 2022-05-30
Actual
2 | Procurement of Cartons of papers , other stationery items and printing of Letter Head / File Jacket | MST/G-F/NS/02/2022 | 1 | 1 | 4800000 | < 50M | NS | Post | Post | Plan | 2022-01-11 | 2022-01-25 | 2022-02-15 | 2022-03-08 | 3/03/20220 | 2022-03-29 | 2022-04-05 | 2022-04-06 |  | 2022-04-13 | 2022-04-20 | 2022-05-03 | 2022-05-17 | 2022-05-31
Actual
3 | Procurement of Protective Outfit and Uniform | MST/G/NS/01/2022 | 1 | 1 | 500000 | < 50M | NS | Post | Post | Plan | 2022-01-13 | 2022-01-27 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-12 |  | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-30 | 2022-05-16
Actual
4 | Procurement of Management Information System accessories ( Replacement of minor part of IT equipment, IT consumables ( Tonner, Cables etc.) | MST/G/NS/02/2022 |  |  | 3500000 | < 50M | NS | Post | Post | Plan | 2022-01-10 | 2022-01-24 | 2022-02-14 | 2022-03-07 | 2/03/20220 | 2022-03-28 | 2022-04-04 | 2022-04-05 |  | 2022-04-12 | 2022-04-19 | 2022-05-02 | 2022-05-16 | 2022-05-30
Actual
5 | Procurement of Cleaning and other Janitorial items | MST/G/NS/03/2022 | 1 | 1 | 1500000 | < 50M | NS | Post | Post | Plan | 2022-01-11 | 2022-01-25 | 2022-02-15 | 2022-03-08 | 3/03/20220 | 2022-03-29 | 2022-04-05 | 2022-04-06 |  | 2022-04-13 | 2022-04-20 | 2022-05-03 | 2022-05-17 | 2022-05-31
Actual
6 | Purchase of Diesel for 4nos Gen. Set | MST/G-F/NS/03/2022 | 1 | 1 | 23133000 | < 50M | NS | Post | Prior | Plan | 2022-01-13 | 2022-01-27 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-12 |  | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-30 | 2022-05-16
Actual
7 | Procurement of Blade Server, Virtualisation software& Brocade Switch 7 Additional Storage for MDAs Digitalisation | MST/G/NS/04/2022 | 1 | 1 | 75000000 | < 50M | NS | Post | Prior | Plan | 2022-01-11 | 2022-01-25 | 2022-02-15 | 2022-03-08 | 3/03/20220 | 2022-03-29 | 2022-04-05 | 2022-04-06 |  | 2022-04-13 | 2022-04-20 | 2022-05-03 | 2022-05-17 | 2022-05-31
Actual
8 | Procurement of Desktop and Laptops and payment for oustanding on Procurement of Desktop and Laptops | MST/G/NCB/01/2022 | 1 | 1 | 118700000 | >100M | NCB | Pre | Prior | Plan | 2022-01-13 | 2022-01-27 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-12 |  | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-30 | 2022-05-16
Actual
9 | Replacement of obsolete/Outdated Cables, Servers & Switches and other hardware (Campus-wide) | MST/G/NCB/02/2022 | 1 | 1 | 67022046.5 | >50M -100M | NCB | Pre | Prior | Plan | 2022-01-11 | 2022-01-25 | 2022-02-15 | 2022-03-08 | 3/03/20220 | 2022-03-29 | 2022-04-05 | 2022-04-06 |  | 2022-04-13 | 2022-04-20 | 2022-05-03 | 2022-05-17 | 2022-05-31
Actual
10 | Additional Equipment for Science Lab | MST/G/NS/05/2022 | 1 | 1 | 20000000 | <50M | NS | Post | Prior | Plan | 2022-01-13 | 2022-01-27 | 2022-02-28 | 2022-03-14 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-12 |  | 2022-04-19 | 2022-05-03 | 2022-05-10 | 2022-05-30 | 2022-05-16
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: MINISTRY OF SCIENCE AND TECHNOLOGY
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Rennovation & Furnishing of MoST Building, ABAT and Digital Village | MST/W/NCB/01/2022 | 1 | 79999997 | >50M - <1B | NCB | Bill of Quantity | Pre | Plan | Prior | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-02 | 2022-02-18 | 2022-02-25 | 2022-03-08 | 2022-03-09 |  | 2021-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-21 | 2022-04-28
Actual
2 | Maintenance of Office Building | MST/W-F/NS/01/2022 | 1 | 1600000 | <50M | NS | Bill of Quantity | Pre | Plan | Prior | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-21 | 2022-02-28 | 2022-03-14 | 2022-03-15 |  | 2022-03-21 | 2022-03-28 | 2022-04-11 | 2022-04-25 | 2022-05-02
Actual
3 | Construction of New Data Centre | MST/W/ICB/01/2022 | 1 | 2500000000 | >1B | ICB | Bill of Quantity | Pre | Plan | Prior | 2022-01-18 | 2022-01-25 | 2022-02-01 | 2022-02-08 | 2022-02-22 | 2022-03-01 | 2022-03-13 | 2022-03-14 |  | 2022-03-22 | 2022-03-29 | 2022-04-12 | 2022-04-26 | 2022-05-03
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Sheet4
LAGOS STATE GOVERNMENT MINISTRY OF SCIENCE AND TECHNOLOGY Y2022 PROCUREMENT PLAN