## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: NEW TOWNS DEVELOPMENT AUTHORITY
BUDGET YEAR: Y2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | Payment of Waste Disposal for 12 months | NTD/NP/NM/001/22 | 120,000.00 | Plan | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 120,000.00
Actual
2 | Allowance for Officers on Monitoring Assignment (Site Selection- Dedicated) | NTD/NP/NM/002/22 | 14,800,000.00 | Plan | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 1233333.33 | 14,800,000.00
Actual
3 | Travel & Transport - Local (Fuel Allownaces) | NTD/NP/NM/003/22 | 486,100.00 | Plan | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 40508.33 | 486,100.00
Actual
4 | Payment for General Utility Services (Electricity/Water Bills) | NTD/NP/NM/004/22 | 5,620,000.00 | Plan | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 468333.33 | 5,620,000.00
Actual
5 | Departmental Allowances for GM's Office/A&HR/F&A/ES/TPS/ICT/Estate/Survey/DCMU(Miscellaneous/Special Duties Expenses) | NTD/NP/NM/005/22 | 8583000 | Plan | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 715250 | 8583000
Actual
6 | Payment of Internet Expenses/DSTV/GOTV Subscription | NTD/NP/NM/006/22 | 1,355,450.00 | Plan | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 112954.17 | 1,355,450.00
Actual
7 | Send Forth Ceremony for Retiring Staff (Special Duties-Dedicated) | NTD/NP/NM/007/22 | 7,000,000.00 | Plan | NA | NA | NA | NA | NA | 3500000 | NA | NA | NA | NA | NA | 3500000 | 7,000,000.00
Actual
8 | Payment for NTDA Website Renewal (Special Duties-Dedicated) | NTD/NP/NM/008/22 | 5,000,000.00 | Plan | 5,000,000.00 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5,000,000.00
Actual
9 | Y2022 Personel Budget Expenses (Special Duties-Dedicated) | NTD/NP/NM/009/22 | 2,500,000.00 | Plan | NA | NA | NA | NA | NA | NA | NA | 500000 | 500000 | 500000 | 500000 | 500000 | 2,500,000.00
Actual
10 | Y2022 Promotion Exercise Expenses (Special Duties - Dedicated) | NTD/NP/NM/010/22 | 4,000,000.00 | Plan | NA | NA | 4,000,000.00 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 4,000,000.00
Actual
11 | Meeting Allowances for Estate/Survey/Monitoring Unit (Special Duties - Dedicated) | NTD/NP/NM/011/22 | 2,500,000.00 | Plan | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 208333.33 | 2,500,000.00
Actual
12 | Payment of Tax Liabilities | NTD/NP/NM/012/22 | 7,000,000.00 | Plan | NA | NA | 1750000 | NA | NA | 1750000 | NA | NA | 1750000 | NA | NA | 1750000 | 7,000,000.00
Actual
13 | Payment of Accrued Right Pension for NTDA Staff (Dedicated) | NTD/NP/NM/013/22 | 37,500,000.00 | Plan | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 3125000 | 37,500,000.00
Actual
14 | Payment for Fuel Technical (Engineering and Town Planning Services) Site Expenses (Dedicated) | NTD/NP/NM/014/22 | 16,000,000.00 | Plan | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 1333333.333 | 16,000,000.00
Actual
Actual
15 | Audit Inspection Expenses (Special Duties - Dedicated) | NTD/NP/NM/015/22 | 3,000,000.00 | Plan | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 3,000,000.00
Actual
16 | Logistics/Honourarium for Land Stakeholders/Vendors Engagement (Special Duties - Dedicated) | NTD/NP/NM/016/22 | 5,000,000.00 | Plan | NA | NA | 1250000 | NA | NA | 1250000 | NA | NA | 1250000 | NA | NA | 1250000 | 5,000,000.00
Actual
17 | Audit Unit Expenses (Running Expenses/Purchase of Auditor General Report/Updating of Assets Register/Payment of Audit fee to External Auditor/Audit Meetings etc. - Subvention & Dedicated) | NTD/NP/NM/017/22 | 4,500,000.00 | Plan | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 4,500,000.00
Actual
21 | Legal Unit Expenses (Running Expenses/Servicing of Litigation related expenses/Purchase of Legal Journals etc. - Subvention & Dedicated ) | NTD/NP/NM/021/22 | 16,600,000.00 | Plan | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 1383333.33 | 16,600,000.00
Actual
18 | Planning Research & Statistics Unit Expenses ( Running Expenses/Preparation & Production of Annual Budget/MTSS Document/Preparation/Performance Management Report/ProjecMonitoring/PMR/Survey Expenses/Budget Sensitization etc.) - Subvention & Dedicated) | NTD/NP/NM/018/22 | 8,000,000.00 | Plan | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 666666.66 | 8,000,000.00
Actual
19 | Procurement Unit Expenses (Running Expenses/Market Survey/Servicing of PTB/PPC/Production of Bidding Documents/Preparation of Procurement Plan/Sensitization Programme etc.) - Subvention & Dedicated | NTD/NP/NM/019/22 | 7,500,000.00 | Plan | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 625000 | 7500000
Actual
19 | Participation/Incidental Expenses for Exhibition/Trade Fair and World Habitat Day/Housing Fair (Subvention & Dedicated) | NTD/NP/NM/019/22 | 8500000 | Plan | NA | NA | NA | NA | NA | NA | NA | 4250000 | NA | NA | 4250000 | NA | 8500000
Actual
20 | Provision of Grants/Donations/Presents to Professional Bodies/Public/Social Responsibilities etc. (Subvention & Dedicated) | NTD/NP/NM/020/22 | 600000 | Plan | NA | NA | 150000 | NA | NA | 150000 | NA | NA | 150000 | NA | NA | 150000 | 600000
Actual
21 | Financial Assistance for Staff/Reimbursement for Repairs of Staff Quarters (Subvention & Dedicated) | NTD/NP/NM/021/22 | 14000000 | Plan | NA | NA | 3500000 | NA | NA | 3500000 | NA | NA | 3500000 | N A | NA | 3500000 | 14000000
Actual
21 | Annual Renewal Subscription (Maintenance) of Security Software | NTD/NP/NM/021/22 | 2200000 | Plan | 2200000 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2200000
Actual
22 | Site Inspection and Identification Expenses -Engagement of Task Force (Site Selection -Dedicated) | NTD/NP/NM/022/22 | 64800000 | Plan | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 64800000
Actual
23 | Monitoring & Development Control of NTDA Schemes and Miscellaneous Expenses (Site Selection - Dedicated) | NTD/NP/NM/023/22 | 12000000 | Plan | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 12000000
Actual

## trg conf wsh
nh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: NEW TOWNS DEVELOPMENT AUTHORITY (NTDA)
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Nigeria Bar Association Conference (Subvention & Dedicated) | NTD/S-WTC/SS/001 | Capacity Development | 2 | 5 | Plan | Abuja | 267000 | 148000 | 885000 | 1300000
Actual
2 | Engineering Conference (Subvention & Dedicated) | NTD/S-WTC/SS/002 | Capacity Development | 11 | 5 | Plan | Abuja | 550000 | 825000 | 11175000 | 12550000
Actual
3 | Nigeria Institute of Town Planners (Subvention & Dedicated) | NTD/S-WTC/SS/003 | Capacity Development | 9 | 5 | Plan | Abuja | 360000 | 738000 | 9852000 | 10950000
Actual
4 | Nigeria Institute of Personnel Management (Subvention & Dedicated) | NTD/S-WTC/SS/004 | Capacity Development | 9 | 5 | Plan | Abuja | 900000 | 675000 | 11075000 | 12650000
Actual
5 | Accountants Conference (Subvention & Dedicated) | NTD/S-WTC/SS/005 | Capacity Development | 8 | 5 | Plan | Abuja | 440000 | 1000000 | 7060000 | 8500000
Actual
6 | Nigeria Institute of Public Relations | NTD/S-WTC/SS/006 | Capacity Development | 2 | 5 | Plan | Port Harcourt | 210000 | 146000 | 594000 | 950000
Actual
7 | Nigeria Statistical Association Conference (Subvention & Dedicated) | NTD/S-WTC/SS/007 | Capacity Development | 4 | 5 | Plan | Abuja | 160000 | 296000 | 1194000 | 1650000
Actual
8 | Chartered Institute of Purchasing & Supply Management of Nig Conf (Subvention & Dedicated) | NTD/S-WTC/SS/008 | Capacity Development | 4 | 5 | Plan | Abuja | 240000 | 296000 | 714000 | 1250000
9 | Estate Surveyor & Valuers Conf | NTD/S-WTC/SS/009 | Capacity Development | 4 | 5 | Plan | Lagos | 200000 | 25000 | 25000 | 250000
Actual
10 | Nigeria Institute of Quantity Surveyors (Subvention & Dedicated) | NTD/S-WTC/SS/010 | Capacity Development | 4 | 5 | Plan | Abuja | 200000 | 292000 | 3108000 | 3600000
Actual
11 | Information Communication Technology Conference (Subvention & Dedicated) | NTD/S-WTC/SS/011 | Capacity Development | 4 | 5 | Plan | Abuja | 140000 | 296000 | 2564000 | 3000000
12 | Nigeria Economics Society Conference (Subvention & Dedicated) | NTD/S-WTC/SS/012 | Capacity Development | 2 | 5 | Plan | Abuja | 100000 | 146000 | 1384000 | 1630000
13 | Auditors Conference (Subvention & Dedicated | NTD/S-WTC/SS/014 | Capacity Development | 3 | 5 | Plan | Abuja | 150000 | 219000 | 1981000 | 2350000
Actual
TOTAL | [10 empty] | 60630000

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: NEW TOWNS DEVELOPMENT AUTHORITY (NTDA)
BUDGET YEAR: Y2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Provision of Consulting Services - Feasibility Studies/Vaibility Reports/Financial Analysis (Subvention & Dedicated) | NTD/S-C/LCS/001/22 | LCS | Lumpsum | 16000000 | Prior | Plan | 2022-03-02 | 2022-03-09 | NA | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-27 | 2022-05-04 | 11-May-22 | 18-May-22 | 25-May-22 | 1-Jun-22 | 29-Jun-22 | 30-Jun-22 | NA | 6-Jul-22 | 20-Jul-22 | 3-Aug-22 | 10-Aug-22 | 17-Aug-22 | NA
Actual
2 | Review / Amendment/ Updating of Scheme - Ipaja New Town. | NTD/S-C/LCS/002/22 | LCS | Lumpsum | 35000000 | Prior | Plan | 2022-04-06 | 2022-04-13 | NA | 2022-04-13 | 2022-04-20 | 2022-04-20 | 2022-05-04 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-05-25 | 2022-01-06 | 2022-06-29 | 2022-06-30 | NA | 2022-07-07 | 2022-07-14 | 2022-08-11 | 2022-08-25 | 2022-09-08 | NA
80000000
Actual
3 | Review / Amendment/ Upgrade of Oko Oba I, II, III, Iv & Extension 1,2,3 | NTD/S-C/LCS/003/22 | LCS | Lumpsum | 25000000 | Prior | Plan | 2022-04-06 | 2022-04-13 | NA | 2022-04-13 | 2022-04-20 | 2022-04-20 | 2022-05-04 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-05-25 | 2022-01-06 | 2022-06-29 | 2022-06-30 | NA | 2022-07-07 | 2022-07-14 | 2022-08-11 | 2022-08-25 | 2022-09-08 | NA
Actual
4 | Review / Amendment/ Upgrade of Ilupeju Industrial Scheme | NTD/S-C/LCS/004/22 | LCS | Lumpsum | 20000000 | Prior | Plan | 2022-04-06 | 2022-04-13 | NA | 2022-04-13 | 2022-04-20 | 2022-04-20 | 2022-05-04 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-05-25 | 2022-01-06 | 2022-06-29 | 2022-06-30 | NA | 2022-07-07 | 2022-07-14 | 2022-08-11 | 2022-08-25 | 2022-09-08 | NA
Actual
5 | Provisional/Preliminary Survey Plan/Reconnaisance/Site Inspection and Acquisition of Data/Satelite Imagery in Government Schemes etc). | NTD/S-C/LCS/005/22 | LCS | Lumpsum | 10000000 | Post | Plan | 2022-03-02 | 2022-03-09 | NA | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-27 | 2022-05-04 | 11-May-22 | 18-May-22 | 25-May-22 | 1-Jun-22 | 29-Jun-22 | 30-Jun-22 | NA | 6-Jul-22 | 20-Jul-22 | 3-Aug-22 | 10-Aug-22 | 17-Aug-22 | NA
Actual
6 | Capacity Building Training/Workshop for NTDA Staff, Allen. | NTD/S-C/ICS/001/22 | ICS | Lumsum | 3750000 | Post | Plan | 2022-03-02 | 2022-03-09 | NA | 2022-03-23 | 2022-03-30 | 2022-04-06 | 2022-04-27 | 2022-05-04 | 11-May-22 | 18-May-22 | 25-May-22 | 1-Jun-22 | 29-Jun-22 | 30-Jun-22 | NA | 6-Jul-22 | 20-Jul-22 | 3-Aug-22 | 10-Aug-22 | 17-Aug-22 | NA
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: NEW TOWNS DEVELOPMENT AUTHORITY
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/ AGENCY: NEW TOWNS DEVELOPMENT AUTHORITY (NTDA)
BUDGET YEAR: Y2022
[9 empty] | Pre-or Post Qualification | Prior or Post review
S/N | Contract Description | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Maintenance and Servicing of NTDA Official Vehicles, Allen. | NTD/S-NC-F/NS/001/22 | NA | 24 | 15000000 | <N50M | NS | Plan | Post | Prior | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | Plan | 2022-04-27 | 2022-04-29 | NA | 2022-05-27 | 2022-06-24 | 2022-07-08 | 2022-07-15
[8 empty] | Actual | [9 empty] | Actual
2 | Payment of Clearing and Beautification of Office Lawns | NTD/S-NC-F/DC/001/22 | NA | 12 | 360000 | <N10M | DC | Plan | Post | Post | 2022-02-17 | NA | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | NA | Plan | 2022-03-16 | 2022-03-18 | NA | 2022-04-15 | NA | AA | AA
[8 empty] | Actual | [9 empty] | Actual
3 | Maintenance of Computers and Servers at NTDA, Allen | NTD/S-NC-F/NS/002/22 | NA | 9 | 800000 | <N10M | NS | Plan | Post | Post | 2022-02-17 | NA | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | NA | Plan | 2022-03-16 | 2022-03-18 | NA | 2022-04-15 | NA | AA | AA
[8 empty] | Actual | [9 empty] | Actual
4 | Maintenance of Printers/Photocopiers at NTDA, Allen. | NTD/S-NC-F/NS/003/22 | NA | 12 | 1000000 | <N10M | NS | Plan | Post | Post | 2022-02-17 | NA | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | NA | Plan | 2022-03-16 | 2022-03-18 | NA | 2022-04-15 | NA | AA | AA
Actual
5 | Organization of Retreat for Directors/Management Staff (Subvention & Dedicated) | NTD/S-NC/NS/004/22 | NA | 25 | 41000000 | <N50M | NS | Plan | Post | Prior | 2022-08-03 | 10-Aug-22 | 17-Aug-22 | 2022-08-31 | 2022-09-07 | 2022-09-14 | 2022-09-21 | Plan | 2022-10-19 | 2022-10-21 | NA | 2022-11-18 | 2022-12-23 | 2022-01-17 | 2022-01-24
[8 empty] | Actual | [9 empty] | Actual
6 | Removal/Site Clearance of Schemes and Shanties (Site Selection - Dedicated) | NTD/S-NC/NCB/001/22 | NA | 1 | 68000000 | <N100M | NCB | Plan | Post | Prior | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 | 2022-03-30 | Plan | 2022-04-27 | 2022-04-29 | NA | 2022-05-27 | 2022-06-24 | 2022-07-08 | 2022-07-15
[8 empty] | Actual | [9 empty] | Actual
7 | Maintenance/Repair of Office Plant & Machine (Generators) at NTDA (Subvention & Dedicated) | NTD/S-NC-F/NS/005/22 | NA | 2 | 6200000 | <N10M | NS | Plan | Post | Post | 2022-02-17 | NA | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | NA | Plan | 2022-03-16 | 2022-03-18 | NA | 2022-04-15 | NA | AA | AA
[8 empty] | Actual | [9 empty] | Actual
8 | Servicing of Project Inspection Tour (Dedicated) | NTD/S-NC-F/NS/006/22 | NA | 48 | 24,000,000.00 | <N50M | NS | Plan | Post | Post | 2022-02-17 | 2022-02-24 | 2022-02-24 | 2022-03-03 | 2022-03-09 | 2022-03-16 | 2022-03-23 | Plan | 2022-03-30 | 2022-04-01 | NA | 2022-04-15 | NA | AA | AA
[8 empty] | Actual | [9 empty] | Actual
9 | Servicing/Expenses for Routine Meetings (Special Duties - Dedicated) | NTD/S-NC-F/NS/007/22 | NA | 12 | 4,000,000.00 | <N10M | NS | Plan | Post | Post | 2022-02-17 | NA | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-09 | NA | Plan | 2022-03-16 | 2022-03-18 | NA | 2022-04-01 | NA | AA | AA
Actual
10 | Public Relations Expenses (Running expenses/Public Enlightenments/Press Briefing/Allowances/Newspapers/Advert & Publicity etc - Subvention & Dedicated) | NTD/S-NC-F/NS/008/22 | NA |  | 7,300,000.00 | <N10M | NS | Plan | Post | Post | 2022-02-17 | NA | 2022-02-17 | 2022-02-24 | 2022-03-03 | 2022-03-09 | NA | Plan | 2022-03-16 | 2022-03-18 | NA | 2022-04-01 | NA | AA | AA
[8 empty] | Actual | [9 empty] | Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: NEW TOWNS DEVELOPMENT AUTHORITY
BUDGET YEAR: Y2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Fuel (Petro) for 32 NTDA Official/Site Vehicles. | NTD/G-F/NS/001/22 | NA | 32 | 17343450 | <N50M | NS | Post | Prior | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-04-05 | 2022-04-07 | NA | 2022-04-07 | 2022-04-12 | NA | 2022-12-31 | 2022-12-31
Actual
2 | Procurement of Stationery Items at NTDA, Headquarters, Allen. | NTD/G-F/NS/002/22 | NA | Various | 5450000 | < N10M | NS | Post | Post | Plan | 2022-01-25 | NA | 2022-02-01 | 2022-02-15 | 2022-02-22 | NA | 2022-03-22 | 2022-03-24 | NA | 2022-03-24 | 2022-03-29 | NA | 2022-12-31 | 2022-12-31
Actual
3 | Procurement of Toileteries/Cleaning Materials for Office Use, Allen. | NTD/G-F/NS/003/22 | NA | Various | 1697000 | < N10M | NS | Post | Post | Plan | 2022-01-25 | NA | 2022-02-01 | 2022-02-15 | 2022-02-22 | NA | 2022-03-08 | 2022-03-10 | NA | 2022-03-11 | 2022-03-18 | NA | 2022-12-31 | 2022-12-31
Actual
4 | Procurement of Computer Consumables | NTD/G/NS/004/22 | NA | Various | 1500000 | < N10M | NS | Post | Post | Plan | 2022-02-08 | NA | 2022-02-15 | 2022-02-22 | 2022-03-01 | NA | 2022-03-29 | 2022-03-31 | NA | 2022-04-05 | 2022-04-12 | NA | 2022-05-24 | 2022-05-31
Actual
5 | Procurement of Diesel for 2 Office Generators, Allen (Subvention & Dedicated) | NTD/G-F/NS/005/22 | NA | 2 | 3900000 | < N10M | NS | Post | Post | Plan | 2022-01-25 | NA | 2022-02-01 | 2022-02-15 | 2022-02-22 | NA | 2022-03-08 | 2022-03-10 | NA | 2022-03-11 | 2022-03-18 | NA | 2021-12-31 | 2021-12-31
Actual
6 | Procurement of Generator Parts and Consumables (Subvention & Dedicated) | NTD/G/NS/006/22 | NA | Various | 2400000 | < N10M | NS | Post | Post | Plan | 2022-02-08 | NA | 2022-02-15 | 2022-02-22 | 2022-03-01 | NA | 2022-03-29 | 2022-03-31 | NA | 2022-04-05 | 2022-04-12 | NA | 2022-05-24 | 2022-05-31
Actual
7 | Provision of Birthday Gifts for NTDA Staff Welfare, Allen (Dedicated) | NTD/G/NS/007/22 | NA | Various | 7750000 | < N10M | NS | Post | Post | Plan | 2022-02-01 | NA | 2022-02-15 | 2022-02-22 | 2022-03-01 | NA | 2022-03-15 | 2022-03-17 | NA | 2022-03-17 | 2022-03-24 | NA | 2022-04-28 | 2022-05-05
Actual
8 | Procurement of Drugs/Medical Utensils to the NTDA Staff Clinic, Allen (Subvention & Dedicated) | NTD/G/NS/008/22 | NA | Various | 10850000 | < N50M | NS | Post | Prior | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-03-17 | NA | 2022-03-17 | 2022-03-24 | NA | 2022-04-28 | 2022-05-05
Actual
9 | Procurement of Uniforms for NTDA Drivers/Cleaners/Security/Gardeners/PPE for Field Officers, Allen (Subvention & Dedicated) | NTD/G/NS/009/22 | NA | Various | 7665000 | < N10M | NS | Post | Post | Plan | 2022-06-01 | NA | 2022-06-08 | 2022-06-22 | 2022-06-29 | NA | 2022-07-27 | 2022-07-29 | NA | 2022-08-03 | 2022-08-10 | NA | 2022-10-05 | 2022-10-19
Actual
10 | Procurement of Toners and Ink Cartridges, NTDA Headquarters, Allen. | NTD/G/NS/010/22 | NA | Various | 800000 | < N10M | NS | Post | Post | Plan | 2022-02-08 | NA | 2022-02-15 | 2022-02-22 | 2022-03-01 | NA | 2022-03-29 | 2022-03-31 | NA | 2022-04-05 | 2022-04-12 | NA | 2022-05-24 | 2022-05-31
Actual
11 | Procurement of Electrical/Mechanical fittings/Aluminium Door Locks and others for the maintenance of NTDA Staff Quarters. | NTD/G/NS/011/22 | NA | Various | 2020000 | < N10M | NS | Post | Post | Plan | 2022-07-06 | NA | 2022-07-13 | 2022-07-20 | 2022-07-27 | NA | 2022-08-03 | 2022-08-05 | NA | 2022-08-05 | 2022-08-12 | NA | 2022-09-16 | 2022-09-23
Actual
12 | Procurement of Various Office Furniture & Fittings | NTD/G/NS/012/22 | NA | Various | 45000000 | < N50M | NS | Post | Prior | Plan | 2022-06-01 | 2022-06-08 | 2022-06-08 | 2022-06-22 | 2022-06-29 | 2022-07-06 | 2022-07-27 | 2022-07-29 | NA | 2022-08-03 | 2022-08-10 | NA | 2022-10-05 | 2022-10-19
Actual
13 | Procurement of Various Engineering/Survey Equipment | NTD/G/NS/013/22 | NA | Various | 5000000 | < N10M | NS | Post | Post | Plan | 2022-02-08 | NA | 2022-02-15 | 2022-02-22 | 2022-03-01 | NA | 2022-03-29 | 2022-03-31 | NA | 2022-04-05 | 2022-04-12 | NA | 2022-05-24 | 2022-05-31
Actual
14 | Procurement of Monitoring and Development Control Tools | NTD/G/NS/014/22 | NA | Various | 9000000 | <N10M | NS | Post | Post | Plan | 2022-07-06 | NA | 2022-07-20 | 2022-08-03 | 2022-08-10 | NA | 2022-09-14 | 2022-09-16 | NA | 2022-09-23 | 2022-09-30 | 2022-10-28 | 2022-11-11 | 2022-11-18
Actual
15 | Procurement of Working Tools for NTDA ICT Unit,Allen (Dedicated) | NTD/G/NS/015/22 | NA | Various | 1000000 | <N10M | NS | Post | Post | Plan | 2022-02-08 | NA | 2022-02-15 | 2022-02-22 | 2022-03-01 | NA | 2022-03-29 | 2022-03-31 | NA | 2022-04-05 | 2022-04-12 | 2022-05-10 | 2022-05-24 | 2022-05-31
Actual
16 | Procurement of Personal Protectictive Equipment for NTDA Monitoring Team, Allen (Site Selection - Dedicated) | NTD/G/NS/016/22 | NA | Various | 18000000 | <N50M | NS | Post | Prior | Plan | 2022-07-06 | 2022-07-13 | 2022-07-20 | 2022-08-03 | 2022-08-10 | 2022-08-17 | 2022-09-14 | 2022-09-16 | NA | 2022-09-23 | 2022-09-30 | 2022-10-28 | 2022-11-11 | 2022-11-18
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: NEW TOWNS DEVELOPMENT AUTHORITY (NTDA)
BUDGET YEAR: Y2022
| CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
S/N | Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of NTDA Zonal Office, Lekki Phase II. | NTD/W/NCB/001/22 | NA | 85000000 | <N100M | NCB | BOQ | Post | Plan | Prior | 2022-02-03 | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-15 | 2022-05-13 | 2022-09-09 | 2022-09-23
Actual
2 | Construction of Road 6, Near Laura Stephen, Lekki Phase II. | NTD/W/NCB/002/22 | NA | 297531635.91 | <N500M | NCB | BOQ | Post | Plan | Prior | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-13 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
3 | Completion of Electrical Infrastructure Development/Connection to National Grid via 33kv line, Lekki II. | NTD/W/NCB/003/22 | NA | 552504346.96 | >N500M | NCB | BOQ | Post | Plan | Prior | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-13 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
4 | Construction of Conner Road, Block 10A, Lekki Scheme II. | NTD/W/NCB/004/22 | NA | 55235291.03 | <N100M | NCB | BOQ | Post | Plan | Prior | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-06-15 | 2022-06-17 | NA | 2022-06-17 | 2022-06-24 | 2022-07-22 | 2022-11-18 | 2022-12-30
Actual
5 | Construction of Fola Osibo, Off Freedom Road, Lekki I. | NTD/W/NCB/005/22 | NA | 118970500 | <N500M | NCB | BOQ | Post | Plan | Prior | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-29 | 2022-03-31 | 1-Apr-2022 | NA | 2022-04-12 | 2022-05-10 | 2022-05-24 | 2022-05-31 | 2022-12-13
Actual
6 | Construction of Esther Adeleke Lekki Scheme I | NTD/W/NCB/006/22 | NA | 580688577.12 | >N500M | NCB | BOQ | Post | Plan | Prior | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-06-15 | 2022-06-17 | NA | 2022-06-17 | 2022-06-24 | 2022-07-22 | 2022-11-18 | 2022-12-30
Actual
7 | Desilting of Drains within NTDA Schemes | NTD/W/NS/001/22 | NA | 20000000 | <50M | NS | BOQ | Post | Plan | Prior | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
8 | Rehabilitation of NTDA Staff Quarters (Block 67 & 68) | NTD/W/NS/002/22 | NA | 31000000 | <50M | NS | BOQ | Post | Plan | Prior | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
9 | General Repair (Maintenance) of NTDA Office Building, Allen | NTD/W-F/NS/003/22 | NA | 1000000 | <N10M | NS | BOQ | Post | Plan | Post | 2022-02-10 | NA | 2022-02-24 | 2022-03-02 | 2022-03-09 | NA | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
10 | Structural Cabling and Networking of the New Towns Development Authority Digital Building, Allen. | NTD/W/NS/004/22 | NA | 10000000 | <N10M | NS | BOQ | Post | Plan | Post | 2022-02-10 | NA | 2022-02-24 | 2022-03-02 | 2022-03-09 | NA | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
11 | Upgrading of Office Buiding at the 3 Zonal Offices | NTD/W/NS/005/22 | NA | 1500000 | <10M | NS | BOQ | Post | Plan | Post | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-04 | 2022-05-11 | NA | 2022-06-15 | 2022-06-17 | NA | 2022-06-17 | 2022-06-24 | 2022-07-22 | 2022-11-18 | 2022-12-02
Actual
12 | Construction of Canaan Land, Lekki I | NTD/W/NCB/007/22 | NA | 76150430.58 | <100M | NCB | BOQ | Post | Plan | Prior | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
13 | Construction of Oyibo Adjara, Lekki I | NTD/W/NS/006/22 | NA | 41326935.06 | <50M | NS | BOQ | Post | Plan | Prior | 2022-02-10 | 2022-02-17 | 2022-02-24 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-04-06 | 2022-04-08 | NA | 2022-04-08 | 2022-04-22 | 2022-05-20 | 2022-06-17 | 2022-07-01
Actual
14 | Completion of ROAD 31 (Abayomi Shouga) PART OF and Adebisi Ladejobi, Lekki scheme I. | NTD/W/NCB/008/22 | NA | 89628468.4 | <100M | NCB | BOQ | Post | Plan | Prior | 2022-04-06 | 2022-04-13 | 2022-04-20 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-06-15 | 2022-06-17 | NA | 2022-06-17 | 2022-06-24 | 2022-07-22 | 2022-11-18 | 2022-12-30
Actual

## Sheet4
NEW TOWNS DEVELOPMENT AUTHORITY
YEAR 2022 PROCUREMENT PLAN
COMMITTEE MEMBERS
|  | 1 | ____________________________________
Tpl. O.J. Aboyeji
General Manager
2 | ____________________________________ | 3 | _________________________________ | 4 | ___________________________
| Engr. W.A. Johnson |  | Mrs. T. Noibi |  | Olufunmilayo Adeniran
| HOD, Engineering Services |  | HOD, Admin & HR/Board Secretary |  | HOD, Finance & Accounts
5 | ____________________________________ | 6 | ____________________________ | 7 | ___________________________
| Tpl. E. O. Orebiyi |  | Mrs. A.O. Odeyemi |  | Mrs. Daley-Oladele Senami
| HOD, Town Planning Services |  | Head, Legal Unit |  | Head, Internal Audit
8 | ____________________________________ | 9 | ____________________________ | 10 | ___________________________
| Engr. (Mrs) M.B. Akinyele |  | Mr. S.M. Salami |  | Mrs. W.A. Abe
| Head, ICT Unit |  | Head, Planning Unit |  | Head, Public Affairs Unit
11 | ____________________________________ | 12 | ____________________________ | 13
| Mr. Popoola Okesanya |  | Surv. Kofolapamo Johnson |  | Tpl. Olalekan Yusuf
| Head, Estate Unit |  | Head, Survey Unit |  | Head, DCMU
14 | ____________________________
Mr. Wole Olusesi
Head, Procurement Unit/Secretary