## GOODS
PROCUREMENT PLAN FOR GOODS
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BIDS EVALUATION (DATES) |  |  | CONTRACT FINALIZATION (DATES)
Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan/Actual | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance | Plan | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Complete Delivery/Istall | Inspection and Final Acceptance
|  |  |  | 0 | 0 |  |  |  |  | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks | Actual | 0 | 4-6 wks | 2-4 wks | 4wks | 4wks
PROCUREMENT OF TEXTBOOKS FOR SECONDARY SCHOOLS (E-LEARNING DEVICE) | MoE/G/NCB/01/22 |  |  |  |  | NCB | PRE | PRIOR | Plan | 07/03/22 | 14/03/22 | 28/03/22 | 18/04/22 | 03/05/22 | 09/05/22 | Plan |  | 16/05/22 | 23/05/22
|  |  |  | 1700000000 |  |  |  |  | Actual | [6 empty] | Actual
PROCUREMENT OF AUDIO VISUAL EQUIPMENT | MoE/G/NS/01/22 |  |  | 50000000 | <50M | NS | POST | PRIOR | Plan | 09/05/22 | 18/05/22 | 22/05/22 | 12/06/22 | 26/06/22 | 03/07/22 | Plan |  | 17/07/22 | 24/07/22
Actual
Actual
PROCUREMENT OF COMPUTERS HARDWARE | MoE/G/NCB/02/22 |  |  | 2103295807 | <10M | NCB | PRE | POST | Plan | 09/05/22 | 18/05/22 | 22/05/22 | 12/06/22 | 26/06/22 | 03/07/22 |  |  | 25/07/22 | 01/08/22
Actual
CONSUMPTION OF FUEL FOR OPERATIONAL BUSES | MoE/G-F/NS/01/22 |  |  | 8180181 | <10M | NS | POST | POST | Plan | 03/04/22 | N/A | 10/04/22 | 17/04/22 | 24/04/22 | 02/05/22 | Plan |  | 10/05/22 | 17/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT OF STATIONERIES | MoE/G-F/NS/02/22 |  |  | 11614173 | <50M | NS | POST | PRIOR | Plan | 03/04/22 | 20/03/22 | 17/04/22 | 2/05/22 | NA | 08/05/22 | Plan |  | 10/05/21 | 17/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT & SUPPLY OF TEXTBOOKS TO PUBLIC SCHOOLS/E LEARNING DEVICE | MoE/G/ICB/01/22 |  |  | 1700000000 | >1B | ICB | PRIOR | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT OF PERISHABLE ITEMS AND MATERIALS FOR SCIENCE PRACTICALS | MoE/G/NCB/03/22 |  |  | 80000000 | <500M | NCB | PRIOR | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT AND ESTABLISHMENT OF RADIO STATION EQUIPMENT FOR EDUCATION TESOURCE CENTRE | MoE/G/NCB/04/22 |  |  | 250,000,000.00 | <50M | NCB | PRE | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT OF FURNITURE FOR SECONDARY SCHOOLS/TEACHERS/PRINCIPALS. | MoE/G/ICB/02/22 |  |  | 2,061,032.196.00 | >N1B | ICB | PRIOR | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PRINTING OF COPIES OF LAGOSSTATE EDUCATION POLICY, ANNUAL SCHOOL CENSUS REPORT, ANNUAL EDUCATION SECTOR PERFORMANCE REPORT & PRINTING OF 6,000TRANSFER FORMS | MoE/G-F/NS/03/22 |  |  | 10891000 | <50M | NS | PRIOR | PRIOR | Plan | 2022-03-27 | 2022-03-27 | 2022-07-14 | 2022-04-24 | N/A | 08/05/22 | Plan |  | 2022-05-15 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PRINTING OF EARLY CHILD CARE EDUCATION SCHEME OF WORK | MoE/G/NS/02/22 |  |  | 40,828,650.00 | <50M | NS | POST | PRIOR | Plan | 2022-03-27 | 2022-03-27 | 2022-04-17 | 2022-04-24 | 02/05/22 | 08/05/22 | Plan |  | 2022-05-15 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
[9 empty] | Actual | [6 empty] | Actual
PRINTING OF COPIES OF CONTINOUS ASSESSMENT SCORES FOR SS1 (PUBLICATION AND DOCUMENTATION OF STATUTORY RECORDS) (GOODS) | MoE/G/NS/03/22 | SS | Lump Sum | 30837080 | <50M | NS | POST | PRIOR | Plan | 2022-03-27 | 2022-03-27 | 2022-07-14 | 2022-04-24 | 02/05/22 | 08/05/22 | Plan |  | 2022-05-15 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT OF COMPUTER CONSUMABLES | MoE/G/NS/04/22 |  |  | 8,000,000.00 | <50M | NS | PRIOR | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
POLICIES AND PROGRAMME STUDIES | MoE/G/NS/05/22 |  |  | 40828650 | <50M | NS | POST | PRIOR | Plan | 2022-03-27 | 2022-03-27 | 2022-04-17 | 2022-04-24 | 02/05/22 | 08/05/22 | Plan |  | 2022-05-15 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
UNIFORM AND PROTECTIVE OUTFIT | MoE/G/NS/06/22 |  |  | 9613000 | <10M | NS | POST | POST | Plan | 2022-03-27 | 2022-03-27 | 2022-04-17 | 2022-04-24 | 02/05/22 | 08/05/22 | Plan |  | 2022-05-15 | 22/05/22
Actual
PROCUREMENT OF REFERENCE BOOKS FOR SCHOOL LIBARIES | MoE/G/NS/07/22 |  |  | 500000 | >1OM | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
REPAIR OF STUDENTS FURNITURES IUN EACH DISTRICT | MoE/G/NS/08/22 |  |  | 32669670 | <50M | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT OF SMART TELEVISIONS FOR ALL COLLEGES IN THE STATE | MoE/G/NCB/05/22 |  |  | 177500000 | <50M | NCB | PRE | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT AND INSTALLATION OF 10 NUMBERS CCTV CAMERA IN ALL MODEL COLLEGES | MoE/G/NCB/6/22 |  |  | 90000000 | <50M | NCB | PRE | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
MOTOR VEHICLE FUEL CONSUMPTION | MoE/G/NS/08/22 |  |  | 8180181 | >1OM | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
LIBRARY SERVICE | MoE/G/NS/09/22 |  |  | 74000 | >1OM | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
Actual
BOOKS | MoE/G/NS/10/22 |  |  | 500000 | >1OM | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
Actual
PUBLICATION AND DOCUMENTATION OF STATUTORY RECORDS | MoE/G/NS/11/22 |  |  | 30837080 | <50M | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
MANAGEMENT INFORMATION SYSTEM | MoE/G/NS/12/22 |  |  | 8000000 | >1OM | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
APTITUDE TEST | MoE/G/NS/09/22 |  |  | 17480060 | >1OM | NS | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
EDUCATION RESOURCE CENTRE | MoE/NCS/NS/02/22 |  |  | 20001558 | <50M | NS | POST | PRIOR | Plan | 2022-03-27 | 2022-03-27 | 2022-04-17 | 2022-04-24 | 02/05/22 | 08/05/22 | Plan |  | 2022-05-15 | 22/05/22

## Sheet1
| PROCUREMENT OF OFFICE EQUIPMENT FOR OUTSTATION OFFICERS | MoE/G/NS/04/22 |  |  | 15,000,000.00 | <50M | NS | PRIOR | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[10 empty] | Actual | [6 empty] | Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
PROCUREMENT OF EQUIPMENT TO ENHANCE ERC OPERATIONS | MoE/G/NS/03/22 |  |  | 50000000 | <50M | NS | POST | PRIOR | Plan | 03/04/22 | N/A | 17/04/22 | 24/04/22 | 2/05/22 | 2/05/22 | Plan |  | 10/05/22 | 17/05/22
[9 empty] | Actual | [6 empty] | Actual
PROCUREMENT OF SCIENCE MATERIALS FOR THE SENIOR SECONDARY SCHOOLS CERTIFICATE EXAMINATION | MoE/G/ICB/05/22 |  |  | 833786082.47 | >50M<1B | ICB | POST | PRIOR | Plan | 06/03/22 | 20/03/22 | 27/03/22 | 17/04/22 | 01/05/22 | 08/05/22 | Plan |  | 15/05/22 | 22/05/22
[9 empty] | Actual | [6 empty] | Actual
Multi-Lingual Centers | MoE/W/NS/05/21 |  | 12259144 |  | <50M | NS | Lumpsum | Post |  | PRIOR | 17/02/21 | 24/02/21 | 27/02/21 | 06/03/21 | 13/03/21 | 27/03/21 | Plan |  | 17/04/21 | 2021-05-01
Actual
6 | Exibition and Trade Fair | MoE/W/NS/06/21 |  | 50000 |  | <50M | NS | Lumpsum | Post |  | PRIOR | 17/02/21 | 24/02/21 | 27/02/21 | 06/03/21 | 13/03/21 | 27/03/21 | Plan |  | 17/04/21 | 2021-05-01
Actual
Maintainance of Office Building
| MoE/W-NC/NS/02/22 |  | 1819221 |  | <50M | NS | Lumpsum | POST |  | POST | 6/03/22 | 13/03/22 | 20/03/22 | 3/04/22 | 10/04/22 | 17/04/22 | Plan |  | 24/04/22 | 2022-05-01

## WORKS
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  | Plan vs. Actual | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Avail | Source of Funding | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qual |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance |  | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[11 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks |  | 0 | 4-6 wks | 2-4 wks
Construction/Rehabilitation of Schools | MoE/W/NCB/02/2020 |  | 7800175210 |  | <1B | ICB | BOQ | Post | Plan |  | 17/04/2020 | 2/05/2020 | 16/05/2020 | 30/05/2020 | 13/06/2020 | 27/06/2020 | Plan |  | 25/07/2020 | 2020-08-01
[9 empty] | Actual | [7 empty] | Actual
Installation/ Rehabilitation of Science Laboratories in Senior Secondary Schools | MoE/W/NCB/03/2020 | 1 | 519998612 |  | >100M | NCB | BOQ | Post | Plan | NA | 6/3/2020 | 13/3/2020 | 20/3/2020 | 3/4/2020 | 10/4/2020 | 17/4/2020 | Plan |  | 24/4/2020 | 2020-05-01
Actual
Actual
Renovation of 20 Nos Classroom blocks | MoE/W/NCB/04/2020 | 1 | 360,000,000.00 |  | >100M | NS | BOQ | Post | Plan |  | 6/3/2020 | 13/3/2020 | 20/3/2020 | 3/4/2020 | 10/4/2020 | 17/4/2020 | Plan |  | 17/4/2020 | 2020-05-01
[9 empty] | Actual | [7 empty] | Actual
Facility Management / Maintainance of School Structure | MoE/W-ncs/NS/02/2020 |  | 144657574 |  | >100M | NSC/NS | Lumpsum | Post | Plan |  | 6/3/2020 | 13/3/2020 | 20/0/2020 | 3/4/2020 | 10/4/2020 | 17/0/2020 | Plan |  | 24/0/2020 | 2020-01-05
[9 empty] | Actual | [7 empty] | Actual
Rehabilitation of Offices | MoE/W/NCB/04/2020 | 1 | 80000000 |  | >50M | NS | BOQ | Post | Plan | NA | 17/2/2022 | 24/2/2022 | 27/2/2022 | 06/3/2022 | 13/3/2020 | 27/0/2020 | Plan |  | 17/4/2020 | 2020-05-01
[9 empty] | Actual | [7 empty] | Actual
Rehabilitation of staff Quarters for the Teacher in Model Colleges at Badore and Kankon. | MoE/W/NS/04/2020 | 2 | 50,000,000.00 |  | <50M | NS | BOQ | Post | Plan |  | 6/3/22 | 13/3/2020 | 20/3/2020 | 3/4/20 | 10/4/2020 | 17/4/2020 | Plan |  | 24/4/2020 | 2020-05-01
[9 empty] | Actual | [7 empty] | Actual

## PRO
PROCUREMENT PLAN FOR PROGRAMMES
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
S/N | DESCRIPTION OF ITEMS | PACKAGE NUMBER | DURATION | PLAN & ACTUAL | TOTAL COST
1 | YOUTH PROGRAMME | PPA/P/NM/01/22 |  | Plan | 110369654
Actual
.
2 | ARTS AND FESTIVAL | PPA/P/NM/02/22 |  | Plan | 5000000
Actual
3 | APTITUDE TEST | PPA/P/NM/03/22 |  | Plan | 17480060
Actual
|  |  |  | Plan | 13,500,000.00
4 | QUIZ COMPETION | PPA/P/NM/05/22 |  | Actual
5 | FESTIVAL OF INSTRUCTIONAL MATERIAL LOCALLY PRODUCED |  |  | Plan | 2100000
|  | PPA/P/NM/06/22 |  | Actual
6 | EDUCATION SUMMIT | PPA/P/NM/08/22 |  | Plan | 45000000
Actual

## TRAINING
PROCURMENT PLAN FOR TRAINING
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR:2022
TRAINING CALENDER
S/N | Department | Description of Training & Venue | Participants | Designation | Plan vs Actual | Duration | Tuition Fee | Transport Fare | Allowance/Estacode | Visa Fee | Total Cost
1 | ADMIN&HUMAN RESOURCES | LEADERSHIP & CAREER DEVELOPMENT SKILLS | 5 OFFICERS | PS/DIRECTORS | Plan | 5 DAYS | 375000 | 52000 | 1149500 |  | 1576500
Actual
2 | ADMIN&HUMAN RESOURCES | LEADERSHIP AND STRATEGIC MANAGEMENT SKILLS (ASCON) | 5 OFFICERS | D DIRECTORS | Plan | 5 DAYS | 450000 | 30000 | 30000 |  | 510000
Actual
3 | ADMIN&HUMAN RESOURCES | PRODUCTIVITY MGT | 4 OFFICERS | ASST. DIRECTORS | Plan | 5DAYS | 750000 | 50000 | 50000 |  | 850000
Actual
4 | HR & ADMIN | ADVANCE HUMAN RESOURCES & INDUSTRIAL RELATIONS IN THE PUBLIC SERVICES SECTOR | 15 OFFICERS | CHIEF ADMIN OFFICERS | Plan | 5DAYS | 390000 | 60000 | 30000 |  | 480000
Actual
5 | HR & ADMIN | CHANGE MGT ATTITUDINAL CHANGE &INTERPERSONAL BEHAVIOUR IN ORGANIZATION | 10 OFFICERS | ASST. CHIEF ADMIN OFFICERS | Plan | 5DAYS | 375000 | 52000 | 1249500 |  | 1676500
Actual
6 | HR & ADMIN | EFFECTIVE GENERAL SAFETY MANAGEMENT IN WORK PLACE | 10 OFFICERS | ASST. CHIEF ADMIN OFFICERS | Plan | 5DAYS | 375000 | 50000 | 1190000 |  | 1615000
Actual
7 | HR & ADMIN | CHALLENGING ROLE OF ADMINSTRATIVE PROFESSIOALS (IBRM) | 5 OFFICERS
|  |  |  | CHIEF ADMIN OFFICERS | Plan | 4DAYS | 300000 | 40000 | 952000 |  | 1292000
Actual
8 | HR & ADMIN | SPEECH MAKING AND REPORT WRITING FOR PERSONAL ASSITANTS & SPEECH | 15 OFFICERS | GL08-09 OFFICER | Plan | 4DAYS | 1050000 | 60000 | 22500
Actual
9 | PROCUREMENT | PROCUREMENT AND MATERIALS MANAGEMENT(ASCON) | 2 OFFICERS | ASST. DIRECTORS | Plan | 5DAYS | 150000 | 10000 | 230000 |  | 323000
Actual
10 | HR & ADMIN | RECORD MANAGEMENT & RECORD TRACKING FOR OFFICERS (IBRM) | 10 OFFICERS | GL 07 | Plan | 4DAYS | 700000 | 40000 | 15000
Actual
11 | HR & ADMIN | WORKSHOP ON DOCUMENT & OFFICE SECURITY MANAGEMENT | 10 OFFICERS | GL04-07 | Plan | 5DAYS | 200000 | 22500 | 12500 |  | 235000
Actual
12 | ICT | MANAGEMENT INFORMATION SYSTEM | 15 OFFICER | GL08-09 | Plan | 2DAYS | 800000 | 40000 | 30000 |  | 870000
Actual
13 | PPRS | CHALLENGES OF POLICY IMPLEMENTATION IN THE PUBLIC SERVICE | 1 OFFICER | GL12 | Plan | 4DAYS | 70000 | 6000 | 2500 |  | 78500
Actual
14 | PPRS | PROCESS PLANNING & TIMING FOR PEAK PERFORMANCE (ACDMC) | 10 OFFICER | GL14 | Plan | 5DAYS | 800000 | 125000 | 50000 |  | 975000
Actual
| ADMIN &HR | PRODUCTIVITY IMPROVEMENT WORKSHOP FOR LOWER CADRE STAFF (LATERAL TECHNIQUES) | 20 OFFICERS | GL01-06 | Plan | 5DAYS | 800000 | 28000 | 20000 |  | 848000
Actual
PLAN TOTAL

## NPI
PROCUREMENT PLAN FOR NON PROCURERABLE ITEMS
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
S/N+A4:F33B26A4:F22A4:GA4:F67+A4:F22 | DESCRIPTION OF ITEMS | PACKAGE NO | DURATION | PLAN & ACTUAL | TOTAL COST
1 | SPECIALIZED SCHOOL EXPENSES | PPA/NP/NM/01/22 |  | Plan | 45000000
Actual
2 | GRANT,CONTRIBUTION,AND SOCIETIES | PPA/NP/NM/02/22 |  | Plan | 4,550,000.00-
Actual
3
Actual
4 | AWARD AND REWARD | PPA/NP/NM/07/22 |  | Plan | 30000000
Actual
5 | TRAVEL AND TRANSPORT-LOCAL | PPA/NP/NM/08/22 |  | Plan | 11635186
Actual
| SPONSORHIP EXPENSES | PPA/NP/NM/28/22 |  | Plan | 500000
Actual
6 | State Contribution To Community Projects to Odo-AYandelu in Epe | PPA/NP/NM/09/22 |  | Plan | 20000000
Actual
7 | Honorarium for External Consultant (RESEARCH AND DEVELOPMENT) | PPA/NP/NM/10/22 |  | Plan | 1371143
Actual
8 | INCLUSIVE UNIT SCHOOLS | PPA/NP/NM/10/22 |  | Plan | 21500000
Actual
9 | EDUCATION DATA BANK EXPENSES | PPA/NP/NM/12/22 |  | Plan | 25957387
Actual
10 | MULTILINGUAL AGENCIES | PPA/NP/NM/13/22 |  | Plan | 15259144
Actual
11 | SPECIAL DUTIES EXPENSES | PPA/NP/NM/14/22 |  | Plan | 101006484
Actual
12 | WAEC DATA CAPTURING | PPA/NP/NM/15/22 |  | Plan | 13915000
Actual
| EXAMINATION EXPENSES | PPA/NP/NM/16/22 |  | Plan | 1487272991
13
Actual
14 | UP KEEP AND MAINTAINANCE OF BOARDING FACILITIES IN LAGOS STATE | PPA/NP/NM/17/22 |  | Plan | 1000000000
Actual
15 | EDUCATION SUMMIT | PPA/NP/NM/03/22 |  | Plan | 45000000
Actual
16 | MEETING EXPENSES | PPA/NP/NM/04/22 |  | Plan | 15000000
Actual
17 | FIRST TERM TEST | PPA/NP/NM/05/22 |  | Plan | 34370000
Actual
18 | SECOND TERM TEST | PPA/NP/NM/18/22 |  | Plan | 218000000
Actual
19 | 3RD TERM/MOCK/PROMOTION | PPA/NP/NM/19/22 |  | Plan | 153397044
Actual
20 | WAEC (51,653 CANDIDATES) | PPA/NP/NM/20/22 |  | Plan | 783277702
Actual
21 | PLACEMENT TEST | PPA/NP/NM/21/22 |  | Plan | 36405020
Actual
22 | WAEC STATE COMMITTEE MEETINGS | PPA/NP/NM/22/22 |  | Plan | 250000
Actual
23 | AUDIO VISUAL | PPA/NP/NM/23/22 |  | Plan | 4000000
Actual
24 | GENERAL UTILITY SERVICES | PPA/NP/NM/24/22 |  | Plan | 6604020
Actual
25 | MISCELLANEOUS | PPA/NP/NM/25/22 |  | Plan | 2912041
Actual
26 | PUBLICITY AND PRESS COVERAGE | PPA/NP/NM/26/22 |  | Plan | 10891000
Actual
27 | RESEARCH AND DEVELOPMENT | PPA/NP/NM/27/22 |  | Plan | 1371143
Actual

## CONWKS
PROCUREMENT PLAN FOR CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
S/N | Description of Workshop/Conference | Package Number | Objective of Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | CHARTERED INSTITUTE OF PERSONNEL MANAGEMENT (CIPM) | MoE/S-WTC/01/21 |  | 9 OFFICERS | 4DAYS | Plan | ABUJA/JOS | 690000 | 756,000.00 | 1,548,000.00
2 | [5 empty] | Actual
3 | CSN | MoE/S-WTC/02/21 |  | 2 OFFICERS | 4DAYS | Plan | P/HARCOURT | 140000 | 130000 | 384000
Actual
4 | ICAN | MoE/S-WTC/03/21 |  | 1 OFFICER | 4DAYS | Plan | ABUJA | 110,000.00 | 65,000.00 | 192,000.00
Actual
5 | STAN | MoE/S-WTC/04/21 |  | 1 OFFICER | 4DAYS | Plan | ADO-EKITI | 70000 | 65000 | 192000
Actual
6 | CIPSMN/CIPS | MoE/S-WTC/05/21 |  | 2 OFFICER | 4DAYS | Plan | ABUJA | 246000 | 193000 | 476000
Actual
7 | NIM | MoE/S-WTC/06/21 |  | 6 OFFICERS | 4DAYS | Plan | ABUJA | 480000 | 390000 | 1152000
Actual
8 | AUDIT CONFERENCE | MoE/S-WTC/07/21 |  | 5 OFFICERS | 4DAYS | Plan | ABUJA | 150000 | 128000 | 284000
Actual
9 | NITAD | MoE/S-WTC/08/21 |  | 5 OFFICERS | 4DAYS | Plan | ENUGU | 375,00.00 | 320000
Actual
Mo+B28:M30/09/21 | Sponsorship of Ministry's delegates to National Meetings (NCE MEETINGS EXPENSES) | MoE/S-WTC/09/21 |  |  |  | Plan |  |  |  |  | 15000000

## NCS
PROCUREMENT PLAN FOR NON- CONSULTANCY SERVICES
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  | Plan vs. Actual | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | Budget Avail | Source of Funding | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qual |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance |  | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
[12 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks |  | 0 | 4-6 wks | 2-4 wks
1 | POLICIESAND PROGRAMME STUDIES | MoE/S-NC/NS/01/22 |  | 40828650 |  | <50M | NS | Lumpsum | POST |  | PRIOR | 6/03/22 | 13/03/22 | 20/03/22 | 3/04/22 | 10/04/22 | 17/04/22 | Plan |  | 24/04/22 | 2022-05-01
Actual
2 | MOTOR VEHICLE REPAIR AND MAINTAINANCE | MoE/W-NC/NS/01/22 |  | 5235378 |  | <50M | NS |  | POST |  | POST | 6/03/22 | 13/03/22 | 20/03/22 | 3/04/22 | 10/04/22 | 17/04/22 | Plan |  | 24/04/22 | 2022-05-01
Actual
3 | Minor Repair and Maintainance of Science Laboratories in Secondary Schools. | MoE/W-NC/NS/02/22 |  | 10,000,000.00 |  | <50M | NS | Lumpsum | POST |  | POST | 6/03/22 | 13/03/22 | 20/03/22 | 3/04/22 | 10/04/22 | 17/04/22 | Plan |  | 24/04/22 | 2022-05-01
Actual
4 | School Improvement Project | MoE/W-NC/NS/03/22 |  | 645,104,297.00 |  | >50M&1B | ICB | BOQ | PRE |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
5 | Food and Nutrition | MoE/S-NC/NS/02/22 |  | 10000000 |  | <50M | NS | Lumpsum | Post |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
Actual
6 | MAINTAINANCE AND REPAIRS OF OTHER | MoE/W/NS/04/22 |  | 500000 |  | <50M | NS | Lumpsum | POST |  | PRI+L26:T27OR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
7 | MONITORING AND EVALUATION EXPENSES | MoE/S/NS/03/22 |  | 8300000 |  | <50M | NS | Lumpsum | Post |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
| YOUTH PROGRAMME | MoE/S/NS/04/22 |  | 110369654 |  | >50M | NCB | Lumpsum | PRE |  | PRE | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Actual |  | 17/04/22 | 2022-05-01
Plan
| ARTS AND FESTIVAL | MoE/S/NS/05/22 |  | 5000000 |  | <50M | NS |  |  |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
| APTITUDE TEST | MoE/S/NS/06/22 |  | 17480060 |  | <50M | NS |  |  |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
| QUIZ COMPETION | MoE/S/NS/07/22 |  | 13,500,000.00 |  | <50M | NS |  |  |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
| FESTIVAL OF INSTRUCTIONAL MATERIALS | MoE/S/NS/08/22 |  | 2100000 |  | <50M | NS |  |  |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
| EXHIBITION AND TRADE FAIR | MoE/S/NS/09/22 |  | 50000 |  | <50M
| RESOURCES CENTRE EXPENSES (TRAINING OF TEACHERS ON SPECIAL AUDIO VISUAL) | MoE/S/NS/08/22 |  | 20001558 |  | <50M | NS | Lumpsum | Post |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual
| MONITORING AND EVALUATION | MoE/S/NS/08/22 |  | 8300000 |  | <50M | NS | Lumpsum | Post |  | PRIOR | 17/02/22 | 24/02/22 | 27/02/22 | 06/03/22 | 13/03/22 | 27/03/22 | Plan |  | 17/04/22 | 2022-05-01
Actual

## CONSULT
CONSULTANCY
MINISTRY/ AGENCY: EDUCATION
BUDGET YEAR: 2022
S/N | PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
| Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
1 | SCHL ONLINE PROJECT | MoE/S-C/SS/001/2022 | SS | LumpSum | 100000000 | Prior | Plan | 09/5/22 | 18/5/22 | 24/5/22 | 8/6/22 | 16/6/22 | 24/6/22 | 4/7/22 | 2022-07-15 | 2022-07-19 | 29/7/22 | 10/8/22 | 18/8/22 | 26/8/21 | 8/9/22 |  | 11/11/22 | 2022-09-27 | 2022-10-18 | 2022-10-02 | 2022-11-10 | 2022-11-22
Actual
2 | EDUCATION SUMMIT | MoE/S-C/SS/002/22 | SS | LumpSum | 45000000 |  | Plan | 09/5/22 | 18/5/22 | 24/5/22 | 8/6/22 | 16/6/22 | 24/6/22 | 4/7/22 | 2022-07-15 | 2022-07-19 | 29/7/22 | 10/8/22 | 18/8/22 | 26/8/21 | 8/9/22 |  | 11/11/22 | 2022-09-27 | 2022-10-18 | 2022-10-02 | 2022-11-10 | 2022-11-22
Actual

## WORKS2
PROCUREMENT PLAN FOR WORKS
MINISTRY/ AGENCY: MINISTRY OF EDUCATION
BUDGET YEAR: 2022
WORKS |  | BASIC DATA | [6 empty] | Plan vs. Actual | Prior or Post Review | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  | Plan vs. Actual | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Avail | Source of Funding | Approval Threshold | Procurement Method | Lumpsum or Bill of Quantities | Pre-or Post Qual |  |  | Bid Prep & Submission by MDA | PPA No-Objection | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | PPA Issues Certificate of Compliance |  | Contract Amount in N'000 | Date Contract Signature | Mobilization/ Advance Payment | Substantial Completion/Istall | Inspection and Final Acceptance
Maintainance of Office Building | [10 empty] | 1-4 wks | 1-2 wks | 1-2 wks | 2-6 wks | 1-2 wks | 1-2 wks |  | 0 | 4-6 wks | 2-4 wks
| MoE/W/NS/01/22 | 1 | 1819221 |  | >10M | NS | BOQ | Post | Plan |  | 17/2/22 | 24/2/22 | 27/2/22 | 06/3/22 | 13/3/22 | 27/0/22 | Plan |  | 17/4/22 | 5/1/22
Construction / Rehabilitation of Schools. | [8 empty] | Actual | [7 empty] | Actual
| MoE/W/ICB/01/22 |  | 8,186,475,792.00 |  | >1B | ICB | BOQ | Pre | plan | PRIOR | 17/04.22 | 2022-02-05 | 2022-05-16 | 2022-05-30 | 2022-06-13 | 2022-06-27 | Actual |  | 2022-06-25 | 8/08/22
[9 empty] | Actual | [7 empty] | Actual
Installation/ Rehabilitation of Science Laboratories in Senior Secondary Schools | MoE/W/NCB/01/22 | 1 | 689079407 |  | <1B | NCB | BOQ | PRE | Plan | Prior | 6/3/22 | 13/3/22 | 20/3/22 | 3/4/22 | 10/4/22 | 17/4/22 | Plan |  | 24/4/22 | 5/1/22
Actual
Actual
Renovation of Special and Inclusive Schools in theState | MoE/W/NCB/02/22 | 1 | 110,000,000.00 |  | <1B | NCB | BOQ | PRE | Plan | Prior | 6/3/22 | 13/3/22 | 20/3/22 | 3/4/22 | 10/4/22 | 17/4/22 | Plan |  | 17/4/22 | 5/1/22
[9 empty] | Actual | [7 empty] | Actual
Rehabilitation of Offices | MoE/W/NCB/03/22 | 1 | 100000000 |  | <50M | NCB | BOQ | PRE | Plan | NA | 17/2/22 | 24/2/22 | 27/2/22 | 06/3/22 | 13/3/22 | 27/0/22 | Plan |  | 17/4/22 | 5/1/22
[9 empty] | Actual | [7 empty] | Actual
Maintainance of Model Colleges | MoE/W/ICB/02/22 | 1 | 1000000000 |  | >100M=1B | ICB | BOQ | PRE | Plan | Prior | 17/2/22 | 24/2/22 | 27/2/22 | 06/3/22 | 13/3/22 | 27/0/22 | Plan |  | 17/4/22 | 5/1/22
[9 empty] | Actual | [7 empty] | Actual
MINOR REPAIRS AND MAINTAINANCE OF SCIENCE LABORATORIES IN SCHOOLS | MoE/W/NS/02/22 | 1 | 10000000 |  | >100M=1B | NS | BOQ | Post | Plan | Prior | 17/2/22 | 24/2/22 | 27/2/22 | 06/3/22 | 13/3/22 | 27/0/22 | Plan |  | 17/4/22 | 5/1/22
[9 empty] | Actual | [7 empty] | Actual
PAINTING OF FENCE IN 30 NUMBERS OF MODEL COLLEGES IN THE STATE | MoE/W/ICB/03/22 | 1 | 234934627 |  | >100M=1B | ICB | BOQ | PRE | Plan | Prior | 17/2/22 | 24/2/22 | 27/2/22 | 06/3/22 | 13/3/22 | 27/0/22 | Plan |  | 17/4/22 | 5/1/22
[9 empty] | Actual | [7 empty] | Actual