## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: Works & Infrastructure (Office of Works).
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | ENLIGHTMENT & CAMPAIGN: (i) Admin = N63,809.84, (ii) Support Service: cost of publicity on Television per annum = N1,000,000.00. Cost of publicity on radio & print media =N1,725,175.61 | MWI/OW/NP/NM/001/2022 | 2,788,985.45 | Plan |  |  | 697246.37 |  |  | 697246.37 |  |  | 697246.37 |  |  | 697246.37 | 2788985.45
Actual
2 | Senior Special Assistant Allowance | MWI/OW/NP/NM/002/2022 | 4974751.4216 | Plan |  |  | 1243687.85 |  |  | 1243687.85 |  |  | 1243687.85 |  |  | 1243687.85 | 4974751.42
Actual
Plan
Actual
Plan
Actual
Plan
Actual
14 |  |  |  | Plan
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: MINISTRY OF WORKS AND INFRASTRUCTURE (Office of Works)
BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
|  | Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | MAINTENANCE OF OFFICE BUILDING: (i) Admin-N1,500,447.49, (ii) Account -N66,103.26, (iii) PRS-N55,151.00, (iv) Mechanical Service-N144,605.03, (v) Electrical Services-N1,165,798.37, (vi) Building Department-N1,592,446.88, (vii) Support Services-N204,185.12 | MWI/OW/S-NC/NS/001/2022 | 1 | 7 | 4728737.14 | <10M | NS | Plan | Post | Post | 2022-02-18 | N/A | 2022-03-01 | 2022-03-30 | 2022-04-13 | N/A | N/A | Plan | 2022-05-13 | 2022-05-16 |  | 2022-06-24 | 2022-07-25 | 2022-09-21 | 2022-10-21
[8 empty] | Actual | [9 empty] | Actual
2 | GENERAL UTILITY SERVICE: (i) Admin-N803,378.89, (ii) Account -N96,755.33, (iii) PRS-N31,735.93, (iv) Mechanical Service-N388,147.49, (v) Electrical Services-N863,096.34, (vi) Building Department-N507,905.84, (vii) Support Services-N812,055.27 | MWI/OW/S-NC/NS/002/2022 | 1 | 7 | 3503075.09 | <10M | NS | Plan | Post | Post | 2022-02-21 | N/A | 2022-03-01 | 2022-03-30 | 2022-04-13 | N/A | N/A | Plan | 2022-05-13 | 2022-05-16 |  | 2022-06-24 | 2022-07-25 | 2022-09-21 | 2022-10-21
[8 empty] | Actual | [9 empty] | Actual
3 | MOTOR VEHICLE REPAIR AND MAINTENANCE: (i) Admin-N2,242,041.63, (ii) Account -N252,855.75, (iii) PRS-N16,125.88, (iv) Mechanical Service-N385,029.27, (v) Electrical Services-N983,160.64, (vi) Building Department-N507,905.84, (vii) Support Services-N522,844.17 | MWI/OW/S-NC/NS/003/2022 | 1 | 7 | 5064954.18 | <10M | NS | Plan | Post | Post | 2022-03-01 | N/A | 2022-03-21 | 2022-04-28 | 2022-05-09 | N/A | N/A | Plan | 2022-06-07 | 2022-06-09 |  | 2022-07-27 | 2022-08-25 | 2022-11-02 | 2022-11-22
[8 empty] | Actual | [9 empty] | Actual
4 | MAINTENANCE AND REPAIR OF OTHER EQUIPMENT: (i)Mechanical Service-N350,000.00, (ii) Electrical Services-N350,000.00 | MWI/OW/S-NC/NS/004/2022 | 1 | 2 | 7000000 | <10M | NS | Plan | Post | Post | 2022-03-02 | N/A | 2022-03-11 | 2022-04-20 | 2022-04-28 | N/A | N/A | Plan | 2022-06-07 | 2022-06-09 |  | 2022-07-27 | 2022-08-25 | 2022-11-02 | 2022-11-22
[8 empty] | Actual | [9 empty] | Actual
5 | Maintanance of Generators | MWI/OW/S-NC/NS/005/2022 | 1 | 1 | 2047169.81 | <10M | NS | Plan | Post | Post | 2022-03-03 | N/A | 2022-03-23 | 2022-05-02 | 2022-04-11 | N/A | N/A | Plan | 2022-05-31 | 2022-06-02 |  | 2022-07-12 | 2022-08-19 | 2022-10-27 | 2022-11-16
[8 empty] | Actual | [9 empty] | Actual
6 | Upgrading of Electrical Distribution/Equipment within the Secretariat | MWI/OW/S-NC/NS/006/2022 | 1 | 1 | 22623849.04 | <50M | NS | Plan | Post | Prior | 2022-03-07 | N/A | 2022-03-16 | 2022-04-25 | 2022-05-13 | N/A | N/A | Plan | 2022-06-22 | 2022-06-24 |  | 2022-08-12 | 2022-09-01 | 2022-10-31 | 2022-11-18
[8 empty] | Actual | [9 empty] | Actual
7 | Security Services | MWI/OW/S-NC/NS/007/2022 |  | 1 | 19500000 | <50M | NS | Plan | Post | Prior | 2022-03-09 | N/A | 2022-03-16 | 2022-04-25 | 2022-05-13 | N/A | N/A | Plan | 2022-06-22 | 2022-06-24 |  | 2022-08-12 | 2022-09-01 | 2022-10-31 | 2022-11-18
[8 empty] | Actual | [9 empty] | Actual
8 | Janitorial Services | MWI/OW/S-NC/NS/008/2022 | 1 | 1 | 7462127.12 | <10M | NS | Plan | Post | Prior | 2022-03-10 | N/A | 2022-03-30 | 2022-05-09 | 2022-05-18 | N/A | N/A | Plan | 2022-06-22 | 2022-06-24 |  | 2022-08-12 | 2022-09-01 | 2022-10-31 | 2022-11-18
[8 empty] | Actual | [9 empty] | Actual
9 | MOTOR VEHICLE FUEL CONSUMPTION: (i) Admin-N1,591,506.09, (ii) Account -N213,830.64, (iii) PRS-N94,176.11, (iv) Mechanical Service-N420,799.42, (v) Electrical Services-N857,741.12, (vi) Building Department-N833,268.16, (vii) Support Services-N3,053,440.23 | MWI/OW/S-NC/NS/009/2022 |  | 7 | 7064761.75 | <10M | NS | Plan | Post |  | 2022-03-11 | N/A | 2022-03-30 | 2022-05-09 | 2022-05-18 | N/A | N/A | Plan | 2022-06-22 | 2022-06-24 |  | 2022-08-12 | 2022-09-01 | 2022-10-31 | 2022-11-18
[8 empty] | Actual | [9 empty] | Actual
10 | Fuel for Generator and Plants | MWI/OW/S-NC/NS/010/2022 |  | 1 | 1062049.83 | <10M | NS | Plan | Post | Post | 2022-03-14 | N/A | 2022-04-01 | 2022-05-11 | 2022-05-20 | N/A | N/A | Plan | 2022-06-22 | 2022-06-24 |  | 2022-08-12 | 2022-09-01 | 2022-10-31 | 2022-11-18
[8 empty] | Actual | [9 empty] | Actual
11 | Monitoring Enforcement & Compliance | MWI/OW/S-NC/NS/011/2022 |  | 1 | 1748162.99 | <10M | NS | Plan | Post | Post | 2022-03-16 | N/A | 2022-04-05 | 2022-05-24 | 2022-06-13 | N/A | N/A | Plan | 2022-07-21 | 2022-07-26 |  | 2022-09-22 | 2022-10-21 | 2022-11-30 | 2022-12-20
[8 empty] | Actual | [9 empty] | Actual
12 | Repair of R & A, amount set aside for the repair and maintenance of Refridgerators and Air-Conditioners | MWI/OW/S-NC/NS/012/2022 |  | 1 | 8000000 | <10M | NS | Plan | Post | Post | 2022-03-17 | N/A | 2022-03-28 | 2022-05-16 | 2022-06-03 | N/A | N/A | Plan | 2022-07-13 | 2022-07-15 |  | 2022-09-20 | 2022-10-19 | 2022-12-09 | 2022-12-21
[8 empty] | Actual | [9 empty] | Actual
13 | PUBLICATION & DOCUMENTATION: (i) 1 appearane of SA(MoWI) on TV/Radio Per appearance =N125,000.00, (ii) PR Event Management @ N150,000 per Event,(iii) 2 Documentary of MoWI Activities @N122,565.00 per Activities i.e 4 X N122,565.00=490,260.00, (iv)Specialised Correspondents @ N114,062.00 | MWI/OW/S-NC/NS/013/2022 |  | 1 | 879322 | <10M | NS | Plan | Post | Post | 2022-03-21 | N/A | 2022-03-28 | 2022-05-16 | 2022-06-03 | N/A | N/A | Plan | 2022-07-13 | 2022-07-15 |  | 2022-09-20 | 2022-10-19 | 2022-12-09 | 2022-12-21
[8 empty] | Actual | [9 empty] | Actual
14 | (FUEL DUMP) Service of 2 Nos. Fuel Dispenser @ N76,541.28 per dispenser i.e, 2 X N76,541.28= N153,082.56 | MWI/OW/S-NC/NS/014/2022 |  |  | 153082.56 | <10M | NS | Plan | Post | Post | 2022-03-22 | N/A | 2022-03-28 | 2022-05-16 | 2022-06-03 | N/A | N/A | Plan | 2022-07-13 | 2022-07-15 |  | 2022-09-20 | 2022-10-19 | 2022-12-09 | 2022-12-21
[8 empty] | Actual | [9 empty] | Actual
15 | (SPECIAL DUTIES EXPENSES)Servicing of Mangement Meeting for 12 months & Honorarium: (i) Admin- 1,761,968.38 & 3,500,000.00, (ii) Mechanical Service - 556,743.09, (iii) Electrical Services - 2,180,175.66, (iv) Building Development- 1,659,015.27, (v) Support Services - 8, 082, 965.90 | MWI/OW/S-NC/NS/015/2022 |  |  | 20240868.29 | <50M | NS | Plan | Post | Post | 2022-03-23 | N/A | 2022-03-28 | 2022-05-16 | 2022-06-03 | N/A | N/A | Plan | 2022-07-13 | 2022-07-15 |  | 2022-09-20 | 2022-10-19 | 2022-12-09 | 2022-12-21
[8 empty] | Actual | [9 empty] | Actual
16 | Refurbishment of Operational Motor Vehicle | MWI/OW/S-NC/NS/016/2022 |  |  | 13034320.11 | <50M | NS | Plan | Post | Prior | 2022-03-24 | N/A | 2022-04-04 | 2022-05-03 | 2022-05-23 | N/A | N/A | Plan | 2022-06-28 | 2022-07-01 |  | 2022-08-10 | 2022-08-30 | 2022-11-07 | 2022-11-25
[8 empty] | Actual | [9 empty] | Actual
17 | MISELLANEOUS: (i) Admin= 1,325,253.43, (ii) Account = 487,006,38, (iii) PRS = 55,151.00, (iv) Mechanical Services = 200,815.86, (v) Electrical Services = 1,816,523.00, (vi) Bulding Development = 662,498.32 | MWI/OW/S-NC/NS/017/2023 |  |  | 4547247.99 | <10M | NS | Plan | Post | Post | 2022-03-25 | N/A | 2022-04-04 | 2022-05-03 | 2022-05-23 | N/A | N/A | Plan | 2022-06-28 | 2022-07-01 |  | 2022-08-10 | 2022-08-30 | 2022-11-07 | 2022-11-25
[8 empty] | Actual | [9 empty] | Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY:
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package No | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Conference & Seminars for 11 Nos Officers @182,493.36/Officer, 11 X 182,493.36 = 2,007,426.94 and Workshop &Training for 110 Nos Officers@ N32,076.98 /Officer. i.e 110 X N32,076.98 = N 3,528,467.64 for Admin. | MWI/OW/S-WTC/001/2022 | To enhance professionalism and efficient service delivery | 121 |  | Plan |  |  |  |  | 5535894.58
Actual
2 | Conference & Seminars for 15 Nos Officers @ N185,992.97/Officer: 15 X 185,992.97 = N2,789,894.62 for Account | MWI/OW/S-WTC/002/2022 | To enhance professionalism and efficient service delivery | 15 |  | Plan |  |  |  |  | 2789894.62
Actual
3 | Workshop&Training for 25 Officer @N38,166.71/ Officer = 954,167.99 and Seminars & Conference for 10 Officers @ N212,545.27/Officer = N2,125,452.66 for Mechanical Services | MWI/OW/S-WTC/003/2022 | To enhance professionalism and efficient service delivery | 35 |  | Plan |  |  |  |  | 3079620.65
Actual
4 | Workshop & Training for 50 Officers @40,554.56 / Officer = N2,027,728.45 and Seminars & Conference for 25 Officers @ N160,000.00 /Officer = N4,000,000.00 for Electrical Services | MWI/OW/S-WTC/004/2022 | To enhance professionalism and efficient service delivery | 75 |  | Plan |  |  |  |  | 6027728.45
Actual
5 | Workshop & Training for 40 Officers @ N65,885.07 / Officer. i.e 40 X N65,885.07 = N2,635,403.09 and Seminars & Conference for 25 Officers @ N160,000.00 /Officer = N4,000,000.00 for Architect, Builder and Quantity Surveyors (ABQS) | MWI/OW/S-WTC/005/2022 | To enhance professionalism and efficient service delivery | 65 |  | Plan |  |  |  |  | 6635403.07
Actual
6 | Workshop&Training for 40 Officers @ 51,344.20 / Officer = N2,053,768.01 and Seminars & Conference for 50 Officers @ N147,057.64 /Officer. i.e 50 X 147,057.64 = N7,352,882.10 for Support Services | MWI/OW/S-WTC/006/2022 | To enhance professionalism and efficient service delivery | 90 |  | Plan |  |  |  |  | 9406650.11
Actual
7 | Retreat for the Management Offiers in the Office of Works, for 43Staff @N144,614.87 per Staff : 43 X N144,614.87 =N6,218,439.27 . | MWI/OW/S-WTC/007/2022 | To enhance professionalism and efficient service delivery | 43 |  | Plan |  |  |  |  | 6218439.27
Actual
8 | TRAVEL AND TANSPORT: (i) Admin-N1,560,286.00, (ii) Account -N127,407.39, (iii) PRS-N47,345.98, (iv) Mechanical Service-N388,147.49, (v) Electrical Services-N731,981.96, (vi) Building Development-N507,905.84, (vii) Support Services-N1,101,266.36 | MWI/OW/S-WTC/008/2022 | To enhance efficient service delivery | 65 |  | Plan |  |  |  |  | 4464341.03
Actual
9 | Workshop &Traning for 100 Officers @ 47,554.49/ Officer i.e: N47,554.49 X 100 = N4,755,449.75 For Human Resources and Training. | MWI/OW/S-WTC/009/2022 | To enhance efficient service delivery | 100 |  | Plan |  |  |  |  | 4755449.75
Actual
10 | Conference & Seminars for 5 Nos Officers @215,200.81/Officer, 5 X 215,200.81 = 1,076,004.05 and Workshop &Training for 5 Nos Officers@ N162,389.51/Officer. i.e 5 X N162,389.51 = N811,947.56 for Planning, Research and Statistics. | MWI/OW/S-WTC/010/2022 | To enhance efficient service delivery | 10 |  | Plan |  |  |  |  | 1887951.61
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICE
MINISTRY/ AGENCY: Works & Infrastructure(Office of Works)
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Research and Development | MWI/OW/S-C/001/2022 |  | Time based | 3645917.92 | Post | Plan | 2022-02-10 | N/A | 2022-03-02 | 2022-03-16 | 2022-04-20 | N/A | 2022-04-14 | 2022-05-10 | 2022-05-31 | 2022-06-09 | 2022-06-29 | 2022-07-19 | 2022-08-17 | 2022-08-19 |  | 2020-07-08 | 2022-08-30 | 2022-09-19 | 2022-10-14 | 2022-11-03
Actual
2 | [6 empty] | Plan
Actual
Plan
Actual
Plan
Actual

## Goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: Works and Infrastructure (Office of Works)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (1-2wks) | 1-2wks) | (1-2wks) | (1-4 wks) | 48Hrs | 0 | 1wk | (1-2 wks) | (2-4wks)
1 | Procurement of 2Nos. 100KVA Generating Sets for MoWI | MWI/OW/G/NCB/001/2022 | 1 | 1 | 100000000 | ≤100M | NCB | Pre | Prior | Plan | 2022-02-10 | N/A | 2022-03-02 | 2022-03-16 | 2022-03-25 | N/A | 2022-04-14 | 2022-04-18 |  | 2022-04-27 | 2022-05-06 | 2022-05-26 | 2022-06-07 | 2022-06-16
Actual
2 | PROCUREMENT OF MANAGEMENT INFORMATION SYSTEM ACCESSORIES: (i)Admin=134,583.63, (ii) Account =41,529.66, (iii) Mechanical Services = 38,109.09, (iv) Electrical services = 85,276.07, (v)Building Development = 109,304.92, Support Services = 2,462,627.42 | MWI/OW/G/NS/002/2022 |  | 6 | 2871430.79 | <10M | NS | Post | Post | Plan | 2022-02-11 | N/A | 2022-03-02 | 2022-03-16 | 2022-03-25 | N/A | 2022-04-14 | 2022-04-18 |  | 2022-04-27 | 2022-05-06 | 2022-05-26 | 2022-06-07 | 2022-06-16
Actual
3 | Office Funiture & Equipment | MWI/OW/G/NS/003/2022 |  | 1 | 14224129.72 | <50M | NS | Post | Prior | Plan | 2022-02-14 | N/A | 2022-03-02 | 2022-03-16 | 2022-03-25 | N/A | 2022-04-14 | 2022-04-18 |  | 2022-04-27 | 2022-05-06 | 2022-05-26 | 2022-06-07 | 2022-06-16
Actual
4 | Procurement of Drawing Office Materials PROCUREMENT OF DRAWING OFFICE MATERALS: (i) Mechanical Service =39,986.95, (ii) Building Development = 43,694.61, (iii) Electrical Services = 177, 167.78 | MWI/OW/G/NS/004/2022 |  | 3 | 260849.342 | <10M | NS | Post | Post | Plan | 2022-02-15 | N/A | 2022-03-02 | 2022-03-16 | 2022-03-25 | N/A | 2022-04-14 | 2022-04-18 |  | 2022-04-27 | 2022-05-06 | 2022-05-26 | 2022-06-07 | 2022-06-16
Actual
5 | PROCUREMENT OF UNIFORM & PROTECTIVE OUTFITS : (i) Admin = 542,843.90, (ii) Mechanical Services =278,526.70, (iii) Building Development =913,626.04, Support Services = 1,677,949.85 | MWI/OW/G/NS/005/2022 |  | 4 | 3412946.49 | <10M | NS | Post | Post | Plan | 2022-02-17 | N/A | 2022-02-28 | 2022-03-10 | 2022-03-30 | N/A | 2022-04-28 | 2022-05-02 |  | 2022-05-11 | 2022-05-31 | 2022-06-29 | 2022-07-27 | 2022-08-08
Actual
6 | PROCUREMENT OF STATIONERY: (i) Admin-N3,236,645.78, (ii) Account -N877,257.43, (iii) PRS-N55,151.00, (iv) Mechanical Service-N394,715.82, (v) Electrical Services-N223,929.73, (vi) Building Department-N558,016.39, (vii) Support Services-N2,330,412.73 | MWI/OW/G/NS/006/2022 | 1 | 7 | 7676128.87 | <10M | NS | Post | Post | Plan | 2022-02-18 | N/A | 2022-02-28 | 2022-03-10 | 2022-03-30 | N/A | 2022-04-28 | 2022-05-02 |  | 2022-05-11 | 2022-05-31 | 2022-06-29 | 2022-07-27 | 2022-08-08
Actual
7 | PROCUREMENT OF TOOLS : (i) Mechanical Service-N363,102.06, (ii) Electrical Services-N1,083,629.52, (iii) Building Department-N854,751.64, (iv) Support Services-N4,434,195.48 | MWI/OW/G/NS/007/2022 |  | 4 | 6735678.7226 | <10M | NS | Post | Post | Plan | 2022-02-21 | N/A | 2022-03-11 | 2022-03-22 | 2022-04-11 | N/A | 2022-05-19 | 2022-05-23 |  | 2022-06-01 | 2022-06-21 | 2022-07-29 | 2022-08-18 | 2022-09-07
Actual
8 | (SPECIAL DUTIES EXPENSES) Procurement of Jerseys, Boots, Hand gloves,Socks, balls and payment of allowance to male and female footballers in the Office of works for HOS cup competition. | MWI/OW/G/NS/008/2022 |  | 5 | 2500000 | <10M | NS | Post | Post | Plan | 2022-02-22 | N/A | 2022-03-11 | 2022-03-22 | 2022-04-11 | N/A | 2022-05-19 | 2022-05-23 |  | 2022-06-01 | 2022-06-21 | 2022-07-29 | 2022-08-18 | 2022-09-07
Actual
9 | (FUEL DUMP) Procurement of 8 Nos. fire fighting equipment civil work @ N18,364.68 =8 X N18,364.68 =N146,917.44 | MWI/OW/G/NS/009/2022 |  | 1 | 146917.44 | <10M | NS | Post | Post | Plan | 2022-02-23 | N/A | 2022-03-11 | 2022-03-22 | 2022-04-11 | N/A | 2022-05-19 | 2022-05-23 |  | 2022-06-01 | 2022-06-21 | 2022-07-29 | 2022-08-18 | 2022-09-07
Actual
10 | Replacement / Upgrading of Low Voltage Infrastructure Equipment for Blocks 1-23 | MWI/OW/G/NS/010/2022 |  | 1 | 22623849.0385 | <50M | NS | Post | Prior | Plan | 2022-02-24 | N/A | 2022-03-11 | 2022-03-22 | 2022-04-11 | N/A | 2022-05-19 | 2022-05-23 |  | 2022-06-01 | 2022-06-21 | 2022-07-29 | 2022-08-18 | 2022-09-07
Actual
11 | Procurement of Building Materials for the (Upgrading of Mechanical Workshop) Construction of fabrication/ Research Workshop and Automobile Workshop | MWI/OW/G/NCB/011/2022 |  | 1 | 113252261.21 | <500M | NCB | Pre | Prior | Plan | 2022-02-28 | N/A | 2022-03-18 | 2022-03-29 | 2022-04-18 | N/A | 2022-05-17 | 2022-05-19 |  | 2022-05-30 | 2022-06-17 | 2022-07-18 | 2022-08-16 | 2022-09-05
Actual
12 | Provision for Computer and Accessories | MWI/OW/G/NCB/012/2022 |  | 1 | 74905671 | <100M | NCB | Pre | Prior | Plan | 2022-02-28 | N/A | 2022-03-18 | 2022-03-29 | 2022-04-18 | N/A | 2022-05-17 | 2022-05-19 |  | 2022-05-30 | 2022-06-17 | 2022-07-18 | 2022-08-16 | 2022-09-05
Actual
13 | Procuremen of goods for Public Affairs Expenses | MWI/OW/G/NS/013/2022 |  | 1 | 9985303.98 | <10M | NS | Post | Post | Plan | 2022-02-28 | N/A | 2022-03-18 | 2022-03-29 | 2022-04-18 | N/A | 2022-05-17 | 2022-05-19 |  | 2022-05-30 | 2022-06-17 | 2022-07-18 | 2022-08-16 | 2022-09-05
Actual
14 | Procurement of goods for Legal Expenses | MWI/OW/G/NS/014/2022 |  | 1 | 3653055.53 | <10M | NS | Post | Post | Plan | 2022-03-02 | N/A | 2022-03-31 | 2022-04-20 | 2022-04-29 | N/A | 2022-05-09 | 2022-05-11 |  | 2022-05-20 | 2022-06-09 | 2022-07-19 | 2022-08-08 | 2022-08-26
Actual
15 | Procurement of goods for Audit Expenses | MWI/OW/G/NS/015/2022 |  | 1 | 3870901.57 | <10M | NS | Post | Post | Plan | 2022-03-03 | N/A | 2022-03-31 | 2022-04-20 | 2022-04-29 | N/A | 2022-05-09 | 2022-05-11 |  | 2022-05-20 | 2022-06-09 | 2022-07-19 | 2022-08-08 | 2022-08-26
Actual
16 | Procurement of goods for ICT unit Expenses | MWI/OW/G/NS/016/2022 |  | 1 | 2487375.7 | <10M | NS | Post | Post | Plan | 2022-03-07 | N/A | 2022-04-05 | 2022-05-04 | 2022-05-24 | N/A | 2022-07-01 | 2022-07-04 |  | 2022-07-13 | 2022-08-02 | 2022-08-31 | 2022-09-20 | 2022-10-10
Actual
17 | Procurement of goods for Procuremunt Unit (Expenses) | MWI/OW/G/NS/017/2022 |  | 1 | 3356675.05 | <10M | NS | Post | Post | Plan | 2022-03-08 | N/A | 2022-04-05 | 2022-05-04 | 2022-05-24 | N/A | 2022-07-01 | 2022-07-04 |  | 2022-07-13 | 2022-08-02 | 2022-08-31 | 2022-09-20 | 2022-10-10
Actual
18 | Procurement of Awards, Rewards and Ceremonies Items | MWI/OW/G/NS/018/2022 |  | 1 | 1047169.81 | <10M | NS | Post | Post | Plan | 2022-03-10 | N/A | 2022-03-30 | 2022-04-08 | 2022-04-28 | N/A | 2022-05-27 | 2022-05-31 |  | 2022-06-09 | 2022-06-20 | 2022-07-28 | 2022-08-17 | 2022-08-26
Actual
19 | Procurement of goods for Planning Research & Statistics Expences | MWI/OW/G/NS/019/2022 |  | 1 | 4913391.99 | <10M | NS | Post | Post | Plan | 2022-03-14 | N/A | 2022-04-01 | 2022-04-21 | 2022-05-02 | N/A | 2022-05-31 | 2022-06-02 |  | 2022-06-13 | 2022-07-01 | 2022-08-01 | 2022-08-19 | 2022-08-30
Actual
20 | (MISCELLANEOUS) Goods for Building Development = 929,948.56, Support Services = 2,330,402.92 | MWI/OW/G/NS/020/2022 |  | 4 | 3260351.48 | <10M | NS | Post | Post | Plan | 2022-03-15 | N/A | 2022-04-01 | 2022-04-21 | 2022-05-02 | N/A | 2022-05-31 | 2022-06-02 |  | 2022-06-13 | 2022-07-01 | 2022-08-01 | 2022-08-19 | 2022-08-30
Actual

## Works 2
| Works & infrastructure | 2
Works & infrastructure(Office 0f Works)
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description |  | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[12 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | 1-4wks | 48 Hours | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Ogombo Shoprite Road |  | MWI/OW/W/ICB/001/2022 | 1 | 1260501220 | <2B | ICB | BOQ | Pre | Plan | Prior | 2022-03-02 | N/A | 2022-03-16 | 2022-04-06 | 2022-04-26 | N/A | 2022-05-25 | 2022-05-26 |  | 2022-06-06 | 2022-06-24 | 2022-07-05 | 2022-08-12 | 2022-09-16
Actual
2 | Rehabilitation of offices/office Buildings |  | MWI/OW/W/ICB/002/2022 | 1 | 538093058.72 | <1B | ICB | BOQ | Pre | Plan | Prior | 2022-03-03 | N/A | 2022-03-16 | 2022-04-06 | 2022-04-26 | N/A | 2022-05-25 | 2022-05-26 |  | 2022-06-06 | 2022-06-24 | 2022-07-05 | 2022-08-12 | 2022-09-16
Actual
3 | Renovation and Maintanance of Staff Quarters in the State for 2022 |  | MWI/OW/W/ICB/001/2022 | 30 | 1158803023.06 | <2B | ICB | BOQ | Pre | Plan | Prior | 2022-03-11 | N/A | 2022-03-22 | 2022-04-20 | 2022-05-10 | N/A | 2022-06-08 | 2022-06-10 |  | 2022-06-21 | 2022-06-30 | 2022-08-09 | 2022-09-30 | 2022-10-20
Actual
4 | Renovation of Area/Zonal Offices |  | MWI/OW/W/NCB/003/2022 | 25 | 300000000 | <500M | NCB | BOQ | Post | Plan | Prior | 2022-03-14 | N/A | 2022-03-22 | 2022-04-20 | 2022-05-10 | N/A | 2022-06-08 | 2022-06-10 |  | 2022-06-21 | 2022-06-30 | 2022-08-09 | 2022-09-30 | 2022-10-20
Actual

## On-Going 2021
PROCUREMENT PLAN
MINISRTY/AGENCY: WORKS & INFRASTRUCTURE(OFFICE OF WORKS)
BUDGET YEAR: ON - GOING 2021
CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Contract Amount | Date Contract Signature | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[10 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) | 0 | (4-6wks) | (2-4wks)
Resusitation of Lift in the Secretariat Building | MWI/OW/W/NCB/001/21 | [6 empty] | Plan
|  |  | 306951094.49 | <500M | NCB | BOQ | Pre | Actual | Prior
Outstanding Payment on Completed/Ongoing Projects for years 2017, 2018, 2019, 2020, 2021 | MWI/OW/W/NCB/002/21 | [6 empty] | Plan
|  |  | 141630480.1012 | <500M | NCB | BOQ | Pre | Actual | Prior
Special Building/Strategic Projects | MWI/OW/W/ICB/003/21 | [6 empty] | Plan
|  |  | 1111959536 | <2B | ICB | BOQ | Pre | Actual | Prior
Completion of Multi-Agency Office Complex. | MWI/OW/W/ICB/004/21 | [6 empty] | Plan
|  |  | 1161158280 | <2B | ICB | BOQ | Pre | Actual | Prior