## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: AGRICULTURE
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Year 2022 Counterpart Fund for Agric Processing Productivity Enhancement and Livelihood Support (APPEALS) | MOA/NP/NM/001/22 | 2,260,920,449.00 | Plan | Nil | Nil | Nil | Nil | Nil | 2,260,920,449.00 | Nil | Nil | Nil | Nil | Nil | Nil
Actual
2 | Acquisition, Payment of Compensation, Clearing and layout of Igbodu Farm Estate | MOA/NP/NM/002/22 | 250000000 | Plan | Nil | Nil | Nil | Nil | Nil | 125000000 | Nil | Nil | Nil | Nil | Nil | 125000000
Actual
3 | Monitoring, Enforcement and Complaince- Engagement of Special Task Force, Fuelling of Vehicles, Publicity, Disinfection and Decontamination of Markets across Lagos State. | MOA/NP/NM/003/22 | 50000000 | Plan | Nil | Nil | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Actual
4 | Establishment of Rabbitry, Snailery, Goat Production, Grasscutter Production and Vegetable Production projects in 32 Secondary Schools under the Y2022 School Agric Programme | MOA/NP/NM/004/22 | 50,000,000.00 | Plan | Nil | Nil | Nil | 30000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Actual
5 | Monitoring Project of Federal and other Initiated Projects | MOA/NP/NM/005/22 | 22,850,000.00 | Plan | Nil | Nil | Nil | 2850000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Actual
6 | Technological Generation on Farm Adaptive Research (OFAR) 6 on Fisheries, Farm Mechanisation, Crop Development and Livestockand its dissemination through Boluyo Radio Programme and Television Programme. | MOA/NP/NM/006/22 | 22,522,276.15 | Plan | Nil | Nil | 12522276.15 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | Nil
Actual
7 | Maintenance of Earten Road Network within existing Farm Estates . | MOA/NP/NM/007/22 | 22,119,277.00 | Plan | Nil | Nil | Nil | 22,119,277.00 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
|  |  |  | Actual | [8 empty] | .
8 | Documentation of 10 Agricultural Formations across the State | MOA/NP/NM/008/22 | 21000000 | Plan | Nil | Nil | Nil | Nil | 21000000 | Nil | Nil | Nil | Nil | Nil | Nil | Nil
Actual
9 | Impact Assessment of Government Intervention in the Agricultural Sector on Productivity and Agricultural Development | MOA/NP/NM/009/22 | 20,000,000.00 | Plan | Nil | Nil | 20000000 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
Actual
10 | Coconut Value Chain Promotion and Awareness Campaign including Land Preparation of 500 Hectares of land for Coconut Plnatation | MOA/NP/NM/010/22 | 16500000 | Plan | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 16500000 | Nil | Nil | Nil | Nil
Actual
11 | Implementation of Y2022 Agric Summer School | MOA/NP/NM/011/22 | 15000000 | Plan | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 15000000 | Nil | Nil | Nil
Actual
12 | Motor vehicle repairs and maintenance of Tractors and Heavy Equipments | MOA/NP/NM/012/22 | 6,400,000.00 | Plan | Nil | Nil | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000 | 640000
Actual
13 | Agriculural Production Survey (Wet and Dry Seasons) and project monitoring | MOA/NP/NM/013/22 | 6,000,547.00 | Plan | Nil | Nil | Nil | 3000547 | Nil | Nil | Nil | Nil | Nil | 3000000 | Nil | Nil
Actual
14 | Motor Vehicle Fuel Consumption | MOA/NP/NM/014/22 | 6000000 | Plan | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Actual
15 | Maintenance of Office Building | MOA/NP/NM/015/22 | 5,500,000.00 | Plan | Nil | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Actual
16 | Travel and Transport | MOA/NP/NM/016/22 | 5,000,000.00 | Plan | Nil | Nil | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Actual
17 | Maintanence of Management Trainning Plots on Fisheries, Livestock and Crop Development. | MOA/NP/NM/017/22 | 4,523,548.00 | Plan | Nil | Nil | Nil | 2523548 | Nil | Nil | Nil | 2000000 | Nil | Nil | Nil | Nil
Actual
18 | Utility services | MOA/NP/NM/018/22 | 4,500,000.00 | Plan | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000 | 375000
Actual
19 | Purchase of 5 Photocopy Machines | MOA/NP/NM/019/22 | 4,500,000.00 | Plan | Nil | Nil | Nil | Nil | 4500000 | Nil | Nil | Nil | Nil | Nil | Nil | Nil
Actual
20 | Printing of 10 Agric Account form and Production of 5 Account Form Booklet | MOA/NP/NM/020/22 | 4000000 | Plan | Nil | Nil | Nil | 4000000 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
Actual
21 | Weekly Market Surveyto be carried out 50 times | MOA/NP/NM/021/22 | 3,700,000.00 | Plan | Nil | Nil | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000
Actual
MINISTRY/ AGENCY: AGRICULTURE
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
22 | Demonsration on:(i). The use of garlic and its effect on the shelf life of smoked dried catfish. (ii). Sweet Orange peeled powderas insect repellant against fish beetles infesting smoked African Catfish. | MOA/NP/NM/022/22 | 2,008,600.00 | Plan | Nil | Nil | Nil | Nil | Nil | 2008600 | Nil | Nil | Nil | Nil | Nil | Nil
Actual
23 | Grants and Subvention | MOA/NP/NM/023/22 | 2000000 | Plan | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
Actual
24 | Servicing of Meetings on a montly baisis for 12 months | MOA/NP/NM/024/22 | 1500000 | Plan | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000 | 125000
Actual
25 | Running of Public Affairs Unit | MOA/NP/NM/025/22 | 1,150,000.00 | Plan | Nil | Nil | 287500 | Nil | Nil | 287500 | Nil | Nil | 287500 | Nil | Nil | 287500
Actual
26 | Procurement of 50 books for the Library | MOA/NP/NM/026/22 | 1,000,000.00 | Plan | Nil | Nil | 1000000 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
Actual
27 | HIV/AIDS Advocay and Multilateral Agencies visit to 10 Farming Communities | MOA/NP/NM/027/22 | 709794.39 | Plan | Nil | Nil | 70979.5 | 70979.5 | 70979.5 | 70979.5 | 70979.5 | 70979.5 | 70979.5 | 70979.5 | 70979.5 | 70979.5
Actual
28 | Tree Planting to commemorate annual tree planting date and Maintenance of Farm and Nurserie. | MOA/NP/NM/028/22 | 500000 | Plan | Nil | Nil | Nil | Nil | Nil | Nil | 500000 | Nil | Nil | Nil | Nil | Nil
Actual
29 | Running of Livestock Trainning Centre. | MOA/NP/NM/029/22 | 400000 | Plan | Nil | Nil | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
Actual
| TOTAL |  | 2810304491.54 | Plan | 1000000 | 1500000 | 41930755.65 | 73864351.5 | 39870979.5 | 2402587528.5 | 14870979.5 | 32870979.5 | 29658479.5 | 17370979.5 | 14370979.5 | 138408479.5
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: AGRICULTURE
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Packaging Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Training and Empowerment of 1,000 Youth and Women across the Coconut Value Chain. | MOA/S-T/SS/001/22 | Empowerment of Youth and Women on Coconut Value Chain | 1000 | 5 Weeks | Plan | Each Lagos State Divisions | Free | 28500000 | 10000000 | 38500000
Actual
2 | Stakeholders Capacity Building in the wood and Furniture Industry | MOA/S-T/SS/002/22 | To herness all the potential in the Wood and Furniture Industry | 1000 | 4 Weeks | Plan | Each Lagos State Divisions | Free | 20000000 | 10000000 | 30000000
Actual
3 | Agric Summer School Programme: Training of 25 Education Officers and 100 students drawn from the six Educational zones. | MOA/S-T/SS/003/22 | To engage holiday-in students in Agricultural activities. | 100 Students and 25 Teachers | 2 weeks | Plan | Different Secondary Schools acroos the six Educational zones | Free | 10000000 | 5000000 | 15000000
Actual
4 | Workshop and Training for 50 Number Staff | MOA/S-W/SS/001/22 | To build capacity of Staff | 50 | 3 Days | Plan | To be decided by Min. Of Establishment, Training and Pension. | Free | 10000000 | 5000000 | 15000000
Actual
5 | International Conferences,Conferences and Seminars for Staff | MOA/S-C/SS/001/22 | To upgrade proffesional staffs in recent techologies and renovations | 14 | 1 week | Plan | Professional Bodies Centres | 7169145 | 14830855 | Nil | 22000000
Actual
6 | Participation in Mandatory Professional Conference for Procurement Officers | MOA/S-C/SS/002/22 | To Upgrade Procurement officers in the recent Procurement Activities. | 5 | 1 week | Plan | Abuja | 2500000 | 750000 | 250000 | 3500000
Actual
| TOTAL |  |  |  |  | Plan |  |  |  |  | 124000000
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY: AGRICULTURE
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Hosting of Y2022 World Food Day and Lagos Food Festival | MOA/S-NC/NCB/001/22 | 1 | 1 | 65000000 | >50m | NCB | Plan | Post | Prior | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | Plan | 2022-04-25 | 2022-04-27 |  | 2022-05-25 | 2022-06-08 | 2022-06-22 | 2022-07-30
[7 empty] | Actual | [9 empty] | Actual
Printing of Audit Account Books | MOA/S-NC/DC/001/22 | 1 | 1 | 1500000 | <50m | NCB | Plan | Post | Post | 2022-02-21 | NA | NA | NA | NA | NA | NA | Plan | 2022-02-28 | 2022-03-02 |  | 2022-03-30 | 2022-04-13 | 2022-04-27 | 2022-05-04
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 66500000 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: AGRICULTURE
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Designs, preparation of all drawings, Layout designs and site preparation consultancy services for the Central Produce and Processing Hub. | MOA/S-C/QCBS/001/22 | QCBS | LS | 5167830299 | Prior | Plan | 2022-02-16 | 2022-02-23 | 2022-03-02 | 2022-03-16 | 2022-03-30 | 2022-04-06 | 2022-04-27 | 2022-05-04 | 2022-05-11 | 2022-05-18 | 2022-06-01 | 2022-06-08 | 2022-06-22 | 2022-06-24 |  | 2022-07-01 | 2022-07-15 | 2022-07-29 | 2022-08-12 | 2022-08-26
Actual
2 | Development of Coconut based website and digitization of LASCODA activities | MOA/S-C/IC/001/22 | IC | LS | 15740000 | Prior | Plan | 2022-02-28 | 2022-03-07 | NA | NA | NA | 2022-03-14 | 2022-04-04 | 2022-04-11 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-19 |  | 2022-05-26 | 2022-06-09 | 2022-06-23 | 2022-06-07 | 2022-07-21
Actual
3 | Development of LAISA Online Inputs Sales Application | MOA/S-C/IC/002/22 | IC | LS | 12088828 | Prior | Plan | 2022-02-28 | 2022-03-07 | NA | NA | NA | 2022-03-14 | 2022-04-04 | 2022-04-11 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-19 |  | 2022-05-26 | 2022-06-09 | 2022-06-23 | 2022-06-07 | 2022-07-21
Actual
| TOTAL |  |  |  | 5195659127 |  | Plan
Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: AGRICULTURE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Agricultural Produce, Inputs and Medication for Year 2022 Agricultural Value Chains Activation Programme (Empowerment). | MOA/G/ICB/001/22 | 1 | 1 | 700000000 | >500M | ICB | Post | Prior | Plan | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-04-04 | 2022-04-11 | 2022-04-19 | 2022-05-03 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09 | 2022-07-07 | 2022-07-14
Actual
2 | Procurement of Equipments for the Establishment of Agricultural Resource Centers for e-extension (Phase III) at Epe, Imota and Badagry | MOA/G/NS/001/22 | 1 | 3 | 49631341.48 | <50M | NS | Post | Prior | Plan | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-19 | 2021-04-21 |  | 2022-04-28 | 2022-05-05 | 2022-05-19 | 2022-06-30 | 2022-07-04
Actual
3 | Procurement of 1 Nos 4 x 4 Project Vehicle | MOA/G/NS/002/22 | 1 | 1 | 26849972.82 | <50M | NS | Post | Prior | Plan | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-04-06 | 2021-04-13 | 2021-04-15 |  | 2021-04-22 | 2021-04-29 | 2021-05-13 | 2021-05-27 | 2021-05-31
Actual
4 | Procurement of 10 Laptops,4 Desktops, 5 Printers, 3 Photocopiers, 20 Computer Accessories, consumables and dust covers. | MOA/G/NS/003/22 | 1 | 1 | 11200000 | <50M | NS | Post | Prior | Plan | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-22 | 2021-03-29 | 2021-04-06 | 2021-04-13 | 2021-04-15 |  | 2021-04-22 | 2021-04-29 | 2021-05-13 | 2021-05-27 | 2021-05-31
Actual
5 | Procurement of Office Equipments for the Formation of Agribussiness Desk of the Ministry | MOA/G/NS/004/22 | 1 | 1 | 5000000 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-07 | 2022-03-21 | NA | NA | 2022-04-04 | NA |  | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-06-07 | 2022-06-13
Actual
6 | Procurement of Stationery | MOA/G/NS/005/22 | 1 | 1 | 4,500,000.00 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-07 | 2022-03-21 | NA | NA | 2022-04-04 | NA |  | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-31 | 2022-06-06
Actual
7 | Pprocurement of 300 Units of Cable Network. | MOA/G/NS/006/22 | 1 | 1 | 1500000 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-07 | 2022-03-21 | NA | NA | 2022-04-04 | NA |  | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-06-07 | 2022-06-13
Actual
8 | Procurement of Uniform and Protective Outfit for 50 Utility Staff | MOA/G/NS/007/22 | 1 | 1 | 1,500,000.00 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-07 | 2022-03-21 | NA | NA | 2022-04-04 | NA |  | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-24 | 2022-05-30
Actual
9 | Procurement of 20 Legal Books | MOA/G/NS/008/22 | 1 | 1 | 500000 | <10M | NS | Post | Post | Plan | 2022-02-28 | NA | 2022-03-07 | 2022-03-21 | NA | NA | 2022-04-04 | NA |  | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-17 | 2022-05-23
Actual
10 | Development of Rice Paddy and other unforseen Activities for Rice Value Chain towards the operationalization of the 32MTPH Rice Mill at Imota . | MOA/G-F/DC/001/22 | 1 | 1 | 1848955179 | >500m | DC | Post | Prior | Plan | 2022-02-25 | 2022-03-04 | NA | NA | NA | NA | 2022-03-11 | 2022-03-14 |  | 2022-03-21 | 2022-03-28 | 2022-04-11 | 2021-12-27 | 2021-12-30
Actual
11 | Procurement of 13 Units 80HP,4WD Tractors and their accompany implements | MOA/G/DC/001/22 | 1 | 13 | 400000000 | >50M | DC | Post | Prior | Plan | 2022-03-01 | 2022-03-08 | NA | NA | NA | NA | 2022-03-15 | 2022-03-17 |  | 2022-03-24 | 2022-03-31 | 2022-04-14 | 2022-05-26 | 2022-05-31
Actual
| TOTAL |  |  |  | 3049636493.3 |  |  |  |  | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: AGRICULTURE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Fish Processing and Preservation Hub in Three (3) Senatorial District and Provision of other Developmental Infrastructures | MOA/W/NCB/001/22 | 3 | 300000000 | >50M | NCB | BOQ | Post | Plan | Prior | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-12 |  | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-08-11 | 2023-02-11
Actual
2 | Clearing of 100 Hectares of Land, Its Mapping and Provision of Bore Hole / Mini Wter Works at Igbodu for Lagos State Cattle Farm Programme. | MOA/W/NCB/002/22 | 1 | 205165195 | >50M | NCB | BOQ | Post | Plan | Prior | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-12 |  | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-08-11 | 2023-02-11
Actual
3 | Expansion of Infrastructural Facilities at the Food Production Center, Epe. | MOA/W/NCB/003/22 | 1 | 100000000 | >50M | NCB | BOQ | Post | Plan | Prior | 2022-03-01 | 2022-03-08 | 2022-03-15 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-12 |  | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-08-11 | 2023-02-11
Actual
4 | Renovation of Lagos State Agricultural Inputs and Supply Authority (LAISA) Warehouses at Epe, Ikorodu and Oko Oba, Agege. | MOA/W/NCB/004/22 | 3 | 94500000 | >50M | NCB | BOQ | Post | Plan | Prior | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-04-11 | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-12 |  | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-08-04 | 2023-02-04
Actual
5 | Fencing of LASCODA Seedling Production Centres . | MOA/W/NCB/005/22 | 1 | 90087683.18 | >50M | NCB | BOQ | Post | Plan | Prior | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-04-11 | 2022-04-19 | 2022-04-26 | 2022-05-10 | 2022-05-12 |  | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-08-04 | 2023-02-04
Actual
6 | Rehabilitation of 2 Veterinary Clinics. | MOA/W/NS/001/22 | 2 | 25000000 | <50M | NS | BOQ | Post | Plan | Prior | 2022-02-23 | 2022-03-02 | 2022-03-09 | 2022-02-23 | 2022-03-30 | 2022-04-06 | 2022-04-13 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-17 | 2022-06-28 | 2022-12-28
Actual
7 | Renovation of Lagos State Agricultural Development Authority (LSADA), Phase II. | MOA/W/NS/002/22 | 1 | 20902515.37 | <50M | NS | BOQ | Post | Plan | Prior | 2022-02-23 | 2022-03-02 | 2022-03-09 | 2022-02-23 | 2022-03-30 | 2022-04-06 | 2022-04-13 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-17 | 2022-06-28 | 2022-12-28
Actual
8 | Maintenance of Divisional Offices | MOA/W/NS/003/22 | 1 | 2000000 | <50M | NS | BOQ | Post | Plan | Post | 2022-02-28 | NA | NA | NA | NA | NA | 2022-03-07 | NA |  | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-05-09 | 2022-11-09
Actual
9 | Establishment of Snailery Estate in Lagos State at the Food Production Centre (Second Phase) | MOA/W/DC/001/22 | 1 | 75000000 | >50M | DC | BOQ | Post | Plan | Prior | 2022-03-01 | 2022-03-08 | NA | NA | NA | NA | 2022-03-22 | 2022-03-24 |  | 2022-03-31 | 2022-04-07 | 2022-04-21 | 2022-06-30 | 2022-12-30
Actual
10 | Fencing of the Food Production Centre (second phase) | MOA/W/DC/002/22 | 1 | 50000000 | 50 | DC | BOQ | Post | Plan | Prior | 2022-03-01 | 2022-03-08 | NA | NA | NA | NA | 2022-03-22 | 2022-03-24 |  | 2022-03-31 | 2022-04-07 | 2022-04-21 | 2022-06-16 | 2022-12-16
Actual
11 | Clearing of 500 Hectares of Farmland with the Construction of Drainage and Earthen Road at Igbodu Cattle Feedlot Estate. | MOA/W/FA/001/22 | 1 | 952985697 | >500M | FA | BOQ | Post | Plan | Prior | 2022-03-01 | 2022-03-08 | NA | NA | NA | NA | 2022-03-15 | 2022-03-17 |  | NA | NA | 2022-03-31 | 2022-07-21 | 2022-07-28
Actual
| TOTAL |  |  | 1915641090.5 |  |  |  |  | Plan
Actual
PROCUREMENT PLAN FOR WORKS (ON GOING PROJECT)
MINISTRY OF AGRICULTURE
BUDGET YEAR : 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Construction of Mid Level Produce Hub at Idi Oro, Mushin (Balance Payment) | MOA/W/ICB/001/21 | 1 | 940000000 | >500M | ICB | BOQ | Post | Plan | Prior | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-04-19 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-19 |  | 2021-05-26 | 2021-06-02 | 2021-06-16 | 2022-08-18 | 2023-02-18
[9 empty] | Actual |  | 2021-06-30 | 2021-07-01 | 2021-07-23 | 2021-08-06 | 2021-08-10 | 2021-08-12 | 2021-06-20 | 2021-08-18 |  | 2021-08-18 | 2021-08-18 | 2021-10-04
2 | Establishment of Poultry Pens at the Food Produc tion Centre, Badagry (Balance Payment) | MOA/W/NCB/001/20 | 1 | 125000000 | >50M | NCB | BOQ | Post | Plan | Prior | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2021-04-29 |  | 2021-05-06 | 2021-05-13 | 2021-05-27 | 2022-06-21 | 2022-12-21
[9 empty] | Actual |  | 2021-09-15 | 2021-09-23 | 2020-10-02 | 2020-10-09 | 2020-10-22 | 2020-10-16 | 2020-08-05 | 2020-11-03 |  | 2020-11-02 | 2020-11-02 | 2020-11-13
| TOTAL |  |  | 1,065,000,000.00 |  |  |  |  | Plan
Actual