## GOODS
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: MINISTRY OF HEALTH
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Animals and Bags of Pellets for Laboratory Testing | LSMH/G/NS/001/22 |  |  | 482343.75 | <10M | NS | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
2 | Procurement of ceremonial Outfits for Occupational Health and Safety enforcement Officers | LSMH/G/NS/002/22 |  |  | 241171.88 | <10M | NS | Post | Post | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
3 | Procurement of Motor Parts | LSMH/G/NS/003/22 |  |  | 2806891.08 | <10M | NS | Post | Post | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
4 | Procurement of Stationeries | LSMH/G/NS/004/22 |  |  | 4212900 | <10M | NS | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
5 | Miscellaneous Expenses | LSMH/G/NS/005/22 |  |  | 9397407.996 | <10M | NS | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
6 | Purchase of electrical materials, Taps, Keys and Tools | LSMH/G/NS/006/22 |  |  | 2434109.17 | <10M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
7 | Printing of official documents i.e. Letter Head papers, Complementary cards, and operational tools | LSMH/G/NS/007/22 |  |  | 4550702.97 | <10M | NS | Post | Post | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
8 | Procurement and installation Screen Project for GMO | LSMH/G/NS/008/22 |  |  | 2500000 | <10M | NS | Post | Post | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
9 | Procurement of Books and Goods for Library purposes | LSMH/G/NS/009/22 |  |  | 7989132.06 | <10M | NS | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
10 | Procurement for Games and Sport | LSMH/G/NS/010/22 |  |  | 1078543.76 | <10M | NS | Post | Post | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
11 | Procurement Unit Expenses | LSMH/G/NS/011/22 |  |  | 1730000.04 | <10M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
12 | Procurement of tools and Consumables for ICT Unit | LSMH/G/NS/012/22 |  |  | 2519529.2 | <10M | NS | Post | Post | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
13 | Procurement of Consumables and equipment for Public Affairs Unit | LSMH/G/NS/013/22 |  |  | 5680360 | <10M | NS | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
14 | Planning Unit Expenses | LSMH/G/NS/014/22 |  |  | 2819029.69 | <10M | NS | Post | Post | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
15 | Procuremnt of (MIS) computer accessories / consumables / flash drives etc | LSMH/G/NS/015/22 |  |  | 4010655.24 | <10M | NS | Post | Post | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
16 | Legal Unit Expenses | LSMH/G/NS/016/22 |  |  | 650000 | <10M | NS | Post | Post | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
17 | Audit Unit Expenses | LSMH/G/NS/017/22 |  |  | 2222400 | <10M | NS | Post | Post | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
18 | Procurement of equipment for Lagos State Medical Stores: Procurement & Installation of Twelve (12) Solar Powered Security Light | LSMH/G/NS/018/22 |  |  | 9576082.12 | <10M | NS | Post | Post | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
19 | Printing of store documents such as SRV, Ledgers, Receipt Vouchers, Requisition Vouchers, Bin Cards | LSMH/G/NS/019/22 |  |  | 1523295.93 | <10M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
20 | Purchase of Eye consumables, eye drugs and lenses for Alausa Eye Clinic @ N905,000.00/month | LSMH/G/NS/021/22 |  |  | 11340292.08 | <50M | NS | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
21 | Procurement of AIDS Materials / HIV Test Kits | LSMH/G/NCB/017/22 |  |  | 62500000.76 | <100M | NCB | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
22 | Procurement and Integrated Last Mile Distribution (ILMD) of Family Planning commodities using a 3PL with Community Based Distribution of FP commodities | LSMH/G/NCB/018/22 |  |  | 70000000.02 | <100M | NCB | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
23 | Procurement of Laboratory reagents and materials for fluorescent microscopy | LSMH/G/NS/024/22 |  |  | 15800000 | <50M | NS | Post | Post | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
24 | Procurement of Uniforms & Protective Outfits | LSMH/G/NS/025/22 |  |  | 21580281.24 | <50M | NS | Post | Post | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
25 | Provision and supply of Drugs and consunmables for Rehabilitation of Majidun Rehabilitation Centre, Ikorodu | LSMH/G/NS/026/22 |  |  | 21770800 | <50M | NS | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
26 | Procurement of Life Support Kits for LASAMBUS operation | LSMH/G/NS/027/22 |  |  | 39775000 | <50M | NS | Post | Post | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
27 | Procurement of HMIS Consumables | LSMH/G/NS/028/22 |  |  | 12214000 | <50M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
28 | Procurement & Installation of vision corridor bill board in 499 public state junior and senior secondary schools | LSMH/G/NS/029/22 |  |  | 14000000 | <50M | NS | Post | Post | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
29 | Lagos State Medical Stores Expenses (Goods) | LSMH/G/NCB/019/22 |  |  | 65388594 | <100M | NCB | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
30 | Procurement of e-Health Sector Tool Kit | LSMH/G/NS/031/22 |  |  | 45000000 | <50M | NS | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
31 | Production of key messege booklet on child health , procurement of drugs & consumables, hearing aids and audiometers | LSMH/G/NS/032/22 |  |  | 19190900 | <50M | NS | Post | Post | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
32 | Procurement of drugs, consumables and equipment for Staff Health Services (Goods) | LSMH/G/NCB/020/22 |  |  | 51411276.95 | <100M | NCB | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
33 | Procurement of Vehicle | LSMH/G/NS/034/22 |  | 1 | 32443257.1 | <50M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
34 | PROCUREMENT OF GOODS for State Environmental Health Monitoring Unit (SEHMU) | LSMH/G/NS/035/22 |  |  | 46964852.9863 | <50M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
35 | Procuement and distribution of Ready to Use Therapeutic Food (RUTF), Ready to Use Supplementary Food (RUSF) and Mincronutrients Powder (MNP) for under-5 and school-aged children | LSMH/G/NCB/021/22 |  |  | 56827574.41 | <100M | NCB | Post | Post | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
36 | Printing of newly revised NHMIS tools Version 2019 | LSMH/G/NS/037/22 |  |  | 15000000 | <50M | NS | Post | Post | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
37 | Procurement of Medical Equipments for LASAMBUS Operations | LSMH/G/NS/038/22 |  |  | 58084681.12 | <100M | NCB | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
38 | Procurement of Items for PHARMACEUTICAL INSPECTORATE UNIT | LSMH/G/NS/039/22 |  |  | 11500000 | <50M | NS | Post | Post | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
39 | Procurement of Equipment of Drug Quality Control Laboratory (DQCL) Ikeja | LSMH/G/NS/040/22 |  |  | 37318160.5 | <50M | NS | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
40 | Procurement of specialised eye equipment in 9 secondary eye care centres, 1 tertiary and BPP unit | LSMH/G/NCB/022/22 |  |  | 90000000 | <100M | NCB | Post | Post | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
41 | Procurement of Medical Equipment for the Prevention of Blindness/Special HEALTH Projects | LSMH/G/NCB/023/22 |  |  | 70000000 | <100M | NCB | Post | Post | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
42 | Procurement of Chemicals and Reagents | LSMH/G/NS/043/22 |  |  | 33663079.1 | <50M | NS | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
43 | Procurement of Materials and consumables for CANCER Control | LSMH/G/NS/044/22 |  |  | 25656237.78 | <50M | NS | Post | Post | Plan | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
44 | Procurement of Sickle Cell Diseases RTD kit for eligible new borns | LSMH/G/NS/045/22 |  |  | 45000000 | <50M | NS | Post | Post | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
45 | Procurement of test kits and vaccines for HEPATIS Control | LSMH/G/NS/046/22 |  |  | 40000000 | <50M | NS | Post | Post | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
46 | Procurement of Fuel for LASAMBUS Operations (Petrol & Diesel) | LSMH/G/NCB/001/22 |  |  | 171796336 | <500M | NCB | Prior | Prior | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
47 | Preparedness for Prevention of Emergency/Epidemic Diseases Outbreak (GOODS) | LSMH/G/NCB/002/22 |  |  | 200000000 | <500M | NCB | Prior | Prior | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
48 | Procurement/Installation of 500KVA Generators and inveters for five State Health Facilities | LSMH/G/NCB/003/22 |  |  | 330000000 | <500M | NCB | Prior | Prior | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
49 | Medical Equipment Leasing Scheme | LSMH/G/NCB/004/22 |  |  | 300000000 | <500M | NCB | Prior | Prior | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
50 | Sponsorship Expenses | LSMH/G/NCB/005/22 |  |  | 157000000 | <500M | NCB | Prior | Prior | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
51 | Procurement of Medical Equipments for Hospital Units | LSMH/G/NCB/006/22 |  |  | 601708084 | >500M | NCB | Prior | Prior | Plan | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
52 | Procurement of Furniture for Newly Constructed and Renovated Facilities | LSMH/G/NCB/007/22 |  |  | 400000000 | <500M | NCB | Prior | Prior | Plan | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-04-07 | 2022-04-14 | 2022-04-21 | 2022-04-28 | 2022-05-05 |  | 2022-05-12 | 2022-05-26 | 2022-06-09
Actual
53 | Procurement of Equipment for Occupational Health and Safety/Staff Health Services | LSMH/G/NCB/008/22 |  |  | 107156975.61 | <500M | NCB | Prior | Prior | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
54 | Procurement of 4 Wheel Drive Vehicle | LSMH/G/NCB/009/22 |  | 3 | 108000000 | <500M | NCB | Prior | Prior | Plan | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
55 | Procument of Boat Ambulance and accessories | LSMH/G/NCB/010/22 |  | 1 | 399529522.67 | <500M | NCB | Prior | Prior | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
56 | Malarial Commodities | LSMH/G/NCB/011/22 |  |  | 442000000 | <500M | NCB | Prior | Prior | Plan | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
57 | Procurement of Drugs, Medical Consumables, and Medical Equipment for PUBLIC HEALTH PROJECT (DDC, FHN) | LSMH/G/NCB/012/22 |  |  | 745216338.17 | >500M | NCB | Prior | Prior | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
58 | Procurement of Office Equipment | LSMH/G/NCB/013/22 |  |  | 302374329.33 | <500M | NCB | Prior | Prior | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
59 | Preparedness for Public Epidemics Health | LSMH/G/NCB/014/22 |  |  | 950000000 | >500M | NCB | Prior | Prior | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
60 | Expansion/Acquisition of Property for Hospitals | LSMH/G/NCB/015/22 |  |  | 1949109200 | >500M | NCB | Prior | Prior | Plan | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
61 | DEDICATED EXPENDITURE: Miscellaneous Expenses on Epidemics | LSMH/G/NCB/016/22 |  |  | 3320000000 | >500M | NCB | Prior | Prior | Plan | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
Plan
Actual
Plan
Actual

## WORKS
PROCUREMENT PLAN FOR WORKS
MINISTRY: MINISTRY OF HEALTH
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Upgrading of the library facility in the Ministry of Haelth | LSMH/W/NS/001/22 |  | 10000000 | <50M | NS | BOQ | Post | Plan | Post | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
2 | Rehabilation of Lagos State Medical Stores | LSMH/W/NCB/025/22 |  | 91000000 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
3 | Construction of Additional Ambulance Point Cubicles | LSMH/W/NS/002/22 |  | 22500000 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
4 | Rehabilitation of the Laboratory: (General works, Electrical, Carpentary & plumbing, Painting, Tiling etc) | LSMH/W/NS/003/22 |  | 20000000 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
5 | Renovation of Ebutte Metta | LSMH/W/NCB/026/22 |  | 78381250.65 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
6 | Completion of the Renovation /Upgrading of Epe General Hospital,Epe. | LSMH/W/NS/004/22 |  | 40807788.21 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
7 | Remodeling and Upgrading of Gbagada General Hospital Gbagada. | LSMH/W/NCB/027/22 |  | 77470307.68 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
8 | Remodeling and Upgrading of Orile -Agege General Hospital Orile - Agege. | LSMH/W/NCB/028/22 |  | 66449054.1 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
9 | Completion of the Construction of Four Storey Faculty of Basic Medical Sciencies Office Block (LASUCOM) | LSMH/W/NCB/029/22 |  | 66166526.27 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
10 | Renovation of Badagry General Hospital | LSMH/W/NCB/030/22 |  | 62506960.71 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
11 | Provision of CCTV in 14 General Hospitals | LSMH/W/NS/005/22 |  | 23277942 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
12 | Completion of road network, drainage facility and fencing of mortuary at the Mainland Hospital, Yaba | LSMH/W/NS/006/22 |  | 3687185.96 | <10M | NS | BOQ | Post | Plan | Post | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
13 | Construction of perimeter fencing of Massey Street Children's Hospital at Lagos Island | LSMH/W/NCB/030/22 |  | 57060103.02 | <100M | NCB | BOQ | Prior | Plan | Prior | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
14 | Upward Review of Construction of Sewage Treatment Plant at General Hospital, Lagos | LSMH/W/NS/007/22 |  | 23940292.6 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-03 | 2022-05-10 |  | 2022-05-17 | 2022-05-31 | 2022-06-21
Actual
15 | Renovation of Staff Quarters at Ikorodu GH (1) Contract A | LSMH/W/NS/008/22 |  | 21730250.28 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-28 | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
16 | Renovation of Staff Quarters at Ikorodu GH (Contract B) | LSMH/W/NS/009/22 |  | 23200000 | <50M | NS | BOQ | Prior | Plan | Prior | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
17 | Renovation of offices ( all offices) | LSMH/W/NCB/001/22 |  | 138291690.25 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
18 | Renovation of General Hospital, Isolo | LSMH/W/NCB/002/22 |  | 276042345.39 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
19 | Renovation of Harvey Road Health Centre, Yaba. | LSMH/W/NCB/003/22 |  | 108575144.08 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
20 | Renovation of Mushin General Hospital. | LSMH/W/NCB/004/22 |  | 520021342.26 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
21 | Rehabilitaion of Ibeju Lekki General Hospital | LSMH/W/NCB/005/22 |  | 500000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
22 | Re-award of Renovation of Ifako-Ijaiye General Hospital | LSMH/W/NCB/006/22 |  | 577937550.33 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
23 | Renovation/Expansion of Ajeromi General Hospital. | LSMH/W/NCB/007/22 |  | 620021342.26 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-01-19 | 2022-01-26 | 2022-02-02 | 2022-02-16 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 |  | 2022-03-30 | 2022-04-13 | 2022-04-27
Actual
24 | Renovation of Staff Quarters, General Hospital, Badagry | LSMH/W/NCB/008/22 |  | 38000000 | <50M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
25 | Construction of Traditional Medicine Board | LSMH/W/NCB/009/22 |  | 759683723.03 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-01-19 | 2022-01-26 | 2022-02-02 | 2022-02-16 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 |  | 2022-03-30 | 2022-04-13 | 2022-04-27
Actual
26 | Rehabilitation & Upgrading of General Hospital Lagos | LSMH/W/NCB/009/22 |  | 266329291.79 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-01 | 2022-02-08 | 2022-02-15 | 2022-03-08 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 |  | 2022-04-26 | 2022-05-03 | 2022-05-24
Actual
27 | Contract for early Works( Pilling Foundation) Stage of Construction for the Massey Street 130 Bed Children Hospital along Adeniyi Adele Road, Lagos Island, Lagos State | LSMH/W/NCB/010/22 |  | 177373363.5 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-01-19 | 2022-01-26 | 2022-02-02 | 2022-02-16 | 2022-03-02 | 2022-03-09 | 2022-03-16 | 2022-03-23 |  | 2022-03-30 | 2022-04-13 | 2022-04-27
Actual
28 | Expansion/Rehabilitation of Onikan Health Centre | LSMH/W/NCB/011/22 |  | 300000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
29 | Construction of Doctors Quarters LASUTH | LSMH/W/NCB/012/22 |  | 400000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
30 | Completion of Psychiatric Ward in LASUTH | LSMH/W/NCB/013/22 |  | 100000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
31 | Perimeter Fencing of State Health Facilities | LSMH/W/NCB/014/22 |  | 125000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
32 | Construction of Ambulance bases in G.H Lagos N40M , LASUTH N42.8M, G.H. Ikorodu N39M and G.H. Badagry N45M | LSMH/W/NCB/015/22 |  | 167000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
33 | Construction of Ambulance Point 10 @ N22M | LSMH/W/NCB/016/22 |  | 220000000 | <500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
34 | Construction of Oncology Centre at Gbagada GH | LSMH/W/NCB/017/22 |  | 2437665092.42 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
35 | Construction of New Massey Children Hospital | LSMH/W/NCB/018/22 |  | 2772372720.48 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-04 | 2022-02-11 | 2022-02-25 | 2022-03-18 | 2022-03-25 | 2022-04-08 | 2022-04-08 | 2022-04-08 |  | 2022-04-22 | 2022-05-06 | 2022-05-20
Actual
36 | Management & Maintenance of Health facilities | LSMH/W/NCB/019/22 |  | 1000000000 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
37 | Construction of Infectious Disease Research Centre, Yaba | LSMH/W/NCB/020/22 |  | 1100000000 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
38 | Construction & Equipping of Psychiatric Hospital, Ketu Ejirin | LSMH/W/NCB/021/22 |  | 2577740858.14 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
39 | Construction of 280 Bed General Hospital in Ojo | LSMH/W/NCB/022/22 |  | 2498291916 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-14 | 2022-03-21 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-06 | 2022-06-27
Actual
40 | Maintenance of Health Facilities | LSMH/W/NCB/023/22 |  | 1234674579.38 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-04-28 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 |  | 2022-06-02 | 2022-06-16 | 2022-06-30
Actual
41 | Expansion/Rehabilitation & Equipping of shomolu General Hospital | LSMH/W/NCB/024/22 |  | 1139850214.84 | >500M | NCB | BOQ | Prior | Plan | Prior | 2022-02-14 | 2022-02-21 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 |  | 2022-04-18 | 2022-04-25 | 2022-05-09
Actual
42 | [8 empty] | Plan
Actual

## CONSULTANCY
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY: MINISTRY OF HEALTH
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Pre-requisities for construction and renovation works in the Lagos State Health facilities (Drone shots, Topography survey, Soil test analysis and Integrity test | LSMH/S-C/LCS/002/22 | LCS | Lumpsum | 30000000 | Proir | Plan | 2022-01-28 | 2022-02-04 | 2022-02-04 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  | 2022-06-03 | 2022-06-17 | 2022-07-01 | 2022-07-15 | 2022-07-29
Actual
2 | Proposal of setting up 2 (two) additional secondary eye care units in the state. | LSMH/S-C/LCS/003/2 | LCS | Lumpsum | 148901272.69 | Proir | Plan | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 |  | 2022-07-05 | 2022-07-19 | 2022-08-02 | 2022-08-09 | 2022-08-16
Actual
3 | Consulting Services on all embarked projects and meetings and Technical assistance for Program Managers | LSMH/S-C/FBS/001/22 | FBS | Lumpsum | 100000000 | Proir | Plan | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 |  | 2022-05-30 | 2022-06-13 | 2022-06-27 | 2022-07-11 | 2022-07-25
Actual
4 | Architectural Design for rehabilitation of hospitals | LSMH/S-C/QBS/001/22 | QBS | Lumpsum | 300000000 | Proir | Plan | 2022-02-24 | 2022-03-10 | 2022-03-17 | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-21 | 2022-08-04 | 2022-08-11 | 2022-08-18
Actual
5 | Electronic Medical Records (EMR) Development | LSMH/S-C/QBS/002/22 | QBS | Lumpsum | 92950000 | Proir | Plan | 2022-01-28 | 2022-02-04 | 2022-02-04 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  | 2022-06-03 | 2022-06-17 | 2022-07-01 | 2022-07-15 | 2022-07-29
Actual
6 | Establishment of new Cancer Registries | LSMH/S-C/CQS/001/22 | QCS | Lumpsum | 12000000 | Proir | Plan | 2022-02-24 | 2022-03-10 | 2022-03-17 | 2022-03-31 | 2022-04-07 | 2022-04-14 | 2022-05-05 | 2022-05-12 | 2022-05-19 | 2022-05-26 | 2022-06-09 | 2022-06-16 | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-21 | 2022-08-04 | 2022-08-11 | 2022-08-18
Actual
7 | Cancer and Infectious Disease Research | LSMH/S-C/QCBS/001/22 | QCBS | Lumpsum | 190000000 | Proir | Plan | 2022-01-28 | 2022-02-04 | 2022-02-04 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 |  | 2022-06-03 | 2022-06-17 | 2022-07-01 | 2022-07-15 | 2022-07-29
Actual
8 | International Disease/ Surveillance | LSMH/S-C/QCBS/002/22 | QCBS | Lumpsum | 1039646766.3 | Proir | Plan | 2022-02-22 | 2022-03-08 | 2022-03-15 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-05-03 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 |  | 2022-07-05 | 2022-07-19 | 2022-08-02 | 2022-08-09 | 2022-08-16
Actual
Plan
Actual

## NON-CONS SERV
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
PROCUREMENT PLAN FOR NON-CONSULTING SERVICES
MINISTRY/ AGENCY: MINISTRY OF HEALTH
BUDGET YEAR: 2022
| Contract Description | BASIC DATA | [7 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
SN |  | Package Number |  | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
1 | Repairs/Maintenance of damaged windows, doors and locks etc. | LSMH/S-NC/DC/001/22 |  |  |  | 2277384 | <10M | DC | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
2 | Repairs/Maintenance of 101Nos. Vehicles of the Ministry | LSMH/S-NC/DC/002/22 |  |  |  | 2806917.96 | <10M | DC | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
3 | Servicing of vehicles | LSMH/S-NC/DC/003/22 |  |  |  | 2806917.96 | <10M | DC | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
4 | Promotion and advocacy for the activities | LSMH/S-NC/DC/004/22 |  |  |  | 1038531.23 | <10M | DC | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
5 | Preparation of Personnel Budget & defense at METP Business Process Documents | LSMH/S-NC/DC/005/22 |  |  |  | 1607811.47 | <10M | DC | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
6 | Payement of volunteer doctors, Ophtaimic nurses, Optometrists and support sfaff | LSMH/S-NC/DC/006/22 |  |  |  | 1447031.2 | <10M | DC | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
7 | Payment of water rates, electricity and recharge cards for HC, PS and Directors | LSMH/S-NC/DC/007/22 |  |  |  | 2977078 | <10M | DC | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
8 | Logistics Management Coordinating Unit (LMCU) | LSMH/S-NC/DC/008/22 |  |  |  | 4019581.28 | <10M | DC | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
9 | Organize quarterly Hosting of Health Policy Group Meeting | LSMH/S-NC/DC/009/22 |  |  |  | 2500000 | <10M | DC | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
10 | Advertisement for Procurement of Goods, Works & Services | LSMH/S-NC/NS/001/22 |  |  |  | 5490000 | <10M | NS | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
11 | Repair / servicing of computer systems (MIS) | LSMH/S-NC/NS/002/22 |  |  |  | 8000000 | <10M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
12 | Maintenance of Specialised Eye Equipment | LSMH/S-NC/NS/003/22 |  |  |  | 8039059.45 | <10M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
13 | Fuelling of 101 Nos. Vehicles of the Ministry | LSMH/S-NC/NS/004/22 |  |  |  | 5341203 | <10M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
14 | Maintenance/Repair of other office equipment. E.g. Air-conditioners, Fridges, etc. | LSMH/S-NC/NS/005/22 |  |  |  | 42445563.86 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
15 | Servicing of LASAMBUS MICU Ambulance, 3Mobile Clinics & 15 expected Ambulance Vehicles | LSMH/S-NC/NS/006/22 |  |  | 18 | 12096000 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
16 | Major Repairs of each Ambulance for 21 existing and 15 expected | LSMH/S-NC/NS/007/22 |  |  | 21 | 50400000 | <100M | NS | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
17 | Other Repairs | LSMH/S-NC/NS/008/22 |  |  |  | 14936888.67 | <50M | NS | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
18 | Special Duties Expenses | LSMH/S-NC/NS/009/22 |  |  |  | 66526913.09 | <100M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
19 | Expenses incurred by the SA/HC (Public Health Programs). | LSMH/S-NC/NS/010/22 |  |  |  | 10078118.8896 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
20 | Service of Meeting (PMB)/Task Force | LSMH/S-NC/NS/011/22 |  |  |  | 40527792.31 | <50M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
21 | Grant Management Office Activities | LSMH/S-NC/NS/012/22 |  |  |  | 87363000 | <100M | NS | Plan | Prior | Prior | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
22 | Control of Drug Abuse & celebration of Drug Abuse Day | LSMH/S-NC/NS/013/22 |  |  |  | 10311173.48 | <50M | NS | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
23 | Invitation of Medical experts to lecture on health and health related topics for the State Council on Health ( N20,000,000) | LSMH/S-NC/NS/014/22 |  |  |  | 20000000 | <50M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
24 | Conduct Health Sector Reform Law Review meetings (Residential and non-residential) | LSMH/S-NC/NS/015/22 |  |  |  | 25000000 | <50M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
25 | QUARTERLY REVIEW OF PERFORMANCE MANAGEMENT REPORT | LSMH/S-NC/NS/016/22 |  |  |  | 12128016 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
26 | Publicity and Press Coverage Activities | LSMH/S-NC/NS/017/22 |  |  |  | 70985447.49 | <100M | NS | Plan | Prior | Prior | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
27 | Publicity for Commemoration for 14Nos Special Health Days | LSMH/S-NC/NS/018/22 |  |  |  | 21000000 | <50M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
28 | Enlightenment Campaign (Hypertension & Diabetes) | LSMH/S-NC/NS/019/22 |  |  |  | 32173550.04 | <50M | NS | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
29 | Service Charter Expenses | LSMH/S-NC/NS/020/22 |  |  |  | 41733977.83 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
30 | Lagos State Medical Stores Expenses (Services) | LSMH/S-NC/NS/021/22 |  |  |  | 13320277.91 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
31 | e-HEALTH PROGRAMME | LSMH/S-NC/NS/022/22 |  |  |  | 30000000 | <50M | NS | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
32 | Staff Health Services Expenses (Actities) | LSMH/S-NC/NS/023/22 |  |  |  | 17600000 | <50M | NS | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
33 | Monitoring and Evaluation | LSMH/S-NC/NS/024/22 |  |  |  | 40014885 | <50M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
34 | Occupational Health and Safety Activities | LSMH/S-NC/NS/025/22 |  |  |  | 37618084.34 | <50M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
35 | Blindness Prevention Services | LSMH/S-NC/NS/026/22 |  |  |  | 34000000 | <50M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
36 | AIDS / HIV Control Activities | LSMH/S-NC/NS/027/22 |  |  |  | 28007771 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
37 | TB / Leprosy Control Programme | LSMH/S-NC/NS/028/22 |  |  |  | 84827061.92 | <100M | NS | Plan | Prior | Prior | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
38 | NUTRITION (Control of Diarrhoea) | LSMH/S-NC/NS/029/22 |  |  |  | 36927000 | <50M | NS | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
39 | Non-Communicable Diseases Interventions: CANCER & SICKLE CELL DISEASES | LSMH/S-NC/NS/030/22 |  |  |  | 35500000 | <50M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
40 | Non-Communicable Diseases Interventions: HEPATITIS CONTROL | LSMH/S-NC/NS/031/22 |  |  |  | 15598935.98 | <50M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
41 | Service Quality Improvemnet (Cardiac & Renal Centre) DPRS | LSMH/S-NC/NS/032/22 |  |  |  | 13972702.45 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
42 | Procurement of Drugs, Medical Consumables & Phones for 36 MICU Ambulamnces | LSMH/S-NC/NS/033/22 |  |  |  | 88775000 | <100M | NS | Plan | Prior | Prior | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
43 | Maintenance of LASAMBUS 2-way Radio | LSMH/S-NC/NS/034/22 |  |  |  | 11225000 | <50M | NS | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
44 | ANNUAL RETREAT Retreat for Ministry's Staff on Grade level 1- 10 | LSMH/S-NC/NS/035/22 |  |  |  | 10000000 | <50M | NS | Plan | Post | Post | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
45 | ANNUAL RETREAT Retreat for Ministry's Staff on Grade level 12- 17 | LSMH/S-NC/NS/036/22 |  |  |  | 15000000 | <50M | NS | Plan | Post | Post | 2022-03-11 | 2022-03-18 | 2022-04-01 | 2022-04-22 | 2022-04-29 | 2022-04-29 | 2022-04-29 | Plan | 2022-05-06 | 2022-05-13 |  | 2022-05-20 | 2022-06-03 | 2022-06-24
[9 empty] | Actual | [9 empty] | Actual
46 | Preparedness for Prevention of Emergency/Epidemic Diseases Outbreak (SERVICES) | LSMH/S-NC/NS/037/22 |  |  |  | 50000000 | <100M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
47 | Maintenance/Management and Running of the School of Anaesthesia | LSMH/S-NC/NS/038/22 |  |  |  | 49999999.9999 | <100M | NS | Plan | Post | Post | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
48 | Retreat and Training for HMIS PROJECT | LSMH/S-NC/NS/039/22 |  |  |  | 40464184.81 | <50M | NS | Plan | Post | Post | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
49 | Medical Research Activities | LSMH/S-NC/NS/040/22 |  |  |  | 40286445.74 | <50M | NS | Plan | Post | Post | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
50 | 2 rounds of Maternal Newborn, Child and Adolescent Health Week Statewide | LSMH/S-NC/NCB/001/22 |  |  |  | 100000000 | <500M | NCB | Plan | Prior | Prior | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
51 | CHILD & ADOLESCENT HEALTH (IMMUNISATION PROGRAMME) | LSMH/S-NC/NCB/001/22 |  |  |  | 262546098.85 | <500M | NCB | Plan | Prior | Prior | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
52 | FAMILY PLANNING/REPRODUCTIVE HEALTH | LSMH/S-NC/NCB/002/22 |  |  |  | 161429374.51 | <500M | NCB | Plan | Prior | Prior | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
53 | MENTAL HEALTH PROGRAMME | LSMH/S-NC/NCB/003/22 |  |  |  | 190458251.15 | <500M | NCB | Plan | Prior | Prior | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
54 | Health Financing Unit | LSMH/S-NC/NCB/004/22 |  |  |  | 123801513.6 | <500M | NCB | Plan | Prior | Prior | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
55 | Roll Back Malaria Activities | LSMH/S-NC/NCB/005/22 |  |  |  | 297515339.76 | <500M | NCB | Plan | Prior | Prior | 2022-04-21 | 2022-04-28 | 2022-05-12 | 2022-05-26 | 2022-06-02 | 2022-06-09 | 2022-06-16 | Plan | 2022-06-23 | 2022-06-30 |  | 2022-07-07 | 2022-07-14 | 2022-07-21
[9 empty] | Actual | [9 empty] | Actual
56 | e-Health Platform Activities | LSMH/S-NC/NCB/006/22 |  |  |  | 202967440 | <500M | NCB | Plan | Prior | Prior | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-23 | Plan | 2022-05-30 | 2022-06-06 |  | 2022-06-13 | 2022-06-27 | 2022-07-25
[9 empty] | Actual | [9 empty] | Actual
57 | Preparedness for Prevention and Treatment of Epidemic Diseases Outbreak. | LSMH/S-NC/NCB/007/22 |  |  |  | 4118285119 | >500M | NCB | Plan | Prior | Prior | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
58 | Celebration and Ceremonies | LSMH/S-NC/NCB/008/22 |  |  |  | 117744256.49 | >500M | NCB | Plan | Prior | Prior | 2022-04-05 | 2022-04-12 | 2022-04-26 | 2022-05-17 | 2022-05-24 | 2022-05-31 | 2022-06-07 | Plan | 2022-06-14 | 2022-06-21 |  | 2022-06-28 | 2022-07-12 | 2022-07-26
[9 empty] | Actual | [9 empty] | Actual
59 | Quantification & Forecasting of Public Health Product and Capacity Building | LSMH/S-NC/NS/041/22 |  |  |  | 32156237.28 | <50M | NS | Plan | Prior | Prior | 2022-03-02 | 2022-03-16 | 2022-03-23 | 2022-04-13 | 2022-04-20 | 2022-04-27 | 2022-05-04 | Plan | 2022-05-11 | 2022-05-18 |  | 2022-05-25 | 2022-06-08 | 2022-06-29
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual
[9 empty] | Plan | [9 empty] | Plan
[9 empty] | Actual | [9 empty] | Actual

## NON-PROC ITEMS
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: MINISTRY OF HEALTH
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
1 | Transport cost on official duties outside the Secretariat | LSMH/NP/NM/001/22 | 3373300 | Plan | 281108 | 281108 | 281108 | 281108 | 281108 | 281108 | 281108 | 281108 | 281108 | 281108 | 281108 | 281108
Actual
2 | Payment of allowance to NYSC and IT Staffs (MoH) | LSMH/NP/NM/002/22 | 1286250.01 | Plan | 107187 | 107187 | 107187 | 107187 | 107187 | 107187 | 107187 | 107187 | 107187 | 107187 | 107187 | 107187
Actual
3 | Payment of salary for 11 Janitors (i) Purchase of cleaning materials for 1 year | LSMH/NP/NM/003/22 | 8650258.96 | Plan | 720854 | 720854 | 720854 | 720854 | 720854 | 720854 | 720854 | 720854 | 720854 | 720854 | 720854 | 720854
Actual
4 | Salaries for Security Services | LSMH/NP/NM/004/22 | 1041861.76 | Plan | 86821 | 86821 | 86821 | 86821 | 86821 | 86821 | 86821 | 86821 | 86821 | 86821 | 86821 | 86821
Actual
5 | Fuelling, Servicing and Maintenance of Generators in the Ministry @ 250/L for approximately 27times | LSMH/NP/NM/005/22 | 10773649.43 | Plan
Actual
6 | Medical Refund | LSMH/NP/NM/006/22 | 80390592.38 | Plan
Actual
7 | Overseas Medical and Surgical Treatment Expenses that cannot be treated locally. | LSMH/NP/NM/007/22 | 160781186.84 | Plan
Actual
8 | Free Health Programme | LSMH/NP/NM/008/22 | 625168625.76 | Plan
Actual
9 | Payment of Outstanding Liability | LSMH/NP/NM/009/22 | 2033325257 | Plan
Actual
10 |  |  |  | Plan
Actual

## TRAIN-CONF-WORK
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: MINISTRY OF HEALTH
BUDGET YEAR: 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Annual Conferences for Procurement Officers | LSMH/S-WTC/NPI/001/22 | CAPACITY DEVELOPMENT | 2 |  | Plan |  |  |  |  | 1450625
Actual
2 | Training of 10 Store Officers | LSMH/S-WTC/NPI/002/22 | CAPACITY DEVELOPMENT | 10 |  | Plan |  |  |  |  | 2000000
Actual
3 | Workshop & Training Expenses for ALL DIRECTORATES | LSMH/S-WTC/NPI/003/22 | CAPACITY DEVELOPMENT | 800 |  | Plan |  |  |  |  | 335707902.27
Actual
4 | Conferences & Seminar Expenses for ALL DIRECTORATES | LSMH/S-WTC/NPI/004/22 | CAPACITY DEVELOPMENT | 800 |  | Plan |  |  |  |  | 388331242.17
Actual
5 | Facilitating the State & Units Continuing Medical Education(CME) for healthcare workers | LSMH/S-WTC/NPI/005/22 | CAPACITY DEVELOPMENT | 110 |  | Plan |  |  |  |  | 24277959.59
Actual
6 | First Aid Defensive Driving Training for LASAMBUS Pilots | LSMH/S-WTC/NPI/006/22 | CAPACITY DEVELOPMENT | 30 |  | Plan |  |  |  |  | 8973854.72
Actual
7 | Specialised training for Healthcare Professionals | LSMH/S-WTC/NPI/007/22 | CAPACITY DEVELOPMENT | 50 |  | Plan |  |  |  |  | 36290103.05
Actual
8 | ALS Training for Nurses and Midwives | LSMH/S-WTC/NPI/008/22 | CAPACITY DEVELOPMENT | 30 |  | Plan |  |  |  |  | 11964122.81
Actual
9 | Capacity building of 300 participants from various MDAs (75),Health Professionals (75), teachers/school Administrators (150) in eight (8) trainings | LSMH/S-WTC/NPI/009/22 | CAPACITY DEVELOPMENT | 300 |  | Plan |  |  |  |  | 11350000
Actual
10 | Workshop & Training Expenses for HCPRS | LSMH/S-WTC/NPI/010/22 | CAPACITY DEVELOPMENT | 25 |  | Plan |  |  |  |  | 35966467.96
[6 empty] | Actual |  | C
11 | Workshop & Training Expenses for Planning & Budget Unit | LSMH/S-WTC/NPI/011/22 | CAPACITY DEVELOPMENT | 4 |  | Plan |  |  |  |  | 1770000.84
Actual
12 | Workshop & Training Expenses for HMIS Unit | LSMH/S-WTC/NPI/012/22 | CAPACITY DEVELOPMENT | 6 |  | Plan |  |  |  |  | 7385249.19
Actual
13 | Professional Conferences for 3 ICT Staff | LSMH/S-WTC/NPI/013/22 | CAPACITY DEVELOPMENT | 3 |  | Plan |  |  |  |  | 1500000
[6 empty] | Actual |  | C
14 | Workshop, Conference & Seminar for Public Affairs Unit | LSMH/S-WTC/NPI/014/22 | CAPACITY DEVELOPMENT | 4 |  | Plan |  |  |  |  | 1150000
Actual
15 | Training for Camera men and Photographers | LSMH/S-WTC/NPI/015/22 | CAPACITY DEVELOPMENT | 3 |  | Plan |  |  |  |  | 500000
Actual
16 | Local NBA Annual Conference | LSMH/S-WTC/NPI/016/22 | CAPACITY DEVELOPMENT | 1 |  | Plan |  |  |  |  | 388531.23
[6 empty] | Actual |  | C
17 | Professional Conference: ANAN & ICAN, MCPDE and development courses | LSMH/S-WTC/NPI/017/22 | CAPACITY DEVELOPMENT | 7 |  | Plan |  |  |  |  | 1797131.28
[6 empty] | Actual |  | C
Plan
[6 empty] | Actual |  | C
Plan
[6 empty] | Actual |  | C

## SIGN-OFF
LAGOS STATE MINISTRY OF HEALTH
YEAR 2022 PROCUREMENT PLANNING COMMITTEE
SIGN-OFF ON YEAR 2022 PROCUREMENT PLAN
SN | DIRECTOR/DIRECTORATE | SIGNATURE | DATE
1 | PERMANENT SECRETARY (LSMoH)
2 | Director, Pharmaceutical Services (DPS)
3 | Director, Admin and Human Resources (DA&HR)
4 | Director, Medical Admin, Training & Program (DMAT/P)
5 | Director, Family Health & Nutrition (DFHN)
6 | Director, Health Care, Planning, Research & Statistics (DHCPRS)
7 | Deputy Director, Finance & Accounts (DF&A)
8 | Director, Disease Control (DDC)
9 | Director, Occupational Health Service (OHS)
10 | Director, State Env. Health Service (SEHMU)
11 | Director, LASAMBUS (DLASAMBUS)
12 | Director, Nursing Services (DNS)
13 | Director, Epidemiology (DEPID)
14 | Director, Special Project & Mental Health (SPMH)
15 | Head, Public Affairs (HPAU)
16 | Head, Internal Audit (HIA)
17 | Head, Budget & Planning (HB&P)
18 | Head , ICT (HICT)
19 | Head Legal Unit (HLU)
20 | Head, Procurement (HPU)

## Sheet1 (hidden)
(5) Project Consulting Service and meetings on all embarked projects | 200000000 | C
(4) Pre-requisities activies for the construction and renovation works in the Lagos State Health facilities (Drone shots, Topography survey, soil test analysis and integrity test | 39879718.1 | C
(5) Cancer Registry = Establishment of Cancer Registry Training (Annual Cancer registry conference France @5,000,000 for 4 = | 20000000 | C
Cancer Research = 35,000,000 | 35000000 | C
(13)Provision of CCTV in 13 General Hospitals | 2455000 | G
(14) Provision of CCTV in 14 General Hospitals | 23277942 | G
(2) Acquisition of land for Orile Agege GH | 500000000 | G
(6)Procurement of 1Nos 18 seater Toyota Hiace bus for project monitoring | 35000000 | G
(7) Procurement of 1Nos project vehicle for GMO | 25000000 | G
(9) Acquisition of Land for Ajeromi G.H. | 140985595.97 | G
(6). Procurement/Installation of 10nos. 500KVA Generators and inverters for 10 health facilities @ N20,000,000.00= | 330000000 | G
7). Procurement of basic working equipment for PIU Team (lab-tops, printers, scanners etc. | 8500000 | G
(9) Research on Project management by PIU officers in Germany at 3 Million per officer X 10 officers = | 30000000 | NCS
Completion of the Construction of Maternal and Child Centre, Badagry. | 15565484.75 | W
Completion of the Construction of Maternal and Child Centre, Epe. | 24423069.63 | W
Completion of road network, drainage facility and fencing of mortuary at the Mainland Hospital, Yaba | 3687185.96 | W
Upward Review of Construction of Sewage Treatment Plant at General Hospital, Lagos | 23940292.6 | W
Renovation of Staff Quarters at Ikorodu GH (Contract A) | 21730250.28 | W
Renovation of Staff Quarters at Ikorodu GH Contract B | 23200000 | W
Completion of the Renovation /Upgrading of Epe General Hospital,Epe | 40807788.21 | W
Remodeling & Upgrading of Apapa General Hospital | 33255955.62 | W
Remodeling and Upgrading of Ikorodu General Hospital, Ikorodu | 40484699.6 | W
Remodeling and Upgrading of Gbagada General Hospital Gbagada. | 77470307.68 | W
Remodeling and Upgrading of Orile -Agege General Hospital Orile - Agege.66,449,054.1 | 66449054.1 | W
Completion of the Construction of Four Storey Faculty of Basic Medical Sciencies Office Block (LASUCOM) | 66166526.27 | W
Renovation of Badagry General Hospital | 62506960.71 | W
Repair of damaged works at MCC Amuwo Odofin | 13083840 | W
Rehabilitation & Uprading of GH Lagos with archtectural design | 900000000 | W
Expansion/Rehabilitation& Equipping of shomolu General Hospital | 876228907.92 | W
Expansion/Rehabilitation of Onikan Health Centre | 70492797.98 | W
Construction of Doctors Quarters LASUTH | 750000000 | W
Construction of psychiatry centre Ketu Ejinrin | 1500000000 | W
Completion of psychiatric ward in LASUTH | 25500000 | W
Construction and equipping of New Massey St Children Hospital | 2000000000 | W
Perimeter fencing of 10 health facilities | 417000000 | W
Construction Equipping of General Hospital Ojo | 1500000000 | W
Construction of Infectious Disease Research Centre, Yaba Mainland Hospital= | 2500000000 | W
Construction of Ambulance Bases GH Lagos-N40M, LASUTH N43.8M,GH Ikorodu N39M, GH Badagry- N45M (TOTAL-N167M) | 167000000 | W
Construction of ambulance points x10 @N22M- =N220M | 220000000 | W
Demolition, Design and Temporary accommodation of the State Traditional Medicine Board- | 119930065.53 | W