## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: HOUSING
BUDGET YEAR: 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Payment of Judgement Debt | MOH/NP/NM/001/22 | 50,000,000.00 | Plan
Actual
2 | Provision of Media Coverage | MOH/NP/NM/002/22 | 17,500,000.00 | Plan | JANUARY: 4375000; APRIL: 4375000; JULY: 4375000; OCTOBER: 4375000
Actual
3 | Provision of Allowances for Security (Back Up) | MOH/NP/NM/003/22 | 100000000 | Plan | JANUARY: 25000000; APRIL: 25000000; JULY: 25000000; OCTOBER: 25000000
Actual
4 | Posting of Letters to Allotees and Visitation to all Schemes | MOH/NP/NM/004/22 | 500,000.00 | Plan | JANUARY: 125000; APRIL: 125000; JULY: 125000; OCTOBER: 125000
Actual
5 | Provision of Special Duties Expenses (Staff Welfare; HOS Cup). | MOH/NP/NM/005/22 | 147,950,000.00 | Plan | JANUARY: 49316666.67; MAY: 49316666.67; SEPTEMBER: 49316666.67
Actual
6 | Travel & Transport | MOH/NP/NM/006/22 | 6,100,000.00 | Plan | JANUARY: 1525000; APRIL: 1525000; JULY: 1525000; OCTOBER: 1525000
Actual
7 | General Utilities Services | MOH/NP/NM/007/22 | 3,418,000.00 | Plan | JANUARY: 1139333.33; MAY: 1139333.33; SEPTEMBER: 1139333.33
Actual
8 | Exhibition & Trade | MOH/NP/NM/008/22 | 11,000,000.00 | Plan | JANUARY: 3000000; MAY: 4000000; SEPTEMBER: 4000000
Actual
9 | Publication and Documentation & production of quarterly/annual report from departments and units | MOH/NP/NM/009/22 | 34430000 | Plan | JANUARY: 11476666.67; JUNE: 11476666.67; SEPTEMBER: 11476666.67
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: HOUSING
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | Annual Professional Conference | MOH/S-WTC/SS/001/22 |  | 150 |  | Plan |  |  |  |  | 33815000
Actual
2 | Workshop & Training Allowance | MOH/S-WTC/SS/002/22 |  | 150 |  | Plan |  |  |  |  | 10530000
Actual
Plan
Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
BUDGET YEAR: 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[7 empty] | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
1 | Lagos State Estate Management Information System (LAGEMIS)(Phase 2 of the Digitalization of the Estate Dept. and PPSD) | MOH/S-C/QCBS/001/2022 | QCBS |  | 100000000 | Prior |  | 28th Jan. 2022 | 4th Feb. 2022 | 11th Feb. 2022 | 25th Feb.2022 | 1st Mar. 2022 | 8th Mar. 2022 | 22nd Mar.2022 | 29th Mar. 2022 | 5th Apr. 2022 | 10th Apr. 2022 | 15th Apr. 2022 | 19th Apr. 2022 | 11th May 2022 | 13th May 2022 |  | 20th May 2022 | 25th May 2022 | 8th June 2022 | 22nd June 2022 | 30th Jun. 2022 | 30th Nov. 2022
2 | Master Craftmen Projects | MOH/S-C/QCBS/002/2022 | QCBS |  | 84600000 | Prior | Plan | 28th Jan. 2022 | 4th Feb. 2022 | 11th Feb. 2022 | 25th Feb.2022 | 1st Mar. 2022 | 8th Mar. 2022 | 22nd Mar.2022 | 29th Mar. 2022 | 5th Apr. 2022 | 10th Apr. 2022 | 15th Apr. 2021 | 19th Apr. 2022 | 11th May 2022 | 13th May 2022 |  | 20th May 2022 | 25th May 2022 | 8th June 2022 | 22nd June 2022 | 30th Jun. 2022 | 30th Nov. 2022
Actual
3 | Retreat for Review & Evaluation of Strategy used and a way forward for Housing policy | MOH/S-C/QCBS/003/2022 | QCBS |  | 20000000 | Prior | Plan | 28th Jan. 2022 | 4th Feb. 2022 | 11th Feb. 2022 | 25th Feb.2022 | 1st Mar. 2022 | 8th Mar. 2022 | 22nd Mar.2022 | 29th Mar. 2022 | 5th Apr. 2022 | 10th Apr. 2022 | 15th Apr. 2022 | 19th Apr. 2022 | 11th May 2022 | 13th May 2022 |  | 20th May 2022 | 25th May 2022 | 8th June 2022 | 22nd June 2022 | 30th Jun. 2022 | 30th Nov. 2022
Actual
| Project Management Monitoring | MOH/NP/NM/004/22 | QCBS |  |  |  | Plan | 4th Feb. 2022 | 11thFeb. 2022 | 25th Feb. 2022 | 1st Mar. 2022 | 8th Mar. 2022 | 22nd Mar. 2022 | 29th Mar. 2022 | 5th Apr. 2022 | 10th Apr. 2022 | 15th Apr. 2022 | 19th Apr. 2022 | 11th May 2022 | 13th May 2022 | 20th May 2022 |  | 25th May 2022 | 8th Jun. 2022 | 22nd Jun. 2022 | 30th Jun. 2022 | 6th Jul. 2022 | 6th Dec. 2022
4 |  |  |  |  | 137478109 |  | Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
BUDGET YEAR: 2022
Contract Description | BASIC DATA | [8 empty] | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual | Pre-or Post Qualification | Prior or Post review | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
Miscelleneous(Servicing & Repair of Photoccopiers,A/C & Incidentals) | MOH/S-NC-F/NS/001/22 |  |  | 5102830 | <10M | NS | Plan | Post | Post | 2nd Mar. 2022 | 5th Mar. 2022 | 9th Mar. 2022 | 23rd Mar.2022 | 25th Mar.2022 | 27th Mar. 2022 | 17th Apr. 2022 | Plan | 21st Apr.2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 14th May, 2022 | 21st May 2022 | 21st Nov. 2022 | 30th Dec. 2022
[7 empty] | , | [9 empty] | Actual
Motor Vehicle Repair & Maintenance | MOH/S-NC-F/NS/002/22 |  |  | 3558150 | <10M | NS | Plan | Post | Post | 22th Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Jan. 2022 | 14th Jan. 2022 | 17th Jan. 2022 | 31st Jan. 2022 | Plan | 5th Feb. 2022 | 10th Feb. 2022 | 17th Feb. 2022 | 3rd Mar. 2022 | 10th Mar. 2022 | 20th Dec. 2022 | 30th Dec. 2022
[7 empty] | Actual | [9 empty] | Actual
Maintenance of Facilities(Posting of Letters to all allotees,visitation to all existing Hsg Ests.) | MOH/S-NC-F/NS/003/22 |  |  | 500000 | <10M | NS | Plan | Post | Post | 22th Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Jan. 2022 | 14th Jan. 2022 | 17th Jan. 2022 | 31st Jan. 2022 | Plan | 5th Feb. 2022 | 10th Feb. 2022 | 17th Feb. 2022 | 3rd Mar. 2022 | 10th Mar. 2022 | 20th Dec. 2022 | 30th Dec. 2022
[7 empty] | Actual | [9 empty] | Actual

## goods
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: HOUSING
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | Procurement of Book Shelves, File cabinet work stations, chairs, Tables, Fire proof cabinets, Fire equipments and registry partitioning. | MOH/G/NS/001/22 | Lot 1 |  | 37432120 | < 50 M | N/S | Post | Prior | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual
2 | Procurement of Television Sets, Refrigerators, Recheargeable Fans and Shreading Machine and repair and servicing of Air Conditioners. | MOH/G/NS/002/22 | Lot 2 |  | 10162689.82 | < 50 M | N/S | Post | Post | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual
3 | Procurement of Test Kit, Tools, Equipment, PPSD Tools & equipments and Drawing Office Materials | MOH/G/NS/003/22 | Lot 3 |  | 25951500 | < 50M | N/S | Post | Post | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual
4 | Procurement of Public Affairs Equipment(Digital Camera, HD7 Motion/Still Camera, Teleconferencing equipment) | MOH/G/NS/004/22 | Lot 4 |  | 21810999.18 | < 50 M | N/S | Post | Post | Plan | 22th Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Jan. 2022 | 14th Jan. 2022 | 17th Jan. 2022 | 31st Jan. 2022 | 3rd Feb. 2022 |  | 10th Feb. 2022 | 17th Feb. 2022 | 3rd Mar. 2022 | 10th Mar. 2022 | 20th Jan. 2023
Actual
5 | Procurement of Computer System, Equipment (HP Laptops, Desktop Systems,Photocopiers, UPS, Printers, External Hard Drive, Stabilizers, Cable port,Power pack) | MOH/G/NS/005/22 | Lot 5 |  | 26326735 | < 50 M | N/S | Post | Prior | Plan | 2nd Mar. 2022 | 5th Mar. 2022 | 9th Mar. 2022 | 23rd Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 | 17th Apr. 2022 | 20th Apr. 2022 |  | 23rd Apr. 2022 | 30th Apr. 2022 | 14th May, 2022 | 21st May 2022 | 21st Nov. 2023
Actual
6 | Procurement of Units Consumables for Procurement,ICT,Planning, Public Affairs, Auditor, SSA & Legal Units | MOH/G/NS/006/22 | Lot 6 |  | 38820000 | < 50 M | N/S | Post | Post | Plan | 22th Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Jan. 2022 | 14th Jan. 2022 | 17th Jan. 2022 | 31st Jan. 2022 | 3rd Feb. 2022 |  | 10th Feb. 2022 | 17th Feb. 2022 | 3rd Mar. 2022 | 10th Mar. 2022 | 20th Jan. 2023
Actual
7 | Procurement of Uniforms & Protectives for Drivers & Cleaners | MOH/G/NS/007/22 | Lot 7 |  | 1000000 | < 10 M | N/S | Post | Post | Plan | 22th Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Jan. 2022 | 14th Jan. 2022 | 17th Jan. 2022 | 31st Jan. 2022 | 3rd Feb. 2022 |  | 10th Feb. 2022 | 17th Feb. 2022 | 3rd Mar. 2022 | 10th Mar. 2022 | 20th Jan. 2023
Actual
8 | Procurement of Cleaning Materials (Janitorial Services) | MOH/G-F/NS/008/22 | Lot 8 |  | 2000000 | < 10 M | N/S | Post | Post | Plan | 22th Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Jan. 2022 | 14th Jan. 2022 | 17th Jan. 2022 | 31st Jan. 2022 | 3rd Feb. 2022 |  | 10th Feb. 2022 | 17th Feb. 2022 | 3rd Mar. 2022 | 10th Mar. 2022 | 20th Jan. 2023
Actual
9 | Procurement of Stationeries for all Depts & Units | MOH/G-F/NS/009/22 | Lot 9 |  | 6269420 | < 10 M | N/S | Post | Prior | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual
10 | Motor Vehicle Fuel Consumption | MOH/G-F/NS/010/22 | Lot 10 |  | 6161000 | < 10 M | N/S | Post | Post | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual
11 | Procurement of Special required items in the Hon. Commissioners & PS Office | MOH/G-F/NS/011/22 | Lot 11 |  | 25000000 | < 50 M |  | Post | Post | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual
12 | Refurbishment of Operational Vehicles | MOH/G-F/NS/013/22 | Lot 13 |  | 31500000 | < 50 M | N/S | Post | Post | Plan | 4th Feb. 2022 | 7th Feb. 2022 | 10th Feb. 2022 | 24th Feb.2022 | 2nd Mar. 2022 | 4th Mar. 2022 | 25th Mar. 2022 | 27th Mar. 2022 |  | 6th Apr. 2022 | 9th Apr. 2022 | 23rd Apr. 2022 | 30th Apr. 2022 | 30th Apr. 2023
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY: HOUSING
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [7 empty] | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification | Plan Vs Actual | Prior or Post Review | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
1 | NEW SCHEMES |  |  | 3500000000 | [6 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
A | EGAN-IGANDO CLUSTER II: BUILDING | MOH/W/ICB/001/2021 | LOT 1 | 1031957106.48 | > 500M | ICB | BOQ/BEME | Post | Plan | Prior | 13th Jan. 2022 | 17th Jan. 2022 | 20th Jan. 2022 | 3rd Feb. 2022 | 10th Feb. 2022 | 14th Feb. 2022 | 28th Feb. 2022 | 2nd Mar. 2022 |  | 5th Mar.2022 | 12th Mar.2022 | 19th Mar. 2022 | 29th Nov. 2022 | 27th Nov. 2023
Actual
B | IBESHE PHASE II: Building | MOH/W/ICB/002/2022 | LOT 2 | 1370000000 | > 500M | ICB | BOQ/BEME | Post |  | Prior | 13th Jan. 2022 | 17th Jan. 2022 | 20th Jan. 2022 | 3rd Feb. 2022 | 10th Feb. 2022 | 14th Feb. 2022 | 28th Feb. 2022 | 2nd Mar. 2022 |  | 5th Mar.2022 | 12th Mar.2022 | 19th Mar. 2022 | 29th Nov. 2022 | 27th Nov. 2023
Actual
C | IBESHE PHASE II: INFRASTRUCTURE | MOH/W/NCB/003/2022 | LOT 3 | 370000000 | < 500M | NCB | BOQ/BEME | Post | Plan | Prior | 6th Jan. 2022 | 10th Jan. 2022 | 13th Jan. 2022 | 24th Jan. 2022 | 31st Jan. 2022 | 3rd Feb. 2022 | 24th Feb. 2022 | 26th Feb. 2022 |  | 28th Feb. 2022 | 6th Mar. 2022 | 27th Mar.2022 | 27th Dec. 2022 | 8th Jun.2023
Actual
|  |  |  | 728042893.52 | >500M | NCB | BOQ/BEME | Post | Plan | Prior | 6th Jan. 2022 | 10th Jan. 2022 | 13th Jan. 2022 | 24th Jan. 2022 | 31st Jan. 2022 | 3rd Feb. 2022 |  |  |  |  | 6th Mar. 2022 | 27th Mar.2022 | 27th Dec. 2022 | 8th Jun.2023
D | EGAN-IGANDO CLUSTER II | MOH/W/NCB/004/2022 | LOT 4 | [5 empty] | Actual | [7 empty] | 24th Feb. 2022 | 26th Feb. 2022 |  | 28th Feb. 2022
2 | COMPLETION OF ON-GOING HOUSING ESTATE |  |  | 4261850275 |  |  |  |  | Plan
Actual
A | LagosHOMS Sangotedo Phase II (BOND)(MOH/W/ST/04/2019)Building | MOH/W/NCB/002/2022 |  | 758591500 | > 500M | NCB | BOQ/BEME | Post | Plan | Prior | [9 empty] | 30th Jan, 2021
[9 empty] | Actual |  | 31st Dec. 2020 | 6th Jan. 2021 | 6th Jan. 2021 | 13th Jan. 2021 | 20th Jan. 2021 | 24th Jan. 2021 | 26th Jan, 2021 | 27th Jan. 2021 | 749384967.23 |  | 6th Feb 2021 | 10th Feb. 2021 | 11th May 2021 | 30th Oct. 2023
B | LagosHOMS Gbagada 2B(MOH/W/NCB/02/16) Building | MOH/W/NCB/003/2022 |  | 73110507.94 | ˂ 100M | NCB | BOQ/BEME | Post | Plan | Prior | [8 empty] | 193205324.45 | 30th Jan, 2020
[9 empty] | Actual |  | 23rd Apr. 2019 | 23rd Apr. 2019 | 24th Apr. 2019 | 1st May 2019 | 21st May 2019 | 23rd May 2019 | 25th Jan 2020 | 26th Jan 2020 |  |  | 11th Feb. 2020 | 25th Feb. 2020 | 28th Feb. 2020 | 10th Nov. 2023
C | LagosHOMS Odo-Onosa (MOH/W/NCB/01/17) | MOH/W/NCB/004/2022 |  | 375483656.31 | ˂ 500M | NCB | BOQ/BEME | Post | Plan | Prior | 5th Feb 2018 | [5 empty] | 2nd Apr. 2018 |  |  | 28th Apr. 2018
[9 empty] | Actual |  |  | 12th Feb. 2018 | 19th Feb. 2018 | 26th Feb. 2018 | 12th Mar. 2018 | 19th Mar. 2018 |  | 23rd Apr. 2018 | 73353841.1 |  | 2nd May 2018 | 23rd May, 2018 | 2nd Jun. 2019 | 30th Oct. 2023
D | LagosHOMS Egan-Igando (MOH/W/NCB/06/01) Building | MOH/W/NCB/005/2022 |  | 303421237.02 | ˂ 500M | NCB | BOQ/BEME | Post | Plan | Prior | [8 empty] | 192575457.97 | 8th Mar. 2019
[9 empty] | Actual |  | 8th Jan. 2019 | 15th Jan. 2019 | 18th Jan. 2019 | 1st Feb. 2019 | 8th Feb. 2019 | 15th Feb. 2019 | 17th Feb. 2019 | 22nd Feb. 2019 |  |  | 8th Jul. 2019 | 15th Jul. 2019 | 22nd Jul. 2019 | 21st Jul. 2023
E | LagosHOMS Ajara Badagry(MOH/W/NCB/06/16) Building | MOH/W/NCB/006/2022 |  | Amount from Capital Dev. | ˂ 500M | NCB | BOQ/BEME | Post | Plan | Prior | [8 empty] | NIL | 31st Jan. 2020
[9 empty] | Actual |  | 23rd Apr. 2019 | 24th Apr. 2019 | 25th Apr. 2019 | 2nd May 2019 | 23rd May 2019 | 25th May 2019 | 27th May 2019 | 29th Jan. 2020 |  |  | 15th Feb, 2020 | 27th Feb. 2020 | 1st Mar. 2020 | 28th Feb. 2023
F | LagosHOMS Sangotedo Phase I(On-going MOH/W/NCB/04/2017) Infrastructure | MOH/W/NCB/03/2022 |  | 1130000000 | > 500M | ICB | BOQ/BEME | Post | Plan | Prior | [8 empty] | 264775154.01 | 26th Apr. 2018
[9 empty] | Actual |  | 5th Feb 2018 | 14th Feb. 2018 | 22nd Feb. 2018 | 28th Feb.2018 | 10th Mar. 2018 | 17th Mar. 2018 | 31st Mar. 2018 | 21st Apr. 2018 |  |  | 1st May 2018 | 22nd May 2018 | 1st Jun. 2019 | 25th Oct. 2023
G | LagosHOMS Ajara Badagry(MOH/W/NCB/04/16) Infrastructure | MOH/W/NCB/007/2022 |  | 34932514.59 | >100M | NCB | BOQ/BEME | Post | Plan | Prior | [8 empty] | 73404783.04 | 31st Jan. 2020
[9 empty] | Actual |  | 23rd Apr. 2019 | 24th Apr. 2019 | 25th Apr. 2019 | 2nd May 2019 | 23rd May 2019 | 25th May 2019 | 27th May 2019 | 29th Jan. 2020 |  |  | 15th Feb, 2020 | 27th Feb. 2020 | 1st Mar. 2020 | 28th Feb.2023
H | Construction/Purchase of Housing for Government Functionaries in the Five Division | MOH/W/NCB/012/2022 |  | 20000000 | ˂ 100M | NCB | BOQ/BEME | Post | Plan | Prior | 13th Jan. 2022 | 17th Jan. 2022 | 20th Jan. 2022 | 3rd Feb. 2022 | 10th Feb. 2022 | 14th Feb. 2022 | 28 Feb. 2022 | 2nd Mar. 2022 | NEW PROJECT | 5th Mar.2022 | 12th Mar.2022 | 19th Mar. 2022 | 29th Nov. 2022 | 27th Nov. 2023
Actual
I | Epe Housing Scheme,Ita Marun 112 Units(MOH/W/ST-EOI/08/2018) Building | MOH/W/NCB/009/2022 |  | 1095687383.73 | > 500M |  | BOQ/BEME | Post | Plan | Prior | [8 empty] | 4261006492.28 | 20th Nov 2018
[9 empty] | Actual |  | 5th Oct. 2018 | 2018-10-12 | 16th Oct. 2018 | 25th Oct. 2018 | 28th Oct. 2018 | 5th Nov. 2018 | 12th Nov. 2018 | 13th Nov. 2018 |  |  | 22nd Nov. 2018 | 20th Apr. 2019 | 20th Apr. 2021 | 20th Apr. 2023
J | LagosHOMS Gbagada(MOH/W/DC/02/2018) Infrastructure | MOH/W/NCB/010/2022 |  | 120000000 | ˂ 500M | NCB | BOQ/BEME | Post | Plan | Prior | [8 empty] | 94648687.13 | 10th Apr. 2018
[9 empty] | Actual |  | 8th Jan. 2018 | 22nd Jan. 2018 | 7th Feb. 2018 | 21st Feb. 2018 | 28th Feb. 2018 | 12th Mar. 2018 | 26th Mar. 2018 | 29th Mar. 2018 |  |  | 26th Jul. 2018 | 1st Aug. 2018 | 24th Jan. 2019 | 30th Oct. 2023
K | LagosHOMS Egan (BOND)(MOH/W/NCB/002/2020) Infrastructure | MOH/W/NCB/011/2022 |  | 170623475.41 | > 500M | NCB | BOQ/BEME | Post | Plan | Prior | [6 empty] | 20th Mar. 2020 | 26th Mar. 2020 | 347060378.68
[9 empty] | Actual |  | 3rd Feb. 2020 | 7th Feb. 2020 | 10th Feb. 2020 | 24th Feb. 2020 | 2nd Mar. 2020 | 6st Mar. 2020 |  |  |  | 31st Mar. 2020 | 11th Apr.2020 | 25th Apr. 2020 | 1st Oct. 2021 | 27th Arl. 2023
L | Renovation of Offices | MOH/W/NS/001/2022 |  | 23800000 | ˂ 100M | NS | BOQ/BEME | Post | Plan | Prior | 22nd Jan. 2022 | 24th Jan. 2022 | 28th Jan. 2022 | 11th Feb. 2022 | 14th Feb. 2022 | 17th Feb. 2022 | 28th Feb. 2022 | 3rd Mar. 2022 | NEW PROJECT | 10th Mar. 2022 | 17th Mar. 2022 | 3rd Apr. 2022 | 10th Nov. 2022
Actual
M | Completion of Odo-Onasa/Ayandelu : Mixed Development Scheme (MOH/W/NCB/05/2017). Infrastructure | MOH/W/NCB/013/2022 |  | 200000000 | > 500M | NCB | BOQ/BEME | Post | Plan | Prior | [6 empty] | 2nd Apr. 2018 | 23rd Apr. 2018 | 322237782.01 | 28th Apr. 2018
[9 empty] | Actual |  | 8th Jan. 2019 | 12th Feb. 2018 | 19th Feb. 2018 | 26th Feb. 2018 | 12th Mar. 2018 | 19th Mar. 2018 |  |  |  |  | 2nd May 2018 | 23rd May, 2018 | 2nd Jun. 2019 | 30th Oct. 2023