## GOODS
PROCUREMENT PLAN FOR GOODS
MINISTRY : OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT / CABINET OFFICE
|  |  |  | BUDGET YEAR: 2020 |  | BUDGET YEAR: 2021
| BUDGET Y: |  |  | 2019
CONTRACT IDENTIFICATION |  | BASIC DATA | [7 empty] | BIDDING PERIOD |  |  |  | BIDS EVALUATION |  |  | CONTRACT FINALIZATION
Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Type of Expenditure | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Bid Prep & Submission by MDA | MDA Approval /PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission on Eval Rpt | MDA Approval /PPA Issues Certificate of Compliance Date | Date Contract Signature | Mobilization Advance Payment | Complete Delivery/Install | Inspection and Final Acceptance | Champion
|  | N/A | N/A | 13,218,000.00 | <₦10M |  | NS | POST | POST | Plan | 1/2/19 | NA | 8/2/19 | 22/2/19 | 1/3/19 | NA | 29/3/19 | 12/4/19 | 17/5/19 | 27/12/19 | PS
Procurement of Stationery quartely for the entire Cabinet Office | SSG/G/NS/001/19 |  |  |  |  | Recurrent
Procurment of Uniforms and Protective Outfits for drivers and cleaners and other Officers. | SSG/G/NS/002/19 | N/A | N/A | 6,000,000.00 | <₦10M | Recurrent | NS | POST | POST | Plan | 1/2/19 | NA | 8/2/19 | 22/2/19 | 1/3/19 | NA | 29/3/19 | 12/4/19 | 17/5/19 | 27/12/19 | PS
| SSG/GDS/NS/16/02 | [5 empty] | NS
Maintenance of Computer and procurement of computers consumabes and accessories | SSG/G/NS/003/19 | N/A | N/A | 10,000,000.00 | <₦10M |  | NS | POST | POST | Plan | 1/2/19 | NA | 8/2/19 | 22/2/19 | 1/3/19 | NA | 29/3/19 | 12/4/19 | 17/5/19 | 27/12/19 | PS
| SSG/GDS/NS/16/03 |  |  |  |  | Recurrent |  |  |  | Actual
Motor Vehicle Fuel Consumption for vehicles in the Office of the SSG quatertly, Permanent Secretary Office and all the utility Vehicles in the Cabinet Office | SSG/G-F/NS/004/19 | N/A | N/A | 6,000,000,00 | <₦10M |  | NS | POST | POST | Plan | 1/2/19 | NA | 8/2/19 | 22/2/19 | 1/3/19 | NA | 29/3/19 | 12/4/19 | 17/5/19 | 27/12/19 | PS
| SSG/GDS/NS/16/04 |  |  |  |  | Recurrent |  |  |  | Actual
Procurement of Cleaning Materials | SSG/G/DC/005/19 | N/A | N/A | 8,886,000,00 | <₦10M |  | DC | POST | POST | Plan | NA | NA | NA | NA | NA | NA | NA | NA | 30/6/19 | 27/12/19 | PS
| SSG/GDS/DP/16/05 |  |  |  |  | Recurrent |  |  |  | Actual
Printing of Gazette | SSG/G/DC/006/19 | NA | NA | 20000000 | <₦100M | Recurrent | DC | PRIOR | PRIOR | Plan | 2/2/19 | 9/2/19 | NA | NA | NA | NA | 13/4/19 | 27/4/19 | 18/5/19 | 27/12/19 | PS
Actual
Printing of Compedium | SSG/G/DC/007/19 | NA | NA | 6800000 | <N10M | Recurrent | DC | POST | POST | Plan | 2/2/19 | 9/2/19 | NA | NA | NA | NA | 30/3/19 | 13/4/19 | 18/5/19 | 27/12/19 | PS
Actual
Total |  |  |  | 52975000 | [5 empty] | Plan
Actual

## NON PROCURABLE
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: MINISTRY OF ENERGY AND MINERAL RESOURCES
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER
1 | DAWN COMMISION GRANT | SSG/NP/DC/001/21 | 20000000 | Plan
Actual
2 | CHRISTMAS/NEW YEAR GIFTS | SSG/NP/DC/002/21 | 10850000 | Plan
Actual
3 |  |  |  | Plan
Actual
4 |  |  |  | Plan
Actual
5 |  |  |  | Plan
Actual
7 |  |  |  | Plan
Actual
8 |  |  |  | Plan
Actual
9 |  |  |  | Plan
Actual
10 |  |  |  | Plan
Actual
11 |  |  |  | Plan
Actual
12 |  |  |  | Plan
Actual
13 |  |  |  | Plan
Actual
14 |  |  |  | Plan
Actual
15 |  |  |  | Plan
Actual
16 |  |  |  | Plan
Actual
17 |  |  |  | Plan
Actual
18 |  |  |  | Plan
Actual
19 |  |  |  | Plan
Actual
20 |  |  |  | Plan
Actual
21 |  |  |  | Plan
Actual
22 |  |  |  | Plan
Actual
23 |  |  |  | Plan
Actual
24 |  |  |  | Plan

## SERVICES
PROCUREMENT PLAN FORCONSULTANCY SERVICES | PROCUREMENT PLAN FOR NON CONSULTING SERVICES
MINISTRY:OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT,CABINET OFFICE
BUDGET YEAR: |  |  |  |  | 2019
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  |  | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [5 empty] | DRAFT CONTRACT |  | CONTRACT FINALIZATION |  |  |  | CONTRACT IMPLEMENTATION
| Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDA | MDA Approval /PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | MDA Approval /PPA No-Objection | Negotiation Meeting | Plan vs. Actual | Submission of Minutes of Negotiation and Draft Contract | PPA Issues Certificate of Compliance / MDA Approval | Contract Amount in N '000 | Contract Award | Date Contract Advert | Contract Signature | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
| Catering Services ( Servicing 48 Exco Satutory meeting | SSG/NCS/DC/001/19 | DC |  | 12,000.000.00 | POST | Plan | 01/02/19 | 9/2/19 | NA | NA | NA | 16/2/19 | 23/2/19 | 2/3/19 | 9/3/19 | 16/3/19 | 23/3/19 | 30/3/19 | Plan | 2019-06-04 | 13/4/19 |  | 20/4/19 | NA | 27/4/19 | 4/5/19 | quartely | 27/12/19
|  | SSG/CONS/16/05 | SSS |  |  |  | Actual | [12 empty] | Actual
| Servicing and Maintenance of Phtocopy machines | SSG/NCS/DC/002/19 | DC |  | 3,000.000.00 | POST | Plan Actual | 01/02/19 | NA | NA | NA | NA | 16/2/19 | 23/2/19 | 2/3/19 | 9/3/19 | 16/3/19 | 23/3/19 | 30/3/19 | Plan Actual | 2019-06-04 | 13/4/19 |  | 20/4/19 | NA | 27/4/19 | 2019-04-05 |  | 27/12/19
| Motor Vehicle Repair And Maintenance | SSG/NCS/DC/003/19 | DC |  | 3,150,000.00 | POST | Plan Actual | 01/02/19 | NA | NA | NA | NA | 16/2/19 | 23/2/19 | 2/3/19 | 9/3/19 | 16/3/19 | 23/3/19 | 30/3/19 | Plan Actual | 6/4/2019 | 13/4/19 |  | 20/4/19 | NA | 27/4/19 | 4/5/19 |  | 27/12/19
| TOTAL |  |  |  | 18,150,000.00

## TRAINING
PROCUREMENT PLAN FOR TRAINING AND WORKSHOP
MINISTRY/ AGENCY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT,CABINET OFFICE
BUDGET YEAR: …2019
S/N | Description of Workshop | Objective of workshop & Designation GL | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Accoma / Incidental Allowance | Total Cost
1 | Intergrated Excutive Leadership programme Aug 28 - 30, 2019 | SSG | 1 | 3Days |  | Abuja | 100,000.00 | 85,000.00 | 256,500.00 | 441,500.00
2 | Building and leading an effective Executive Team (NIM) Oct, 8-12 2019 | To improve the leadership skill of the Officer (PS) | 1 | 3 | Plan | Abuja | 95,000 | 82,000 | 182,500.00 | 359,500.00
Actual
3 | Strategic Thinking and Organizational effectivess(NIM) Sep 19-23,2019 | SSA | 1 | 3 | Plan | P/H | 85,000.00 | 65,000 | 146,000.00 | 296,000.00
Actual
F
4 | Strategic Thinking and Organizational effectivess(NIM) Sep 12-16,2019 | D(A&HR) GL.17 D ( F & A) GL 17 | 2 | 3 | Plan | Abuja | 90,000 x2 =180,000.00 | 130,000.00 | 292,000.00 | 602,000.00
5 | Strategic Human Resource Management and Capacity Building Workshop (NIM) 13-17 Sept.2019 | DD,GL16(CAB A ffairs) DD,GL(Pass)DD,GL16(CAB. Affairs)AD,GL.15(CAB.Aff.)AD,GL.15(A&HR)AD,GL.15(SSG)AD,GL.15(PASS) | 7 | 3 | Plan | Abuja | 80,000X7PPL=560,000.00 | 55,000.00+10,000=65,000X7PPL=455,000.00 | 1,022,000.00 | 2,037,000.00
Actual
6 | Procurement Planning for Works Goods and Services in MDAs and Private Sector,3rd-5th oct,2019 . Development Skills and Competence for Effective Fund MGT | DD(Procurement) Officer GL,16 Asst.Dir.GL.15 (Accts) | 2 | 3 | Plan | Abuja Enugu | 80,000 x2 =160,000 | 65,000x 2 Officers =130,000.00 | 292,000.00 | 291,000.00 291,000.00
Actual
6 | Essential Fundamental of Speech Writing and Effective Communication July, 16 - 20 | To improve the skill and effciency of the Officer CEO(Public Affair Office) GL 14 | 1 | 5 | Plan | Ibadan | 85,000 | 12,000 | 178,500.00 | 275,500.00
Actual
7 | Project Monitoring and Evaluation: Tools, Techniques and Reporting July, 2-6 | To improve the skill and efficiency of the officer Chief Compt. Engineer GL.14 Chief Electri Engineer (SSG) GL.14 | 2 | 5 | Plan | Ibadan | 90,000 x 2 no officers =180,000.00 | 20,000 | 357,000.00 | 557,000.00
Actual
8 | Advanced Accounting, Auditing and Management Course May,7-11 | To improve the accounting capabilities of the Officer CEO (Acct) GL 14 PEO1(Audits) GL13 | 2 | 5 | Plan | Ibadan | 180,000.00 | 20,000 | 357,000.00 | 557,000.00
Actual
9 | Advanced Management Skills and Intellectuals July, 9 - 13 | To improve the skill of the Officer Chief Sec.(SSG off) Chief Sec. (CAB Affairs) GL 14 | 2 | 5 | Plan | Ibadan | 150,000.00 | 20,000 | 357,000.00 | 527,000.00
Actual
10 | Feasibility Studies and Investment Analysis: Business Plan July 23 - 27 | To improve the capabilities and effciency of the Officer Principal Planning Officer GL.12 | 1 | 5 | Plan | Ibadan | 80,000.00 | 10,000 | 178,500.00 | 268,500.00
Actual
11 | Developing Dependable Relationship With the Boss | To improve the effciency of the Officer PAO(A&HR) GL.12 PEO GL.12 x 4 SAO GL.10 x 2 | 6 | 5 | Plan | Ibadan | 75,000X6 =450,000.00 | 60,000.00 | 726,000.00 | 1,236,000.00
Actual
12 | Data Processing and Operations September, 24 - 28 | To improve the capabilities of the Officer Prin, Programme Analyst (ICT) GL. 12 Com.Eng. GL.10 | 2 | 5 | Plan | Ibadan | 80,000 x2 =160,000.00 | 10,000x 2 no Officers =20,000.00 | 242,000.00 | 422,000.00
Actual
13 | Speech Making and Report Writing Techniques May, 28 - 1 June. | To improve the skill of the officer GL 10 | 1 | 5 | Plan | Ibadan | 85,000.00 | 9,000.00 | 119,500.00 | 213,500.00
Actual
14 | Arhieving Excellence in Secretariat Duties July, 11 - 13 | To improve the effciency of the Officer. Prin Sec off1(SSG OFF) GL10 Chief Asst Sec off(A&HR) GL 10 CHIEF ASST SEC OFF1 (ACCT) GL10 PRIN SEC OFF1 (CAB) GL12 | 4 | 4 | Plan | Ogun | 55,000 x4 =220,000.00 | 9,000x 6 no Officers =36,000.00 | 386,000.00 | 642,000.00
Actual
15 | Effective Human Relation: Workplace Innovation & Productivity Skill August, 6 - 10 | To improve the skill and capabilities of human resourses Officers. Admin off. & Executive Officers (GD) OFF Rep. GL 07 - 09 | 10 | 5 | Plan | Ibadan | 70,000 x10 no officer =700,000.00 | 5,000 x10 =50,000.00 | 605,000.00 | 1,355,000.00
Actual
16 | Information Management and safe Keeping of Records September, 10 - 14 | To improve the skill and effciency of the Officer Clerical &office Assistants ( GL 01 - 07) | 19 | 5 | Plan | Ibadan | 75,000 x19 =1,425,000.00 | 5,000x 19 no Officers =95,000.00 | 475,000.00 | 1,995,000.00
Actual
17 | Enhancing Driving Competence on the Highways September, 24 28 | To improve the driving skill and capabilities of the Officer. Driver GL 04 - 07 | 3 | 4 | Plan | Ibadan | 70,000x3 no officer =210,000.00 | 15,000.00 | 75,000.00 | 300,000.00
Actual
| Total | [8 empty] | 13,383,500.00
To improve the efficiency of the senior Officers in the Cabinet office. D(A&HR) GL.17 D (Accts.) GL.17
Strategic Human Resource Management and Capacity Building Workshop July, 25 - 27
To improve the efficiency and capabilities of Human Resources Officer in the Cabinet office.DD(A&HR) GL16 DD(CAB Affairs) GL.16 DD (Pass) DD (CAB.Affairs) AD(CAB.Aff.)
IN-HOUSE TRAINING PROGRAMME FOR SUPPORT STAFF OF SSG/CABINET OFFICE GL 01-07
|  | S/N | PROGRAMME | GL | NO OF OFFICERS | VENUE | NO OF DAYS | RESOUCES PERSON’FEE | TRAINING MATERIAL/ | REFRESHMENT(TEA BREAK&LUNCH | TOTAL
LOGITICS
|  | 1 | Effective Human Realation : Workplace Inovation & Productivity Skill. 3Days | Executive Officers & Clerical Off. GL06 - 07 | 12 | Lagos | 3 | 300,00.00 | 150000 | 63000 | 513000
|  | 2 | Information management and safe keeping of Records. | Data processing Off. | 1 | lagos | 3 | 300000 | 15,000 x 8PPL =120,000.00 | 7,000 X 8 =54,000.00 | 474000
|  | 3 | Safety Precaution & Defensive Driving Course | Drivers and Security / Guards GL. 05 - 07 | 16 | lagos | 3 | 300000 | 15,000 x 16PPL =240,000.00 | 7,000 X 16 =112,000.00 | 652000
|  | 4 | Personal Effectiveness & Attitude Re-orientation for Office Assistant & other Support Staff 3Days | GL 02- 04 | 10 | lagos | 3 | 300000 | 15,000 x 10PPL =150,000.00 | 7,000 X 10 =70,000.00 | 520000
2159000
Personal Effectiveness & Attitude Re-orientation for Office Assistant & other Support Staff

## CONFERENCES
o

## workshop 2
PROCUREMENT PLAN FOR TRANING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT,CABINET OFFICE.
BUDGET YEAR: 2021
S/N | Description of Tranining/Workshop/Confernce | Objectives of Traning /Workshop/Conference |  | Duration | Plan vs Actual | Venue | Tuition Fee/Airfare | Transport Fare/Incidental | Allowance | Total Cost
1 | CIPM | SSG | 1 | 5Days | Plan | Abuja | 75,000+70,000+145,000.00 | 15,000+15,000=30,000.00 | 80,000x5nights=402,500.00 | 577,500.00
Actual
2 | CIPM | PS | 1 | 5Days | Plan | Abuja | 75,000+70,000+145,000.00 | 12,000+10,000=22,000 | 57,500x5night=287,500 | 454,500,00
Actuals
3 | CIPM | GL.15-17 | 8 | 5Days | Plan | Abuja | 75,000x8=600,000.55,000x8=440,000=1,040,000.00 | 10,000x8=80,000.8,000x8=64,000.80,000+64,000=144,000.00 | 46,000x5nights=230,000x8ppl=1,840,000.00 | 3024000
Actual
4 | NIM | GL,13-14 | 8 | 5Days | Plan | Abuja | 65,000X8=520,000.55,000X8=440,000.520,000+440,000=960,000 | 9,000X8=72,000.6,000X8=48,000.72,000+48,000=120,000 | 34,500X5nights=172,500x8ppl=1,380,000 | 2460000
Actual
5 | NIM | GL.10 | 1 | 5Days | Plan | Abuja | 65,000+55,000=120,000 | 6,000+4,500=10,500 | 23,000X5nights=115,000.00 | 245,500.00
Actual
6 | ICAN | GL,17 | 1 | 5Days | Plan | Abuja | 70,000+55,000=125,000 | 10,000+8,000=18,000 | 46,000x5nights=230,000 | 373,000,00
Actual
7 | CIPSMN | GL.16 | 1 | 5Days | Plan | Abuja | 100,000+55,000=155,000 | 10,000+8,000=18,000 | 46,000x5nights=230,000 | 403,000.00
Actual
8 | ANAN | GL.15 GL.14 GL12 | 3 | 5Days | Plan | Jos | 70,000x3=210,000.55,000x3=165,000.210,000+165,000=375,000 | 10,000+9,000+6,000=25,000.8,000+6,000+4,500=18,500.25,000+18,500=43,500 | 46,000x5nights=230,000.34,500x5nights=172,500.23,000x5nights=115,000.230,000+172,500+115,000=517,500 | 936,000.00
Actual
9 | CPN | GL.13 GL,12 | 2 | 5Days | Plan | Abuja | 65.000x2=130,000.55,000x2=110,000.130,000+110,000=240,000 | 9,000+6,000=15,000.6,000+4,500=10,500.15,000+10.500=25,500 | 34,000x5nights=172,500.23,000x5nights=115,000.172,500+115,000=287,500 | 553,000.00
Actual
10 | CICRN | GL.13-15 | 2 | 5Days | Plan | Abuja | 65,000x2=130,000.55,000x2ppl=110,000=240,000 | 9,000x2pple=18,000.6,000x2pple=12,000.18,000+12,000=30,000 | 34,500x5nights=172,500x2pple=345,000 | 615,000.00
Actual
11 | Nig Statictic Ass(NSA) | GL.13 | 1 | 5Days | Plan | Kogi | 65,000+55,000=120,000 | 9,000+6,000=15,000 | 34,500x5nights=172,500 | 307,500.00
Actual
12 | Mgt and Supervising Skills for Accountants and Auditors | GL.08 | 1 | 4Days | Plan | Ibadan | 65,000 | 7,500+3,000=10,500 | 11,500x4Days=46,000 | 121,500.00
Actual
13 | Prudent Fin.Mgt and Accountability in Public and Private Sectors (ICAN)14TH-17TH July, 2021.Performanace Improvement Skills for Middle Level Managers and Supervisors (ICAN)31st March 2April,2021 | GL.10 DL.10. GL.08. GL.08 | 4 | 4Days | Plan | Ogun | 70,000x4=280,000 | 10,000x2=20,000.7,500x2=15,000.4,500x2=9,000.3,000x2pple=6,000.20,000+15,000=35,000.9,000+6,000=15,000.35,000+15,000=50,000 | 17,250x4Day=69,000x2pple=138,000.11,500x4Days=46,000x4pple=92,000.138,000+92,000=230,000 | 560,000.00
Actual
14 | Advance Office Mgt and Effective Admin.Skills Workshop for Administrators and Senior Secretaries (ICSAN)20th -21st Oct,2021 | GL.10 GL.09.GL.09 |  |  | Plan | Ogun | 80,000x3=240,000 | 10,000.7,500x2pple=15,000.10,000+15,000=25,000.4,500+3,000x2pple=6,000.4,500+6,000=10,500.25,000+10,500=35,500 | 17,250x3Days=51,750.11,500x3Days=34,500x2pple=69,000.51,750+69,000=120,750 | 396,250.00
Actual
15 | Diditized Record Management (NIM)13th-17th,2021 | GL.09 | 1 | 5Days | Plan | Ogun | 115,000.00 | 7,500+3,000=10,500 | 11,500x5Days=57,500 | 183,000.00
Actual
16 | TOTAL | [8 empty] | 14,952,000.00

## CONSULTANCY
PROCUREMENT PLAN FOR CONSULTANCY SERVICES
MINISTRY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT / CABINET OFFICE
BUDGET YEAR: 2021
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  |  | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [5 empty] | DRAFT CONTRACT |  | CONTRACT FINALIZATION |  |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No Objection | ₦ Governor' s Approval | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
1 | Research and Development | SSG/S/QC/002/2021 | QC |  | 10,000,000.00 | POST | Plan
[7 empty] | Actual | 3/2/2021 | 5/2/2021 | NA | NA | NA | 8/2/2021 | 10/2/2021 | 11/2/2021 | 15/2/2021 | 18/2/2021 | 20/2/2021 | 22/2/2021 |  |  |  | 25/2/2021 | 27/2/2021 | 2021-01-03 | Quartely | 31/3/2021
2 | TOTAL |  |  |  | 10,000.000.00

## Sheet9
PROCUREMENT PLAN FOR CONSULTANCY SERVICES
MINISTRY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT / CABINET OFFICE
BUDGET YEAR: 2021 |  | 2022
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  |  | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) | [5 empty] | DRAFT CONTRACT
S/N | Project Description | Project Package | Selection Method | Lumpsum or Time-Based | Estimated Amount in N '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Submission of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No Objection | ₦ Governor' s Approval | Register Approval with PPA | Contract Amount in N '000
1 | Research and Development | SSG/S/QC/002/2022 | QC |  | 10,000,000.00 | POST | Plan
[7 empty] | Actual | 3/2/2022 | 4/2/2022 | NA | NA | NA | 8/2/2022 | 10/2/2022 | 11/2/2022 | 15/2/2022 | 18/2/2022 | 21/2/2022 | 22/2/2022
2 | TOTAL |  |  |  | 10,000.000.00 |  |  | .

## WORKS
PROCUREMENT PLAN FOR GOODS
MINISTRY : OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT / CABINET OFFICE
BUDGET YEAR: 2022
CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan vs. Actual | BIDDING PERIOD
Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening
|  | N/A |  | 1,500,000,00 | <₦50M |  | POST | POST | Plan | (1-4wks) | (1-2wks) | (1-2wks) | (2-6wks)
Procurement of Stationery quartely for the entire Cabinet Office | SSG/G/NS/001/2022 |  | NA |  |  | NS | POST | POST | Plan | 25/1/2022 | N/A | 7/1/2022 | 28/2/2022
Actual
Procurement of Suits,Uniforms and Protective Outfits for director,senior officers and drivers and cleaners | SSG/G/NS/002/2022 | N/A | N/A | 4000,000.00 | <₦50M | NS | POST | POST | Plan | 24/1/2022 | N/A | 7/1/2022 | 28/2/2022
Actual
Maintenance of Computers and procurement of computers consumabes and accessories | SSG/G/NS/003/2022 | N/A | N/A | 100,000.00 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 7/1/2022 | 22/2/2022
Actual
Motor Vehicle Fuel Consumption | SSG/G/NS/004/2022 | N/A | N/A | 3500000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 7/1/2022 | 22/2/2022
Actual
Quarterly conpilation of compendium of Exco minutes(Cab Affair) | SSG/G/NS/005/2022 | N/A | N/A | 27000000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | NA | 7/1/2022 | 22/2/2022
Actual
Printing of official Gazetteand official stationery items.etter head | SSG/G/DC/006/2022 | N/A | N/A | 5000000 | <₦50M | DC | PRIOR | POST | Plan | 25/1/2022 | N/A | 7/1/2022 | 22/2/2022
Actual
Production of conpendium of past and present state Executive Council (EXCO)members | SSG/G/NS/007/2022 | N/A | N/A | 1,885,000,00 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 7/1/2022 | 22/2/2022
Actual
store equipment e.g store Requistion booklet,SRV,store card and Register | SSG/G/DC/008/2022 | N/A | N/A | 2500000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 7/1/2022 | 22/2/2022
Actual
TOTAL |  |  |  | 23285000 |  |  |  |  | Plan | 25/1/2022 | N/A | 7/1/2022 | 22/2/2022
Actual

## Sheet5
IN - HOUSE TRAINING PROGRAMME FOR JUNIOR STAFF/DRIVERS OF SSG/CABINET OFFICE GL.02-07
MINISTRY/ AGENCY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT,CABINET OFFICE
BUDGET YEAR: …2022
S/N | PROGRAMME | GL | NO OF OFFICRES | VENUE | NO OF DAYS | RESOURCES PERSON FEE |  | TRAINNING MATERIALS/LOGISTICS | REFRESHMENT TEABREAK/LUNCH | TOTAL
1 | Personal Effectiveness and Attitude Re- | 2 -7 | 10 | Office Conference Room | 3Days | Plan | 600,000.00 | 25,000x10pple=250,000.00 | 5,000x10pple=50,000x3Days=150,000 | 1000000
Actual
| TOTAL | [8 empty] | 1000000

## NON-CONSULTANCY
PROCUREMENT PLAN FOR NON CONSULTING SERVICES
| MINISTRY/ AGENCY: | OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT, CABINET OFFICE
BUDGET YEAR: 2022
| CONTRACT IDENTIFICATION |  | BASIC DATA | [8 empty] | BIDDING PERIOD DATE |  | BID EVALUATION DATE |  | CONTRACT FINALIZATION
S/N | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Plan vs. Actual | Prior or Post Qualification | Prior or post review | Bid Prep & Submission by MDA (1-4wks) by MDA | PPA No-Objection Date (1-2wks) Date | Bid Invitation Date(1-2wks) | Bid Closing & Opening(2-6wks) | Submission of Bid Evaluation Report (1-2wks) Bid Eval Rpt | minutes of Negotiation (1wk) | PPA Issues Certificate of Compliance | Plan vs Actual | Mr. Governor's Approval(1-4wks) | Register Mr. Governor's Approval with PPA (48Hours) | Contract Amount in Naira N '000 | Date Contract Signature (4-6 wks) Signature | Mobilization Advance payment (2-4 wks) Advance Payment | Complete Delivery/Install(2-8wks) | Inspection and Final Acceptance
1 | Catering Services for 48 Exco Memebers,Secretariat | SSG/NCS/NS/001/2022 | N/A | N/A | 26,000,000.00 | <₦50M | NS | Plan | POST | POST | 27/2/2022 | N/A | 31/1/2022 | 14/2/2022 | 21/2/2022 | 27/2/2022 | N/A | Plan | 17/2/2022 | 19/3/2022 |  | 20/3/2022 | 4/3/2022 | NA | NA
[8 empty] | Actual | [8 empty] | N/A | Actual
2 | Servicing and Maintenance of (3)Photocopy machines | SSG/NCS/NS/002/2022 | N/A | N/A | 1,942,000.00 | <₦50M | NS | Plan |  |  | 27/2/2022 |  | 31/1/2022 | 14/2/2022 | 22/2/2022 | 1/3/2022 |  | Plan | 18/2/2022 | 20/3/2022 |  | 22/3/2022 | 5/3/2022 | NA | NA
3 | Motor Vechicles Repair and Maintenance | SSG/NCS/NS/003/2021 | N/A | N/A | 3,000,000.00 | <₦50M | NS | Plan | POST | POST | 27/2/2022 |  | 31/1/2022 | 14/2/2022 | 21/2/2022 | 1/3/2022 |  | Plan | 17/2/2021 | 19/3/2022 |  | 20/3/2022 | 4/3/2022 | NA | NA
|  | SSG/GDS/NS/16/03 | [5 empty] | Actual |  | Actual |  | NA | [5 empty] | Actual
4 | Services and Maintenanceof generated set | SSG/NCS/NS/004/2021 | N/A | N/A | 3500000 | <₦50M | NS | Plan | POST | POST | 27/2/2022 |  | 31/1/202\2 | 14/2/2022 | 21/2/2022 | 27/2/2022 |  | Plan | 17/2/2022 | 19/3/2022 |  | 20/3/2022 | 4/01/2022 | NA | NA
[8 empty] | Actual |  |  |  | NA | [5 empty] | Actual
5 | provision for janitoral services,cleaning and maintenance of the office. | SSG/NCS/NS/005/2022 | N/A | N/A | 13000000 | <₦50M | NS | Plan | prior |  | 27/2/2022 | 29/2/2022 | 31/1/2022 | 14/2/2022 | 21/2/2022 | 27/2/2022 | 29/2/2022 | Plan | 17/2/2022 | 19/3/2022 |  | 20/3/2022 | 2022-04-01 | NA | NA
[8 empty] | Actual |  |  |  | NA | [5 empty] | Actual
6 | maintenance of office Building | SSG/NCS/NS/006/2022 | N/A | N/A | 3250000 | <₦50M | NS | Plan | POST |  | 27/2/2022 |  | 31/1/2022 | 14/2/2021 | 21/2/2022 | 27/2/2022 |  | Plan | 17/2/2022 | 19/3/2022 |  | 20/3/2022 | 2022-04-01 | NA | NA
[8 empty] | Actual |  |  |  | NA | [5 empty] | Actual
| TOTAL |  |  |  | 50692000 |  |  | Plan | POST |  | 27/2/2022 |  | 31/1/2022 | 14/2/2022 | 21/2/2022 | 27/2/2022 |  | Plan | 17/2/2022 | 19/3/2022 |  | 20/3/2022 | 2022-04-01 | NA | NA
[8 empty] | Actual | [9 empty] | Actual

## Sheet4
PROCUREMENT PLAN FOR NON - PROCUREMENT ITEMS (SPECIAL PROGRAMMES)
MINISTRY/ AGENCY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT,CABINET OFFICE
BUDGET YEAR: YR 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER
1 | Travel and Traansportation:Local | SSG/NP/NM/01/2022 | 3600000
2 | General Utility Services,DSTV Subscription e.t.c | SSG/NP/NM/02/2022 | 3150000
3. | Miscellaneous ()for unforseen circustances | SSG/NP/NM/03/2022 | 3900000
4 | Grant and Donations:to voluntatry organisation and NGO's Quasi Political Groups,Individuals,Group in life Treatering situation,receptions e.t.c | SSG/NP/NM/04/2022 | 10,000,000.00
5 | Upkeep and maintenance Allowance : To facilatate recruitment processs for Lagos State indigenes into the Arm Forces,Nigeria Police,Customs and Immigration. | SSG/NP/NM/05/2022 | 5000000
6 | Banking Operation services | SSG/NP/NM/06/2022 | 500,000.00
7 | Provission for creating awarness, mobilisation and Sensitization of the Genaral public on policies,project and programmes of Government:Public peace and security and other intervention and special programmes. | SSG/NP/NM/07/2022 | 280783586.72
8 | Special Duties Expenses. E.g Provision for last day in office ceremony for retiring members of staff, personnel Management Board(PMB) and other contigency matters. | SSG/NP/NM/08/2022 | 53573675.28
| TOTAL | SSG/NP/NM/09/2022 | 360507262

## Sheet6
PROCUREMENT PLANNING COMMITTEE MEMBERS (PPC)
S/N | NAME | DEPARTMENT/UNIT | REMARK | SIGNATURE/DATE
1 | Mrs Tolani Oshodi | Permanent Secretary | Chairman
2 | Mr. Abiodun Kuye | Director (F & A) | Member
3 | Mrs. Omotayo Gbajabiamila-Olamona .O | Director (A&HR) | Member
4 | Mr. F.A Adeyemi | D(Cabinet Affairs) | Member
5 | Mrs.O.I Shonibare | DD(PASS) | Member
6 | Mrs. O.G Ajose | HOU (PRS) | Member
7 | Mr. O. G Ojapinwa | DD(Procurement) | Secretary

## Sheet7
PROCUREMENT PLAN FOR GOODS
MINISTRY : OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT / CABINET OFFICE
BUDGET YEAR: 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan vs. Actual | BIDDING PERIOD |  |  |  | BIDS EVALUATION(DATE) |  | APPROVAL |  | CONTRACT FINALLIZATION
1 | Contract Description | Package Number | Lot Number | No. of Unit | Budget Avail | Approval Threshold | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDA | PPA No-Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission on Eval Rpt | PPA Issues Certificate of Compliance | Mr.Governor's Approval | Register Mr Governor 's approval with PPA | Contract Amount | Notification Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection &Final Acceptance
2 |  |  | N/A |  | 3,600,000,00 | <₦50M |  | POST | POST | Plan | (1-4wks) | (1-2wks) | (1-2wks) | (2-6wks) | (1-2wks) | (1-2wks) | (1-4wks) | (48hours) | 0.00 | (1wk) | (1-2wks) | (2-4wks)
| Procurement of Stationery quartely for the entire Cabinet Office | SSG/G/NS/001/2022 |  | NA |  |  | NS | POST | POST | Plan | 25/1/2022 | N/A | 8/1/2022 | 27/2/2022 | 1/3/2022 | N/A | 15/3/2022 | 17/3/2022 |  | 30/3/2022 | 31/3/2022 |  | 7/4/2022 | 14/4/2022
Actual
3 | Procurment of Suits, Uniforms and Protective Outfits for drector,senior officers and drivers and cleaners. | SSG/G/NS/002/2022 | N/A | N/A | 4,000,000.00 | <₦50M | NS | POST | POST | Plan | 24/1/2022 | N/A | 8/1/2022 | 27/2/2022 | 1/3/2022 | N/A | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2022-06-04 | 13/4/2022
Actual
4 | Maintenance of Computer and procurement of computers consumabes and accessories | SSG/G/NS/003/2022 | N/A | N/A | 100,000.00 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 8/1/2022 | 22/2/2022 | 29/2/2022 | N/A | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022
[23 empty] | 2022-06-04 | 13/4/2022
Actual
5 | Motor Vehicle Fuel Consumption | SSG/G/NS/004/2022 | N/A | N/A | 3500000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 8/1/2022 | 22/2/2022 | 29/2/2022 |  | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2022-06-04 | 13/4/2022
Actual
6 | Quarterly conpilation of compendium of Exco minutes | SSG/G/NS/005/2022 | N/A | N/A | 2700000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | NA | 8/1/2022 | 22/2/2022 | 29/2/2022 | N/A | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2021-06-04 | 13/4/2022
Actual
7 | Printing of official Gazetteand official stationery items.etter head | SSG/G/DC/006/2022 | N/A | N/A | 5000000 | <₦50M | DC | PRIOR | POST | Plan | 25/1/2022 | N/A | 8/1/2022 | 22/2/2022 |  | 29/2/2022 | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2022-06-04 | 13/4/2022
Actual
8 | Production of conpendium of past and present state Executive Council (EXCO)members | SSG/G/NS/007/2022 | N/A | N/A | 1885000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 8/1/2022 | 22/2/2022 | 29/2/2022 | N/A | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2022-06-04 | 13/4/2022
Actual
9 | store equipment e.g store Requistion booklet,SRV,store card and Register | SSG/G/DC/008/2022 | N/A | N/A | 2500000 | <₦50M | NS | POST | POST | Plan | 25/1/2022 | N/A | 8/1/2022 | 22/2/2022 | 29/2/2022 | N/A | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2022-06-04 | 13/4/2022
Actual
| TOTAL |  |  |  | 23285000 |  |  |  |  | Plan | 25/1/2022 | N/A | 8/1/2022 | 22/2/2022 | 29/2/2022 | N/A | 14/3/2022 | 16/3/2022 |  | 30/3/2022 | 30/3/2022 |  | 2022-06-04 | 13/4/2022
Actual

## Sheet8
PROCUREMENT PLAN FOR TRANING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: OFFICE OF THE SECRETARY TO THE STATE GOVERNMENT,CABINET OFFICE.
BUDGET YEAR: 2022
S/N | Description of Tranining/Workshop/Confernce | Objectives of Traning /Workshop/Conference | Days | DURATION | PLAN VS ACTUAL | VENUE | CON, FEE | FEEDING AND ACCOM | AIRFARE | TRANSPORT | INCIDENTAL | TOTAL
1 | CIPM | PS | 1 | 3Days | Plan | ABUJA | 75,000.00 | 92,000x3nights=276,000 | 140,000 | 18,000 | 15,000 | 524,000.00
Actual
2 | CIPM | GL-15-17 | 7 | 3Days | Plan | ABUJA | 75,000x7=525,000. | 73,600x3nights=220,800x7pple=1,545,600.00 | 110,000x7pple=770,000.00 | 15,000x7=105,000.00 | 12,000x7=84,000 | 3,029,600.00
Actuals
3 | NIM | GL. 15-17 | 4 | 3Days | Plan | ABUJA | 55,000x4=220,000.00 | 73,600x3nights=220,800x4pple=883,200.00 | 110,000x4pple=440,000.00 | 15,000x4pple=60,000.00 | 12,000x4pple=48,000.00 | 1651200
Actual
4 | NIM | GL,13-14 | 4 | 3Days | Plan | ABUJA | 55,000x5pple=275,000.00 | 55,500x3niights=166,500.00x5pple=832,500.00 | 110,000x5pple=550,000.00 | 13,500x5pple=67,500.00 | 9,000x5pple=45,000.00 | 1770000
Actual
5 | CIPSMN | GL.16 | 1 | 3Days | Plan | ABUJA | 50,000.00 | 73,600x3nights=220,800 | 110,000.00 | 15,000.00 | 12,000 | 405,800.00
Actual
6 | ANAN | GL,15 | 2 | 3Days | Plan | JOS | 50,000.00x2pple=100,000.00 | 73,600x3nights=220,800x2pple=441,600.00 | 110,000x2pple=220,000.00 | 15,000x2pple=30,000.00 | 12,000x2pple=24,000.00 | 815,600.00
Actual
7 | ANAN | GL.13 | 1 | 3Days | Plan | JOS | 50,000.00 | 55,500x3nights=166,500.00 | 110,000.00 | 13,500.00 | 9,000.00 | 349,000.00
Actual
8 | NIG. STATISTICS ASS (NSA) | GL.13 | 3 | 3Days | Plan | KOGI | 50,000.00 | 55,500x3nights=166,500.00 | 110,000.00 | 13,500.00 | 9,000.00 | 349,000.00
Actual
9 | CICSRN | GL.13 | 1 | 3Days | Plan | ABUJA | 50,000.00 | 55,500x3nights=166,500.00 | 110,000.00 | 13,500.00 | 9,000.00 | 349,000.00
Actual
10 | NSE | GL.15 | 1 | 3Days | Plan | ABUJA | 50,000.00 | 73,600x3nights=220,800 | 110,000.00 | 15,000.00 | 12,000.00 | 407,800.00
Actual
11 | NIPR | GL.14 | 1 | 2Days | Plan | ABUJA | 50,000.00 | 55,500x2nights=111,000.00 | 110,000.00 | 13,500.00 | 9,000.00 | 349,000.00
Actual
| TOTAL | [10 empty] | 10,000,000.00