## Non-Proc items
PROCUREMENT PLAN FOR NON-PROCURABLE ITEMS
MINISTRY/ AGENCY: ONIKAN GENERAL HOSPITAL
BUDGET YEAR 2022
S/N | Activity Description | Package Number | Budget Available (=N=) | Plan/Actual | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | TOTAL
1 | TRAVEL & TRANSPORT | OGHL/NP/NM/001/22 | 400,000.00 | Plan | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 33333.33 | 400000
Actual
2 | PROCUREMENT OF COOKING GAS,SUBSCRITION OF INTERNET & HOSPITAL TELEPPHONE BILLS. | OGHL/NP/NM/002/22 | 2,000,000.00 | Plan | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 166666.66 | 2000000
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## trg conf wsh
PROCUREMENT PLAN FOR TRAINING/CONFERENCE/WORKSHOP
MINISTRY/ AGENCY: ONIKAN GENERAL HOSPITAL
BUDGET YEAR 2022
S/N | Description of Training/Workshop/ Conference | Package Number | Objective of Training/Workshop/Conference | No. of Participants | Duration | Plan vs Actual | Venue | Tuition Fee | Transport Fare | Allowance | Total Cost
1 | COWSLO | OGHL/S-WTC/SS/001/22 |  | 5 | 3 DAYS | Plan | EKO HOTEL | 80000 |  |  | 400000
Actual
2 | CIPSMN | OGHL/S-WTC/SS/002/22 |  | 2 | 3 DAYS | Plan |  | 60000 |  |  | 120000
Actual
3 | NURSES CONFERENCE | OGHL/S-WTC/SS/003/22 |  | 10 | 3 DAYS | Plan |  | 30000 |  |  | 300000
Actual
4 | ANNUAL CONFERENCE FOR LABORATORY SCIENTIST | OGHL/S-WTC/SS/004/22 |  | 2 | 3 DAYS | Plan |  | 200000 |  |  | 400000
Actual
5 | ANNUAL CONFERENCE FOR HEALTH INFORMATION | OGHL/S-WTC/SS/005/22 |  | 3 | 3 DAYS | Plan |  | 51000 |  |  | 153000
Actual
6 | NMA HEALTH SUMMIT FOR DOCTORS | OGHL/S-WTC/SS/006/22 |  | 4 | 3 DAYS | Plan |  | 50000 |  |  | 200000
Actual
7 | ASSOCIATION OF NATIONAL ACCOUNTANT OF NIGERIA | OGHL/S-WTC/SS/007/22 |  | 2 | 3 DAYS | Plan |  | 350000 |  |  | 700000
Actual
8 | CHARTERD INSTITUTE OF PERSONNEL MANAGEMENT | OGHL/S-WTC/SS/008/22 |  | 2 | 3 DAYS | Plan |  | 263500 |  |  | 527000
Actual
9 | [5 empty] | Plan
Actual
10 | [5 empty] | Plan
Actual
11 | [5 empty] | Plan
Actual
12 |  |  | TOTAL |  |  | Plan |  |  |  |  | 3000000
Actual

## non-cons
PROCUREMENT PLAN FOR NON - CONSULTING SERVICES.
MINISTRY/AGENCY:
MINISTRY/AGENCY: ONIKAN GENERAL HOSPITAL
BUDGET YEAR 2022
Contract Description | BASIC DATA | [6 empty] | Pre-or Post Qualification | Prior or Post review | BIDDING PERIOD |  |  | BID EVALUATION |  |  | CONTRACT FINALIZATION
| Package Number | Lot No. | No of Unit | Budget Available in Naira | Approval Threshold | Procurement Method | Plan Vs Actual |  |  | Bid Prep & Submission by MDA (1-4wks) | PPA No Objection Date (1-2wks) | Bid Invitation Date (1-2wks) | Bid Closing & Opening Date (2-6 wks) | Submission of Bid Evaluation Report (1-2 wks) | Minutes of Negotiation (1 wk) | PPA issue "Cert. of Compliance Date (1-2 wks)/MDA Aprroval | Plan Vs Actual | Mr. Governor's Approval (1-4 wks) | Register Mr. Governor's Approval with PPA (48 Hours) | Contract Amount in Naira | Date Contract Signature (4-6 wks) | Mobilization Advance Payment (2-4 wks) | Complete Delivery/Install (2-8 wks) | Inspection & Final Acceptance
MAINTENANCE OF OFFICE BUILDING | OGHL/S-NC/NS/001/22 | 1 |  | 2500000 | <10M | NS | Plan | POST | POST | 2022-11-01 | N/A | 13/1/22 | 18/1/22 | 21/1/22 | 24/1/22 | N/A | Plan | N/A | N/A |  | 2022-01-02 | N/A | 2022-04-02 | 2022-07-02
[7 empty] | Actual | [9 empty] | Actual
MOTOR VEHICLE MAINTENANCE AND REPAIRS | OGHL/S-NC/NS/002/22 | 1 |  | 2000000 | <10M | NS | Plan | POST | POST | 13/1/22 | N/A | 18/1/22 | 21/1/22 | 24/1/22 | 2022-01-02 | N/A | Plan | N/A | N/A |  | 2022-04-02 | N/A | 2022-07-02 | 2022-09-02
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE & REPAIR OF OTHER EQUIPMENT | OGHL/S-NC/NS/003/22 | 1 |  | 1000000 | <10M | NS | Plan | POST | POST | 18/1/22 | N/A | 21/1/22 | 24/1/22 | 2022-01-02 | 2022-04-02 | N/A | Plan | N/A | N/A |  | 2022-07-02 | N/A | 2022-09-02 | 14/2/22
[7 empty] | Actual | [9 empty] | Actual
MAINTENANCE OF SPECIALIZED HOSPITAL EQUIPMENT | OGHL/S-NC/NS/004/22 | 1 |  | 1000000 | <10M | NS | Plan | POST | POST | 21/1/22 | N/A | 24/1/22 | 2022-01-02 | 2022-04-02 | 2022-07-02 | N/A | Plan | N/A | N/A | N/A | 2022-09-02 | N/A | 14/2/22 | 17/2/22
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
[7 empty] | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual
TOTAL |  |  |  | 800000 |  |  | Plan | [9 empty] | Plan
[7 empty] | Actual | [9 empty] | Actual

## consultancy
PROCUREMENT PLAN FOR CONSULTING SERVICES
MINISTRY/ AGENCY:
BUDGET YEAR:
| PROJECT IDENTIFICATION |  |  | BASIC DATA |  |  | Plan vs. Actual | PREPARATION (EOI & TOR) |  | SHORTLISTING |  |  | REQUEST FOR PROPOSALS |  | TECHNICAL (T) & FINANCIAL (F) & NEGOTIATION (N) |  |  |  |  | APPROVAL |  | CONTRACT FINALIZATION |  |  | CONTRACT IMPLEMENTATION
S/N | Project Description | Project Package | Selectn Method | Lump sum or Time-Based | Estimated Amount in N '000 | Prior/ Post Review |  | Prep & Submission by MDA | PPA No-Objection | MDA Advertise for EOI | Submission of EOI Report & Draft RFP to PPA | PPA No-Objection | Invitation to Submit Proposals | Submission of Proposals by Shortlisted Consultants | Opening/ Evaluation of Technical Proposals | Opening/ Evaluation of Financial Proposals | Subm of Eval Report to PPA (T) (F) | Negotiation Meeting | PPA No-Objection | Mr. Governor's approval. | Register Approval with PPA | Contract Amount in N '000 | Notification of Award | Contract Award | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
[5 empty] | 0 |  | Plan | 1-4 wks | 1-2 wks | 1wk | 2-4 weeks | 1-2 wks | 1-2 wks | 3-6 wks | 1-2 wks | 1-2 wks | 1wk | 1-2 wks | 1-2 wks | 1-4 wks | 48 Hrs | 0 | 1 wk | 2wks | 2-4 wks | 1-2 wks | 1-2 wks | 0
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual

## Goods 1
PROCUREMENT PLAN FOR GOODS.
MINISTRY/AGENCY: ONIKAN GENERAL HOSPITAL
YEAR 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | PROCUREMENT OF FUEL FOR MOTOR VEHICLE CONSUMPTION | OGHL/G-F/NS/001/22 | 1 |  | 1000000 | <10M | NS | POST | POST | Plan | 2022-10-01 | N/A | 2022-12-01 | 17/1/2022 | 20/1/22 | 25/1/22 | N/A | N/A |  | 28/1/22 | 2022-02-02 | N/A
Actual
2 | PURCHASE OF CLEANING MATERIALS (MOP STICKS, SWEEPING BRUS) ETC | OGHL/G-F/NS/002/22 | 1 |  | 458584 | <10M | NS | POST | POST | Plan | 2022-12-01 | N/A | 17/1/22 | 20/1/22 | 25/1/22 | 28/1/2022 | N/A | N/A |  | 2022-02-02 | 2022-07-02 | N/A
Actual
3 | PROCUREMENT OF STATIONERY | OGHL/G-F/NS/003/22 | 1 |  | 500000 | <10M | NS | POST | POST | Plan | 17/1/22 | N/A | 20/1/22 | 25/1/22 | 28/1/2022 | 2022-02-02 | N/A | N/A |  | 2022-07-02 | 2022-10-02 | N/A
Actual
4 | PROCUREMENT OF MEDICAL FORMS (DRUG PRESCRIPTION BOOKLETS, CONTINUATION SHEET ETC | OGHL/G-F/NS/004/22 | 1 |  | 2000000 | <10M | NS | POST | POST | Plan | 20/1/22 | N/A | 25/1/2022 | 28/1/2022 | 2022-02-02 | 2022-07-02 | N/A | N/A |  | 2022-10-02 | 15/2/2022 | N/A
Actual
5 | PROCUREMENT OF CHEMICAL AND LABORATORY REAGENT | OGHL/G-F/NS/005/22 | 1 |  | 2000000 | <10M | NS | POST | POST | Plan | 25/1/2022 | N/A | 28/1/22 | 2022-02-02 | 2022-07-02 | 2022-10-02 | N/A | N/A |  | 15/2/2022 | 18/2/22 | N/A
Actual
6 | PROCUREMENT OF MEDICAL GAS CONSUMPTION | OGHL/G-F/NS/006/22 | 1 |  | 2543682 | <10M | NS | POST | POST | Plan | 28/1/2022 | N/A | 2022-02-02 | 2022-07-02 | 2022-10-02 | 15/2/2022 | N/A | N/A |  | 18/2/2022 | 23/2/22 | N/A
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| TOTAL | [8 empty] | Plan
Actual

## Goods 2
PROCUREMENT PLAN FOR IGR.
MINISTRY/AGENCY: ONIKAN GENERAL HOSPITAL
YEAR 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | DRUG REVOLVING FUND(procurement of drugs and anti-biotics etc.) | OGHL/G-F/NS/007/22 | 1 |  | 88421572.08 | >10M | NS | POST | POST | Plan | 2022-12-01 | N/A | 17/1/22 | 20/1/2022 | 25/1/2022 | 28/1/2022 | N/A | N/A |  | 2022-02-02 | 2022-07-02 | N/A
Actual
2 | OBSTETRICS(maintenance & repair of incubators,phototherapy lamp etc). | OGHL/G-F/NS/008/22 | 1 |  | 13355060.4 | >10M | NS | POST | POST | Plan | 17/1/22 | N/A | 20/1/2022 | 25/1/2022 | 28/1/2022 | 2022-02-02 | N/A | N/A |  | 2022-07-02 | 2022-10-02 | N/A
Actual
3 | THEATRE PACK(procurement of theatre packs,medical gas etc). | OGHL/G-F/NS/009/22 | 1 |  | 7861795.92 | <10M | NS | POST | POST | Plan | 20/1/2022 | N/A | 25/1/2022 | 28/1/2022 | 2022-02-02 | 2022-07-02 | N/A | N/A |  | 2022-10-02 | 15/2/2022 | N/A
Actual
4 | ANAESTHESIA(provision of anaesthetic consumables & software etc). | OGHL/G-F/NS/010/22 | 1 |  | 9659493.36 | <10M | NS | POST | POST | Plan | 25/1/2022 | N/A | 28/1/2022 | 2022-02-02 | 2022-07-02 | 2022-10-02 | N/A | N/A |  | 15/2/2022 | 18/2/22 | N/A
Actual
5 | SURGERY(provision of sugical consumables & instrument etc). | OGHL/G-F/NS/011/22 | 1 |  | 7174462.68 | <10M | NS | POST | POST | Plan | 28/1/2022 | N/A | 2022-02-02 | 2022-07-02 | 2022-10-02 | 15/2/2022 | N/A | N/A |  | 18/2/22 | 23/2/22 | N/A
Actual
6 | GYNAECOLOGY(provision of gynae consumables etc). | OGHL/G-F/NS/012/22 | 1 |  | 9383283.36 | <10M | NS | POST | POST | Plan | 2022-01-02 | N/A | 2022-04-02 | 2022-09-02 | 2022-11-02 | 14/2/22 | N/A | N/A |  | 17/2/22 | 22/2/2022 | N/A
Actual
7 | LABORATORY(chemical reagent & payment of blood screen etc). | OGHL/G-F/NS/013/21 | 1 |  | 64169107.2 | >10M | NS | POST | POST | Plan | 2022-04-02 | N/A | 2022-09-02 | 2022-11-02 | 14/2/22 | 17/2/22 | N/A | N/A |  | 22/2/2022 | 25/2/2022 | N/A
Actual
8 | ACC0MMODATION(provision of delivery packs etc). | 0GHL/G-F/NS/014/22 | 1 |  | 13962722.4 | >10M | N/S | POST | POST | Plan | 2022-09-02 | N/A | 2022-11-02 | 14/2/22 | 17/2/22 | 22/2/2022 | N/A | N/A |  | 25/2/2022 | 2022-02-03 | N/A
Actual
9 | GOWN(patient gown etc). | OGHL/G-F/NS/015/22 | 1 |  | 4678997.4 | <10M | N/S | POST | POST | Plan | 2022-11-02 | N/A | 14/2/22 | 17/2/22 | 22/2/2022 | 25/2/2022 | N/A | N/A |  | 2022-02-03 | 2022-07-03 | N/A
Actual
| TOTAL | [8 empty] | Plan
Actual

## Goods 3
PROCUREMENT PLAN FOR IGR.
MINISTRY/AGENCY: ONIKAN GENERAL HOSPITAL
YEAR 2022
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [6 empty] | Plan Vs Actual | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION (DATES) |  | APPROVAL |  | CONTRACT FINALIZATION
| Contract Description | Package Number | Lot Number | No of Unit | Budget Available in Naira | Approval Threshold (=N=) | Procurement Method | Pre-or Post Qualification | Prior or Post Review |  | Bid Prep & Submission by MDAs | PPA No Objection Date | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report ( | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | 1-2wks) | (1-2wks) | (1-4 wks) | (48 Hours) | 0 | (1 wk) | (1-2 wks) | (2-4wks)
1 | DIET/CANTEEN(In-patient & doctors food). | OGHL/G-F/NS/016/22 | 1 |  | 13417176.96 | >10M | NS | POST | POST | Plan | 14/2/2022 | N/A | 17/2/22 | 22/2/2022 | 25/2/2022 | 2022-02-03 | N/A | N/A |  | 2021-07-03 | 2022-10-03 | N/A
Actual
2 | MISCELLANEOUS(Post-Natal consumablesetc). | OGHL/G-F/NS/017/22 | 1 |  | 5590490.4 | <10M | NS | POST | POST | Plan | 17/2/2022 | N/A | 22/2/2022 | 25/3/2022 | 2022-02-03 | 2022-07-03 | N/A | N/A |  | 2022-10-03 | 15/3/2022 | N/A
Actual
3 | ADMISSION PACK(Dilevery packs etc). | OGHL/G-F/NS/018/22 | 1 |  | 6056364.6 | <10M | NS | POST | POST | Plan | 22/2/2022 | N/A | 25/2/2022 | 2022-02-03 | 2022-07-03 | 2022-10-03 | N/A | N/A |  | 15/3/2022 | 18/3/2022 | N/A
Actual
4 | DRESS & SUTURING(C/S packs & delivery pack etc). | OGHL/G-F/NS/019/22 | 1 |  | 2041744.32 | <10M | NS | POST | POST | Plan | 25/2/2022 | N/A | 2022-02-03 | 2022-07-03 | 2022-10-03 | 15/3/2022 | N/A | N/A |  | 18/3/2022 | 23/3/2022 | N/A
Actual
5 | MEDICAL RECORDS & YELLOW CARD(printing of medical forms | OGHL/G-F/NS/020/22 | 1 |  | 10280760 | >10M | NS | POST | POST | Plan | 2022-02-03 | N/A | 2022-07-03 | 2022-10-03 | 15/3/2022 | 18/3/2022 | N/A | N/A |  | 23/3/2022 | 25/3/2022 | N/A
Actual
6 | SCAN(Scan film, gel &paper etc). | OGHL/G-F/NS/021/22 | 1 |  | 4901806.8 | <10M | NS | POST | POST | Plan | 2022-07-03 | N/A | 2022-10-03 | 15/3/2022 | 18/3/2022 | 23/3/2022 | N/A | N/A |  | 25/3/2022 | 28/3/2022 | N/A
Actual
7 | CASUALTY ADMISSION(Emergency & casualty kit etc). | OGHL/G-F/NS/022/22 | 1 |  | 3583855.44 | <10M | NS | POST | POST | Plan | 2022-10-03 | N/A | 15/3/2022 | 18/3/2022 | 23/3/2022 | 25/3/2022 | N/A | N/A |  | 28/3/2022 | 30/3/2022 | N/A
Actual
8 | X-RAY(X-ray film etc). | OGHL/G-F/NS/023/22 | 1 |  | 5564833.56 | <10M | N/S | POST | POST | Plan | 15/3/2022 | N/A | 18/3/2022 | 23/3/2022 | 25/3/2022 | 28/3/2022 | N/A | N/A |  | 30/3/2022 | 2022-04-04 | N/A
Actual
Plan
Actual
| TOTAL | [8 empty] | Plan
Actual

## works
PROCUREMENT PLAN FOR WORKS
MINISTRY:
BUDGET YEAR:
S/N | CONTRACT IDENTIFICATION |  | BASIC DATA | [5 empty] | Plan Vs Actual | Prior or Post Review | BIDDING PERIOD (DATES) |  |  |  | BID EVALUATION |  | APPROVAL |  | CONTRACT FINALISATION
| Contract Description | Package Number | Lot Number | Budget Available in Naira | Approval Threshold | Procurement Method | Lump Sum or Bill of Quantity | Pre-or Post Qualification |  |  | Bid Prep & Submission by MDAs | PPA No Objection | Bid Invitation Date | Bid Closing & Opening | Submission of Bid Evaluation Report | PPA Issue Certificate of Compliance | Mr. Governor's Approval | Register Mr. Governor's approval with PPA | Contract Amount | Notification of Award | Contract Award | Mobilization Advance Payment | Substantial Completion/Install | Inspection & Final Acceptance
[11 empty] | (1-4wks) | (1-2wks) | (1-2wks) | (2-6 wks) | (1-2wks) | (1-2wks) |  |  | 0 | (1 wk) | (1-2 wks) | (2-4wks)
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual